## TYADB (Shah-S & N)
Municipal Corporation of Delhi
Engineering Department
Target Achievement (Phy./ Financial) report of Schemes under TYADB of Shah. (South) & Shah. (North) Zone for the year 2010-11 upto 31.05.10
Sl. No. | AC | Name of Scheme | Year of passing by TYADB | Total outlay of scheme | Phy. Target of the scheme | Financial Achievement upto 31.03.10 | Physical Achievement upto 31.03.10 | Finacial Target for 2010-11 | Phy Target for 2010-11 | Phy achievement as on 31.05.10 | Fin achievement as on 31.05.10 | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Regular Scheme | [8 empty] | Phy. Achievement |  | Fin. Achievement
1 | 55 To 70 | Development works with the consent of area MLA. | 2010-11 | 1120 | M/P-1.10 CC-24.30, Dr.-8.2, Dense-7.00, Mastic-5.58, High mast-25 Nos | 578.98 | M/P 1.00,Drain - 7.20 CC - 21.90 Mastic - 4.95 , Dense -6.80 , High Mast 21 Nos. | 1120 | M/P 2.40, CC-17.50 Dr.-4.70, Mastic-10.25 Dense-6.30 | Dr-0.95 CC 1.90 | __ | 4% Completed and remaining are at different stages like under approval, under tender and under award.
2 | 55 To 70 | Development works in approved/ UR Colonies. | 2010-11 | 400 | M/P-1.10, CC-8.60, Dr.-5.70, Mastic-1.85, Dense-1.40 | 164.41 | Drain - 5.00 CC - 7.90 M/P- 1.10, Dense-1.10. Mastic - 1.50 | 400 | CC-6.25, M/P 0.90, Dr.-1.70, Mastic -3.65 Dense- 2.30 | Dr-0.40 CC 0.95 | __ | 2% Completed and remaining are at different stages like under approval, under tender and under award.
3 | 55 To 70 | Development works for strengthening of road. | 2010-11 | 400 | Dense-10.70, Mastic-6.50 | 44.61 | Dense - 7.80 , Mastic 6.10 | 400 | Dense-5.50, Mastic-7.35 | Mastic-0.95 | __ | 1% Completed and remaining are at different stages like under approval, under tender and under award.
4 | 55 To 70 | Develoment of street light and High mast light. | 2010-11 | 200 | 65 Nos | 86.06 | 34 Nos. | 200 | 65 Nos | 3 Nos | __ | 4% Completed
NOTE :- Column no. 5 to 8 reflects the report prior to 2010=11 of AC No. 55 to 70 of Shah (South) & Shah (North ) Zone.
Target Achievement (Phy./ Financial) report of Schemes under TYADB of Shah. (South) Zone for the year 2010-11 upto 31.05.10
Ongoing Scheme
Sl. No. | AC | Name of Scheme | Year of passing by TYADB | Total outlay of scheme | Phy. Target of the scheme | Financial Achievement upto 31.03.10 | Physical Achievement upto 31.03.10 | Finacial Target for 2010-11 | Phy Target for 2010-11 | Phy achievement as on 31.05.10 | Fin achievement as on 31.05.10 | Remarks
1 | 55 | Widening & Imp. of Khudi Ram Bose Marg from Noida road to Block No. 15 in Trilok Puri AC 37 Sh. (S) Zone. (I) Widening of road by providing M/P and construction of Central verge. (ii) Imp. & Stg. of road providing dense carpeting. | 2005-06 | 177 | M/P-4.00, F/P-1.00, CV-3.00, Shifting of Elec/Tele Poles, Dense-8.00 | 163 | (i) 90% (ii) 100% | 8.53 | CV-0.05 | ___ | ___ | (i) 90% completed and held up due to permission of cuttting trees awaited from forest deptt. (ii) Completed
2 | 55 | Khel Parisar 1/3 portion at Block 7-8, Trilok Puri in AC-37 | 2007-08 | 270 | 1 No. | 20 | Work of boundary wall 60% completed | 100 | Work of boundary wall 40% completed | Work of boundary wall 35% completed | ___ | Tender called three times but no response. Work of boundary wall started and 98% completed.
3 | 55 | Imp. of road from Block No. -13 to 18 Trilok Puri in AC-37. | 2008-09 | 350.6 | Dense-20.00 | 20 | Drain/ CV 0.45 | 350 | Dense-20.00 Drain/CV 0.45 | Drain/CV 0.45 | ___ | Dense- To be started. Drain/CV - completed.
4 | 55 | I/S of Chilla Road, Samachar Apptt. Road & Road near ASN Public School & Kalka Apptt. By Carpetting. | 2008-09 | 172.71 | Dense 11.50 | 45 | Dense .3.00 | 100 | Dense 4.50 | Dense 4.50 | ___ | completed
5 | 56 | Imp. of road, footpath & drain from Ghazipur Red Light to T-Section of Kondli Village. | 2008-09 | 280 | Dense 4.80 F/Path 2.70 Drain 2.70 | __ | __ | 20 | Dense 4.80 F/Path 2.70 Drain 2.70 | __ | __ | Tender received & sent to fin. For approval of rate and agency.
6 | 57 | Community Center at Khichri Pur AC 38 (Demolition and Re-Const.) | 2006-07 | 103.28 | 1 No. | 48 | 95% | 103.28 | 5% | 3% | ___ | 98% Completed and in Progess.
7 | 57 | C/o drain from ayappa mandir road to noida raod drain ( Shah Link Road ) in Pkt.- IV M.Vihar - I in AC 40 | 2007-08 | 50 | Drain -0.70 | 15 | Drain 0.18 | 35 | __ | __ | ___ | 50% work completed and remaiming work is not required & the case is processed for closing.
8 | 57 | Remodeling of drain from NH-24 to Kotla Road along the Khichripur road. | 2008-09 | 90 | Drain 0.90 | __ | __ | 90 | Drain 0.90 | __ | __ | Work order issued, to be started.
9 | 58 | I/S of road & intersection by pdg mastic asphalt in lane No.3 to 10, Lalita Park and lanes parallel to main road Laxmi Nagar from main Bazar to H.No.84 and opposite M.C.Pry School Kishan Kunj in AC-40 | 2007-08 | 50 | Mastic-1.9 | 24.5 | Mastic 1.08 | 24 | Mastic-0.82 | Mastic 0.70 | __ | 90% Completed and in progress..
10 | 58 | Imp of drainage system by constructing drain from main Mandawali Road towards Sadbhawana Appartment. AC-39. | 2008-09 | 195 | Drain 1.50 | 168 | Drain 1.18 | 30 | __ | __ | ___ | Completed in 2009-10
11 | 58 | Const. of road along Pusta from C/Hall Ramesh Park to SDM office AC-40. | 2008-09 | 100 | M/P-1.5 | __ | __ | 100 | M/P-1.5 | __ | __ | 2% completed & in progress
12 | 58 | C/o foot over bridge connecting Mandawali & South Ganesh Nagar near RUB Madhuban. | 2008-09 | 100 | 1 No. | __ | __ | 100 | 1 No |  | __ | Tender received & sent to fin. For approval of rate and agency.
13 | 58 | C/o Community Hall at Satabdi Park Mandawali. | 2008-09 | 231.56 | 1 No. | __ | __ | 231.56 | 1 No | __ | __ | Held up due to water body
14 | 58 | I/S of main Mkt. Shakarpur Mkt. road by pdg. mastic from Vikas Marg to Mother Dairy road. | 2008-09 | 49.96 | Mastic 1.80 | 27 | Mastic 1.44 | 22.96 | Mastic 0.36 | __ | __ | 80% completed and held the due to c/o nalla.
15 | 59 | Imp. of drain & road in Sainy Enclave AC-43. | 2008-09 | 25 | Dr.0.50, C.C.-0.30, Mastic-0.30 | __ | __ | 25 | Dr.0.50, C.C.-0.30, Mastic-0.30 | __ | __ | Work order issued, to be started.
16 | 59 | Const . of C/Hall at OCF Pkt. in CGHS Mandawali Fazalpur near Sidh Appartment in AC-43 Shah.(S). | 2008-09 | 120 | 1 No. | 30 | 30% | 80 | 70% | 20% | __ | 50% completed and in progress.
17 | 59 | Const. of C/Hall at OCF Pkt. In CGHS Mandawali Near Balco Appartment AC-43 Shah.(S) near Patparganj depot. | 2008-09 | 125 | 1 No. | 50 | 70% | 65 | 30% | 15% | __ | 85% completed and inprogress
18 | 59 | C/o Community Hall at Vishwas Nagar AC-43. | 2008-09 | 178 | 1 No. | __ | __ | 178 | 1 No | __ | __ | Land yet to be handed over by DDA.
19 | 58 | C/o Community Hall at Mandawali. | 2008-09 | 170.76 | 1 No. | __ | 5% | 170.76 | 95% | 5% | __ | 10% completed and in progress
20 | 59 | Stg. of internal road by pdg. mastic asphalt in D-Block, Vivek Vihar. | 2008-09 | 23.2 | Mastic 0.90 | __ | __ | 23.2 | Mastic 0.90 | __ | __ | Tender received & sent to fin. For approval of rate and agency.
21 | 59 | Stg. of internal roads by pdg. mastic asphalt in Gujrat Vihar. | 2008-09 | 18.5 | Mastic 0.75 | __ | __ | 18.5 | Mastic 0.75 | __ | __ | Tender received & is under approval of rate & agency
22 | 60 | I/S of road by pdg Mastic Asphalt in South Anarkali & Old Govind Pura in AC-42 | 2007-08 | 120 | Mastic-4.10 | __ | __ | 120 | Mastic-4.10 | __ | __ | Tender received and DFA sent for approval of rate and agency.
23 | 60 | Const. of drain near Chhachi builidng to near Chander Nagar Govt School in Krishna Nagar, AC-42 | 2007-08 | 108.37 | Drain-1.50 | 50 | Drain-0.50 | 58 | Drain-1.00 | Drain 0.50 | __ | 50% completed and inprogress
24 | 60 | Imp. of road by pdg mastic asphalt in Brijpuri, Khureji, Radhey Shyam Park and Hasanpur village in AC-43, Shahdara South. | 2007-08 | 71 | Mastic-2.30 | __ | __ | 71 | Mastic-2.30 | __ | __ | Work order issued, to be started.
25 | 60 | Const. of C/Hall in block -12 Geeta Colony AC-40. | 2008-09 | 200 | 1 No. | __ | 10% | 133.54 | 90% | __ | __ | 10% completed and in progress.
26 | 60 | Pdg. Mastic asphalt in New Layal Pur, Gyan Park & Krishna Nagar AC-42. | 2008-09 | 100 | Mastic-3.80 | 80 | Mastic 3.40 | 20 | Mastic-0.40 | Mastic-0.25 | __ | 85% Completed and in progress
27 | 60 | Stg. of Parvana road by pdg. CC pavement from Road No.-57 to Patparganj Road. | 2008-09 | 230 | CC 4.50 | __ | __ | 230 | CC 4.50 | __ | __ | Tender called, due on 04.06.2010
28 | 60 | C/o of community Hall at Block 10 Geeta Colony. | 2008-09 | 220 | 1 No. | 103 | 60% | 85.15 | 40% | 10% | ___ | 20% completed and in progress.
29 | 61 | Remodelling of Gandhi Nagar and Raghubar pura Drain SH:- C/o drain in Gandhi Nagar (One side) from Kailash Nagar to Jheel Chowk. | 2001-02 | 207 | Drain-1.50 Km. | 153 | Drain 1.25 | 41.96 | Drain-0.25 | __ | ___ | 80% Completed and in progress
30 | 61 | Const. /Remodelling of Gandhi Nagar drain from Pusta to Jheel Chowk in AC-41 | 2007-08 | 175 | Drain-.1.30 Km | 147 | Drain 1.05 | 27 | Drain-0.25 | __ | __ | 80% Completed and in progress.
31 | 62 | Community Center at Bhola Nath Nagar near MCD Pry School AC 44. | 2006-07 | 152 | 1 No. | 128 | 98% | 25 | 2% | 1% | __ | 99% completed and inprogress.
32 | 62 | Construction of bldg. of Poly Clinic in place of Civil Hospital at Chhota Bazar SH:C/o bldg for Chest Clinic (T.B. Clinic). | 2006-07 | 206 | 1 No. | 120 | 98% | 35 | 2% | __ | __ | 98% cpmpleted and in progress.
33 | 62 | I/S of road by mastic asphalt from Bhola Nath Nagar (Road No. 57) to Babu Ram School to Metro Bridge in Shah. AC-44. | 2007-08 | 87.29 | Mastic-3.33 | __ | __ | 87.29 | Mastic-3.33 | __ | __ | Work awarded, notice has been issued to be contractor to start the work.(Court Case)
34 | 62 | I/S of road by pdg. Mastic asphalt from Geeta Bhawan to Mani Ram Mandir Road and Gali No. 5 in Behari Colony and GT Road from R- Block to Aggarwal Sweets Dilshad Garden in AC-44. | 2007-08 | 83.39 | Mastic-3.2 | __ | __ | 83.39 | mastic-3.2 | __ | __ | Work awarded, notice has been issued to be contractor to start the work.(Court Case)
35 | 62 | I/S of road by pdg Mastic Asphalt in Jwala Nagar, Kasaiwara, Jharkhandi road, Ram Gopal Sharma Marg & Bhola Nath Nagar, DCP Office to Pandav road in AC-44. | 2007-08 | 92 | Mastic-2.00 | __ | __ | 92 | Mastic-2.00 | __ | __ | Work order issued, to be started
36 | 62 | Imp./Stg. of road by pdg. mastic asphalt on main Govind Khand road AC-44. | 2008-09 | 83.4 | Mastic-3.10 | 55 | Mastic-3.10 | 7 | __ | __ | __ | Completed in 2009-10
37 | 62 | Imp./Stg. of road by pdg. mastic asphalt in Pratap Khand & Vishkarma Nagar AC-44. | 2008-09 | 83.4 | Mastic-3.20 | __ | __ | 83.4 | Mastic-3.20 | __ | __ | Work order issued, held up due to laying of sewer line.
38 | 62 | Imp./Stg. of road by pdg. dense carpeting in E-block, Jhilmil Colony and A & B block Vivek Vihar Ph-II AC-44. SH:- M/P | 2008-09 | 24.86 | M/P-1.70 | __ | M/P-1.70 | 15 | __ | __ | __ | Completed in 2009-10
39 | 62 | Const./Imp. of footpath from G.T.road. to J&K Pkt. Dilshad garden AC-44. | 2008-09 | 25 | F/Path-0.70 | 10 | F/Path-0.70 | 8 | __ | __ | __ | Completed in 2009-10
40 | 62 | Imp. of Gali No.1 by pdg. RMC & construction of drain in Friends Colony. | 2008-09 | 24.5 | CC 0.95 | __ | __ | 24.5 | CC 0.95 | __ | __ | Estimate is under A/A & E/S
41 | 62 | Imp. of drainage system parallal to Metro Line under G.T.Road flyover by construction of drain with culverts of various entrance points in Friends Colony Galis. | 2008-09 | 22.5 | Drain 0.60 Culvert 8 NO. | __ | __ | 22.5 | Drain 0.60 Culvert 8 NO. | __ | __ | Estimate is under A/A & E/S
42 | 55 to 70 | One room for library at ground floor in each Community Center should be constructed by MCD project Deptt. SH:- C/O Library room at Bhola Nath Nagar | 2006-07 | 6 | 1 No. | __ | 80% | 6 | 20% | 20% | __ | completed
NEW SCHEMES SANCTIONED ON 7.7.09
1 | 55 | Improvement & Strengthening of road of Pkt-I and Pkt II Mayur Vihar, Phase-I, Idgah Road AC-55 | 2009-10 | 130 | Dense 4.60 | __ | __ | 116.53 | Dense 4.60 | __ | __ | Tender received and sent to fin. For conc.
2 | 56 | Imp of roads by pdg RMC in left out link lanes of Pkt A-1, A-2, A-3 Mayur Vihar Phase-III, Shahdara AC-56 | 2009-10 | 155.9 | CC 7.10 | __ | __ | 150.67 | CC 7.10 | __ | __ | Estimate sent to finance for A/A and E/S
3 | 57 | Improvement of drainage system and road dense carpeting from Kalyan Marg to Engineers Apptt to Railway culvert AC-57 | 2009-10 | 240 | Drain 1.50 Dense 1.50 Mastic 0.50 | __ | __ | 240 | Drain 1.50 Dense 1.50 Mastic 0.50 | __ | __ | Work order issued, to be started
4 | 57 | Stg of road by pdg RMC in Blc A, E and F in East Vinod Nagar AC-57 | 2009-10 | 140 | CC 5.50 | __ | __ | 140 | CC 5.00 | __ | __ | Work order issued, to be started
5 | 58 | Stg of road in South Ganesh nagar H.No.27,91,64,31,61,P45 H.No.412,418,712,730,739 near M.C. Primary School by pdg Mastic asphalt-II Shakarpur AC-58 | 2009-10 | 76.58 | Mastic 3.35 | __ | Mastic 0.35 | 76.58 | Mastic 3.00 | Mastic 1.50 | __ | 55% completed and in progress.
6 | 58 | St road by pdg mastic asphalt in Dayanand Block and WA Block and WB Block Shakarpur AC-58 | 2009-10 | 68.94 | Mastic 3.20 | __ | __ | 68.94 | Mastic 2.90 | __ | __ | Work order issued, to be started.
7 | 58 | Stg of road by pdg mastic in upadhaya Block School Block in Shakarpur AC-58 | 2009-10 | 72.98 | Mastic 3.50 | __ | __ | 72.98 | Mastic 3.50 | _ | __ | Work order issued, to be started.
8 | 58 | Remodeling of drain from A-15 to Flood drain and from shop plot No.28 to Flood drain in Pandav Nagar AC-58 | 2009-10 | 50 | Drain 1.50 | __ | __ | 50 | Drain 1.50 | Drain 0.10 | __ | 5% completed & in progress
9 | 59 | Remodelling of Kasturba Nagar drain (Ph-II) from Shastri Gali to Nehru Gali in Vishwas Nagar AC-59 | 2009-10 | 301.65 | Drain 0.45 | __ | __ | 20 | Drain 0.04 | __ | __ | Tender received and sent for approval of rate & agency.
10 | 59 | Stg of road by mastic asphalt in Dayanand Vihar, Defence Enclave and road between Swasthya Vihar and Gujrat Vihar AC-59 | 2009-10 | 91.08 | Mastic 3.90 | __ | __ | 91.09 | Mastic 3.90 | __ | __ | Estimate is under A/A & E/S
11 | 61 | Constuction of Ayurvedic Dispensary Gali No.5, Reghubar Pura, Gandhi Nagar AC-61 | 2009-10 | 49 | 1 No. | __ | __ | 49 | 1 NO | __ | __ | Tender received and sent to fin. For approval of rate and agency.
12 | 62 | Improvement and Stg of road and drainage systems from G.T. Road Dharam Kanta to Malaria Office AC-62 | 2009-10 | 128 | Drain 0.50 CC 1.00 Dense 1.00 | __ | __ | 30 | Drain 0.50 CC 0.30 | __ | __ | Estimate is under A/A & E/S
NEW SCHEMES SANCTIONED ON 20.03.10
1 | 61 | C/o Drain from pump house old G.T.Road to New G.T.Road in Shastri park AC-61. | 2009-10 | 199.81 | Drain 0.65 | __ | __ | 50 | Drain 0.15 | __ | __ | PE Checked by planning deptt. and tender received for design and consultancy and is under justification.
2 | 62 | Re-const. of drain along railway track from tolet block to drain no. 1 in Bihari colony AC-62 | 2009-10 | 224.97 | Drain 1.05 | __ | __ | 50 | Drain 0.20 | __ | __ | Estimate sent to planning department for checking
Target Achievement (Phy./ Financial) report of Schemes under TYADB of Shah. (North) Zone for the year 2010-11 upto 31.05.10
1 | 62 | Community Center at C-Block, Dilshad Colony AC 45. | 2006-07 | 200 | 1 No. | 158 | 100% | 6.02 | __ | __ | __ | Completed in 2009-10
2 | 62 | C/o RCC box culvert across PWD road No.62 to connect the existing drain from Bus depot to Dilshad Colony Pump House AC-45. | 2008-09 | 24.25 | Drain 0.30 | __ | __ | 24.25 | Drain 0.30 | __ | __ | Scheme to be dropped
3 | 62 & 63 | Imp/Stg. of Main / Internal Road / Drains and side berms in Dilshad Colony, Shah. in AC-45. | 2007-08 | 270 | Drain 3.70 km Dense-10 km B/P-4.00 km | 142 | Drain 3.40 km Dense-10.00 km B/P-2.20 km | 130 | Drain 0.30 km Dense-10 km B/P-1.8km | Drain 0.15 | __ | (i) 65% completed and In progress. (ii) Dense work completed
4 | 63 | Const. of drain from E-1, Block Nand Nagri to E-4 Block Nand Nagari (both side) Shah.(N). | 2007-08 | 94 | Drain-0.85 km | 72 | Drain-0.80 km | 22 | Drain-0.05 | Drain-0.04 | __ | 99% completed and In progress.
5 | 63 | Imp. & Stg. of road along G.T.B. Enclave from road no.69 to road no.68 in AC-45 Shah.(N). SH ;- C/o of drain,footpath & Imp.of side berm. | 2008-09 | 155 | Dense-3.06 CC-2.50 Drain-0.30 | __ | __ | 155 | Dense-3.06 CC-2.50 Drain-0.30 | __ | __ | (i) Tender received for CC Pav.and sent for approval of rate and agency. (ii) Work order issued, to be started..
6 | 64 | Covering of 52 cusec Bhagwan Pur Khera drain by steel mash in AC-47. | 2007-8 | 149.21 | Wire mash | __ | __ | 149.21 | Wire mash | __ | __ | Work order issued, the work of feasibility for covering of drain Is in progress.
7 | 64 | Imp.of internal storm water drainage system at DDA, MIG flats, East of Loni road in AC-47. | 2008-09 | 55.4 | Drain-2.00 | __ | __ | 55.4 | Drain-2.00 | __ | __ | Work order issued, to be started
8 | 65 | Widening I/S of main roads in Seelampur AC 49. | 2006-07 | 274.37 | Wid. 12 km. Dense 12 km. | 107 | Wid. 12 km., Dense-12 KM | 66.74 | __ | __ | __ | Completed in 2009-10
9 | 65 | C/o Barat Ghar CPJ Block, Seelampur AC 49. | 2006-07 | 250 | 1 no. | __ | __ | 250 | 1 No. | 5% | __ | 5% completed & in progress
10 | 65 | Imp. to Gokulpur drain by const. RCC drain from RDO to 790m and 1120 to 1560m along with CC pavment on both sides of drain from RDOm to 1560 m and const. of culverts in AC-49 and AC-50. | 2007-08 | 1373.65 | Drain 1.23, CC-2.05 & culvert- 3 Nos. | __ | __ | 1030 | Drain 1.23, CC-2.05 & culvert- 3 Nos. | 1% | __ | 1% completed & in progress
11 | 65 | Imp. of Maujpur road and Noor-elahi road in AC-51 | 2007-08 | 70 | Dense-5.00 | __ | __ | 70 | Dense-5.00 | __ | __ | Scheme to be dropped
12 | 65 | Remodelling of main drain on Maujpur road. | 2008-09 | 180 | Drain 1.32 | __ | __ | 180 | Drain 1.32 | __ | __ | Tender recevied & fair preamble sent for approval of rate & agency.
13 | 66 | Re-modelling of Moni Baba Nalla from gali No.1 to Gokul Pur Drain AC-50. | 2004-05 | 50 | Drain-0.84 | 23.5 | Drain 0.78 | 26.5 | Drain 0.06 | Drain 0.02 | __ | 90% completed and in progress.
14 | 66 | Community Center at Usmanpur AC 50. | 2006-07 | 250 | 1 No. | __ | __ | 250 | 1 No. | __ | __ | Land yet to be handed over by DDA.
15 | 66 | Remodelling of main Outfall drain of Yamuna Vihar. | 2008-09 | 220 | Drain 2.28 | __ | __ | 220 | Drain 2.28 | __ | __ | Tender recevied & fair preamble sent for approval of rate & agency.
16 | 67 | Community Center at Ghonda Chowk AC 51. | 2006-07 | 362.91 | 1 No. | __ | 2% | 290 | 98% | 5% | __ | 7% completed & in progress
17 | 68 | C/o Community Hall at Gokulpur village. | 2006-07 | 115.45 | 1No. | 113 | 99% | 2.45 | 1% | __ | __ | 99% completed and In progress.
18 | 68 | Imp.& stg.of loni road from wazirabad road to UP border in Shah.(N). | 2007-08 | 94.39 | (i) C.C-1.10 (ii) F/Path & C/verge | __ | 5% | 94.39 | (i) C.C-1.10 (ii) F/Path & C/verge | (i) C.C-0.70 (ii) F/Path & C/verge | __ | 80% completed and in progress
19 | 68 | Imp of drainage system by pdg RCC drain along right side on Sewadham road in AC-46 Shah. North Zone. | 2007-08 | 275 | Drain-0.65 | __ | __ | 137.5 | Drain-0.60 | __ | __ | Tender received and is being sent to fin. For conc..
20 | 68 | I/S of post office road, Police Station Road and connecting roads by dense carpeting in Nand Nagari. | 2008-09 | 76.3 | Dense 4.80 | __ | __ | 76.3 | Dense 4.80 | _ | __ | Work order issued, to be started
21 | 70 | C/o Barat Ghar at Village Khajuri Khas AC 52. | 2006-07 | 250 | 1 No. | _ | _ | 250 | 1 nos. | _ | __ | Land to be handed over by Revenue Deptt.
22 | 70 | Widening/ I/S of Karawal Nagar road from Wazirabad road to Sherpur Chowk in Phase-I AC 52. | 2006-07 | 485.08 | wmm-2.80, BM 1.08, AC 2.80, drain 0.54, CC 0.37 km | 155 | wmm-0.10, Drain 0.25, CC 0.37 km | 330 | Dense 2.80 drain 1.40 | __ | ___ | 30% Completed and tender received for remaining work and fair preamble sent for approval of rate and agency.
23 | 69 & 70 | Widening/Imp./Stg. of Kerawal Nagar Raod from Wazirabad Raod to Shiv Vihar Tiraha Shah. North AC-52. | 2007-08 | 2178.33 | Wid 12.8, Dence12.80, &Cc 4.36 Drain-6.40 | 203 | Land acquired charges | 370 | Drain-0.70 |  | ___ | (i) 50% land acquired and tender received and fair preamble sent for approval of rate and agency. (ii) 50% land is under acquisition.
NEW SCHEMES SANCTIONED ON 7.7.09
1 | 63 | Improvement /Stg of internal roads of Pocket F GTB Enclave by mastic AC-63 | 2009-10 | 44.18 | Mastic 1.80 | __ | __ | 44.18 | Mastic 1.80 | __ | __ | Tender received & being sent to fin. For conc.
2 | 63 | Construction of Community Hall /Multipurpose Hall at A Block Dilshad Colony, Shahdara North AC-63 | 2009-10 | 498 | 1 No. | __ | __ | 175 | 50% | __ | __ | Revised scheme was placed in 46th meeting of TYADB & minutes of the same is awaited for further action
3 | 65 | Construction of underground sumpwell at Zeenat Mahal Sr Sec School road No 66 North Zone AC-65 | 2009-10 | 100.8 | 1 No. | __ | __ | 100.08 | 100% | __ | __ | Tender received and DFA is being sent to fin. For conc.
4 | 65 | Construction of drain from CPJ culvert to Shiv Mandir in C-250/ AC-65 | 2009-10 | 69.63 | Drain 0.18 | __ | __ | 69.63 | Drain 0.18 | __ | __ | Estimate is under A/A & E/S
5 | 66 | Improvement/Stg of Gali No.1 Brahmpuri, AC-66 | 2009-10 | 65.12 | CC 0.86 | __ | __ | 65.12 | CC 0.86 | __ | __ | Tender recived, work executed by other agency and the case is under consideration.
6 | 67 | Improvement/Satg of Noor-E-Elahi road from DTC Yamuna Vihar Deport to Ghonda Chowk AC-67 | 2009-10 | 187.27 | CC 2.95 | __ | __ | 139.33 | CC 2.95 | CC-2.95 | __ | Completed
7 | 68 | Improvement of Loni road by pdg cc pavement Wazirabad road to Loni UP Border, AC No.68 | 2009-10 | 170 | CC 2.16 | __ | __ | 170 | CC 2.16 | __ | __ | Finance concurred the proposal and sent for approval of A/A and E/S.
8 | 62 / 63 | Improvement/Stg of road from PWD road No.62 to Road No 64 along Dilshad Colony, Shah, North AC-62 & 63 | 2009-10 | 98.85 | Drain 0.38 Dense 2.37 Mastic 0.50 | __ | __ | 98.85 | Drain 0.38 Dense 2.37 Mastic 0.50 | __ | __ | Tender received and is being sent to fin. For conc..
NEW SCHEMES SANCTIONED ON 20.03.10
1 | 64 | Imp. of drain from Sant Ravidass Temple to Drain No. 1 in Welcome Seelampur Phase - III AC-64 | 2009-10 | 90.55 | Drain 0.33 | __ | __ | 90.55 | Drain 0.33 | __ | __ | PE checeked and sent to fin. For conc.
2 | 65 | I/S of road from zero pusta to Brahampuri culvert and from Northern Engg. College to over head tank Gautam puri AC-65 | 2009-10 | 283 | Dense 4.16 Drain 2.28 CC 1.24 F/Path 1.40 C/Verge 0.70 | __ | __ | 250 | Drain 2.28 CC 1.24 | __ | __ | PE checeked and sent to fin. For conc.