## TYADB (Shah-S & N)
Municipal Corporation of Delhi
Engineering Department
Target Achievement (Phy./ Financial) report of Schemes under TYADB of Shah. (South) & Shah. (North) Zone for the year 2010-11 upto 31.12.10
Sl. No. | Div. | AC | Name of Scheme | Year of passing by TYADB | Total outlay of scheme | Phy. Target of the scheme | Financial Achievement upto 31.03.10 | Physical Achievement upto 31.03.10 | Finacial Target for 2010-11 | Phy Target for 2010-11 | Phy achievement as on 31.12.10 | Fin achievement as on 31.12.10 | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Regular Scheme | [9 empty] | Phy. Achievement |  | Fin. Achievement
1 | All Division of Shah(S) & Shah(N) | 55 To 70 | Development works with the consent of area MLA. | 2010-11 | 1120 | M/P-1.10 CC-24.30, Dr.-8.2, Dense-7.00, Mastic-5.58, High mast-25 Nos | 578.98 | M/P 1.00,Drain - 7.20 CC - 21.90 Mastic - 4.95 , Dense -6.80 , High Mast 21 Nos. | 1120 | M/P 2.40, CC-17.50 Dr.-4.70, Mastic-10.25 Dense-6.30 | M/P 2.20 CC 10.10 Dr. 3.10 Mastic 4.60 Dense 3.50 | 346.24 | 50% Completed and remaining are at different stages like under approval, under tender and under award.
2 | All Division of Shah(S) & Shah(N) | 55 To 70 | Development works in approved/ UR Colonies. | 2010-11 | 400 | M/P-1.10, CC-8.60, Dr.-5.70, Mastic-1.85, Dense-1.40 | 164.41 | Drain - 5.00 CC - 7.90 M/P- 1.10, Dense-1.10. Mastic - 1.50 | 400 | CC-6.25, M/P 0.90, Dr.-1.70, Mastic -3.65 Dense- 2.30 | CC 3.70 M/P 0.90 Dr. 1.20 Mastic 2.25 Dense 1.20 | 240.27 | 55% Completed and remaining are at different stages like under approval, under tender and under award.
3 | All Division of Shah(S) & Shah(N) | 55 To 70 | Development works for strengthening of road. | 2010-11 | 400 | Dense-10.70, Mastic-6.50 | 44.61 | Dense - 7.80 , Mastic 6.10 | 400 | Dense-5.50, Mastic-7.35 | Dense- 2.10 Mastic-2.55 | 20.29 | 35% Completed and remaining are at different stages like under approval, under tender and under award.
4 | All Division of Shah(S) & Shah(N) | 55 To 70 | Develoment of street light and High mast light. | 2010-11 | 200 | 65 Nos | 86.06 | 34 Nos. | 200 | 65 Nos | 30 Nos | 77.27 | 45% Completed
NOTE :- Column no. 5 to 8 reflects the report prior to 2010=11 of AC No. 55 to 70 of Shah (South) & Shah (North ) Zone.
Target Achievement (Phy./ Financial) report of Schemes under TYADB of Shah. (South) Zone for the year 2010-11 upto 31.12.10
Ongoing Scheme
Sl. No. | Div. | AC | Name of Scheme | Year of passing by TYADB | Total outlay of scheme | Phy. Target of the scheme | Financial Achievement upto 31.03.10 | Physical Achievement upto 31.03.10 | Finacial Target for 2010-11 | Phy Target for 2010-11 | Phy achievement as on 31.12.10 | Fin achievement as on 31.12.10 | Remarks
1 | M-III | 55 | Widening & Imp. of Khudi Ram Bose Marg from Noida road to Block No. 15 in Trilok Puri AC 37 Sh. (S) Zone. (I) Widening of road by providing M/P and construction of Central verge. (ii) Imp. & Stg. of road providing dense carpeting. | 2005-06 | 177 | M/P-4.00, F/P-1.00, CV-3.00, Shifting of Elec/Tele Poles, Dense-8.00 | 163 | (i) 90% (ii) 100% | 8.53 | CV-0.05 | ___ | ___ | (i) 90% completed and held up due to permission of cuttting trees awaited from forest deptt. (ii) Completed
2 | Pr.Sh-S | 55 | Khel Parisar 1/3 portion at Block 7-8, Trilok Puri in AC-37 | 2007-08 | 270 | 1 No. | 20 | Work of boundary wall 60% completed | 100 | Work of boundary wall 40% completed | Work of boundary wall completed | 14 | Tender received for main work and is under justification. Work of boundary wall completed.
3 | Pr.Sh-S | 55 | Imp. of road from Block No. -13 to 18 Trilok Puri in AC-37. | 2008-09 | 350.6 | Dense-20.00 | 20 | Drain/ CV 0.45 | 350 | Dense-20.00 Drain/CV 0.45 | Drain/CV 0.45 | 145 | Dense- completed Drain/CV - completed.
4 | Pr.Sh-S | 55 | I/S of Chilla Road, Samachar Apptt. Road & Road near ASN Public School & Kalka Apptt. By Carpetting. | 2008-09 | 172.71 | Dense 11.50 | 45 | Dense .3.00 | 100 | Dense 4.50 | Dense 4.50 | 122 | completed
5 | Pr.Sh-S | 55 | Improvement & Strengthening of road of Pkt-I and Pkt II Mayur Vihar, Phase-I, Idgah Road AC-55 | 2009-10 | 130 | Dense 4.60 | __ | __ | 116.53 | Dense 4.60 | __ | __ | Work order issued, to be started.
6 | Pr.Sh-S | 56 | Imp. of road, footpath & drain from Ghazipur Red Light to T-Section of Kondli Village. | 2008-09 | 280 | Dense 4.80 F/Path 2.70 Drain 2.70 | __ | __ | 20 | Dense 4.80 F/Path 2.70 Drain 2.70 | 25% | __ | 25% completed and in progress.
7 | Pr.Sh-S | 56 | Imp of roads by pdg RMC in left out link lanes of Pkt A-1, A-2, A-3 Mayur Vihar Phase-III, Shahdara AC-56 | 2009-10 | 155.9 | CC 7.10 | __ | __ | 150.67 | CC 7.10 | __ | __ | Estimate concurred by finance and fare preamble sent for A/A and E/S
8 | Pr.Sh-S | 57 | Community Center at Khichri Pur AC 38 (Demolition and Re-Const.) | 2006-07 | 103.28 | 1 No. | 48 | 95% | 103.28 | 5% | 3% | 50 | 98% Completed and in Progess.
9 | Pr.Sh-S | 57 | C/o drain from ayappa mandir road to noida raod drain ( Shah Link Road ) in Pkt.- IV M.Vihar - I in AC 40 | 2007-08 | 50 | Drain -0.70 | 15 | Drain 0.18 | 35 | __ | __ | ___ | 50% work completed and remaiming work is not required & the case is processed for closing.
10 | M-IV | 57 | Remodeling of drain from NH-24 to Kotla Road along the Khichripur road. | 2008-09 | 90 | Drain 0.90 | __ | __ | 90 | Drain 0.90 | Drain 0.09 | __ | 10% completed and in progress
11 | M-IV | 57 | Improvement of drainage system and road dense carpeting from Kalyan Marg to Engineers Apptt to Railway culvert AC-57 | 2009-10 | 240 | Drain 1.50 Dense 1.50 Mastic 0.50 | __ | __ | 240 | Drain 1.50 Dense 1.50 Mastic 0.50 | Drain 1.50 Dense 1.35 | 110 | 85% completed & in progress
12 | M-IV | 57 | Stg of road by pdg RMC in Blc A, E and F in East Vinod Nagar AC-57 | 2009-10 | 140 | CC 5.50 | __ | __ | 140 | CC 5.00 | CC-4.50 | 35 | 90% completed & in progress
13 | M-I | 58 | I/S of road & intersection by pdg mastic asphalt in lane No.3 to 10, Lalita Park and lanes parallel to main road Laxmi Nagar from main Bazar to H.No.84 and opposite M.C.Pry School Kishan Kunj in AC-40 | 2007-08 | 50 | Mastic-1.9 | 24.5 | Mastic 1.08 | 24 | Mastic-0.82 | Mastic 0.82 | __ | Completed
14 | Pr.Sh-S | 58 | Imp of drainage system by constructing drain from main Mandawali Road towards Sadbhawana Appartment. AC-39. | 2008-09 | 195 | Drain 1.50 | 168 | Drain 1.18 | 30 | __ | __ | 17 | Completed in 2009-10
15 | Pr.Sh-S | 58 | Const. of road along Pusta from C/Hall Ramesh Park to SDM office AC-40. | 2008-09 | 100 | M/P-1.5 | __ | __ | 100 | M/P-1.5 | M/P 0.25 | __ | 15% completed & in progress
16 | Pr.Sh-S | 58 | C/o foot over bridge connecting Mandawali & South Ganesh Nagar near RUB Madhuban. | 2008-09 | 100 | 1 No. | __ | __ | 100 | 1 No |  | __ | Work order issued, and held up due to the shifting of water line.
17 | Pr.Sh-S | 58 | C/o Community Hall at Satabdi Park Mandawali. | 2008-09 | 231.56 | 1 No. | __ | __ | 231.56 | 1 No | __ | __ | Held up due to water body
18 | Pr.Sh-S | 58 | I/S of main Mkt. Shakarpur Mkt. road by pdg. mastic from Vikas Marg to Mother Dairy road. | 2008-09 | 49.96 | Mastic 1.80 | 27 | Mastic 1.44 | 22.96 | Mastic 0.36 | Mastic 0.36 | __ | Completed
19 | Pr.Sh-S | 58 | C/o Community Hall at Mandawali. | 2008-09 | 170.76 | 1 No. | __ | 5% | 170.76 | 95% | 65% | __ | 70% completed and in progress
20 | M-IV | 58 | Stg of road in South Ganesh nagar H.No.27,91,64,31,61,P45 H.No.412,418,712,730,739 near M.C. Primary School by pdg Mastic asphalt-II Shakarpur AC-58 | 2009-10 | 76.58 | Mastic 3.35 | __ | Mastic 0.35 | 76.58 | Mastic 3.00 | Mastic 3.00 | __ | Completed.
21 | M-IV | 58 | St road by pdg mastic asphalt in Dayanand Block and WA Block and WB Block Shakarpur AC-58 | 2009-10 | 68.94 | Mastic 3.20 | __ | __ | 68.94 | Mastic 3.20 | Mastic 2.56 | __ | 80% completed and in progress
22 | M-IV | 58 | Stg of road by pdg mastic in upadhaya Block School Block in Shakarpur AC-58 | 2009-10 | 72.98 | Mastic 3.50 | __ | __ | 72.98 | Mastic 3.50 | Mastic 1.75 | __ | 50% completed and in progress.
23 | M-IV | 58 | Remodeling of drain from A-15 to Flood drain and from shop plot No.28 to Flood drain in Pandav Nagar AC-58 | 2009-10 | 50 | Drain 1.50 | __ | __ | 50 | Drain 1.50 | Drain 0.60 | __ | 40% completed & in progress
24 | Pr.Sh-S | 59 | Imp. of drain & road in Sainy Enclave AC-43. | 2008-09 | 25 | Dr.0.50, C.C.-0.30, Mastic-0.30 | __ | __ | 25 | Dr.0.50, C.C.-0.30, Mastic-0.30 | Drain 0.50 CC 0.30 Mastic 0.30 | 10 | Completed
25 | Pr.Sh-S | 59 | Const . of C/Hall at OCF Pkt. in CGHS Mandawali Fazalpur near Sidh Appartment in AC-43 Shah.(S). | 2008-09 | 172.4 | 1 No. | 30 | 30% | 80 | 70% | 45% | 45 | 75% completed and in progress.
26 | Pr.Sh-S | 59 | Const. of C/Hall at OCF Pkt. In CGHS Mandawali Near Balco Appartment AC-43 Shah.(S) near Patparganj depot. | 2008-09 | 145 | 1 No. | 50 | 70% | 65 | 30% | 30% | 55 | Completed
27 | Pr.Sh-S | 59 | C/o Community Hall at Vishwas Nagar AC-43. | 2008-09 | 178 | 1 No. | __ | __ | 178 | 1 No | __ | __ | Land yet to be handed over by DDA.
28 | Pr.Sh-S | 59 | Stg. of internal road by pdg. mastic asphalt in D-Block, Vivek Vihar. | 2008-09 | 23.2 | Mastic 0.90 | __ | __ | 23.2 | Mastic 0.90 | __ | __ | Tender received & sent to fin. For approval of rate and agency.
29 | Pr.Sh-S | 59 | Stg. of internal roads by pdg. mastic asphalt in Gujrat Vihar. | 2008-09 | 18.5 | Mastic 0.75 | __ | __ | 18.5 | Mastic 0.75 | __ | __ | Tender received & is under approval of rate & agency
30 | Pr.Sh-S | 59 | Remodelling of Kasturba Nagar drain (Ph-II) from Shastri Gali to Nehru Gali in Vishwas Nagar AC-59 | 2009-10 | 301.65 | Drain 0.45 | __ | __ | 20 | Drain 0.04 | Consultancy work in progress | __ | Tender received and DFA sent to fin. For A/A and E/S and onsultancy work completed
31 | Pr.Sh-S | 59 | Stg of road by mastic asphalt in Dayanand Vihar, Defence Enclave and road between Swasthya Vihar and Gujrat Vihar AC-59 | 2009-10 | 91.08 | Mastic 3.90 | __ | __ | 91.09 | Mastic 3.90 | __ | __ | Tender received and the case is under policy decision.
32 | Pr.Sh-S | 60 | I/S of road by pdg Mastic Asphalt in South Anarkali & Old Govind Pura in AC-42 | 2007-08 | 120 | Mastic-4.10 | __ | __ | 120 | Mastic-4.10 | Mastic 4.10 | __ | Completed
33 | Pr.Sh-S | 60 | Const. of drain near Chhachi builidng to near Chander Nagar Govt School in Krishna Nagar, AC-42 | 2007-08 | 108.37 | Drain-1.50 | 50 | Drain-0.50 | 58 | Drain-1.00 | Drain 0.55 | 25 | 55% completed and inprogress
34 | Pr.Sh-S | 60 | Imp. of road by pdg mastic asphalt in Brijpuri, Khureji, Radhey Shyam Park and Hasanpur village in AC-43, Shahdara South. | 2007-08 | 71 | Mastic-2.30 | __ | __ | 71 | Mastic-2.30 | Mastic 1.05 | __ | 45% completed & in progress
35 | Pr.Sh-S | 60 | Const. of C/Hall in block -12 Geeta Colony AC-40. | 2008-09 | 200 | 1 No. | __ | 10% | 133.54 | 90% | 40% | 42 | 50% completed and in progress.
36 | Pr.Sh-S | 60 | Pdg. Mastic asphalt in New Layal Pur, Gyan Park & Krishna Nagar AC-42. | 2008-09 | 100 | Mastic-3.80 | 80 | Mastic 3.40 | 20 | Mastic-0.40 | Mastic-0.25 | __ | 85% Completed and in progress
37 | Pr.Sh-S | 60 | Stg. of Parvana road by pdg. CC pavement from Road No.-57 to Patparganj Road. | 2008-09 | 230 | CC 4.50 | __ | __ | 230 | CC 4.50 | __ | __ | Tender received and sent to fin. For approval of rate and agency.
38 | Pr.Sh-S | 60 | C/o of community Hall at Block 10 Geeta Colony. | 2008-09 | 250 | 1 No. | 103 | 60% | 85.15 | 40% | 40% | 67 | Completed
39 | Pr.Sh-S | 61 | Remodelling of Gandhi Nagar and Raghubar pura Drain SH:- C/o drain in Gandhi Nagar (One side) from Kailash Nagar to Jheel Chowk. | 2001-02 | 207 | Drain-1.50 Km. | 153 | Drain 1.25 | 41.96 | Drain-0.25 | Drain 0.25 | 41 | Completed.
40 | Pr.Sh-S | 61 | Const. /Remodelling of Gandhi Nagar drain from Pusta to Jheel Chowk in AC-41 | 2007-08 | 175 | Drain-.1.30 Km | 147 | Drain 1.05 | 27 | Drain-0.25 | Drain 0.24 | 13 | 97% Completed and in progress.
41 | Pr.Sh-S | 61 | Constuction of Ayurvedic Dispensary Gali No.5, Reghubar Pura, Gandhi Nagar AC-61 | 2009-10 | 49 | 1 No. | __ | __ | 49 | 1 NO | 10% | __ | 10% completed and in progress.
42 | Pr.Sh-S | 61 | C/o Drain from pump house old G.T.Road to New G.T.Road in Shastri park AC-61. | 2009-10 | 199.81 | Drain 0.65 | __ | __ | 50 | Drain 0.15 | __ | __ | Detail estimate is under checking
43 | Pr.Sh-S | 62 | Community Center at Bhola Nath Nagar near MCD Pry School AC 44. | 2006-07 | 152 | 1 No. | 128 | 98% | 25 | 2% | 2% | 15 | Completed
44 | Pr.Sh-S | 62 | Construction of bldg. of Poly Clinic in place of Civil Hospital at Chhota Bazar SH:C/o bldg for Chest Clinic (T.B. Clinic). | 2006-07 | 206 | 1 No. | 120 | 98% | 35 | 2% | 2% | __ | Completed
45 | Pr.Sh-S | 62 | I/S of road by mastic asphalt from Bhola Nath Nagar (Road No. 57) to Babu Ram School to Metro Bridge in Shah. AC-44. | 2007-08 | 87.29 | Mastic-3.33 | __ | __ | 87.29 | Mastic-3.33 | __ | __ | Work awarded, notice has been issued to be contractor to start the work.(Court Case)
46 | Pr.Sh-S | 62 | I/S of road by pdg. Mastic asphalt from Geeta Bhawan to Mani Ram Mandir Road and Gali No. 5 in Behari Colony and GT Road from R- Block to Aggarwal Sweets Dilshad Garden in AC-44. | 2007-08 | 83.39 | Mastic-3.2 | __ | __ | 83.39 | mastic-3.2 | __ | __ | Work awarded, notice has been issued to be contractor to start the work.(Court Case)
47 | Pr.Sh-S | 62 | I/S of road by pdg Mastic Asphalt in Jwala Nagar, Kasaiwara, Jharkhandi road, Ram Gopal Sharma Marg & Bhola Nath Nagar, DCP Office to Pandav road in AC-44. | 2007-08 | 92 | Mastic-2.00 | __ | __ | 92 | Mastic-2.00 | Mastic 1.60 | __ | 80% completed and in progress.
48 | Pr.Sh-S | 62 | Imp./Stg. of road by pdg. mastic asphalt on main Govind Khand road AC-44. | 2008-09 | 83.4 | Mastic-3.10 | 55 | Mastic-3.10 | 7 | __ | __ | 5 | Completed in 2009-10
49 | Pr.Sh-S | 62 | Imp./Stg. of road by pdg. mastic asphalt in Pratap Khand & Vishkarma Nagar AC-44. | 2008-09 | 83.4 | Mastic-3.20 | __ | __ | 83.4 | Mastic-3.20 | Mastic 0.80 | __ | 25% completed and in progress.
50 | Pr.Sh-S | 62 | Imp./Stg. of road by pdg. dense carpeting in E-block, Jhilmil Colony and A & B block Vivek Vihar Ph-II AC-44. SH:- M/P | 2008-09 | 24.86 | M/P-1.70 | __ | M/P-1.70 | 15 | __ | __ | 10 | Completed in 2009-10
51 | Pr.Sh-S | 62 | Const./Imp. of footpath from G.T.road. to J&K Pkt. Dilshad garden AC-44. | 2008-09 | 25 | F/Path-0.70 | 10 | F/Path-0.70 | 8 | __ | __ | 10 | Completed in 2009-10
52 | Pr.Sh-S | 62 | Imp. of Gali No.1 by pdg. RMC & construction of drain in Friends Colony. | 2008-09 | 24.5 | CC 0.95 | __ | __ | 24.5 | CC 0.95 | __ | __ | Estimate is under A/A & E/S
53 | Pr.Sh-S | 62 | Imp. of drainage system parallal to Metro Line under G.T.Road flyover by construction of drain with culverts of various entrance points in Friends Colony Galis. | 2008-09 | 22.5 | Drain 0.60 Culvert 8 NO. | __ | __ | 22.5 | Drain 0.60 Culvert 8 NO. | __ | __ | Estimate is under A/A & E/S
54 | Pr.Sh-S | 62 | Improvement and Stg of road and drainage systems from G.T. Road Dharam Kanta to Malaria Office AC-62 | 2009-10 | 128 | Drain 0.50 CC 1.00 Dense 1.00 | __ | __ | 30 | Drain 0.50 CC 0.30 | __ | __ | P/E concurred from fin. & DFA of PE sent for A/A & E/S.
55 | Pr.Sh-S | 62 | Re-const. of drain along railway track from tolet block to drain no. 1 in Bihari colony AC-62 | 2009-10 | 224.97 | Drain 1.05 | __ | __ | 50 | Drain 0.20 | __ | __ | Estimate concurred by fin. And DFA sent for A/A and E/S.
56 | Pr.Sh-S | 55 to 70 | One room for library at ground floor in each Community Center should be constructed by MCD project Deptt. SH:- C/O Library room at Bhola Nath Nagar | 2006-07 | 6 | 1 No. | __ | 80% | 6 | 20% | 2% | 2.5 | completed
NEW SCHEMES SANCTIONED ON 19.05.10
1 | M-IV | 58 | Stg. of Mandawali main road from RUB to M.C.Pry.School by pdg. Mastic | 2010-11 | 93.5 | Mastic 2.85 | __ | __ | 10 | Masic 0.30 | __ | __ | Tender received and sent to fin. For approval of rate and agency.
2 | M-IV | 58 | Remodelling of drain on main market road Shakarpur from H.No. U-38 to R-30 in Shakarpur | 2010-11 | 44.8 | Drain 0.80 | __ | __ | 44.8 | Drain 0.80 | __ | __ | Tender due on 19.01.2011
3 | M-I | 58 | Dev. of road and intersection by pdg. Mastic asphalt from H.No. N-8 to N-33 and N-34 to N-50 in N Block and Keshav Marg Gali No. 4 & 5 in Guru Ram Dass Nagar | 2010-11 | 25 | Mastic 0.80 | __ | __ | 25 | Mastic 0.80 | __ | __ | Estimate is under A/A & E/S
4 | M-I | 58 | Dev. of lane by pdg. RMC and D/S from H.No. L-107 to L-36 and L-108 to L-35 in Laxmi Nagar | 2010-11 | 25 | Drain 0.40 CC 0.60 | __ | __ | 25 | Drain 0.40 CC 0.60 | __ | __ | Estimate is under A/A & E/S
5 | M-I | 58 | Dev. of lanes of Ramesh Park from R-82/4 to R-90, R-103/7 to R-91/B, R-114/2 to R-109B and R-94 to R-105 by providing RMC | 2010-11 | 18.39 | Drain 0.20 CC 0.35 | __ | __ | 18.39 | Drain 0.20 CC 0.35 | __ | __ | Tender called.
6 | Pr.Sh-S | 56 | Improvement of lanes of DDA Flats, C-Block (left out) lanes and D-Block by providing drain and RMC in Gazipur Dairy from in ward no. 214 | 2010-11 | 517.08 | Drain 10.25 CC 10.25 | __ | __ | 10 | Drain 0.10 CC 0.10 | __ | __ | Under Tender
7 | M-IV | 57 | Reconstruction of drain on samaspur road from Pataparganj road to back side of Delhi Police Aptt. In ward no. 220 | 2010-11 | 99.87 | Drain 1.10 | __ | __ | 10 | Drain 0.10 | __ | __ | Estimate sent to fin. For A/A & E/S
8 | M-IV | 57 | Remodelling of Nalla of Mandawali main road from Kalyan Marg to Sriram Chowk in ward no 218 | 2010-11 | 96.41 | Drain 0.90 | __ | __ | 10 | Drain 0.10 | __ | __ | Estimate sent to fin. For A/A & E/S
9 | M-I | 60 | Imp. of drain from Happy English School to Geeta Colony Kachcha Drain in Geeta Colony ward no. 230 | 2010-11 | 45.5 | Drain 1.00 | __ | __ | 10 | Drain 0.10 | __ | __ | Estimate is under A/A & E/S
10 | Pr.Sh-S | 60 | Imp./Stg. of roads pdg. Dense carpeting at Mandir Marg from road no. 57 to Market road, Lal Quarter Crossing to Raghunath Mandir, Satnam road from chhachi Building to Jheel Chowk, Sethi Chowk to Ghondli Chowk and Gurudwara road at link road Chander Nagar | 2010-11 | 107.69 | Dense 5.72 | __ | __ | 10 | Dense 0.50 | __ | __ | Estimate is under A/A & E/S
Target Achievement (Phy./ Financial) report of Schemes under TYADB of Shah. (North) Zone for the year 2010-11 upto 31.12.10
1 | Pr.Sh-N-I | 62 | Community Center at C-Block, Dilshad Colony AC 45. | 2006-07 | 200 | 1 No. | 158 | 100% | 6.02 | __ | __ | 6.31 | Completed in 2009-10
2 | Pr.Sh-N-I | 62 | C/o RCC box culvert across PWD road No.62 to connect the existing drain from Bus depot to Dilshad Colony Pump House AC-45. | 2008-09 | 24.25 | Drain 0.30 | __ | __ | 24.25 | Drain 0.30 | __ | __ | Scheme to be dropped
3 | Pr.Sh-N-I | 62 & 63 | Imp/Stg. of Main / Internal Road / Drains and side berms in Dilshad Colony, Shah. in AC-45. | 2007-08 | 270 | Drain 3.70 km Dense-10 km B/P-4.00 km | 142 | Drain 3.40 km Dense-10.00 km B/P-2.20 km | 130 | Drain 0.30 km Dense-10 km B/P-1.8km | Drain 0.30 B/P 0.90 | __ | (i) 65% completed and In progress. (ii) Dense work completed
4 | Pr.Sh-N-I | 62 / 63 | Improvement/Stg of road from PWD road No.62 to Road No 64 along Dilshad Colony, Shah, North AC-62 & 63 | 2009-10 | 98.85 | Drain 0.38 Dense 2.37 Mastic 0.50 | __ | __ | 98.85 | Drain 0.38 Dense 2.37 Mastic 0.50 | __ | __ | (i) Dense work completed. (ii) Work order issued, to be started.
5 | Pr.Sh-N-I | 63 | Const. of drain from E-1, Block Nand Nagri to E-4 Block Nand Nagari (both side) Shah.(N). | 2007-08 | 94 | Drain-0.85 km | 72 | Drain-0.80 km | 22 | Drain-0.05 | Drain-0.05 | __ | Completed
6 | Pr.Sh-N-I | 63 | Imp. & Stg. of road along G.T.B. Enclave from road no.69 to road no.68 in AC-45 Shah.(N). SH ;- C/o of drain,footpath & Imp.of side berm. | 2008-09 | 155 | Dense-3.06 CC-2.50 Drain-0.30 | __ | __ | 155 | Dense-3.06 CC-2.50 Drain-0.30 | __ | __ | (i) Drain work just started. (ii) Dense work completed .
7 | Pr.Sh-N-I | 63 | Improvement /Stg of internal roads of Pocket F GTB Enclave by mastic AC-63 | 2009-10 | 44.18 | Mastic 1.80 | __ | __ | 44.18 | Mastic 1.80 | __ | __ | Tender received & sent for approval of rate and agency.
8 | Pr.Sh-N-I | 64 | Covering of 52 cusec Bhagwan Pur Khera drain by steel mash in AC-47. | 2007-8 | 149.21 | Wire mash | __ | __ | 149.21 | Wire mash | __ | __ | Scheme to be dropped
9 | Pr.Sh-N-I | 64 | Imp.of internal storm water drainage system at DDA, MIG flats, East of Loni road in AC-47. | 2008-09 | 55.4 | Drain-2.00 | __ | __ | 55.4 | Drain-2.00 | Drain 0.50 | __ | 25% completed & in progress.
10 | Pr.Sh-N-I | 64 | Imp. of drain from Sant Ravidass Temple to Drain No. 1 in Welcome Seelampur Phase - III AC-64 | 2009-10 | 90.55 | Drain 0.33 | __ | __ | 90.55 | Drain 0.33 | __ | __ | Estimate Approved and is under technically sanction.
11 | Pr.Sh-N-II | 65 | Widening I/S of main roads in Seelampur AC 49. | 2006-07 | 274.37 | Wid. 12 km. Dense 12 km. | 107 | Wid. 12 km., Dense-12 KM | 167 | __ | __ | 189 | Completed in 2009-10
12 | Pr.Sh-N-II | 65 | C/o Barat Ghar CPJ Block, Seelampur AC 49. | 2006-07 | 250 | 1 no. | __ | __ | 250 | 1 No. | 40% | 32 | 40% completed & in progress
13 | Pr.Sh-N-II | 65 | Imp. to Gokulpur drain by const. RCC drain from RDO to 790m and 1120 to 1560m along with CC pavment on both sides of drain from RDOm to 1560 m and const. of culverts in AC-49 and AC-50. | 2007-08 | 1373.65 | Drain 1.23, CC-2.05 & culvert- 3 Nos. | __ | __ | 1030 | Drain 1.23, CC-2.05 & culvert- 3 Nos. | 15% | 99.47 | 15% completed & in progress
14 | Pr.Sh-N-II | 65 | Imp. of Maujpur road and Noor-elahi road in AC-51 | 2007-08 | 70 | Dense-5.00 | __ | __ | 70 | Dense-5.00 | __ | __ | Scheme dropped
15 | Pr.Sh-N-II | 65 | Remodelling of main drain on Maujpur road. | 2008-09 | 180 | Drain 1.32 | __ | __ | 180 | Drain 1.32 | __ | __ | Work order to be issued.
16 | Pr.Sh-N-II | 65 | Construction of underground sumpwell at Zeenat Mahal Sr Sec School road No 66 North Zone AC-65 | 2009-10 | 100.8 | 1 No. | __ | __ | 100.08 | 100% | 10% | __ | 10% completed and in progress.
17 | Pr.Sh-N-II | 65 | Construction of drain from CPJ culvert to Shiv Mandir in C-250/ AC-65 | 2009-10 | 69.63 | Drain 0.18 | __ | __ | 69.63 | Drain 0.18 | __ | __ | Tender received and sent to fin. For conc.
18 | Pr.Sh-N-II | 65 | I/S of road from zero pusta to Brahampuri culvert and from Northern Engg. College to over head tank Gautam puri AC-65 | 2009-10 | 283 | Dense 4.16 Drain 2.28 CC 1.24 F/Path 1.40 C/Verge 0.70 | __ | __ | 250 | Drain 2.28 CC 1.24 | __ | __ | Work order issued, to be started.
19 | Pr.Sh-N-II | 66 | Re-modelling of Moni Baba Nalla from gali No.1 to Gokul Pur Drain AC-50. | 2004-05 | 50 | Drain-0.84 | 23.5 | Drain 0.78 | 26.5 | Drain 0.06 | Drain 0.06 | 21.78 | Completed.
20 | Pr.Sh-N-II | 66 | Community Center at Usmanpur AC 50. | 2006-07 | 250 | 1 No. | __ | __ | 250 | 1 No. | __ | __ | Land yet to be handed over by DDA.
21 | Pr.Sh-N-II | 66 | Remodelling of main Outfall drain of Yamuna Vihar. | 2008-09 | 220 | Drain 2.28 | __ | __ | 220 | Drain 2.28 | Drain 0.30 | __ | 10% completed and in progress.
22 | Pr.Sh-N-II | 66 | Improvement/Stg of Gali No.1 Brahmpuri, AC-66 | 2009-10 | 65.12 | CC 0.86 | __ | __ | 65.12 | CC 0.86 | __ | __ | Tender recived, work executed by other agency and the case is under consideration for dropping.
23 | Pr.Sh-N-II | 67 | Community Center at Ghonda Chowk AC 51. | 2006-07 | 362.91 | 1 No. | __ | 2% | 290 | 98% | 28% | 87.77 | 30% completed & in progress
24 | Pr.Sh-N-II | 67 | Improvement/Satg of Noor-E-Elahi road from DTC Yamuna Vihar Deport to Ghonda Chowk AC-67 | 2009-10 | 187.27 | CC 2.95 | __ | __ | 139.33 | CC 2.95 | CC-2.95 | 140.29 | Completed
25 | Pr.Sh-N-I | 68 | C/o Community Hall at Gokulpur village. | 2006-07 | 115.45 | 1No. | 113 | 99% | 2.45 | 1% | 1% | __ | Completed
26 | Pr.Sh-N-I | 68 | Imp.& stg.of loni road from wazirabad road to UP border in Shah.(N). | 2007-08 | 94.39 | (i) C.C-1.10 (ii) F/Path & C/verge | __ | 5% | 94.39 | (i) C.C-1.10 (ii) F/Path & C/verge | (i) C.C-1.10 (ii) F/Path & C/verge | 130 | Completed
27 | Pr.Sh-N-I | 68 | Imp of drainage system by pdg RCC drain along right side on Sewadham road in AC-46 Shah. North Zone. | 2007-08 | 275 | Drain-0.65 | __ | __ | 137.5 | Drain-0.60 | __ | __ | Tender received and is under negotiation.
28 | Pr.Sh-N-I | 68 | I/S of post office road, Police Station Road and connecting roads by dense carpeting in Nand Nagari. | 2008-09 | 76.3 | Dense 4.80 | __ | __ | 76.3 | Dense 4.80 | Dense 4.80 | 50 | Completed.
29 | Pr.Sh-N-I | 68 | Improvement of Loni road by pdg cc pavement Wazirabad road to Loni UP Border, AC No.68 | 2009-10 | 170 | CC 2.16 | __ | __ | 170 | CC 2.16 | CC 0.70 | __ | 30% completed & in progress
30 | Pr.Sh-N-II | 70 | C/o Barat Ghar at Village Khajuri Khas AC 52. | 2006-07 | 250 | 1 No. | _ | _ | 250 | 1 nos. | _ | __ | Land to be handed over by Revenue Deptt.
31 | Pr.Sh-N-II | 70 | Widening/ I/S of Karawal Nagar road from Wazirabad road to Sherpur Chowk in Phase-I AC 52. | 2006-07 | 485.08 | wmm-2.80, BM 1.08, AC 2.80, drain 0.54, CC 0.37 km | 155 | wmm-0.10, Drain 0.25, CC 0.37 km | 330 | Dense 2.80 drain 1.40 | (i) 30% completed. (ii) the remaining work 10% completed. | 74.42 | 30% Completed and the remaining work 10% completed and in progress.
32 | Pr.Sh-N-II | 69 & 70 | Widening/Imp./Stg. of Kerawal Nagar Raod from Wazirabad Raod to Shiv Vihar Tiraha Shah. North AC-52. | 2007-08 | 2178.33 | Wid 12.8, Dence12.80, &Cc 4.36 Drain-6.40 | 203 | Land acquired charges | 370 | Drain-0.70
NEW SCHEMES SANCTIONED ON 19.05.10
1 | Pr.Sh-N-I | 64 | Imp. & Stg. of main road Welcome Seelampur Ph-III and Subhash Park (Extn.) | 2009-10 | 97.61 | Dense 2.50 Mastic 0.50 CC 0.40 | __ | __ | 10 | CC 0.04 Mastic 0.05 Dense 0.25 | __ | __ | Tender received and is under justification.
2 | Pr.Sh-N-I | 63 | Shifting of New Seema Puri pump house at road no. 70 and laying of rising main in ward no. 242 | 2009-10 | 297.2 | 1 No. | __ | __ | 10 | 5% | __ | __ | PE is under checking
3 | Pr.Sh-N-I | 63 | Construction of Community Hall at A-Block Dilshad Colony | 2009-10 | 762.06 | 1 No. | __ | __ | 10 | 2% | __ | __ | Estimate concurred from fin. & sent for A/A & E/S