## TYADB
Municipal Corporation of Delhi
Engineering Department
Target Achievement (Phy./ Financial) report of Schemes under TYADB of Shah. (South) & Shah. (North) Zones for the year 2009-10 upto 30.09.09
Sl. No. | AC | Name of Scheme | Year of passing by TYADB | Total outlay of scheme | Phy. Target of the scheme | Financial Achievement upto 31.03.09 | Physical Achievement upto 31.03.09 | Finacial Target for 2009-10 | Phy Target for 2009-10 | Phy achievement as on 30.09.09 | Fin achievement as on 30.09.09 | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Regular Scheme | [8 empty] | Phy. Achievement |  | Fin. Achievement
1 | 55 To 70 | Development works with the consent of area MLA. | 2009-10 | 1680 | M/P-2.60, CC-27.10, Dr.-15.40, Dense-8.85, Mastic-19.60, High mast-26 Nos | 1306.15 | M/P 2.60, CC-24.30 Dr.-15.40, Mastic-13.25 Dense 8.85 High mast 26Nos. | 1040 | M/P 1.00, CC-24.30 Dr.-6.20, Mastic-5.58 Dense 7.00 High mast 25Nos. | M/P 0.50,Drain - 2.00 CC - 5.20 Mastic - 2.25 , Dense -0.50 , High Mast 6 Nos. | 217.39 | 32% Completed and remaining are at different stages like under approval, under tender and under award.
2 | 55 To 70 | Development works in approved/ UR Colonies. | 2009-10 | 400 | M/P-1.20, CC-8.70, Dr.-5.80, Mastic-1.80, Dense-1.50 | 644.16 | CC-8.70, M/P1.20 Dr.-5.80, Mastic -1.80 Dense- 1.50 | 400 | CC-8.60, M/P1.10 Dr.-5.70, Mastic -1.85 Dense- 1.40 | Drain - 2.00 CC - 3.50 M/P- 0.40 | 107.85 | 36% Completed and remaining are at different stages like under approval, under tender and under award.
3 | 55 To 70 | Environment improvement works. | 2009-10 | 200 | Parks (approx. 35 Nos.) | 231.24 | Parks (approx. 35 Nos.) | 200 | Parks (approx. 30 Nos.) | 9 No. | 50.21 | 26% Completed and remaining are at different stages like under approval, under tender and under award.
4 | 55 To 70 | Development works for strengthening of road. | 2009-10 | 400 | Dense-12.50, Mastic-8.50 | 403.13 | Dense-12.50, Mastic-8.50 | 400 | Dense-10.70, Mastic-6.50 | Dense - 5.20 , Mastif 4.50 | 150.6 | 45% Completed and remaining are at different stages like under approval, under tender and under award.
5 | 55 To 70 | Construction of new Community Hall. | 2009-10 | 900 | C/Hall, 6 Nos. | 519.85 | C/Hall, 9 Nos. | 900 | C/Hall, 9 Nos. | C/Hall - 9 Nos. In progress | 198.64 | 9 In progress and 9 Nos. are at diffrent stages.
6 | 55 To 70 | Develoment of street light and High mast light. | 2009-10 | 200 | 68 Nos | 148.07 | 60 Nos | 200 | 65 Nos | 7 Nos. | 22.5 | 11% completed and in progress.
Target Achievement (Phy./ Financial) report of Schemes under TYADB of Shah. (South) & Shah. (North) Zones for the year 2009-10 upto 31.08.09
Ongoing Scheme
Sl. No. | AC | Name of Scheme | Year of passing by TYADB | Total outlay of scheme | Phy. Target of the scheme | Financial Achievement up to 31.03.09 | Physical Achievement upto 31.03.09 | Finacial Target for 2009-10 | Phy Target for 2009-10 | Phy. achievement as on 30.09.09 | Fin. achievement as on 30.09.09 | Remarks
1 | 55 | Widening & Imp. of Khudi Ram Bose Marg from Noida road to Block No. 15 in Trilok Puri AC 37 Sh. (S) Zone. (I) Widening of road by providing M/P and construction of Central verge. (ii) Imp. & Stg. of road providing dense carpeting. | 2005-06 | 177 | M/P-4.00, F/P-1.00, CV-3.00, Shifting of Elec/Tele Poles, Dense-8.00 | 22 | (i) 80% (ii) 80% | 155 | M/P-0.70 CV-0.50 | (i) 90% (ii) 100% | 109.04 | (i) 90% completed and held up due to permission of cuttting trees awaited from forest deptt. (ii) Completed
2 | 55 | C/o Community Hall at Chilla village AC-37 | 2006-07 | 106 | 1 No. | 30 | 65% | 76 | 1 No | 98% | 60.5 | 98% completed and inprogress.
3 | 55 | Khel Parisar 1/3 portion at Block 7-8, Trilok Puri in AC-37 | 2007-08 | 270 | 1 No. | Nil | Nil | 100 | 40% | Nil | Nil | Tender called three times but no response, separate tender for B/Wall received and DFA sent for approval for rate and agency..
4 | 55 | Imp. of road from Block No. -13 to 18 Trilok Puri in AC-37. | 2008-09 | 350.6 | Dense-20.00 | __ | __ | 350 | Dense-20.00 | __ | __ | Tender received and sent to standing committee for approval of rate and agency
5 | 55 | I/S of Chilla Road, Samachar Apptt. Road & Road near ASN Public School & Kalka Apptt. By Carpetting. | 2008-09 | 172.71 | Dense 11.50 | __ | __ | 100 | Dense 7.00 | __ | __ | Sent to corporation for A/A
6 | 55 | Improvement & Strengthening of road of Pkt-I and Pkt II Mayur Vihar, Phase-I, Idgah Road AC-55 | 2009-10 | 130 | Dense 4.60 | __ | __ | 15 | Dense 0.20 | __ | __ | PE sent to finance for concurrence
7 | 56 | I/s of main roads and links of A & B Block of Gharoli Dairy Farm AC 38. | 2006-07 | 215 | Dense -8.00 km | 61.95 | 40% | 155.03 | Dense -4.80 km | Dense -4.80 km | 209.41 | Completed
8 | 56 | Imp. of nalla at bus stand karayan puri | 2006-07 | 45.69 | Drain-0.70 | 31.82 | 80% | 13.87 | Drain-0.14 | Drain-0.14 | 46.5 | Completed
9 | 56 | imp. of internal roads in Block A,B & C New Kondli reselltlemnet colony in AC 38 | 2007-08 | 98.85 | RMC-3.01 & drain-1.55 | 74.43 | Drain 1.55, RMC 2.20 | 24.42 | RMC-0.81 | RMC-0.81 | 98.5 | Completed
10 | 56 | Imp. of road by pdg mastic asphalt in Brijpuri, Khureji, Radhey Shyam Park and Hasanpur village in AC-43, Shahdara South. | 2007-08 | 71 | Mastic-2.30 | Nil | Nli | 71 | Mastic-2.30 | Nli | Nil | The case is processed for re-tendering.
11 | 56 | Imp. / Stg. of road by pdg. RMC in diff. Pkt. / Blocks in Mayur Vihar Ph-III AC-38. | 2008-09 | 121.36 | CC 5.28 | 52 | CC 3.15 | 69.36 | CC 2.13 | CC 2.13 | 127 | Completed
12 | 56 | Imp. of road, footpath & drain from Ghazipur Red Light to T-Section of Kondli Village. | 2008-09 | 280 | Dense 4.80 F/Path 2.70 Drain 2.70 | __ | __ | 20 | Drain 1.50 | __ | __ | P/E concurred by finance and DFA sent to Commissioner for apporval ( letter sent to I & FC deptt. For widening.
13 | 56 | Imp of roads by pdg RMC in left out link lanes of Pkt A-1, A-2, A-3 Mayur Vihar Phase-III, Shahdara AC-56 | 2009-10 | 155.9 | CC 5.95 | __ | __ | 15 | CC 0.25 | __ | __ | PE under checking.
14 | 57 | Community Center at Khichri Pur AC 38 (Demolition and Re-Const.) | 2006-07 | 103.28 | 1 No. | Nil | 15% | 103.28 | 1 No. | 55% | 28.1 | 55% Completed and in Progess.
15 | 57 | C/o Community Hall at OCF Pkt Mayur Vihar Ph-II | 2006-07 | 111 | 1 No. | 68 | 70% | 43 | 1 no | 97% | 90 | 97% work completed and inprogress.
16 | 57 | C/o drain from ayappa mandir road to noida raod drain ( Shah Link Road ) in Pkt.- IV M.Vihar - I in AC 40 | 2007-08 | 50 | Drain -0.70 | 15 | Drain 0.18 | 35 | Drain -0.35 | Drain 0.18 | 15 | 50% work completed and remaiming work is not required & the case is processed for closing.
17 | 57 | Stg. of internal road of A, B, C, D,E,and F Pkt. in Mayur Vihar Phase-II in AC-38 Shah.(S). | 2008-09 | 130 | Dense-9.10 | __ | __ | 130 | Dense-9.10 | Dense-9.10 | 185 | completed
18 | 57 | Remodeling of drain from NH-24 to Kotla Road along the Khichripur road. | 2008-09 | 90 | Drain 1.20 | __ | __ | 15 | Drain 0.30 | __ | __ | Tender called, due on 16.10.09.
19 | 57 | Improvement of drainage system and road dense carpeting from Kalyan Marg to Engineers Apptt to Railway culvert AC-57 | 2009-10 | 240 | Drain 0.60 Dense 3.80 Mastic 2.20 | __ | __ | 100 | Drain 0.60 Dense 1.50 | __ | __ | Fin. Concurred the case, DFA sent for approval.
20 | 57 | Stg of road by pdg RMC in Blc A, E and F in East Vinod Nagar AC-57 | 2009-10 | 140 | CC 5.50 | __ | __ | 80 | CC 3.10 | __ | __ | Fin. Concurred the case, DFA sent for approval.
21 | 58 | Imp of drainage system by constructing drain on main Mandawali road in AC-39 Shah South. | 2007-08 | 195 | Drain-2.50 | Nil | Drain 1.50 | 195 | Drain-2.00 | Drain 2.00 | 30 | Completed .
22 | 58 | I/S of road & intersection by pdg mastic asphalt in lane No.3 to 10, Lalita Park and lanes parallel to main road Laxmi Nagar from main Bazar to H.No.84 and opposite M.C.Pry School Kishan Kunj in AC-40 | 2007-08 | 50 | Mastic-1.9 | __ | Mastic 0.10 | 50 | Mastic-1.80 | Mastic 1.08 | 24.5 | 60% Completed and in progress
23 | 58 | Remodelling of drain from Gurudwara Laxmi Nagar to Marginal Bund in AC-40 | 2007-08 | 33 | Drain-1.7 | Nil | Drain- 1.60 | 33 | Drain-0.10 | Drain-0.10 | 27.82 | Completed
24 | 58 | Imp of drainage system by constructing drain from main Mandawali Road towards Sadbhawana Appartment. AC-39. | 2008-09 | 195 | Drain 1.50 | 44 | Drain 0.32 | 100 | Drain 1.18 | Drain 0.90 | 44 | 75% Completed and in progress.
25 | 58 | Stg. of Budha Marg from Shanti Marg to Sadbhawana Chowk by pdg. Mastic in Mandawali Fazalpur in Ward No223/39. | 2008-09 | 24.77 | Mastic 0.94 | __ | __ | 24.77 | Mastic 0.94 | __ | __ | Work order issued (Held up due to DJB cutting.)
26 | 58 | Stg. of Gali No.1,2,3,7 & its links by pdg. Mastic in Master Block Shakarpur Ward No.223/39. | 2008-09 | 24.43 | Mastic 0.94 | __ | __ | 24.43 | Mastic 0.94 | __ | __ | Work order issued (Held up due to DJB cutting.)
27 | 58 | Stg. of road near H.No.D-1, A-1 and A-70 by pdg. Mastic in Pandav Nagar Ward No224/39. | 2008-09 | 24 | Mastic 0.94 | __ | __ | 24 | Mastic 0.94 | Mastic 0..75 | __ | 80% Completed and Inprogress.
28 | 58 | Const. of road along Pusta from C/Hall Ramesh Park to SDM office AC-40. | 2008-09 | 100 | M/P-1.5 | __ | __ | 100 | M/P-1.5 | __ | __ | Estimate to be prepared as per the revised drawing received from RITES Ltd.
29 | 58 | C/o foot over bridge connecting Mandawali & South Ganesh Nagar near RUB Madhuban. | 2008-09 | 100 | 1 No. | __ | __ | 5 | 5% | __ | __ | Proposal under approval.
30 | 58 | C/o Community Hall at Satabdi Park Mandawali. | 2008-09 | 231.56 | 1 No. | __ | __ | 50 | 20% | __ | __ | Held up due to water body
31 | 58 | I/S of main Mkt. Shakarpur Mkt. road by pdg. mastic from Vikas Marg to Mother Dairy road. | 2008-09 | 49.96 | Mastic 1.80 | __ | __ | 49.96 | Mastic 1.80 | __ | __ | Tender received and fair preamble sent to standing committee for approval of Rate and Agency
32 | 58 | I/S of Mangal Bazar road by pdg. Mastic asphalt form Patparganj Road to Main Bazar Laxmi Nagar. | 2008-09 | 30 | Mastic 1.30 | __ | __ | 30 | Mastic 1.30 | __ | __ | Tender received & sent for approval of rate & agency.
33 | 58 | Stg of road in South Ganesh nagar H.No.27,91,64,31,61,P45 H.No.412,418,712,730,739 near M.C. Primary School by pdg Mastic asphalt-II Shakarpur AC-58 | 2009-10 | 76.58 | Mastic 3.35 | __ | __ | 40 | Mastic 1.70 | __ | __ | Tender called, due on 16.10.09.
34 | 58 | St road by pdg mastic asphalt in Dayanand Block and WA Block and WB Block Shakarpur AC-58 | 2009-10 | 68.94 | Mastic 2.90 | __ | __ | 40 | Mastic 1.50 | __ | __ | Tender to be called.
35 | 58 | Stg of road by pdg mastic in upadhaya Block School Block in Shakarpur AC-58 | 2009-10 | 72.98 | Mastic 3.10 | __ | __ | 40 | Mastic 1.90 | __ | __ | Tender to be called.
36 | 58 | Remodeling of drain from A-15 to Flood drain and from shop plot No.28 to Flood drain in Pandav Nagar AC-58 | 2009-10 | 50 | Drain 2.10 | __ | __ | 20 | Drain 1.00 | __ | __ | Tender to be called.
37 | 59 | Imp. of Kasturva Nagar Drain in Ward No. 80 Shahdara (S) Zone AC 43. | 2005-06 | 204.56 | Drain-0.40 Km. | 123.64 | Drain 0.30 | 80.92 | Drain-0.10 Km. | Drain 0.05 | 123.64 | 80% completed and inprogress.
38 | 59 | Imp.of road by pdg mastic asphalt in D-Block Preet Vihar, E-Block Preet Vihar, Madhuban Colony, Swasthaya Vihar and New Rajdhani Enclave in AC-43, Shahdara South. | 2007-08 | 190 | Mastic-5.10 | 81.27 | Mastic 4.60 | 108.73 | Mastic-0.50 | Mastic-0.50 | 81.27 | Completed
39 | 59 | Imp. of drain & road in Sainy Enclave AC-43. | 2008-09 | 25 | Dr.0.50, C.C.-0.30, Mastic-0.30 | __ | __ | 25 | Dr.0.50, C.C.-0.30, Mastic-0.30 | __ | __ | Estimate under sanction.
40 | 59 | Const . of C/Hall at OCF Pkt. in CGHS Mandawali Fazalpur near Sidh Appartment in AC-43 Shah.(S). | 2008-09 | 120 | 1 No. | __ | __ | 80 | 70% | 5% | __ | 5% completed and held up due to revise plan.
41 | 59 | Const. of C/Hall at OCF Pkt. In CGHS Mandawali Near Balco Appartment AC-43 Shah.(S) near Patparganj depot. | 2008-09 | 125 | 1 No. | __ | __ | 80 | 70% | 35% | __ | 35% completed and inprogress
42 | 59 | C/o Community Hall at Vishwas Nagar AC-43. | 2008-09 | 178 | 1 No. | __ | __ | __ | __ | __ | __ | Land yet to be handed over by DDA.
43 | 59 | Remodeling of footpath from Sharad Vihar to End of Ram Vihar AC-43 | 2008-09 | 93 | F/Path-2.20 | __ | __ | 93 | F/Path-2.20 | __ | __ | Tender received and fair preamble sent for approval of rate and agency.
44 | 59 | C/o Community Hall at Mandawali. | 2008-09 | 170.76 | 1 No. | __ | __ | 50 | 30% | __ | __ | Work order to be issued.
45 | 59 | Stg. of internal road by pdg. mastic asphalt in D-Block, Vivek Vihar. | 2008-09 | 23.2 | Mastic 0.90 | __ | __ | 23.2 | Mastic 0.90 | __ | __ | Estimate is under A/A & E/S
46 | 59 | Stg. of internal roads by pdg. mastic asphalt in Gujrat Vihar. | 2008-09 | 18.5 | Mastic 0.75 | __ | __ | 18.5 | Mastic 0.75 | __ | __ | Estimate is under A/A & E/S
47 | 59 | Remodelling of Kasturba Nagar drain (Ph-II) from Shastri Gali to Nehru Gali in Vishwas Nagar AC-59 | 2009-10 | 301.65 | Drain 0.45 | __ | __ | 20 | Drain 0.04 | __ | __ | Estimate under sanction.
48 | 59 | Stg of road by mastic asphalt in Dayanand Vihar, Defence Enclave and road between Swasthya Vihar and Gujrat Vihar AC-59 | 2009-10 | 91.08 | Mastic 3.90 | __ | __ | 10 | Mastic 0.39 | __ | __ | Estimate under sanction.
49 | 60 | I/S of road by pdg Mastic Asphalt in South Anarkali & Old Govind Pura in AC-42 | 2007-08 | 120 | Mastic-4.10 | __ | __ | 120 | Mastic-4.10 | __ | __ | Tender called, due on 15.10.09
50 | 60 | Const. of drain near Chhachi builidng to near Chander Nagar Govt School in Krishna Nagar, AC-42 | 2007-08 | 108.37 | Drain-1.50 | Nil | Nil | 108.37 | Drain-1.50 | Nil | Nil | Tender received and fair preamble sent to Stadning Committee for approval of rate & agency.
51 | 60 | Imp./Stg. of road by pdg. Dense carpeting in PD Vihar , Kishan Kunj Road, back of Ramesh Park C/Hall Road, Mahila Colony Road, block -11 Geeta Colony, West Guru Angad Nagar & Raja Ram Kohli Marg in AC-40. | 2008-09 | 157.65 | Dense-11.10 | __ | __ | 157.65 | Dense-11.10 | Dense- 11.10 | 157.65 | Completed
52 | 60 | Const. of C/Hall in block -12 Geeta Colony AC-40. | 2008-09 | 200 | 1 No. | __ | __ | 20 | 10% | __ | __ | Tender received & DFA sent for approval of rate and agency .
53 | 60 | Const. of C/Hall in block -10 Geeta colony AC-40. | 2008-09 | 212 | 1 No. | __ | __ | 80 | 40% | 10% | __ | 10% completed and inprogress
54 | 60 | Pdg. Mastic asphalt in New Layal Pur, Gyan Park & Krishna Nagar AC-42. | 2008-09 | 100 | Mastic-3.80 | Nil | Mastic 1.50 | 100 | Mastic-3.80 | Mastic 1.50 | 16.6 | 40% completed and held up due to public resistance.
55 | 60 | I/S of roads by pdg. Dense carpeting of road from Pusta Road via Rani Garden to 17 - Block Geeta Colony, Gurudwara Road Block-7, road Nat Taj Appartment, Work Centre Road and R-Block Ramesh Park. | 2008-09 | 253.64 | Dense 15.50 | __ | __ | 100 | Dense 3.50 | __ | __ | Tender received and sent to fin. For conc.
56 | 60 | Stg. of Parvana road by pdg. CC pavement from Road No.-57 to Patparganj Road. | 2008-09 | 169.17 | CC 4.50 | __ | __ | 50 | CC 1.20 | __ | __ | P/E concured for finance and DFA sent for A/A and E/S.
57 | 61 | Remodelling of Gandhi Nagar and Raghubar pura Drain SH:- C/o drain in Gandhi Nagar (One side) from Kailash Nagar to Jheel Chowk. | 2001-02 | 207 | Drain-1.50 Km. | 23 | Drain 0.10 | 184 | Drain-1.40 | Drain 0.50 | 61 | 35% Completed and in progress
58 | 61 | Const. /Remodelling of Gandhi Nagar drain from Pusta to Jheel Chowk in AC-41 | 2007-08 | 175 | Drain-.1.30 Km | 68 | Drain 0.22 | 107 | Drain-1.08 Km | Drain 0.85 | 110 | 80% Completed and in progess
59 | 61 | Constuction of Ayurvedic Dispensary Gali No.5, Reghubar Pura, Gandhi Nagar AC-61 | 2009-10 | 49 | 1 No. | __ | __ | 5 | 5% | __ | __ | PE concurred from fin. & detailed estamate is under prepration.
60 | 62 | Community Center at Bhola Nath Nagar near MCD Pry School AC 44. | 2006-07 | 152 | 1 No. | 40 | 45% | 100 | 1 No. | 90% | 40 | 90% completed and inprogress.
61 | 62 | Construction of bldg. of Poly Clinic in place of Civil Hospital at Chhota Bazar SH:C/o bldg for Chest Clinic (T.B. Clinic). | 2006-07 | 206 | 1 No. | 38.2 | 45% | 125 | 1 No | 75% | 38.2 | 75% cpmpleted and in progress.
62 | 62 | I/S of road by mastic asphalt from Bhola Nath Nagar (Road No. 57) to Babu Ram School to Metro Bridge in Shah. AC-44. | 2007-08 | 87.29 | Mastic-3.33 | __ | __ | 55 | Mastic-3.33 | __ | __ | Work awarded, notice has been issued to be contractor to start the work.(Court Case)
63 | 62 | I/S of road by pdg. Mastic asphalt from Geeta Bhawan to Mani Ram Mandir Road and Gali No. 5 in Behari Colony and GT Road from R- Block to Aggarwal Sweets Dilshad Garden in AC-44. | 2007-08 | 83.39 | Mastic-3.2 | __ | __ | 58 | mastic-3.2 | __ | __ | Work awarded, notice has been issued to be contractor to start the work.(Court Case)
64 | 62 | I/S of road by pdg Mastic Asphalt in Jwala Nagar, Kasaiwara, Jharkhandi road, Ram Gopal Sharma Marg & Bhola Nath Nagar, DCP Office to Pandav road in AC-44. | 2007-08 | 92 | Mastic-2.00 | __ | __ | 92 | Mastic-2.00 | __ | __ | Tender received and the case is under negotiation.
65 | 62 | I/S of road by pdg Mastic Asphalt in A-Block, B-Block. Jhilmil, Janta flats Vivek Vihar and A&B Block, Vivek Vihar Ph-II in AC-44. | 2007-08 | 95 | Mastic-2.70 | __ | __ | 95 | Mastic-2.70 | Mastic-2.70 | 20 | Completed
66 | 62 | Community Center at C-Block, Dilshad Colony AC 45. | 2006-07 | 200 | 1 No. | 91 | 70% | 109 | 1 No. | 95% | 91 | 95% completed and In progress.
67 | 62 | Imp./Stg. of road by pdg. mastic asphalt in near A & B block, Jhilmil Colony AC-44. | 2008-09 | 24.75 | Mastic-0.95 | __ | __ | 24.95 | Mastic-0.95 | Mastic-0.95 | __ | Completed
68 | 62 | Imp./Stg. of road by pdg. mastic asphalt on main Govind Khand road AC-44. | 2008-09 | 83.4 | Mastic-3.10 | __ | __ | 83.44 | Mastic-3.10 | __ | __ | Tender received & fair preamble sent for approval of rate & agency.
69 | 62 | Imp./Stg. of road by pdg. mastic asphalt in Pratap Khand & Vishkarma Nagar AC-44. | 2008-09 | 83.4 | Mastic-3.20 | __ | __ | 84.4 | Mastic-3.20 | __ | __ | Tender received & fair preamble sent for approval of rate & agency.
70 | 62 | Imp./Stg. of road by pdg. dense carpeting in E-block, Jhilmil Colony and A & B block Vivek Vihar Ph-II AC-44. | 2008-09 | 24.86 | Dense-1.70 | __ | __ | 24.86 | Dense-1.70 | __ | __ | Tender received & fair preamble sent for approval of rate & agency.
71 | 62 | Const./Imp. of footpath from G.T.road. to J&K Pkt. Dilshad garden AC-44. | 2008-09 | 25 | F/Path-0.70 | __ | __ | 25 | F/Path-0.70 | __ | __ | Tender received & fair preamble sent for approval of rate & agency.
72 | 62 | Imp. of existing drains fro PWD Road to G-block, Old Seemapuri opposite Old Seemapuri police station. AC-45. | 2008-09 | 24.5 | Drain-1.20 | __ | __ | 24.5 | Drain-1.20 | Drain-0.72 | __ | 60% completed & in progress.
73 | 62 | Covering of drain from A-Block Seemapuri to round about along PWD road no.62 Ward No.240/45 | 2008-09 | 24.66 | Drain 0.40 | __ | __ | 24.66 | Drain 0.20 | Drain 0.16 | __ | 80% completed & in progress.
74 | 62 | C/o RCC box culvert across PWD road No.62 to connect the existing drain from Bus depot to Dilshad Colony Pump House AC-45. | 2008-09 | 24.25 | Drain 0.30 | __ | __ | 24.25 | Mrain 0.30 | __ | __ | Tender received sent to fin. for conc.
75 | 62 | Imp. of Gali No.1 by pdg. RMC & construction of drain in Friends Colony. | 2008-09 | 24.5 | CC 0.95 | __ | __ | 24.5 | CC 0.95 | __ | __ | Estimate is under A/A & E/S
76 | 62 | Imp. of drainage system parallal to Metro Line under G.T.Road flyover by construction of drain with culverts of various entrance points in Friends Colony Galis. | 2008-09 | 22.5 | Drain 0.60 Culvert 8 NO. | __ | __ | 22.5 | Drain 0.60 Culvert 8 NO. | __ | __ | Estimate is under A/A & E/S
77 | 62 | Improvement and Stg of road and drainage systems from G.T. Road Dharam Kanta to Malaria Office AC-62 | 2009-10 | 128 | Drain 0.50 CC 1.00 Dense 1.00 | __ | __ | 20 | Drain 0.50 CC 0.30 | __ | __ | Estimate is under A/A & E/S
78 | 63 | Const. of drain from E-1, Block Nand Nagri to E-4 Block Nand Nagari (both side) Shah.(N). | 2007-08 | 94 | Drain-0.85 km | Nil | 0.05 | 94 | Drain-0.85 km | Drain-0.35 km | Nil | 40% completed and In progress.
79 | 63 | Imp. & Stg. of road along G.T.B. Enclave from road no.69 to road no.68 in AC-45 Shah.(N). | 2008-09 | 155 | Dense-10.90 | __ | __ | 155 | (i) C.C- 2.50 (ii) Dense-10.90 | __ | __ | (i) Tender received for CC Pav.and tsent to fin. for conc. (ii) Tender called for dense carpeting, due on 29.10.09.
80 | 63 | Improvement /Stg of internal roads of Pocket F GTB Enclave by mastic AC-63 | 2009-10 | 44.18 | Mastic 1.80 | __ | __ | 20 | Mastic 0.90 | __ | __ | Estimate is under A/A & E/S
81 | 63 | Construction of Community Hall /Multipurpose Hall at A Block Dilshad Colony, Shahdara North AC-63 | 2009-10 | 498 | 1 No. | __ | __ | 10 | 10% | __ | __ | PE sanctioned and revise drawing is awaited.
82 | 64 | C/o of sump well and pump house at Bhola Nath Nagar. |  | 22.45 | 1 No. | 7.46 | 95% | 14.49 | 1 No. | 1 No. | 7.46 | Completed
83 | 64 | Covering of 52 cusec Bhagwan Pur Khera drain by steel mash in AC-47. | 2007-8 | 149.21 | Wire mash | __ | __ | 149.21 | Wire mash | __ | __ | The case is under study of feasibility for covering of drain.
84 | 64 | Imp.of internal storm water drainage system at DDA, MIG flats, East of Loni road in AC-47. | 2008-09 | 55.4 | Drain-2.00 | __ | __ | 55.4 | Drain-2.00 | __ | __ | Work to be awarded shortly.
85 | 65 | Widening I/S of main roads in Seelampur AC 49. | 2006-07 | 274.37 | Wid. 12 km. Dense 12 km. | Nil | (i) 8% | 274.37 | Wid. 12 km., Dense-12 KM | (i) 55% | 10 | (I) 55% Completed and in progress. (II) Case closed.
86 | 65 | C/o Barat Ghar CPJ Block, Seelampur AC 49. | 2006-07 | 250 | 1 no. | Nil | Nil | 250 | 1 No. | Nil | Nil | Work awarded recently, to be started.
87 | 65 | Imp. of Gokal Pur Drain. SH: Pdg. laying CC pavement on both sides on Gokal Pur drain & widening, improvement, construction and upgradation of culvert. | 2005-06 | 986.73 | CC-13.80, Culvert-65 Nos. | 763.04 | 50% | 223 | Culvert-1 Nos. | 60% | 136.81 | Almost completed (except 1 Culvert in Progess, 60% Completed.
88 | 65 | Imp. to Gokulpur drain by const. RCC drain from RDO to 790m and 1120 to 1560m along with CC pavment on both sides of drain from RDOm to 1560 m and const. of culverts in AC-49 and AC-50. | 2007-08 | 1373.65 | Drain 1.23, CC-3.90 & culvert- 3 Nos. | __ | __ | 600 | Drain 0,70 | __ | __ | Tender recallaed, due on 13.10.09.
89 | 65 | Imp. of Maujpur road & Noor Elahi Road in AC-51 Shah.(N) Zone. | 2007-08 | 70 | Dense-5.00 | __ | __ | 70 | Dense-5.00 | __ | __ | Tender called, due on 13.10.09.
90 | 65 | Remodelling of main drain on Maujpur road. | 2008-09 | 130 | Drain 1.3 | __ | __ | 20 | Drain 0.20 | __ | __ | Tender called, due on 13.10.09.
91 | 65 | Construction of underground sumpwell at Zeenat Mahal Sr Sec School road No 66 North Zone AC-65 | 2009-10 | 100.8 | 1 No. | __ | __ | 20 | 20% | __ | __ | Tender called, due on 13.10.09.
92 | 65 | Construction of drain from CPL culvert to Shiv Mandir in C-250/ AC-65 | 2009-10 | 69.63 | Drain 0.30 | __ | __ | 7 | Drain 0.03 | __ | __ | PE under checking.
93 | 66 | Re-modelling of Moni Baba Nalla from gali No.1 to Gokul Pur Drain AC-50. | 2004-05 | 50 | Drain-0.84 | 23.5 | Drain 0.40 | 26.5 | Drain 0.44 | Drain 0.35 | 23.5 | 80% completed and held up due to stay of court. Next date of hearing is 23.10.09
94 | 66 | Community Center at Usmanpur AC 50. | 2006-07 | 250 | 1 No. | Nil | Nil | 250 | 1 No. | Nil | Nil | Land yet to be handed over by DDA.
95 | 66 | Remodelling of main Outfall drain of Yamuna Vihar. | 2008-09 | 220 | Drain 1.10 | __ | __ | 20 | Drain 0.20 | __ | __ | Tender called, due on 13.10.09.
96 | 66 | Improvement/Stg of Gali No.1 Brahmpuri, AC-66 | 2009-10 | 65.12 | CC 0.68 | __ | __ | 20 | CC 0.20 | __ | __ | Tender called, due on 13.10.09.
97 | 67 | Imp & Stg of Babarpur Road from Shivaji Park to DTC Bus Terminal Babarpur in AC-48 Shah.(N). | 2007-08 | 95 | Dense-4.00 Mastic-1.5 | Nil | 30% | 95 | Dense-2.80 Mastic-1.05 | Dense-2.80 Mastic-1.05 | Nil | Completed
98 | 67 | Community Center at Ghonda Chowk AC 51. | 2006-07 | 258 | 1 No. | Nil | Nil | 80 | 35% | Nil | Nil | Tender received and is being sent for approval of rate & agency.
99 | 67 | Improvement/Satg of Noor-E-Elahi road from DTC Yamuna Vihar Deport to Ghonda Chowk AC-67 | 2009-10 | 187.27 | CC 2.95 | __ | __ | 40 | CC 0.70 | __ | __ | Tender called, due on 13.10.09.
100 | 68 | C/o Community Hall at Gokulpur village. | 2006-07 | 110 | 1No. | 49 | 35% | 61 | 1 No | 60% | 49 | 60% completed and In progress.
101 | 68 | Imp.& stg.of loni road from wazirabad road to UP border in Shah.(N). | 2007-08 | 94.39 | Dense-6.70 | __ | __ | 94.39 | (i) C.C-4.50, (ii) F/Path & C/verge | __ | __ | (i) Scope of the work changed to CC pav.,Tender recevied & file is under checking of justification (ii) 60% Completed & in progress.
102 | 68 | Imp & Stg of roads from Gokulpuri main road to Sr. Sec. School and behind MC Pry. School Gokulpuri in AC-46 Shah.(N) Zone. | 2007-08 | 43.33 | Dense-3.05 | __ | __ | 43.33 | Dense-3.05 | Dense-3.05 | __ | completed
103 | 68 | Imp & Stg of road along cement store & back side of bus depot Nand Nagari in AC-46 Shah. North Zone. | 2007-08 | 67.66 | Dense-4.80 | __ | __ | 67.66 | Dense-4.80 | Dense-4.80 | __ | completed
104 | 68 | Imp of drainage system by pdg RCC drain along right side on Sewadham road in AC-46 Shah. North Zone. | 2007-08 | 275 | Drain- | __ | __ | 275 | Drain- | __ | __ | Tender called, but no response.
105 | 68 | I/S of post office road, Police Station Road and connecting roads by dense carpeting in Nand Nagari. | 2008-09 | 76.3 | Dense 4.80 | __ | __ | 76.3 | Dense 4.80 | __ | __ | Tender called, due on 29.10.09.
106 | 68 | Improvement of Loni road by pdg cc pavement Wazirabad road to Loni UP Border, AC No.68 | 2009-10 | 170 | CC 1.86 | __ | __ | 30 | CC 0.55 | __ | __ | Detailed estimated sent to fin. For conc.
107 | 70 | C/o Barat Ghar at Village Khajuri Khas AC 52. | 2006-07 | 250 | 1 No. | Nil | Nil | 250 | 1 nos. | Nil | Nil | Land to be handed over by Revenue Deptt.
108 | 70 | Widening/ I/S of Karawal Nagar road from Wazirabad road to Sherpur Chowk in Phase-I AC 52. | 2006-07 | 485.08 | wmm-2.80, BM 1.08, AC 2.80, drain 0.54, CC 0.37 km | 155 | wmm-0.10, Drain 0.25, CC 0.37 km | 330 | Dense 2.80 drain 1.40 | wmm-0.10, Drain 0.25, CC 0.37 km | 155 | 30% Completed and tender received for remaining work and is being sent to fin. For conc.
109 | 55 to 70 | One room for library at ground floor in each Community Center should be constructed by MCD project Deptt. | 2006-07 | No Land is Available | __ | __ | __ | __ | __ | __ | __ | Proposal is under examination for availability of land .
110 | 62 & 63 | Imp/Stg. of Main / Internal Road / Drains and side berms in Dilshad Colony, Shah. in AC-45. | 2007-08 | 270 | Drain 3.70 km Dense-10 km CC-4.00 km | Nil | (i) 2% | 270 | Drain 3.70 km Dense-10 km CC-4.00 km | Drain 1.10 km Dense-8.00 km CC-1.20 km | Nil | (i) 35% completed and In progress. (ii) completed
111 | 62 / 63 | Improvement/Stg of road from PWD road No.62 to Road No 64 along Dilshad Colony, Shah, North AC-62 & 63 | 2009-10 | 98.85 | Drain 0.38 Dense 2.37 Mastic 0.50 | __ | __ | 20 | Drain 0.38 Dense 0.50 | __ | __ | Estimate is under A/A & E/S
112 | 69 & 70 | Widening/Imp./Stg. of Kerawal Nagar Raod from Wazirabad Raod to Shiv Vihar Tiraha Shah. North AC-52. | 2007-08 | 2178.33 | Wid 12.8, Dence12.80, &Cc 4.36 Drain-6.40 | 203 | Land acquired charges | 700 | Drain-0.70 | Land acquired charges | 203 | (i) 50% land acquired and tender received and is being sent to fin. For conc. (ii) 50% land is under acquisition.
NEW SCHEMS SANCTIONED ON 7.7.09