## Sheet1
DELHI STATE INDUSTRIAL & INFRASTRUCTURE DEVELOPMENT CORPORATION LTD.
Detailed work wise status of MLA Local Area Development Scheme for the year 2009-10 in compliance with section 4 of the RTI
S.No. | MLA Name and A/C No. | Date of Release | Name of Agency | Amount Released | Department | Name of work | Estimated Cost | Name of Contractor | Date of Start | Date of Completion | Status | Expenditure | Remarks
1 | Sh. Veer Singh Dhingan/AC-45 | 25.08.08 | U.D. | 31.42 | DSIIDC | S/F of semi high mast pole (12mtr.height) at PC Pocket, Dilshad Garden | 2.87 | M/s. Gyan Enterprises | 06.11.08 | 20.11.08 | 90% | 3.08 | Maintenance balance
2 | Sh. Veer Singh Dhingan/AC-45 | 25.08.08 | U.D. | 31.42 | DSIIDC | S/F of semi high mast pole (12mtr.height) at Flat No.D1LU8, Dilshad Garden | 2.87 | M/s. Sachdeva Electricals | 06.11.09 | 20.11.09 | 90% | 3.07 | Maintenance balance
3 | Sh. Veer Singh Dhingan/AC-45 | 25.08.08 | U.D. | 31.42 | DSIIDC | S/I/T/C of mini high mast pole (12mtr.& 8mtr. height) at E-2, Main Choke, Nand Nagri | 3.04 | M/s. Gyan Enterprises | 22.02.09 | 06.03.09 | 100% | 3.21
4 | Sh. Veer Singh Dhingan/AC-45 | 25.08.08 | U.D. | 31.42 | DSIIDC | S/I/T/C of mini high mast pole (12mtr.& 8mtr. height) at E-4market, Nand Nagri & B-1Mandir, Nand Nagri | 3.04 | M/s. Rajesh Electrical works | 24.02.09 | 10.03.09 | 100% | 3.22
5 | Sh. Veer Singh Dhingan/AC-45 | 25.08.08 | U.D. | 31.42 | DSIIDC | S/I/T/C of mini high mast pole (12mtr.& 8mtr. height) at DDA Quarter Park, New Seema Puri & E-4, Akhada wala park, Nand Nagri | 2.99 | M/s. Pranav Sales & Project (India) Pvt. Ltd. | 25.03.09 | 08.04.09 | 90% | 3.19
6 | Sh. Veer Singh Dhingan/AC-45 | 25.08.08 | U.D. | 31.42 | DSIIDC | S/I/T/C of mini mast pole (12mtr.& 8mtr. height) at Arya Samaj Mandir, GTB Chowk and Silai centre near fish market, Seemapuri | 3.04 | M/s. MJ Electricals & Electronics | 25.03.09 | 08.04.09 | 100% | 3.2
|  |  | EE(ED-VI) |  |  |  | A.E.E. (E) |  |  |  | J.E. (E)
NAME OF THE DIVISION- (ED-VII)
Detailed Work Wise Status Of M.L.A. LAD for the year of 09-10
| S.No. | MLA Name and AC No. | Date of Release | Amount Released | Department | Name of work | Estimated Cost | Name of Cotractor | Date of start | Date of Completion | Status | Expenditure | Remarks
| 1 | Sh. Amrish Singh Gouttam AC- 38 | 17.9.08 | 50.00 Lacs | DSIIDC | SITC of 9.5 MS Pole Gazipur | 859650 | M/s Bhola Ref.Elect.Co. | 27.06.09 | 20.07.09 | Complete | 817350 | Completed
| 2 |  | 17.9.08 | 50.00 Lacs | DSIIDC | Upgradation of water supply of MIG Flate Kondli (Boring of Tube well) | 520496 | M/s Sinkwell Dill Co. | 24.09.09 | ………. | In Progress | ………… | Work in Progress