## MCD
SECTOR-WISE / SCHEME-WISE FINANCIAL AND PHYSICAL ACHIEVEMENTS UNDER ANNAUAL PLAN 2007-08
Name of the Agency / Department = MCD | [13 empty] | Rs. in Lacs
Sl.No. | Name of the Sector / Scheme | Approved Outlay XIth F.Y.P. (2007-12) | 2007-08 | [5 empty] | 2008-09
|  |  | Revised Estimates | Funds Released up to date | Morato-rium granted (%) | Total Fund available 2007-08 (6+7) | Expendit-ure upto March 2008 (%) (tentative) | Unspent Balance (8-9) | Budget Estimate | Fund Released upto July,08 | Expenditure upto July,08 | Physical (upto Jue-2008) |  |  | Remarks
[12 empty] | Target |  | Achievements (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  | 14 | 15
(A) | UD Sector
1 | Development of Urban Villages | 8000 | 2200 | 2200 | 112.65 | 2312.65 | 2264.08 (102.91 %) | 48.57 | 2200 | 550 | 55 | MP/Dense (km) Drain (km) BP (km) CCP(km) Parks (nos) | 20.00 20.00 1.00 45.00 10.00 | 11.12 18.46 0.18 29.78 5.00
2 | Development of Regularised / Unauthorised Colonies | 20000 | 5200 | 5200 | 21.62 | 5221.62 | 5090.09 (97.88 %) | 131.53 | 5200 | 1300 | 130 | Dense (km) MP (km) BP (km) CC/Kota Stone (km) Drain (km) Parks (nos) | 15.00 10.00 2.00 90.00 90.00 10.00 | 7.9 3.13 0.30 54.09 31.22 4.00
3 | Additional Facilities in JJR Colonies | 15000 | 5000 | 5000 | 53.71 | 5053.71 | 4979.07 ( 99.58%) | 74.64 | 5000 | 1250 | 125 | Dense (km) MP (km) CC/Kota Stone (km) Drain (km) Parks (nos) | 25.00 5.00 60.00 25.00 20.00 | 0.92 1.59 25.43 10.39 9.00
4 | Strengthening& machanisation of Conservancy and Sanitation Services | 70000 | 23500 | 23500 |  | 23500 | 20457.00 ( 87.05%) | 3042.78 | 20000 | 5000 | 1225.04
5 | Environmental imp. Through Horticulture developments | 6000 | 1500 | 1500 | 265.44 | 1765.44 | 1012.42 (67.49 %) | 753.02 | 1500 | 375 | 59.58
Name of the Agency / Department = MCD | [13 empty] | Rs. in Lacs
Sl.No. | Name of the Sector / Scheme | 3: Approved Outlay XIth F.Y.P. (2007-12); 4: 2007-08; 10: 2008-09
|  |  | Revised Estimates | Funds Released up to date | Morato-rium granted (%) | Total Fund available 2007-08 (6+7) | Expendit-ure upto March 2008 (%) (tentative) | Unspent Balance (8-9) | Budget Estimate | Fund Released | Expenditure | Physical (upto Jue-2008) |  |  | Remarks
|  | Target 13: Target |  | Achievements (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  | 14 | 15
(A) | UD Sector
6 | Construction of community centers / baratghars | 5000 | 2000 | 2000 | 62.17 | 2062.17 | 1845.94 (92.29 %) | 216.23 | 2000 | 500 | 51.46 | C/o. community centers (nos)/ 12 | 12 | 1 completed | 12 nos in progress & 1 Under Tender
7 | Sanitation in JJ Clusters | 50000 | 12500 | 12500 |  | 12500 | 5599.87 (44.79%) | 6900.13 | 2000 | 500 | 248.73
8 | Sanitation in unauthorized # colonies | 10: 10500; 11: 2625; 12: 262.5
9 | Provision of Essential Services in unauthorized colonies | 134000 | 33800 | 18300.00 (MCD) 14850.00 (DSIIDC) 450.00 (I&FC) | 8.78 | 18308.78 | 11011.95 (MCD) (60.17 %) | 7296.83 | 10000 | 2500 | 250 | MP (km) Drain (km) BP (km) Earth Filling (lac) | 50.00 150.00 30.00 0.10 | 32.37 46.50 10.82 0.036
10 | Development works in Approved colonies | 20000 | 11000 | 11000 | 93.06 | 10093.06 | 8465.12 (76.95 %) | 1627.94 | 10000 | 2500 | 250 | MP (km) BM/AC (km) Drain (km) CC/Kota Stone (km) Parks (nos) | 25.00 90.00 80.00 180.00 40.00 | 10.45 47.72 43.83 87.11 22.00
11 | Improvement & Development of Nazafgarh, narela and Mehrauli Towns | 1500 | 430 | 430 | 23.96 | 453.96 | 444.04 (103.26%) | 9.92 | 430 | 107.5 | 10.75 | MP (km) CC/Kota Stone (km) Dense/BM/AC (km) Drain (km) | 1.00 10.00 1.00 1.00 | 1.28 2.54 1.51 2.07
12 | Trans Yamuna Area Develop ment Board (MCD) | 25000 | 5000 | 5000 | 2321.14 | 7321.14 | 7321.14 (146.42%) |  | 5000 | 1250 | 229.74
Name of the Agency / Department = MCD | [13 empty] | Rs. in Lacs
Sl.No. | Name of the Sector / Scheme | 3: Approved Outlay XIth F.Y.P. (2007-12); 4: 2007-08; 10: 2008-09
|  |  | Revised Estimates | Funds Released up to date | Morato-rium granted (%) | Total Fund available 2007-08 (6+7) | Expendit-ure upto March 2008 (%) (tentative) | Unspent Balance (8-9) | Budget Estimate | Fund Released | Expenditure | Physical (upto Jue-2008) |  |  | Remarks
|  | Target 13: Target |  | Achievements (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  | 14 | 15
(A) | UD Sector
13 | Yamuna A.P. Phase-II Projects | 3: 400; 4: 100; 8: nil; 10: 100
14 | Development of Heritage | 3: 50; 4: 10; 8: nil; 10: 20; 11: 5; 12: 0.5
| Total | 355000 | 97750 | 95580 | 2962.53 | 98542.53 | 39875.30 (40.79%) |  | 73950
(B) | Transport
15 | (a) Roads & Bridges (b) C.R.F. (c ) CWG (d) JNNURM | 30000.00 15000.00 7500.00 100000.00 | 9000.00 3000.00 5000.00 nil | 5625.00 2250.00 2800.00 |  | 5625.00 2250.00 2800.00 | 5538.03 (61.53 %) 866.40 (28.88 %) 291.98 (5.83 %) nil |  | 7500.00 3000.00 4000.00 14000.00 |  |  | WBM/AC (km) Drain (km) Footpath (km) | 45.00 10.00 40.00 | 63.50 4.00 5.70 | 7500.00 3000.00 4000.00 14000.00
| Total | 3: 152500; 4: 17000; 5: 10675; 7: 10675; 8: 6696.41 (39.39%); 10: 28500 |  |  | 28500
(C ) | Secretariat Economic Service
16 | Strengg. of MCD P&M Unit | 3: 500; 4: 100; 5: 75; 7: 75; 8: 7.50 (7.50 %); 10: 50 |  |  | 50
17 | MCD for Computerization | 500 | 100 | 100 | 27.28 | 127.28 | 40.79 (40.79 %) |  | 100 | [5 empty] | 100
| Total | 1000 | 200 | 175 | 27.28 | 202.28 | 48.29 (24.14 %) |  | 150
(D) | SCB Sector
18 | const. & imp. Of dhobi ghat | 3: 450; 4: 90; 5: 67; 7: 67; 8: 20.04 (22.26 %); 10: 20
| Total | 3: 450; 4: 90; 5: 67; 7: 67; 8: 20.04 (22.26 %); 10: 20
| Grand Total (A+B+C+D) | 508950 | 115040 | *106497.00 (92.57%) 12300.00 (DSIIDC) 3000.00 (I&FC) | 2989.81 | *109486.84 (95.17%) 12300.00 (DSIIDC) 3000.00 (I&FC) | 46640.04 (40.54 %) |  | 102620

## MLA FUND
Status of MLA Fund for the year 2004-05 to 2008-09 |  |  |  |  | (Rupees in Lakhs)
Agency |  | Total Release of Fund (upto June 2008)
Year | 2004-05 | 2005-06 | 2006-07 | 2007-08 | 2008-09 | Total
MCD | 10654.51 | 9999.1 | 10954.55 | 12528.83 | 6785 | 50921.99
DISCOM | 277.98 | 405.28 | 299.22 | 907.03 | 157.24 | 2046.75
DJB | 1068.8 | 469.2 | 263.06 | 224.6 | 95.2 | 2120.86
I & FC | 118.28 | 514.9 | 819.04 | 801.58 | 330 | 2583.8
PWD / CPWD | - | 12.44 | 93.86 | 5.5 | 14.77 | 126.57
NDMC | 430 | 365 | 313.19 | 499.79 | 365.06 | 1973.04
DDA | 61.5 | 9.89 | 14.06 | 41.51 | - | 126.96
S & JJ | 93.3 | 124 | 126.67 | 162.7 | 37.85 | 544.52
Others DSIDC/EDUN/HEALTH | (DSIDC) 50.00 (TSUNAMI) 10.00 | 40 | 51.24 | 432.29 | 66.49 | 650.02
Total | 12764.37 | 11939.81 | 12934.89 | 15603.83 | 7851.61 | 61094.51

## NDMC
Sector-Wise/Scheme-Wise Financial & Physical Achievement Under Annual Plan 2008-09
|  |  | Name of The Agency / Department - NDMC | [9 empty] | Rs. in Lacs
Sl.No. | Name of the Sector / Scheme | Approved Outlay XIth F.Y.P. (2007-12) |  |  |  | 2007-08 |  |  | 2008-09
|  |  | Total Fund Available 2007-08 (6+7) | Expdt.Upto March 2008 | Unspent Balance (2007-08) | Revised Estimates | Fund Released | Moratorium granted (%) | Budget Estimate | Fund Released | Expenditure | Physical (upto June,08) | Achivement (upto June,08)
1 | 2 | 3 | 9 | 4 | 5 | 6 | 7 | 8 | 10 | 11 | 12 | 13 | 14
(A) | UD SECTOR
1 | Environmental Imp. Along roads and nallas
2 | C/o Community Centers
3 | Mechanization of Sanitation & Garbage removal scheme
4 | EJJ in NDMC Areas
Public Health
5 | Anti-malaria Operation
6 | Health Education & Publicity
8 | Setting up of Epidemiological Unit
9 | Transport
10 | Roads & Bridges
Sawerage
1 | Covering of Nallas & Anti-malaria works by NDMC
NDMC for Strengthing of water supply
NDMC for Sewerage System
Medical
St.Op Hospital Services at NDMC Hospital Moti Bagh
Opening of MCW Hospital at Lodhi Colony
St. of School Health Services
St. of NDMC Poly Clinic and Chest Clinic
St. of Indian System of Medicines
Development
Development of Chankya Complex
C/imp of Dhoby Ghat (SCP)
Restoration of Heritaze Building
Common Wealth Games
TOTAL NDMC

## S&JJ
SECTOR / SCHEME WISE BUDGET ALLOCATION, FUND RELEASE & EXPENDITURE UNDER ANNUAL PLAN 2009-10
|  |  | Name of the Agency / Department = Slum & JJ | [5 empty] | Rs. in Lacs
Sl.No. | Name of the Sector / Scheme | Approved Outlay XIth F.Y.P. (2007-12) | 2008-09 |  |  |  |  | 2009-2010
|  |  | Budget Estimate | Modified R.E. | Moritorium Granted | Fund Released Mar 2009 | Expr. upto Mar 2009 | Budget Estimate | Fund Released upto SEPT, 2009 | Expr. upto SEPT, 2009
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
(A) | UD SECTOR
1 | Relocation of JJ Squatters | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Constn of community halls/bastie vikas kendras | 1600 | 350 | 380 | 0.05 | 380 | 201.32 | 300 | 75 | 84.17
3 | In Situ Upgradation of J.J. Clusters | 1600 | 10 | 10 | 0 | 0 | 0 | 10 | 0 | 0
4 | Environmental Improvement in Urban Slums | 2500 | 500 | 500 | 0.11 | 500 | 482.58 | 450 | 112.5 | 145.53
5 | Structural improvement & rehabilitation of Katras | 1000 | 150 | 150 | 0 | 150 | 141.28 | 100 | 25 | 88.29
6 | Const of of pay & use jansuvidha complexes | 2000 | 400 | 400 | 0.14 | 400 | 254.76 | 350 | 87.5 | 120.04
7 | Const. of Flats/Incremental Houses for Katra dwellers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Shishu Vatikas/Common spaces in JJ Clusters | 1100 | 150 | 150 | 0 | 150 | 97.67 | 100 | 25 | 16.98
9 | Study & preparation of perspective plan of sub standard area for next 20 years | 200 | 40 | 10 | 0 | 0 | 0 | 30 | 0 | 0
10 | National Slum Development Programme(NSDP) | 200 | 300 | 300 | 0.96 | 300 | 230.17 | 160 | 0 | 52.1
(B) | Housing SECTOR
1 | Night Shelter | 300 | 60 | 60 | 16.69 | 60 | 73.57 | 60 | 15 | 31.46
2 | Houses for Weaker Saction (JNNURM) | 6000 | 1000 | 0 | 999.95 | 0 | 6.36 | 1500 | 0 | 0.89
TOTAL MCD (SLUM WING) |  | 19500 | 2960 | 1970 | 1017.9 | 1940 | 1487.71 | 3060 | 340 | 539.46