## Sheet1
DELHI STATE INDUSTRIAL & INFRASTRUCTURE DEVELOPMENT CORPORATION LTD.
419, FIE PATPARGANJ INDUSTRIAL AREA DELHI-92
NAME OF THE DIVISION- (ED-V)
Detailed work wise status of MLA LAD for Year 07-08
S. No. | MLA Name & AC No. | Date of Release | Name of Agency | Amt. Release | Department | Name of Work | Estimated Cost | Date of Start | Date of Completion | Expenditure | Remarks
1 | Sh. Parlad Singh Sawhany A.C. No. 60 | 09.10.07 By. Dy. Secrtary (Accounts) | M/s Gyan Enterprises | 44.25 Lacs | DSIIDC | SITC of 12 Mtr. Long Street Light Pole | 820062 | 02.11.07 | 19.11.07 | 987926 | Completed
2 |  | 09.10.07 | M/s Gyan Enterprises | 44.25 Lacs | DSIIDC | Reparing of existing street light pole | 425400 | 29.10.07 | 16.11.07 | 505200 | Completed
3 |  | 09.10.07 | M/s Gyan Enterprises | 44.25 Lacs | DSIIDC | SITC of 9 Mtr. street light pole | 449680 | 29.10.07 | 17.11.07 | 545822 | Completed
4 |  | 09.10.07 | M/s Gyan Enterprises | 44.25 Lacs | DSIIDC | SITC of Street light on existing pole | 432600 | 07.04.08 | 30.04.08 | 465642 | Completed
5 |  | 09.10.07 | M/s Bansal Enterprises | 44.25 Lacs | DSIIDC | SITC of 9 Mtr. Street Light Pole | 449680 | 12.05.08 | 22.12.08 | 519350 | Completed
6 |  | 09.10.07 | M/s Rajesh Electrical works | 44.25 Lacs | DSIIDC | SITC of Street light on existing pole | 432600 | 20.02.08 | 15.04.08 | 499410 | Completed
7 |  | 09.10.07 | M/s Gyan Enterprises | 44.25 Lacs | DSIIDC | SITC of 12 Mtr. high mast pole | 424970 | 20.02.08 | 15.04.08 | 447280 | Completed
Detailed work wise status of MLA LAD for Year 08-09
1 | Sh. Parlad Singh Sawhany A.C. No. 60 | 09.07.08 | M/s Lord Krishna Enterprises Ind. | 9.79 Lacs | DSIIDC | Supply of decorative fancy pole fitting at Gurudawara Majnu ka Teeli | 317052 | 08.09.08 | 14.09.08 | 456300 | Completed
2 |  | 09.07.08 | M/s Gyan Enterprises | 9.79 Lacs | DSIIDC | ITC of decorative fancy pole at Gurudawara Majnu ka Teeli | 272572 | 08.09.08 | 04.12.08 | 309965 | Completed