## AC-45
S.No. | Date of Booking | Date of Consent | Name of Work | Amount Booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-07-11 | 14.05.08 | Dev of lane from O- block Dalao to MC Pry School, gali no. 1,2,3 in O block Sunder Nagri w.no. 244/Sh(N) | 475000 | 297/26.09.08/EE(M)-I | M/s Ganesh Entp. | 2008-09-27 | P | 288996
2 | 2008-07-11 | 14.05.08 | Pdg water connection in safai Karamchari qtrs. at K & L bloc Sunder nagari in w.no. 244/Sh(N) | 353900 | 324/16.10.08/EE(M-I | M/s Prince Const Co. | 2008-10-25 | 2008-12-23 | 340456
3 | 2008-07-11 | 14.05.08 | Dev of B wall in K block staff qtrs. in Sunder nagari w.no. 244/Sh(N) | 694000 | 304/10.10.08/EE(M)-I | M/s Prince Const Co. | 2008-10-12 | P | 547390
4 | 2008-07-11 | 14.05.08 | C/O B wall near L block MC Pry Scholl Sunder nagari w.no. 244Sh(N) | 191483 | 140/28.07.08/EE(M)-I | M/s RS Const Co. | 2008-08-06 | 2008-12-15 | 191326
5 | 2008-07-11 | 14.05.08 | Dev of culvert in Sunder nagari in w.no. 244 Sh(N) | 199784 | 137/28.07.08/EE(M)-I | M/s Parveen & Co. | 2008-08-11 | 2008-10-10 | 187322
6 | 2008-07-11 | 14.05.08 | Dev of internel lane in L block staff qtrs. in Sunder nagari w.no. 244 Sh(N) | 524000
7 | 2008-07-11 | 14.05.08 | C/o five pressthala on demand of MLA in AC-45 Sunder nagari & Nand nagari Sh(N) | 199000 | 332/16.10.08/EE(M)-I | M/s U.K. Gupta | 2008-10-23 | P | 199000
8 | 2008-07-11 | 14.05.08 | Dev of cover drain/sewer in L,K Sunder Nagri and E block Nanad Nagri Staff qtrs. in Sunder Nagri C-244/SH(N)Zone | 484229
9 | 2008-07-11 | 14.05.08 | Dev of lane in E-1 block gali no. 1 and 2 in Sunder Nagri C-244/SH(N)Zone | 490000
10 | 2008-07-11 | 14.05.08 | Dev of main road in K-Block Safai Karamchari Qtrs. in Sunder Nagri C-244/SH(N)Zone | 407308 | 135/28.07.08/EE(M)-I | M/s Maspro Const Co. | 2008-08-26 | 2008-09-03 | 406551
11 | 2008-07-11 | 14.05.08 | Dev of main road in L-Block Safai Karamchari Qtrs. in Sunder Nagri C-244/SH(N)Zone | 476959 | 138/28.07.08/EE(M)-I | M/s Satish Kumar Goel | 2008-08-18 | 2008-09-02 | 476543
12 | 2008-07-11 | 14.05.08 | Dev of berms at Jholkari Bai Marg in Sunder Nagri C-244/SH(N)Zone | 158986
13 | 2008-08-01 | 19.05.08 | C/O 10 no. Prerss Thadas on Demand of MLA Sh. V.S. Dhingan in AC-45 Dilshad Colony Dilshad Garden GTB Enclave Janta Flat Khera Village Tahirpur Village New Seemapuri in SH(N)Zone | 406000 | 353/23.10.08/EE(M)-I | M/s K-3 Infrastrucuture | 2008-11-01 | 2009-03-02 | 406000
14 | 2008-08-08 | 18.07.08 | Dev of Sump Well in E-Block Nandnagri C-243/SH(N)Z | 498942 | 271/18.09.08/EE(M)-I | M/s Love Kesh Entp. | 2008-11-26 | 2009-01-02 | 498942
15 | 2008-08-08 | 18.07.08 | Dev of road by pdg RMC along Akhada Wala Park E-4 Block Nandnagri C-243/SH(N)Z | 494524 | 281/18.09.08/EE(M)-I | M/s Tomar Const Co. | 2008-09-24 | 2008-11-21 | 494171
16 | 2008-08-08 | 18.07.08 | Dev of B/Wall by pdg brick wall grit wash and grill in E-4 Block Sump Well Nandnagri C-243/SH(N)Z | 499145 | 276/18.09.08/EE(M)-I | M/s Gajender Kumar | 2008-09-22 | 2009-03-26 | 493262
17 | 2008-08-08 | 18.07.08 | Dev of B/Wall of open passage infront h.no.E-4/230 in E-4 Block Nandnagri C-243/SH(N)Z | 199680 | 285/18.09.08/EE(M)-I | M/s Arun Const Co. | 2008-09-27 | 2009-01-13 | 198934
18 | 2008-08-25 | 16.07.08 | P/o lighting arrangement with 12 mtr. long pole near mpl park F-1/469 Sundernagri near Mc Pry school I block Sunder nagari and O block park Sundernagari Ac-45 | 594667 | 58/19.09.08/EE(E)-VI | M/s Bharat Trading Co. | 2008-09-26 | 2009-03-25 | 575021
19 | 2008-08-25 | 02.08.08 | P/o lighting arrangement with 12 mtr. long pole near J-1 Dilshad cly. F pkt park near Mother Dairy, mpl park near Kabristan New Seemapuri AC-45 Shah(N) | 585666 | 106/15.10.08/EE(E)-VI | M/s Super Elect. | 2008-10-15 | 2009-02-26 | 579311
20 | 2008-08-25 | 09.08.08 | P/o lighting arrangement with 12 mtr. long pole near P-25, A-3, O-23, A-3 Dilshad garden near chowk E block New Seemapuri AC-45 Shah(N) Shah(N) | 590000 | 131/15.10.08/(E)-VI | M/s Suneja Lite Engg. | 2008-10-15 | 2009-02-18 | 548059
21 | 2008-09-08 | 26.08.08 | P/O lighting arrangement with 12m lone pole in Mpl Park F-1 Sunder Nagri,F-2 Sunder Nagri and E-Block Staff Qtrs. Nand Nagri AC-45/SH(S)Z | 595594 | 158/31.12.08/EE(E)-VI | M/s Super Elect. | 2009-01-02 | 2009-01-28 | 578294
22 | 2008-09-08 | 26.08.08 | P/O lighting arrangement with 12m lone pole near Nursary Park GTB Enclave Dalao and pkt. Dilshad Garden Tahirpur Village AC-45/SH(S)Z | 600000 | 163/13.12.08/EE(E)-VI | M/s Paras Const Co. | 2009-01-01 | 2009-01-31 | 562263
23 | 2008-09-08 | 26.08.08 | P/O lighting arrangement with 12m lone pole near h.no.67 Janta Flats GTB Enclave near h.no.C-55XL Dilshad Garden and near D pkt.Community Hall Dilshad Garden AC-45/SH(S)Z | 594933 | 164/13.12.08/EE(E)-VI | M/s Ankur Entp. | 2009-01-01 | 2009-02-05 | 566219
24 | 2008-09-08 | 26.08.08 | P/O lighting arrangement with 12m lone pole near E-Block Staff Qtrs.Mpl Park E-1/110 and E-1 Balaji Darbar Nand Nagri AC-45/SH(S)Z | 594699 | 161/13.12.08/EE(E)-VI | M/s Cheena & Co. | 2009-01-05 | 2009-02-03 | 533626
25 | 2008-09-26 | 26.08.08 | P/o lihting arrangement with 12 mtrs long pole in mpl park near h.no. 59A A pkt. GTB enclave under Sh(N) | 205021 | 196/27.02.09/EE(E)-VI | M/s Bharat Trading Co. | 2009-02-28 | 2009-04-02 | 145420

## AC-46
S.No. | Date of Booking | Date of Consent | Name of Work | Amount Booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-06-23 | 04.08.08 | Dev/imp road by pdg RMC and drain from Sh. Nathu Singh house to Lalit house and along Pry School in Johreipur village w.no. 261/Sh(S) Zone | 471500 | 110/06.08.08/EE(M)-IV | M/s Darshan Const. | 2008-09-08 | P | 435753
2 | 2008-07-08 | 30.05.08 | P/L rmc and dev. of drainage system in gali upto Ravi Dass Mandir Chowk through h.no.213/9 in w.no.264 in Mandoli in SH(N)Zone | 465986 | 168/28.07.08/EE(M)-I | M/s Mahesh Bansal | 2008-08-07 | 2008-09-13 | 465652
3 | 2008-07-08 | 30.05.08 | P/L rmc and dev. of drainage system from Nain Singh to Dallu and link upto Mandir Chowk in w.no.264 in Mandoli in SH(N)Zone | 402888 | 169/28.07.08/EE(M)-I | M/s Appar Const & engg. | 2008-08-23 | 2008-09-16 | 402674
4 | 2008-07-08 | 30.05.08 | P/L rmc and dev. of drainage system from Raju Bansal hs. to Hukam Singh hs. and Guni hs. to Raju hs. and Mahipal hs. to Rameshwar hs. in Saboli in w.no.263 SH(N)Zone | 450244 | 166/28.07.08/EE(M)-I | M/s Kushwah Const Co. | 2008-08-01 | 2008-09-05 | 448788
5 | 2008-07-08 | 30.05.08 | P/L rmc and dev. of drainage system from Sri Chand hs. to Pratap Bhawan and Bhim Singh hs. to Shishpal hs. in Saboli in w.no.263 SH(N)Zone | 409963 | 164/28.07.08/EE(M)-I | M/s Rakesh Kumar Tomar | 2008-08-06 | 2008-09-11 | 409486
6 | 2008-07-08 | 30.05.08 | P/L rmc and dev. of drainage system from House of Bedpal to Ramlal and Ravi Dutt Sharma to Vakil Ahemad hs.in w.no.264 SH(N)Zone | 491702 | 124/28.07.08/EE(M)-I | M/s Satish Kumar Const. | 2008-08-07 | 2008-09-29 | 491702
7 | 2008-07-08 | 30.05.08 | P/L rmc and dev. of drainage system from Anand Bhati to Ishu Bhai and link in w.no.264 SH(N)Zone | 353056 | 253/02.09.08/EE(M)-I | M/s R.S. Const. | 2008-09-12 | P | 348056
8 | 2008-07-08 | 30.05.08 | P/L rmc and dev. of drainage system from Rohitpal Dairy to K.D.Public School in w.no.264 SH(N)Zone | 425800 | 202/22.08.08/EE(M)-I | M/s Ved Pal Singh | 2009-02-06 | 2009-07-16 | 350135
9 | 2008-07-08 | 30.05.08 | P/L rmc and dev. of drainage system from Raghuvie hs. to Krishan hs. and upto rajinder hs. in Mandoli in w.no.264 SH(N)Zone | 374700 | 203/22.08.08/EE(M)-I | M/s Ved Pal Singh | 2009-02-16 | 2009-07-16 | 309407
10 | 2008-07-08 | 30.05.08 | P/L rmc and dev. of drainage system from Daulat hs. to Lekh hs. to Lokesh hs. and yoginder Singh hs. to Pritam Ram hs. and adj Birju hs. and Ramesh and Mandir to Davender hs. in Saboli in w.no.263 SH(N)Zone | 499620 | 162/28.07.08/EE(M)-I | M/s Lalit Sharma | 2008-08-13 | 2008-10-04 | 498691
11 | 2008-07-08 | 30.05.08 | P/L rmc and dev. of drainage system from Sudesh hs. to Karan Singh hs. and Laxmi hs. to Mahipal hs. in Saboli in w.no.263 SH(N)Zone | 487902 | 161/28.07.08/EE(M)-I | M/s Lalit Sharma | 2008-08-14 | 2008-10-03 | 486618
12 | 2008-07-08 | 30.05.08 | P/L rmc and dev. of drainage system from Tulsi Ram hs. to Ashok hs.in Saboli in w.no.263 SH(N)Zone | 321378 | 165/28.07.08/EE(M)-I | M/s Anil Sharma | 2008-10-05 | 2009-01-05 | 321109
13 | 2008-07-08 | 30.05.08 | P/L rmc and dev. of drainage system from Jagan hs. to manga Ram and Prem Singh to Daulat hs. and Man Singh to Ramsharan hs. and Jairam to Bolli hs. and adj to Delip hs.in Saboli in w.no.263 SH(N)Zone | 296596 | 163/28.07.08/EE(M)-I | M/s Paras Nath Const Co. | 2008-08-06 | 2008-09-08 | 296201
14 | 2008-07-11 | 28.05.08 | Dev of street National Flower Public School gali by pdg RMC from h.no.857 to h.no. 797 in Mandoli C-264/SH(N)Zone | 334977 | 131/28.07.08/EE(M)-I | M/s Good Well Const Co. | 2008-08-04 | 2008-09-13 | 334977
15 | 2008-07-11 | 28.05.08 | P/L RMC and development of drainage system in gali no. 13 from Sewa Dham road to h.no. 795 in Mandoli C-264/SH(N)Zone | 381274 | 134/28.07.08/EE(M)-I | M/s Rakesh Rawat | 2008-10-06 | 2008-09-10 | 380966
16 | 2008-07-11 | 28.05.08 | P/L RMC and development of drainage system from Ravi Sweets to Shanti Prasad House and gali park to A-83 in Mandoli Extn. C-264/SH(N)Zone | 365645 | 133/28.07.08/EE(M)-I | M/s Dharam Const Co. | 2008-08-04 | 2008-10-03 | 365386
17 | 2008-07-11 | 28.05.08 | P/L RMC and development of drainage system from Ravi Gernal Store to park in Mandoli Extn.C-264/SH(N)Zone | 289519 | 132/28.07.08/EE(M)-I | M/s Maha Laxmi Const Co. | 2008-08-04 | 2009-03-30 | 289519
18 | 2008-07-11 | 28.05.08 | C/O Culvert at the entrence of IBP Outlet and develpoment of drain near Jail Boundary in C-264/SH(N)Zone | 309284 | 30/28.07.08/EE(M)-I | M/s Anil Sharma | 2008-08-02 | 2008-11-04 | 309284
19 | 2008-07-25 | 29.05.08 | P/L RMC and development of drainage system Jagram House to Shibba House in C-264/AC-46/SH(N)Zone | 685000
20 | 2008-07-25 | 29.05.08 | P/L RMC and development of drainage system from Bijender House to Ravi Dass Mandir in Mandoli C-264/SH(N)Zone | 526000 | 508/31.03.09/EE(M)-I | M/s Gaurav Const Co. | 2009-07-03 | P | 212690
21 | 2008-07-25 | 29.05.08 | P/L RMC and development of drainage system from Rajkumar House to Shiv Kumar house and link in C-264/SH(N)Zone | 780000 | 294/26.09.08/EE(M)-I | M/s Gaurav Const Co. | 2008-10-04 | P | 392041

## AC-47
S.No. | Date of Booking | Date of Consent | Name of Work | Amount Booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-06-19 | 17.05.08 | Stg. of Acharaya Vinowa Bhawan marg C-245 in Ram nagar Extn. Sh:- P/l Bitumin msatic wearing course | 383560 | 264/12.08.08/EE(M)-III | M/s Sona Const & Cont. | 2008-11-01 | 2008-12-13 | 383361
2 | 2008-06-19 | 01.04.08 | Stg. of gali no. 2 Jagatpuuri in C-245/Sh(N) Sh:- P/l mastic wearing course | 450867 | 189/18.07.08/EE(M)-III | M/s Y.K. buiders | 2008-09-19 | 2008-10-10 | 447511
3 | 2008-06-19 | 01.04.08 | Pdg and laying bitumin mastic wearing course on road from Wazirabad road to h.no. D-611 in D block Ashok nagar C-246 | 560957 | 179/18.07.08/EE(M)-III | M/s A.K.Entp. | 2008-08-11 | 2008-10-22 | 552800
4 | 2008-06-19 | 01.04.08 | Stg. of gali no. 7 Chander lok C-245 Sh(N) Sh:- P/l bitumin mastic wearing course | 318420 | 180/18.07.08/EE(M)-III | M/s A.K.Entp. | 2008-09-10 | 2008-09-25 | 317784
5 | 2008-06-19 | 01.04.08 | Stg. of gali no. 6 in Durgapuri C-245 Sh(N) Zone Sh:- P/l bitumin mastic wearing course | 256857 | 183/18.07.08/EE(M)-III | M/s A.K.Entp. | 2008-09-08 | 2008-10-11 | 255092
6 | 2008-06-19 | 01.04.08 | Pdg and laying bitumin mastic wearing course from h.ho. A81 to A-62, A61 to A-54, A-87 to near A100 at A block Ashok nagar C-246 Sh(N) | 564387 | 181/18.07.08/EE(M)-III | M/s A.K.Entp. | 2008-09-01 | 2008-10-23 | 522699
7 | 2008-06-19 | 01.04.08 | Pdg and laying bitumin mastic wearing course from Mandoli road to h.no. B-69 at lane no.5 in East Nathu colony C-246/Sh(N) | 301476 | 185/18.07.08/EE(M)-III | M/s Y.K. buiders | 2008-08-11 | 2008-10-20 | 299560
8 | 2008-06-19 | 01.04.08 | Pdg and laying bitumin mastic wearing courseon road from Mandoli road to h.no. B-306 at B block Ashok nagar C-246/Shah(N) | 275307 | 191/18.07.08/EE(M)-III | M/s Y.K. buiders | 2008-08-11 | 2008-10-24 | 257343
9 | 2008-06-23 | 01.05.08 | Pdg and fixing street name boards in C-245 Sh(N) | 495100 | 279/02.09.08/EE(M)-III | M/s Gajendra Kumar | 2008-09-10 | 2009-03-09 | 495089
10 | 2008-06-23 | 01.05.08 | P/L bituman mastic wearing course on road from Sukra Bazar to M.C.Pry.School and B-347/1 at Ashok Ngr. in C-246/SH(N)Zone | 361730 | 187/18.07.08/EE(M)-III | M/s Y.K. buiders | 2008-09-01 | 2008-10-22 | 357810
11 | 2008-06-23 | 01.04.08 | Stg. of Ashok marg from Loni road to h.no.1/3787 to 1/4042 by rmc in C-245/SH(N)Zone | 495070 | 232/11.08.08/EE(M)-III | M/s Ved Pal Singh | 2008-09-12 | 2009-02-27 | 495089
12 | 2008-06-23 | 01.04.08 | P/L bituman mastic wearing course from h.no.621 to D-54 and link upto Lalita Mandir road and from h.no.B-789 to D-533/9 and D-533/12 at Ashok Ngr. C-246/SH(N)Zone | 332508 | 196/18.07.08/EE(M)-III | M/s Ved Pal Singh | 2008-09-01 | 2008-11-26 | 328999
13 | 2008-06-23 | 01.04.08 | P/L cc pav. and drainage in lane from h.no.D-672 to D-1016 and its link from h.no.D-727 to D-525/66 at Ashok Ngr. C-246/SH(N)Zone | 188901 | 199/18.07.08/EE(M)-III | M/s Satish & Bros. | 2008-08-14 | 2008-10-29 | 187960
14 | 2008-06-23 | 03.06.08 | Stg. of road by prov. mastic asphalt from Durga Bhawan to B-1/5 Naveen Shahdra C-248/SH(N)zone | 559500 | 184/18.07.08/EE(M)-III | M/s A.K.Entp. | 2008-07-26 | P | 472896
15 | 2008-06-23 | 03.06.08 | P/F sterrt name board in Naveen Shahdra.Mohan Park,West Rohtash Ngr. and Shivaji Park etc. in C-248/SH(N)Zone | 197586 | 193/18.02.08/EE(M)-III | M/s Aman builders | 2008-07-26 | 2008-09-25 | 197520
16 | 2008-06-23 | 03.06.08 | P/F street name board at Kabool Ngr.Naveen Shahdra.and East Rohtash Ngr.in C-247/SH(N)Zone | 187534 | 175/10.07.08/EE(M)-III | M/s Maha Laxmi Const Co. | 2008-09-04 | 2009-02-16 | 187534
17 | 2008-06-23 | 03.06.08 | Stg. of lane by pdg rmc from h.no.1/3723 to 1/2871 in Ram Ngr. w.no.247/SH(N)Zone | 198600 | 192/18.07.08/EE(M)-III | M/s R.A Assos. | 2008-07-31 | 2008-09-18 | 198544
18 | 2008-06-23 | 03.06.08 | P/F MS name board at MS park Mordern Shahdra.Ram Ngr. and Ram Ngr.Extn. at C-247/SH(N)Zone | 187534 | 194/18.07.08/EE(M)-III | M/s Anil Kumar | 2008-07-31 | 2008-12-26 | 187534
19 | 2008-06-23 | 03.06.08 | Stg. of gali no. 2 and 4 Bhagwanpur Khara from h.no.1/3792 to 1/3903 and 1/3793 to 1/3797 by pdg rmc in C-245/SH(N)Zone | 199800 | 194/10.07.08/EE(M)-III | M/s RS Const | 2008-07-15 | 2008-09-04 | 198789
20 | 2008-06-23 | 03.06.08 | P/L rmc in lane from 1/9448 to 1/9446,1/9417 to 1/9392,1/9480 to 1/9386 and 1/1504 to 1/1505 in gali no.7 West Rohtash Ngr. C-248/SH(N)Zone | 451700 | 194/18.07.08/EE(M)-III | M/s Ved Pal Singh | 2008-07-26 | 2008-10-24 | 376921
21 | 2008-06-23 | 03.06.08 | P/L rmc in lane from 1/9475 to 1/9468,1/9477A to 1/9479,1/9218 to 1/9464 and 1/9463 to 1/10398 in Shahi Mohalla West Rohtash Ngr. C-248/SH(N)Zone | 455900 | 194/18.07.08/EE(M)-III | M/s Satish & Bros. | 2008-07-21 | 2008-09-26 | 407848
22 | 2008-06-23 | 03.06.08 | P/L rmc in lane from 1/9122 to 1/9185, and 1/9185 to 1/9249, and 1/9201 to 1/9193 in gali no.5 West Rohtash Ngr. C-248/SH(N)Zone | 344000 | 194/18.07.08/EE(M)-III | M/s Satish & Bros. | 2008-07-26 | 2008-09-27 | 308681
23 | 2008-06-23 | 03.06.08 | P/L rmc in lane from B-38 to Pipal Chowk in gali no.3 in Mohan Park in C-248/SH(N)Zone | 451900 | 197/18.07.08/EE(M)-III | M/s Satish & Bros. | 2008-07-26 | 2008-09-22 | 295824
24 | 2008-07-03 | 01.04.08 | Stg. of Ashok marg by rmc from Mandoli road h.no.1/4368 and 1/4082 in C-245/SH(N)Zone | 480134 | 261/11.08.08/EE(M)-III | M/s Sharma Const Co. | 2008-08-18 | 2008-11-07 | 478966
25 | 2008-07-08 | 15.04.08 | P/F MS Street board in C-246/SH(N)Zone | 312556 | 306/04.09.08/EE(M)-III | M/s Mani builders | 2008-12-22 | 2009-04-09 | 312556
26 | 2008-05-27 | 03.06.08 | Dev of road from U-18 to U-26 and X-1 to X-6 by pdg RMC in Naveen Shahdra in w.no.248/SH(N)Zone | 529000 | 172/04.07.08/EE(M)-III | M/s Ganesh Entp. | 2008-07-12 | P | 528432
27 | 2008-07-11 | 15.04.08 | Stg of gali no.7 from h.no.1/4153 to 1/4166 in Ram Ngr. Extn. Bhagwanpur Khera C-245/SH(N)ZONE | 196055 | 341/19.09.08/EE(M)-III | M/s Maspro Const Co. | 2008-09-26 | 2008-11-28 | 195990
28 | 2008-07-11 | 15.04.08 | Dev of lane from h.no. B-178 to B-165 by pdg cc pav. and drainage at Ashok Ngr. C-246/SH(N)Zone | 417600 | 346/19.09.08/EE(M)-III | M/s Rajeev & Co. | 2008-09-26 | 2008-12-08 | 374151
29 | 2008-07-11 | 15.04.08 | P/L cc pav. and drainage to link lane of gali no. 3 and 4 from h.no. 210,232,85,98,at Durgapuri Extn. C-246/SH(N)ZONE | 545000
30 | 2008-07-30 | 15.04.08 | P/L NP-2 class RCC pipe 300 mm dia and drain crossing from Mandoli road to Loni road in lane along 52 Cuaic drain C-245/SH(N)ZONE | 686300 | 447/23.12.08/EE(M)-III | M/s Satish & Bros. | 2008-12-24 | 2009-03-03 | 686300
31 | 2008-08-04 | 30.07.08 | P/L RMC in lane from h.no. 1/10512 to 24A in gali no. 3 Mohan Park in C-248/SH(N)ZONE | 580985 | 293/02.09.08/EE(M)-III | M/s Satish & Bros. | 2008-09-04 | 2008-10-31 | 580985
32 | 2008-08-04 | 04.08.08 | Stg of lane by pdg RMC from h.no.G-13 to G-1/1153,h.no. H-56 to 1/1256 and link in MS Park in C-247/SH(N)ZONE | 806400 | 361/26.09.08/EE(M)-III | M/s Ved Pal Singh | 2009-10-27 | P | 779668
33 | 2008-08-04 | 04.08.08 | Stg of lane by pdg RMC from h.no.1/1412 to h.no. H-53 Mansarovar Park C-247/SH(N)ZONE | 693000 | 347/19.09.08/EE(M)-III | M/s Bharat Assos. | 2008-10-10 | 2008-11-27 | 693000
34 | 2008-08-04 | 04.08.08 | Stg of lane by pdg RMC from A-6 to Aggarwal Dharamshala and lane between B-8 to B-55 in MS Park C-247/SH(N)ZONE | 728300 | 448/23.12.08/EE(M)-III | M/s Mayur Entp. | 2009-01-03 | 2009-03-25 | 728300
35 | 2008-08-06 | 04.08.08 | Stg of lane by pdg RMC from 1/1913 to 1/1863,1/2468 to 1/1911 and link in Mprdern Shahdra C-247/SH(N)ZONE | 1228900 | 362/26.09.08/EE(M)-III | M/s Mayur Entp. | 2008-11-18 | P | 1228841
36 | 2008-08-06 | 04.08.08 | Stg of lane by pdg mastic asphalt on Jayaswal Marg from Loni road to Mandoli road C-247/SH(N)ZONE | 1023600 | 363/26.09.08/EE(M)-III | M/s Maman Chand Bansal | 2008-11-10 | 2008-12-22 | 1020411
37 | 2008-08-06 | 04.08.08 | Stg of lane by pdg mastic asphalt from 1/3627 to 1/3225,Ram Ngr. Krishna Marg C-247/SH(N)ZONE | 1016900 | 439/10.10.08/EE(M)-III | M/s Maman Chand Bansal | 2008-12-05 | P | 1007983
38 | 2008-08-06 | 30.07.08 | Stg of lane by pdg RMC from h.no. B-76 to 1/907 and F-7 to 1/1005B MS Prak C-247/SH(N)ZONE | 696300 | 360/26.09.08/EE(M)-III | M/s Bharat Assos. | 2008-10-10 | 2008-12-03 | 696245
39 | 2008-09-03 | 12.08.08 | P/o street light arrangement in w.no.245 and 246 | 599812 | 137/15.10.08/EE(E)-VI | M/s Hitech Elect. | 2008-10-16 | 2009-02-08 | 379627
40 | 2008-09-03 | 10.08.08 | P/o street light arrangement in w.no.247 and 248 AC-47 Shah(N) | 600000 | 136/15.10.08/EE(E)-VI | M/s Hitech Elect. | 2008-10-16 | 2008-11-22 | 580155
41 | 2008-09-18 | 01.09.08 | Covering of 52 Cusic drain from mandoli Road to h.no.1/4649 in Ram Ngr. Ext. by Wire Mesh in C-245/SH(N)Z | 529900
42 | 2008-09-26 | 25.09.08 | Stg of lane by pdg RMC from 1/6943 to Ludhiana building nad Pratap gali in east Rohtas nagar w.no. 247/Sh(N) | 817500 | 624/23.02.09/EE(M)-III | M/s Sharma Const Co. | 2009-03-02 | P | 786929
43 | 2008-10-10 | 08.10.08 | Dev of Loni road from GT road to Jaiswal marg in C-247/Sh(N) by pdg matrrial premixing | 214000 | 450/23.12.08/EE(M)-III | M/s Maspro Const Co. | 2009-03-09 | 2009-03-23 | 213957
44 | 2008-06-19 | 01.04.08 | P/L bitumin mastic wearing course at west nathu colony from Mandoli road to h.no. A-39 in C-246 Sh(N) | 464740 | 626/23.02.09/EE(M)-III | M/s Y.K. buiders | 2009-02-25 | 2009-04-13 | 456074
45 | 2008-06-19 | 20.04.08 | Stg. road by pdg RMC from Loni road top gali no. 9 along 52 cusec drain in jagjivan nagar C-245/Sh(N) | 564405 | 309/04.09.08/EE(M)-III | M/s Love Kush Entp. | 2008-09-12 | 2008-11-12 | 562490
46 | 2008-06-19 | 20.04.08 | Stg. of road by pdg RMC from Nehru memorial School to gali no. 9 Chanderlok along 52 Cesce drain C-245 Sh(N) | 563933 | 308/04.09.08/EE(M)-III | M/s Love Kush Entp. | 2008-09-12 | 2008-11-12 | 562970
47 | 2008-06-19 | 20.04.08 | Stg. of lane by pdg RMC from h.no. 1/4507 to 1/4514 and links of gali no. 8 and Ambedkar gali in Ram nagar extn. C-245 Sh(N) | 499271 | 312/04.09.08/EE(M)-III | M/s Ved Pal Singh | 2008-09-12 | 2009-03-02 | 499270
48 | 2008-06-19 | 20.04.08 | Stg. of lane by pdg RMC from h.no. 1/4634 to 1/4595 in Ram nagar extn. C-245 Sh(N) | 534979 | 281/02.09.08/EE(M)-III | M/s Ved Pal Singh | 2008-11-03 | 2009-02-27 | 534978
49 | 2008-06-19 | 20.04.08 | Stg. of lane by pdg RMC from h.no. 1/4585 to 1/4498A in Ram nagar extn. C-245 Sh(N) | 539336 | 282/02.09.08/EE(M)-III | M/s Ved Pal Singh | 2008-10-10 | 2009-02-27 | 539336
50 | 2008-06-23 | 03.06.08 | Stg. of road by pdg mastic asphalt from h.no. 39 to 1501/B Mohan park Navin Shahdara RMC from h.no. 1/4507 to 1/4514 and links of gali no. 8 and Ambedkar gali in Ram nagar extn. C-248 Sh(N) | 653625

## AC-48
S.No. | Date of Booking | Date of Consent | Name of Work | Amount Booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-06-19 | 22.01.08 | Imp of street light arrangement in New Jafrabad Balbir nagar Ext. Jyoti colony in AC-48/Sh(N) | 299986 | 104/15.10.08/EE(E)-VI | M/s Shivam Elect. | 2009-03-30 | 2009-04-06 | 394304
2 | 2008-06-19 | 22.01.08 | Imp of street light arrangement in Babarpur (east and west) Gorakh park (east and west) Chajjupur in AC-48/Sh(N) | 299501 | 113/15.10.08/EE(E)-VI | M/s Satyam Elect. | 2008-10-15 | 2008-11-23 | 294210
3 | 2008-06-19 | 22.01.08 | Imp of street light arrangement in Sudama puri Subash park, Subash park ext., Janta colony Seelampur ph-III in AC-48/Sh(N) | 298638 | 87/15.10.08/EE(E)-VI | M/s Tyagi Elect. & Trading Co. | 2008-10-15 | 2008-11-23 | 294460
4 | 2008-06-20 | 25.01.08 | P/l RMC from A-1 to A-2, B-17 to B-24 and B-5 to B-8 (back lane) in Jafrabad C-259 Sh(N) | 218800 | 229/21.07.08/EE(M)-III | M/s Ganesh Entp. | 2008-08-23 | P | 173367
5 | 2008-06-23 | 02.06.08 | P/O lighting arrangement with 12m long pole near chopal harijan bastikardampuri and near T point 60 feet road Balbeer nagar in A-C 48 SH. (N) zone | 396558 | 59/19.09.08/EE(E)-VI | M/s Bharat Trading Co. | 2008-09-19 | 2008-10-10 | 368906
6 | 2008-06-23 | 02.06.08 | P/o lighting arrangement with 12 mtr long pole near Masjid 33 feet road kabir Ngr. and near Shanti Bazar Chowk kardampuri in AC-48/SH(N)Z | 398498 | 76/15.10.08/EE(E)-VI | M/s Annapurna Engg. | 2008-10-16 | 2008-11-23 | 398446
7 | 2008-06-23 | 07.06.08 | Dev of Rajmata Mandir Marg by pdg RMC in West Gorakh Park C-259 SH(N)Z | 552000 | 263/11.08.08/EE(M)-III | M/s Pal Const Co. | 2008-11-20 | 2009-03-18 | 411908
8 | 2008-06-23 | 20.05.08 | Pdg RMC on Abhimanyu Marg in Balbir Ngr. Extn. C-260/SH(N)Z | 963100 | 451/23.12.08/EE(M)-III | M/s Ashwini Kumar Aggarwal | 2008-12-26 | 2009-03-30 | 787077
9 | 2008-06-23 | 07.06.308 | Dev and imp of road in link of gali no.1 near Rajmata Mandir by pdg RMC in West Gorakh Park C-259 SH(N)Z SH:Pdg RMC near h.no. 1/10133,1/10164A,1/10166,1/10171,1/10190,1/10098 in West Gorakh Park C-259/SH(N)Z | 917900 | 287/02.09.08/EE(M)-III | M/s Ashok Const Co. | 2008-09-15 | 2008-12-11 | 740202
10 | 2008-06-23 | 07.06.08 | Dev of road from C-38 to C-109 by pdg RMC New Jafrabad West Gorakh Park C-259/SH(N)Z | 744000 | 268/26.08.08/EE(M)-III | M/s Pal Const Co. | 2008-09-27 | 2009-03-18 | 564361
11 | 2008-07-18 | 20.05.08 | P/L RMC and D/O drainage systwem in gali no.5 B-Block Kabir Ngr. C-258 SH(N)Z | 497000 | 155/22.09.08/EE(M)-IV | M/s R.A. Assos. | 2008-09-24 | 2008-11-18 | 495249
12 | 2008-07-18 | 20.05.08 | P/L RMC and D/O drainage systwem in Krishna gali in gali no.3 C-Block North Chajjupur in C-258 SH(N)Z | 187978 | 154/17.09.08/EE(M)-IV | M/s R.S. Const Co. | 2008-09-27 | 2008-12-19 | 187978
13 | 2008-07-18 | 20.05.08 | D/O drainage systwem in gali no.4 linl A-Block Kabir Ngr. C-258 SH(N)Z | 441800 | 151/17.09.08/EE(M)-IV | M/s Aziz builders | 2008-12-24 | 2009-01-14 | 441800
14 | 2008-07-18 | 20.05.08 | P/L RMC and D/O drainage systwem in gali no.7A and its link in Jyoti Colony in C-258 SH(N)Z | 198351 | 167/08.10.08/EE(M)-IV | M/s Manoj Kumar | 2008-10-13 | 2008-12-11 | 197594
15 | 2008-07-30 | 01.07.08 | P/O street light arrangement in Babarpur Sudamapuri East and West Gorakh Park Balbir Ngr.Janta Colony and New Jafrabad in AC-48 | 498900 | 160/31.12.08/EE(E)-VI | M/s Kumar Elect. & Resurfacing Work | 2009-01-09 | P | 294800
16 | 2008-07-30 | 01.07.08 | P/O street light arrangement in Kabir Ngr. Kardampuri Chajjupur North Chajjupur and West Jyoti Ngr.in AC-48 | 499694 | 174/31.12.08/EE(E)-VI | M/s Amit Elect. | 2009-01-03 | 2009-03-06 | 499426
17 | 2008-09-08 | 22.08.08 | Dev of lane by pdg RMC and drainage from 100 feet road to Shiv Mandir(h.no.12/29)in East Babarpur in C-260/SH(N)Z | 450505 | 417/10.10.08/EE(M)-III | M/s Rakesh Kumar Tomar | 2008-12-08 | 2009-01-17 | 449686
18 | 2008-09-08 | 437511 | Dev of lane by pdg near Chhajupur Stand to Shiv Mandir in Chhajju marg by pdg RMC and drainage in East Babarpur in C-260/SH(N)Z | 437511 | 428/10.10.08/EE(M)-III | M/s Kushwaha Const Co. | 2008-10-13 | 2009-02-06 | 426294
19 | 2008-09-09 | 22.08.08 | Dev of lane by pdg cc pav. in lane no.8 from h.no.C-6/27 to C-8/11 and its link along h.no.C-8/16,C-8/82 in C-Block Kabir Ngr.in C-260/SH(N)Z | 480932 | 425/10.10.08/EE(M)-III | M/s Love Kush Entp. | 2008-12-10 | P | 419814
20 | 2008-09-18 | 20.05.08 | Pdg RMC in gali no.7 in Balbir Ngr.Ext.(Nalla Par)in C-260/SH(N)Z | 617700
21 | 2008-09-18 | 20.05.08 | Pdg RMC in gali no.8,9 and gali near h.no.1/5655 in Balbir Ngr. Ext in C-260/SH(N)Z | 577500 | 373/26.09.08/EE(M)-III | M/s Jai Laxmi Const Co. | 2008-11-24 | 2009-01-03 | 340968
22 | 2008-09-26 | 25.09.08 | Pdg RMC in gali no.3J, 3F and 3H (towards gali no.1) and link in west Gorakh park C-259/Sh(N) | 1539565 | 603/02.02.09/EE(M)-III | M/s Mayur Entp. | 2009-02-06 | 2009-05-11 | 1539310
23 | 2008-09-26 | 25.09.08 | Pdg RMC in Govind gali near h.no.44A W-62 and gali near h.no. W-216 and W-126 and gali near h.no. 259 to W-262 in west Babarpur in C-259 Sh(N) | 746283 | 575/02.02.09/EE(M)-III | M/s Aspiration builders | 2009-03-16 | P | 720408
24 | 2008-10-10 | 10.10.08 | Dev link lane of Prem gali by pdg RMC and drainage along h.no.53E 2/51B E-29, E-19, E-74 and E-85 in east Babarpur w.no.260/Sh(N) | 466327 | 472/31.12.08/EE(M)-III | M/s Kushwaha Const Co. | 2009-01-07 | 2009-03-07 | 466226
25 | 2008-10-10 | 10.10.08 | Pdg RMC drainage in link of Saraswati marg along 25/15 and 28/16 in East Babarpur w.no. 260 Sh(N) | 472668 | 474/31.12.08/EE(M)-III | M/s Masko Const Co. | 2009-01-16 | 2009-03-05 | 471910
26 | 2008-10-10 | 03.10.08 | const of lane by pdg RMC from h.no. 1/7570 to 1/7593 in gali no.9 East Gorakh park w.no. 259 Sh(N0 | 399236 | 485/31.12.08/EE(M)-III | M/s Bijender Singh Entp. | 2009-01-24 | 2009-03-06 | 397981
27 | 2008-10-10 | 03.10.08 | Const of Nehru gali no.8 and its links by pdg RMC in West babarpur in w.no.259 Sh(N) | 225793 | 566/31.12.08/EE(M)-III | M/s Dinesh Kumar Sharma-II | 2009-02-20 | 2009-10-30 | 225418
28 | 2008-10-10 | 22.08.08 | dev of lane by pdg RMC from sanjay gandhi marg to Babarpr road and itsr link by pdg RMC and drainage in east Babarpur w.no.260 Sh(N) | 583400

## AC-49
S.No. | Date of Booking | Date of Consent | Name of Work | Amount Booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-05-29 | 29.05.08 | Dev of Dr.Rajender Prashad Marg from Gokulpur drain to Dr.Anand in Zafrabad in w.no.250/Sh(N)Zone | 500000 | 315/12.09.08/EE(M)-III | M/s Jai Laxmi Const Co. | 20.09.08 | P | 269795
2 | 2008-05-29 | 29.05.08 | Dev of road from F-82 to Didpencary by pdg RMC in New Seelampur in w.no.250/Sh(N)ZONE | 199000 | 240/11.08.08/EE(M)-I | M/s Satish Bros. | 12.08.08 | 11.09.08 | 199000
3 | 2008-06-03 | 05.05.08 | P/L RMC and imp of drainage system from h.no.875 to 1117 in Zafrabad in w.no.249/Sh(N)Zone | 503000 | 193/05.08.08/EE(M)-I | M/s RS Const Co. | 15.08.08 | 10.09.08 | 389184
4 | 2008-06-03 | 05.05.08 | P/L RMC and imp of drainage system from h.no.939 to 1278 in Zafrabad in w.no.249/Sh(N)Zone | 449000 | 194/05.08.08/EE(M)-I | M/s RS Const Co. | 10.08.08 | P | 352323
5 | 2008-06-03 | 05.05.08 | P/L RMC and imp of drainage system from h.no.962 to 972 in w.no.249/Sh(N)Zone | 438000 | 195/05.08.08/EE(M)-I | M/s RS Const Co. | 10.08.08 | P | 361962
6 | 2008-06-03 | 05.05.08 | P/L RMC and imp of drainage system from h.no.C-100/4B to C-228 in Chauhan Bangar in w.no.249/Sh(N)Zone | 333000 | 38/12.06.09/EE(M)-I | M/s RS Const Co. | 15.06.09 | 10.08.09 | 333000
7 | 2008-06-03 | 05.05.08 | P/L RMC and imp of drainage system from h.no.125 to 143 and links in Zafrabad in w.no.249/Sh(N)Zone | 503000 | 196/05.08.08/EE(M)-I | M/s Ved Pal Singh | 27.08.08 | 06.10.08 | 418886
8 | 2008-06-03 | 05.05.08 | P/L RMC and imp of drainage system from h.no.398 to Asian Hotel Dhaba in CVhauhan Bangar in w.no.249/Sh(N)Zone | 106000 | 128/28.07.08/EE(M)-I | M/s Dharam Const Co. | 19.08.08 | 23.09.08 | 106000
9 | 2008-06-03 | 05.05.08 | P/L RMC and imp of drainage system from h.no.44/27 to 44/09 in Chauhan Bangar in w.no.249/Sh(N)Zone | 93000 | 125/28.07.08/EE(M)-I | M/s Amar builders | 08.08.08 | 01.09.08 | 93000
10 | 2008-06-23 | 28.05.08 | P/o RMC and development of drainage system from h.no.C-182/16 to C-187/12 and C-182/42 to C-185/36 and links in F block in Chauhan Bangar in w.no.249 Sh(N) | 360000 | 218/22.08.08/EE(M)-I | M/s Princple Const Co. | 22.08.08 | 24.09.08 | 276838
11 | 2008-06-23 | 28.05.08 | P/o RMC and development of drainage system from h.no.C-7/29 to C-7/12 and links in Chauhan Bangar in w.no.249 Sh(N) | 464000 | 210/22.08.08/EE(M)-I | M/s RS Const Co. | 28.08.08 | P | 352784
12 | 2008-06-23 | 28.05.08 | P/o RMC and development of drainage system in Azad gali near Kalyan Cinema wali gali in CB in w.no.249 Sh(N) | 386000 | 209/22.08.08/EE(M)-I | M/s RS Const Co. | 15.09.08 | P | 299497
13 | 2008-06-23 | 28.05.08 | P/o RMC and development of drainage system in Nehru gali near Kalyan Cinema wali gali in w.no.249 Sh(N) | 367000 | 208/22.08.08/EE(M)-I | M/s RS Const Co. | 10.09.08 | P | 286353
14 | 2008-06-23 | 28.05.08 | P/o RMC and development of drainage system from h.no.C-217 to C-236 in Chauhan Bangar in w.no.249 Sh(N) | 586000 | 423/27.01.09/EE(M)-I | M/s Princple Const Co. | 06.02.09 | P | 436218
15 | 2008-06-23 | 28.05.08 | P/o RMC and development of drainage system in Matka wali gali from h.no.1251 to 1185 in Chauhan Bangar in w.no.249 Sh(N) | 512000 | 216/22.08.08/EE(M)-I | M/s RS Const Co. | 22.08.08 | P | 389917
16 | 2008-06-23 | 28.05.08 | P/o RMC and development of drainage system from h.no.1420 to 1431 from h.no.1441 to 1454 and from h.no. 1463 to 1474 in Zafrabad in w.no.249 Sh(N) | 499000 | 241/29.08.08/EE(M)-I | M/s RS Const Co. | 05.09.08 | P | 399188
17 | 2008-06-23 | 28.05.08 | P/o RMC and development of drainage system in opp. h.no. C-217 on main road Brahmpuri road in CB in w.no.249 Sh(N) | 665000 | 238/29.08.08/EE(M)-I | M/s RS Const Co. | 15.09.08 | P | 507045
18 | 2008-06-23 | 28.05.08 | P/o RMC and development of drainage system from Yuvraj communication to Sanjay gali in Chauhan Bangar in w.no.249 Sh(N) | 605000 | 235/29.08.08/EE(M)-I | M/s Princple Const Co. | 29.08.08 | P | 449701
19 | 2008-06-23 | 28.05.08 | P/o RMC and development of drainage system from h.no. 1313 to 1324 in gali no.41 Zafrabad in w.no.249 Sh(N) | 500000 | 239/29.08.08/EE(M)-I | M/s RS Const Co. | 30.08.08 | P | 394690
20 | 2008-06-23 | 28.05.08 | P/o RMC and development of drainage system from h.no.649 to 712 in gali no. 27 and link gali no. 27 and 28 in w.no.249 Sh(N) | 698000 | 234/29.08.08/EE(M)-I | M/s Princple Const Co. | 30.08.08 | 12.12.08 | 513754
21 | 2008-07-21 | 01.07.08 | Dev of lane by cc pav. in between Sarvodya Bal Vidya Mandir and UGR at Gautampuri in w.no.251 Sh(N) | 409983
22 | 2008-07-21 | 01.07.08 | Dev of gali by pdg cc pav. in gali no.13/1 and 14 in Gautampuri w.no.251 Sh(N) | 339991
23 | 2008-07-21 | 01.07.08 | P/l cc pav in gali no.18 and link in Gautampuri w.no.251 Sh(N) | 487700
24 | 2008-07-21 | 01.07.08 | P/l cc pav in gali no.16 and link in Gautampuri w.no.251 Sh(N) | 523400
25 | 2008-07-21 | 01.07.08 | C/o road by pdg RMC from culvert near Sulabh Sauchalaya to UGR at Gautampuri in w.no.251 Sh(N) | 699000
26 | 2008-07-21 | 01.07.08 | Stg. of road from B-53/1 to A-61 in A block New Usmanpur in w.no.251 Sh(N) | 687900
27 | 2008-09-03 | 24.07.08 | Stg. of road by pdg matling premixing from MCD flats gate no.1 to B & c block in w.no. 251 Shah(N) ZOne | 692000 | 449/23.12.08/EE(M)-III | M/s Shri Paras Nath Const Co. | 20.01.09 | 30.03.09 | 672000
28 | 2008-09-03 | 24.07.08 | Stg. of lane by pdg cc pav. frpm A-160 to A-97 and D-104 to A-193 in MCD flats in w.no. 251 Shah(N) ZOne | 689000
29 | 2008-09-03 | 24.07.08 | Stg. of lane by pdg cc pav. from D-129 to D-168 and A-193 to A-251 in MCDflats in w.no. 251 Shah(N) ZOne | 643000
30 | 2008-09-03 | 24.07.08 | Dev of road by pdg metling premixing from pusta road to B block in New Usmanpur in w.no.251 Shah(N) | 620900
31 | 2008-09-03 | 24.07.08 | Stg. of road by pdg bitumin mastic from E-10 to gali no.4 to shahtri park in w.no. 251 Shah(N) Zone | 687000 | 444/23.12.08/EE(M)-III | M/s Pawan Const Co. | 30.01.09 | 25.03.09 | 687000
32 | 2008-09-03 | 24.07.08 | Stg. of road by pdg bitumin mastic from A-75 to A-51 New Usmanpur in w.no. 251 Shah(N) Zone | 695000 | 445/23.12.08/EE(M)-III | M/s Pawan Const Co. | 30.01.09 | 25.03.09 | 694979
33 | 2008-09-03 | 24.07.08 | Stg. of road by pdg bitumin mastic from A-28 to A-19 in A block New Usmanpur in w.no. 251 Shah(N) Zone | 689900 | 446/23.12.08/EE(M)-III | M/s Pawan Const Co. | 30.01.09 | 28.03.09 | 689858
34 | 2008-09-03 | 24.07.08 | Dev of lane by pdg cc pav. in gali no.15 and link in Gautampuri in w.no.251 Shah(N) Zone | 443717
35 | 2008-09-03 | 24.07.08 | Dev of lane by pdg cc pav. in gali no.4, 6, 9 in E block Shahstri park in w.no.251 Shah(N) Zone | 575000
36 | 2008-10-10 | 10.10.08 | Dev of lane by pdg cc pavment and drainage system from h.no. 1/142 to H-36 New seelampur w.no.236 Sh(S) | 198355
37 | 2008-10-10 | 01.09.08 | P/L RMC in galim no.8A block Chauhan Bangar New Seelampur C-250 Sh(N) | 438000
38 | 2008-10-10 | 01.09.08 | P/L RMC on lane along Gokulpyr drain Bharampuri road gali no.6 in A block Chauchan bangar New seelampur C-250/Sh(N) | 496000
39 | 2008-10-10 | 01.09.08 | P/L RMC in link between gali no. 4 and 15 in A block Chauchan Bangar New seelampur C-250/Sh(N) | 324900
40 | 2008-10-10 | 01.09.08 | Dev of road by pdg RMC from C-71 to C-86 and link in new Seelampur C-250 sh(N0 | 352878 | 550/31.12.08/EE(M)-III | M/s S.K. Assos. | 01.01.09 | 31.03.09 | 352563
41 | 2008-10-10 | 01.09.08 | Dev of road by pdg RMC from c-44, and C-48 to fruit mkt road and link in New Seelampur C-250/Sh(N) | 376000 | 500/31.12.08/EE(M)-III | M/s Sarvodya Const. | 10.01.09 | P | 336140
42 | 2008-10-10 | 01.09.08 | Pdg RMC in gal;i no.11 A block Chauchan bangar New seelampur C-250 Sh(N) | 438000
43 | 2008-10-10 | 01.09.08 | P/L RMC in gali no. 16 A block Chauchan bangar new seelampuer C-250 Sh(N) | 322700
44 | 2008-10-10 | 01.09.08 | P/L RMC in gali no.15 A block Chauchan bangar in New Seelampur C-250/sh(N) | 281700
45 | 2008-10-10 | 01.09.08 | P/L RMC in Agarbatti wali gali in A block chauchan bangar new seelampur C-250 sh(N) | 434000
46 | 2008-06-23 | 28.05.08 | P/L RMC and dev of drainage system from h.no. C-39/1 to C-7/02 in Chauchan Banagr in w.no. 249/Sh(N) | 599000 | 219/22.08.08/EE(M)-I | M/s Princple Const Co. | 23.08.08 | 17.10.08 | 440429
47 | 2008-06-23 | 28.05.08 | P/L RMC and dev of drainage system from h.no. 832A to 852 in zafrabad in w.no. 249/Sh(N) | 347000 | 215/22.08.08/EE(M)-I | M/s RS Const Co. | 30.08.08 | P | 260780
48 | 2008-06-23 | 28.05.08 | P/L RMC and dev of drainage system from h.no. 809 to 828 in zafrabad in w.no. 249/Sh(N) | 342000 | 214/22.08.08/EE(M)-I | M/s RS Const Co. | 30.08.08 | P | 259471
49 | 2008-06-23 | 28.05.08 | P/L RMC and dev of drainage system from Brahmpuri road to Sanjay Gali at Kalyan Cinema road in Chauchan Bangar in w.no. 249/Sh(N) | 546000 | 212/22.08.08/EE(M)-I | M/s RS Const Co. | 15.09.08 | P | 410753
50 | 2008-06-23 | 28.05.08 | P/L RMC and dev of drainage system from h.no. 114/1 to Gopalpur in w.no. 249/Sh(N) | 443000 | 213/22.08.08/EE(M)-I | M/s RS Const Co. | 30.08.08 | P | 330470
51 | 2008-06-23 | 28.05.08 | P/L RMC and dev of drainage system in gali no.21 in zafrabad in w.no. 249/Sh(N) | 340000 | 211/22.08.08/EE(M)-I | M/s RS Const Co. | 25.08.08 | P | 275342

## AC-50
S.No. | Date of Booking | Date of Consent | Name of Work | Amount Booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-05-09 | 13.02.08 | Dev of galim no 1 and 2 by pdg RMC near Aggarwal Sweets Kartar Ngr 3/1/2 Pusta W.no.254/Sh(N)Zone | 465000 | 176/24.07.08/EE(M)-II | M/s R.B. Traders | 28.07.08 | P | 334159
2 | 2008-06-19 | 12.06.08 | Dev of gali pdg cc pav from chopal to kumhar mohalla chowk in village Ghonda w.no.255 | 500000 | 352/05.09.08/EE(M)-II | M/s P.K. Assos. | 17.10.08 | P | 377169
3 | 2008-06-19 | 12.06.08 | Dev of pandit Dulli chand wali gali and link by pdg RMC in village Ghonda w.no.255 | 503177
4 | 2008-06-19 | 12.06.08 | Dev of gali and link pdg cc pav in Rajput mohalla in village Ghonda w.no.255 | 600000 | 223/18.08.08/EE(M)-II | M/s Anuj Entp. | 17.10.08 | P | 457708
5 | 2008-06-19 | 12.06.08 | Dev of Indira gali and link pdg cc pav in Gautam vihar w.no.256 | 600000 | 224/18.08.08/EE(M)-II | M/s Anuj Entp. | 17.10.08 | P | 426458
6 | 2008-06-19 | 12.06.08 | Dev of lane adj Rajesh pilot chopal by pdg cc pav. in village Ghonda w.no.255 | 632456 | 585/15.12.08/EE(M)-II | M/s Moni builders | 15.12.08 | P | 611696
7 | 2008-06-19 | 12.06.08 | Dev of Gyani wali gali and link by pdg RMC in village Ghonda w.no.255 Sh(N) | 500000
8 | 2008-07-18 | 02.07.08 | Dev of gali no.13 by pdg RMC in 3.5 Pushta Pratap nagar LHS Vimal wali gali in w.no.254 Sh(N0 | 542000 | 389/10.09.08/EE(M)-II | M/s Ajay Const Co. | 15.01.09 | P | 495721
9 | 2008-07-18 | 02.07.08 | Dev of Bapu gali adj. E-275 by pdg RMC Jagjeet nagar third pushta w.no.254 sh(N) | 542000 | 390/10.09.08/EE(M)-II | M/s Ajay Const Co. | 18.12.08 | P | 489548
10 | 2008-07-18 | 02.07.08 | Dev of gali no.4 by pdg RMC in 3.5 Pushta Kartar nagar in w.no.254 Sh(N) | 185000
11 | 2008-07-18 | 02.07.08 | Dev of Shiv Mandir gali by pdg RMC in 3 Pushta Jagjeet nagar in w.no.254 Sh(N) | 575000 | 451/01.10.08/EE(M)-II | M/s Mahesh Bansal | 06.10.08 | P | 565000
12 | 2008-07-18 | 02.07.08 | Dev of gali no.15 G block by pdg RMC in Jagjeet nagar in w.no.254 Sh(N) Maa Kali gali | 593000 | 376/10.09.08/EE(M)-II | M/s S.K. Const Co. | 22.09.08 | P | 556182
13 | 2008-07-18 | 02.07.08 | Dev of road from Rakesh Done pattal Shop to Chauhan medical centre by pdg RMC in Jagjeet nagar in w.no.254 Sh(N) | 645000 | 388/10.09.08/EE(M)-II | M/s Shiv Raj Sharma | 22.01.08 | P | 569913
14 | 2008-07-18 | 02.07.08 | Dev of gali no.13 by pdg RMC in 3.5 Pushta Kartar nagar RHS in w.no.254 Sh(N0 | 367000 | 374/10.09.08/EE(M)-II | M/s Shri Satpal Const Co. | 17.09.08 | 17.12.08 | 336133
15 | 2008-07-18 | 02.07.08 | Dev of road from Gokulpur drain to Mittal Bhawan by pdg RMC in 3 Pushta road in w.no.254 Sh(N) | 608000 | 387/10.09.08/EE(M)-II | M/s Shiv Raj Sharma | 22.10.08 | P | 569946
16 | 2008-07-18 | 24.07.08 | Dev of gali of h.no. A-114 gali no.9 near Adhura Mandir by pdg RMC A block Gamrhi in w.no.253 Sh(N) | 113000
17 | 2008-07-25 | 24.07.08 | Dev of gali no.9 and link by pdg RMC in A block Bhajan pura in w.no.253 Sh(N) | 613000 | 377/10.09.08/EE(M)-II | M/s S.K. Const Co. | 19.09.08 | P | 534503
18 | 2008-07-25 | 24.07.08 | Dev of gali no.3 (h.no.336 to 337) and 4 A-326 by pdg cc pav in A block Gamrhi in w.no.253 Sh(N) | 303000
19 | 2008-08-05 | 18.07.08 | Dev of gali no.3 by pdg RMC in 3.5 Pushta Kartar nagar from h.no. J-671 to J-662 in w.no.254 Sh(N) | 176000 | 411/18.09.08/EE(M)-II | M/s Ishika Entp. | 24.04.08 | 30.10.08 | 176000
20 | 2008-08-05 | 18.07.08 | Dev of Indira gali from h.no.594 to E-575 and its link Jagjeet nagar 3 Pushta in w.no.254 Sh(N) | 173000 | 596/18.12.08/EE(M)-II | M/s Sarvodya Const Co. | 06.01.09 | 21.02.09 | 172453
21 | 2008-08-05 | 18.07.08 | Dev of Chaudhary wali gali from h.no. D-231 by pdg RMC Vijay colony Vijay jyoti School road in w.no.254 in w.no.254 Sh(N) | 179000 | 501/15.10.08/EE(M)-II | M/s Mahender Const bCo. | 29.10.08 | 04.12.08 | 177281
22 | 2008-08-11 | 26.07.08 | Dev of gali no.13 by pdg RMC in Sudamapuri in w.no.253 Sh(N) | 364415
23 | 2008-08-11 | 26.07.08 | Dev of gali no.14 by pdg RMC in Sudamapuri in w.no.253 Sh(N) | 364415 | 417/22.09.08/EE(M)-II | M/s N.K. Tomar | 01.10.08 | 29.11.08 | 364415
24 | 2008-08-11 | 26.07.08 | Dev of gali no.10 by pdg RMC in Sudamapuri in w.no.253 Sh(N) | 485002 | 421/23.09.08/EE(M)-II | M/s Rajeev Const Co. | 24.09.08 | 22.11.08 | 483509
25 | 2008-08-11 | 26.07.08 | Dev of gali no.11 by pdg RMC in Sudamapuri in w.no.253 Sh(N) | 397610
26 | 2008-08-12 | 25.07.08 | Dev of gali adj h.no. E-556 and h.no. X-31/3 by pdg RMC in Gehlot nallah jagjeet nagar in w.no.254 Sh(N) | 411000
27 | 2008-08-12 | 25.07.08 | Dev of link of gali E-401 and E-425 infront og Dr.Raghav Wali gali by pdg RMC Jagjit Ngr. C-254/SH(N)Z | 408000 | 594/18.12.08/EE(M)-II | M/s Sarvodya Const Co. | 07.01.09 | 20.02.09 | 407334
28 | 2008-08-12 | 25.07.08 | Dev to link of gali infront of Vivekanand gali D-91 by pdg RMC Jagjit Ngr.3rd Pusta(LHS) C-254/SH(N)Z | 249000 | 499/15.10.08/EE(M)-II | M/s Mahinder Const Co. | 29.10.08 | 04.12.08 | 248526
29 | 2008-08-12 | 25.07.08 | Dev of Vivekanand gali and its link by pdg RMC Jagjit Ngr.3rd Pusta(LHS) C-254/SH(N)Z | 380000 | 397/1809.08/EE(M)-II | M/s Pawan Const Co. | 07.10.08 | 26.11.08 | 378792
30 | 2008-08-12 | 25.07.08 | Dev of gali from h.no.J-281/45 and its link by pdg RMC 3.5 Pusta Kartar Ngr.(LHS) C-254/SH(N)Z | 282000 | 412/13.09.08/EE(M)-II | M/s Gupta Const. | 23.09.08 | 31.10.08 | 281237
31 | 2008-08-12 | 25.07.08 | Dev of gali from h.no. J-298/A to gali no.5 by pdg RMC 3.5 Pusta Kartar Ngr.(LHS) C-254/SH(N)Z | 211000 | 399/18.09.08/EE(M)-II | M/s Vikas Jain | 20.09.08 | 24.11.08 | 210762
32 | 2008-08-12 | 25.07.08 | Dev to gali from h.no. C-365 by pdg RMC C-Block Usmanpur C-254/SH(N)Z | 205000 | 420/23.09.08/EE(M)-II | M/s K.P. Entp. | 27.09.08 | 29.11.08 | 203811
33 | 2008-08-12 | 25.07.08 | Dev to gali no.8 by pdg RMC 3.5 Pusta Kartar Ngr.(RHS) C-254/SH(N)Z | 283000 | 409/18.09.08/EE(M)-II | M/s Appar Const & Engg. | 23.09.08 | 18.11.08 | 281906
34 | 2008-08-12 | 25.07.08 | Dev of gali no.4 by pdg RMC 3rd Pusta Jagjit Ngr.(Indira Gali)Fateh Singh Marg C-254/SH(N)Z | 389000 | 457/06.10.08/EE(M)-II | M/s Good Well Const Co. | 22.10.08 | 13.12.08 | 389000
35 | 2008-08-12 | 25.07.08 | Dev of gali no.7 link from h.no.D-65A by pdg RMC Vijay Colony C-254/SH(N)Z | 305000 | 500/15.10.08/EE(M)-II | M/s Vipin Const Co. | 23.10.08 | 13.12.08 | 304123
36 | 2008-08-12 | 25.07.08 | Dev of gali no.7 and its link by pdg RMC X-Block Bharampuri near Shiv Mandir C-254/SH(N)Z | 427000 | 422/23.09.08/EE(M)-II | M/s Mahesh Bansal | 25.09.08 | 20.10.08 | 425111
37 | 2008-08-12 | 25.07.08 | Dev of gali no.6 by pdg RMC X-Block Bharampuri near Shiv Mandir C-254/SH(N)Z | 496000 | 401/18.09.08/EE(M)-II | M/s Tomar Const Co. | 27.09.08 | 25.10.08 | 495847
38 | 2008-08-12 | 25.07.08 | Dev of gali no.3 by pdg RMC X-Block Bharampuri near Shiv Mandir C-254/SH(N)Z | 308000 | 414/18.09.08/EE(M)-II | M/s Kushwaha Const. | 22.09.08 | 20.10.08 | 307550
39 | 2008-08-12 | 25.07.08 | Dev of gali no.7 link from h.no.D-67/24 by pdg RMC Vijay Colony 3rd Pusta C-254/SH(N)Z | 218000 | 410/18.09.08/EE(M)-II | M/s K. S. Aggarwal | 23.09.08 | 03.11.08 | 217714
40 | 2008-08-12 | 25.07.08 | Dev of gali no.4 by pdg RMC X-Block Bharampuri near Shiv Mandir C-254/SH(N)Z | 301000 | 453/01.10.08/EE(M)-II | M/s Dinesh Kumar Sharma-II | 08.10.08 | 15.11.08 | 300201
41 | 2008-08-12 | 25.07.08 | Dev of gali from h.no.C-315 to Gokulpur drain by pdg RMC C-Block Usmanpur in C-254/SH(N)Z | 308000 | 418/22.09.08/EE(M)-II | M/s Lalit Sharma | 24.09.08 | P | 294403
42 | 2008-08-25 | 07.02.08 | Const. of culvert in w.no.253 Shah(N) | 200000 | 448/01.10.08/EE(M)-II | M/s Bijender Kumar | 08.10.08 | 07.01.09 | 199146
43 | 2008-09-29 | 07.02.08 | Dev of gali no.1 and link by pdg RMC in A-block (near Kartar Nagar) Bhajanpura w.no.253 Shah(N) | 766000
44 | 2008-09-03 | 14.08.08 | Dev of gali no.10 (h.no. J-91) and adj. J-150 and J-9/1B by pdg RMc fourth pusta in w.no.254 Shah(N) Zone | 306000 | 529/21.10.08/EE(M)-II | M/s Umang Const. Co. | 04.12.08 | 27.12.08 | 305449
45 | 2008-09-03 | 14.08.08 | Dev of road from Marginal bandth third pusta to Gokumpur drain in w.no.254 Shah(N) Zone | 387000
46 | 2008-09-03 | 14.08.08 | Dev of gali no.1 X-Block(Bharampuri)h.no.V-37 by pdg RMC Feteh Singh Marg in C-254/SH(N)Z | 243000 | 632/05.01.09/EE(M)-II | M/s Rakesh Kumar Tomar | 05.02.09 | 12.03.09 | 242409
47 | 2008-09-03 | 14.08.08 | Dev of gali no.11 adj C-363 and its link by pdg cc pav.in C-Block Usmanpur in C-254/SH(N)Z | 189000 | 315/21.10.08/EE(M)-II | M/s Anil Kumar | 21.10.08 | 27.12.08 | 188716
48 | 2008-09-03 | 14.08.08 | Dev of gali of GBN public School by pdg RMC X-Block Bharampuri in C-254/SH(N)Z | 297000
49 | 2008-09-05 | 28.08.08 | Dev of Prayas Clinic Wali Gali by pdg RMC in Gautam Vihar in C-255/SH(N)Z | 199917 | 476/06.10.08/EE(M)-II | M/s Moni builders | 15.12.08 | 02.01.09 | 199311
50 | 2008-09-05 | 28.08.08 | P/F MS Street Name Boards in Gautam Vihar in C-255/SH(N)Z | 67512 | 593/18.12.08/EE(M)-II | M/s Sarvodya Const Co. | 14.01.09 | 22.01.09 | 67512

## AC-51
S.No. | Date of Booking | Date of Consent | Name of Work | Amount Booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-06-19 | 23.05.08 | Dev of front and side lane by pdg RMC from B-1/312 to B-1/319 and side lane along park B-1 Block Yamuna Vihar | 466000 | 226/18.08.08/EE(M)-II | M/s Mahender Const Co. | 15.09.08 | 30.10.08 | 465681
2 | 2008-06-19 | 23.05.08 | Dev of front and side lane by pdg RMC from C-6/120 to C-6/111, C-6/141 to C-6/150 in C-6 Block Yamuna Vihar | 470000 | 181/31.07.08/EE(M)-II | M/s Umang Const Co. | 05.08.08 | 20.10.08 | 469783
3 | 2008-06-19 | 23.05.08 | Dev of front and side lane by pdg RMC from C-6/45 to C-6/54,C-6/41 to C-6/44 in C-6 Block Yamuna Vihar | 365000 | 221/18.08.08/EE(M)-II | M/s RA Assos. | 20.08.08 | 21.11.08 | 364795
4 | 2008-06-19 | 23.05.08 | Dev of front lane along park and adj back lane by pdg RMC from C-6/276 to C-6/161 in C-6 Block Yamuna Vihar | 495000 | 225/18.08.08/EE(M)-II | M/s Maha Laxmi Const Co. | 22.09.08 | P | 492708
5 | 2008-06-19 | 23.05.08 | Dev of front lane and back lane by pdg RMC from C-6/306 to C-6/292,C-6/402 to C-6/393 in C-6 Block Yamuna Vihar | 495487 | 216/18.08.08/EE(M)-II | M/s KP Entp. | 10.09.08 | 20.11.08 | 495165
6 | 2008-06-19 | 23.05.08 | Dev of front lane along park and adj back lane by pdg RMC from C-6/431 to C-6/438,C-6/430 to C-6/423,C-6/422 to C-6/413 in C-6 Block Yamuna Vihar | 497718
7 | 2008-06-19 | 23.05.08 | Dev of front and back lane by pdg RMC from C-6/333 to C-6/347,C-6/382 to C-6/373 in C-6 Block Yamuna Vihar | 499297 | 227/18.08.08/EE(M)-II | M/s Good Well Const Co. | 18.09.08 | 20.11.08 | 499106
8 | 2008-06-23 | 18.05.08 | C/O walk way and B/Wall in park opp. h.no.B-5/160 B-Block Yamuna Vihar C-256/AC-51 SH(N)Z | 497900 | 17/22.08.08/EE(M)-II | M/s NKG Entp. | 29.08.08 | 21.11.08 | 496043
9 | 2008-06-23 | 20.05.08 | Pdg Fiber Glass Roof and flooring in huts in park of B-4 and B-5 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 668000
10 | 2008-06-23 | 20.05.08 | Pdg Fiber Glass Roof and flooring in huts in park of B-1,B-2 and B-3 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 589258 | 22/04.09.08/EE(M)-II | M/s Mahesh Bansal | 11.09.08 | 12.12.08 | 577694
11 | 2008-06-23 | 20.05.08 | Pdg Fiber Glass Roof and flooring in huts in park of C-1,C-2 and C-3 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 596499 | 23/04.09.08/EE(M)-II | M/s Mahesh Bansal | 11.09.08 | 12.12.08 | 576102
12 | 2008-06-23 | 20.05.08 | Pdg Fiber Glass Roof and flooring in huts in park of C-4,C-5 and C-6 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 606154 | 30/26.09.08/EE(M)-II | M/s Mahesh Bansal | 05.10.08 | 02.01.09 | 594774
13 | 2008-06-23 | 20.05.08 | Pdg Fiber Glass Roof and flooring in huts in park of C-7,C-8 and C-9 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 610982 | 29/26.09.08/EE(M)-II | M/s Mahesh Bansal | 05.10.08 | 04.01.09 | 600952
14 | 2008-06-23 | 20.05.08 | Pdg Fiber Glass Roof and flooring in huts in park of C-10,C-11 and C-12 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 598279 | 24/04.09.08/EE(M)-II | M/s Mahesh Bansal | 11.09.08 | 12.12.08 | 592819
15 | 2008-06-23 | 20.05.08 | C/O walkway in Ambedkar Park in C-8 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 471041 | 19/22.08.08/EE(M)-II | M/s NKG Entp. | 25.08.08 | 18.11.08 | 469436
16 | 2008-06-23 | 20.05.08 | C/O B/wall from Mahila Park to Bapu Asha Ram Park in B-Block Yamuna Vihar C-256/AC-51 SH(N)Z | 624764 | 33/26.09.08/EE(M)-II | M/s Shailender Singh Const | 05.10.08 | P | 578902
17 | 2008-06-23 | 20.05.08 | C/O walkway in Park opp. h.no. C-8/169 and C-8/179 park in C-8 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 473126 | 21/04.09.08/EE(M)-II | M/s NS Chaudhary | 11.09.08 | 28.11.08 | 472644
18 | 2008-06-23 | 20.05.08 | R/O B/wall in Bhagat Singh Park in C-9 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 632074 | 32/26.09.08/EE(M)-II | M/s Bhatia Const Co. | 05.10.08 | 02.01.09 | 412074
19 | 2008-06-23 | 20.05.08 | C/O B/wall in Chitra Gupt Vatika in C-4 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 363558 | 20/04.09.08/EE(M)-II | M/s NS Chaudhary | 12.09.08 | 03.11.08 | 363097
20 | 2008-06-23 | 20.05.08 | C/O walkway and B/Wall in park back side of Rath Wala Mandir in C-4 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 608070 | 31/26.09.08/EE(M)-II | M/s RA Assos. | 05.10.08 | P | 483599
21 | 2008-06-23 | 20.05.08 | C/O walkway in Park opp. h.no. B-3/76 in B-Block Yamuna Vihar C-256/AC-51 SH(N)Z | 364301 | 18/22.08.08/EE(M)-II | M/s NKG Entp. | 25.08.08 | 18.11.08 | 363781
22 | 2008-06-23 | 20.05.08 | C/O B/wall in park in B-3 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 610000 | 41/26.12.08/EE(M)-II | M/s RA Assos. | 03.01.09 | 13.03.09 | 609624
23 | 2008-06-23 | 23.05.08 | Beautification of road side berms opp.Ser.Sec.School C-8 Block Yamuna Vihar C-256/AC-51 SH(N)Z | 602135
24 | 2008-06-23 | 27.05.08 | Dev of side berms and bed raising of drain by pdg RMC from h.no.B-5/154 to B-5/138 and bed raising along back lane of School B-5 Block Yamuna Vihar in C-256/SH(N)Z | 429193
25 | 2008-06-23 | 27.05.08 | Dev of back lane and side along both sides park by pdg RMC from h.no.B-5/327 to B-5/351 and B-5/386 to B-5/370 and back lane B-5/309 in B-5 Block Yamuna Vihar in C-256/SH(N)Z | 459841 | 182/21.07.08/EE(M)-II | M/s Moni buiders | 01.08.09 | 24.10.08 | 459430
26 | 2008-06-23 | 27.05.08 | Dev of back lane by pdg RMC from h.no.B-5/139 to B-5/154 and B-5/91 to B-5/118 in B-5 Block Yamuna Vihar C-256/SH(N)Z | 472741 | 208/13.08.08/EE(M)-II | M/s Rajinder Const Co. | 14.08.08 | 25.09.08 | 472446
27 | 2008-06-23 | 27.05.08 | P/F MS Name Board in Bhajanpura C-Block,K-Block,Gangotri Vihar Subhash Vihar C-256/SH(N)Z | 497590 | 203/17.08.08/EE(M)-II | M/s Amar builders | 21.08.08 | 30.09.08 | 497590
28 | 2008-07-16 | 27.05.08 | P/O lighting arrangement in MPL Ambedkar Park C-8 Yamuna Vihar C-256/SH(N)Z | 471631 | 124/15.10.08/EE(E)-VI | M/s Hitech Elect. | 16.10.08 | 23.12.08 | 459492
29 | 2008-07-25 | 10.07.08 | Dev of gali no.2 and link by pdg RMC in K-Block West Ghonda in C-255/SH(N)Z | 199653 | 327/05.09.08/EE(M)-II | M/s Anil Kumar | 19.09.08 | 17.10.08 | 199149
30 | 2008-07-30 | 08.05.08 | P/O lighting arrangement opp. h.no.B-3/185 Bhajanpura Thana and Bhajanpura Chowk to Dispencary in AC-51/SH(N)Z | 698487 | 212/27.02.09/EE(E)-VI | M/s Unique Elect. | 28.02.09 | 10.07.09 | 692398
31 | 2008-08-26 | 10.07.08 | Dev of lane adj h.no.21/30 by pdg RMC in K-Blocl West Ghonda in C-255/SH(N)Z | 496052 | 328/05.09.08/EE(M)-II | M/s SK Assos. | 11.10.08 | 28.11.08 | 495407
32 | 2008-08-26 | 10.07.08 | Dev of Sidharrth gali and link by pdg RMC in K-Block West Ghonda in C-255/SH(N)Z | 499868 | 370/10.09.08/EE(M)-II | M/s Yoginder Singh Tomar | 24.11.08 | 12.12.08 | 499436
33 | 2008-08-26 | 10.07.08 | Dev of gali no.20 and link by pdg RMC in K-Block West Ghonda in C-255/SH(N)Z | 499513 | 326/05.09.08/EE(M)-II | M/s Adarsh Const Co. | 25.09.08 | 24.11.08 | 499184
34 | 2008-08-26 | 14.07.08 | Dev of gali no.20 Shiv Mandir gali by pdg RMC in C-Block Bhajanpura in C-256/SH(N)Z | 309415 | 356/10.09.08/EE(M)-II | M/s Vikas Jain | 19.09.08 | 10.11.08 | 309335
35 | 2008-08-26 | 14.07.08 | Dev of gali no.23 and its link(Arvind Purohit Wali)by pdg RMC in C-Block Bhajanpura in C-256/SH(N)Z | 410000 | 371/10.09.08/EE(M)-II | M/s RS Const | 03.10.08 | 28.11.08 | 409753
36 | 2008-08-26 | 14.07.08 | Dev of gali no.17 C-Block by pdg RMC in Bhajanpura in C-256/SH(N)Z | 299000 | 367/10.09.08/EE(M)-II | M/s Utkarsh Const Co. | 25.09.08 | 24.10.08 | 298366
37 | 2008-08-26 | 14.07.08 | Dev of front and backlane by pdg RMC from C-4/113 to C-4/124 and backlane C-4/137 to 4/138 in C-4 Block Yamuna Vihar in C-256/SH(N)Z | 336847 | 364/10.09.08/EE(M)-II | M/s Moni buiders | 18.09.08 | 06.11.08 | 336499
38 | 2008-08-26 | 14.07.08 | Dev of B/Wall near C-10/131 along Vijay Park in Yamuna Vihar in C-256/SH(N)Z | 498487
39 | 2008-08-26 | 14.07.08 | Dev of side lane of MC.Pry.School by pdg RMC from h.no.C-12/541 to C-12/520 and C/O culvert at priya Panchvati Resturent in C-11 Yamuna Vihar in C-256/SH(N)Z | 350000 | 333/05.09.08/EE(M)-II | M/s Vipin Const Co. | 23.09.08 | 10.12.08 | 349748
40 | 2008-08-26 | 14.07.08 | D/O front lane and side lane by pdg RMC C-4/63 to C-4/72 and side lane C-4/83 to C-4/92 in C-4 Block Yamuna Vihar C-256/SH(N)Z | 364000 | 332/05.09.08/EE(M)-II | M/s Rajinder Const Co. | 18.09.08 | 10.11.08 | 363721
41 | 2008-08-26 | 14.07.08 | Dev of front lane by RMC from h.no.C-4/262 to C-4/276 and C-4/292 to to C-4/304 and C-4/345 to C-4/352 in C-4 Block Yamuna Vihar in C-256/SH(N)Z | 499947
42 | 2008-08-26 | 14.07.08 | Dev of side lane by RMC from h.no.C-4/247 to C-4/276 in C-4 Block Yamuna Vihar in C-256/SH(N)Z | 390886 | 355/18.09.08/EE(M)-II | M/s Paras Nath Const Co. | 23.09.08 | 03.11.08 | 390535
43 | 2008-08-26 | 14.07.08 | Dev of both side berms and drain on road from h.no.B-4/142 to Subhash Vihar in C-256/SH(N)Z | 499802 | 372/10.09.08/EE(M)-II | M/s RB Traders | 24.09.08 | P | 498459
44 | 2008-08-26 | 14.07.08 | Dev of side berms and drain on Dispencary road from Dispencary Chowk to MCD Pump House near Bhajanpura Thana in C-256/SH(N)Z | 443000 | 368/10.09.08/EE(M)-II | M/s Arun Const Co. | 25.09.08 | 16.10.08 | 442971
45 | 2008-08-26 | 14.07.08 | Dev of side berms on main road by pdg RMC from Dividing road to B-4 near MCD Store B-Block Yamuna vihar in C-256/SH(N)Z | 499856 | 335/05.09.08/EE(M)-II | M/s Mahender Const Co. | 25.09.08 | 10.08.09 | 499668
46 | 2008-08-26 | 14.07.08 | Dev of side berms on main road by pdg RMC from Dividing road to B-3 near MCD Store B-Block Yamuna vihar in C-256/SH(N)Z | 499850 | 339/05.09.08/EE(M)-II | M/s Rajeev Const Co. | 08.09.08 | 14.10.08 | 499820
47 | 2008-08-26 | 14.07.08 | Dev of side berms on main road by pdg RMC from road no.66 to h.no.C-7/4 C-Block Yamuna vihar in C-256/SH(N)Z | 499850 | 366/10.09.08/EE(M)-II | M/s Manoj Kumar | 05.11.08 | 02.01.09 | 499456
48 | 2008-08-26 | 14.07.08 | Dev of side berms on main road by pdg RMC from h.no.C-7/4 to Dividing road C-Block Yamuna vihar in C-256/SH(N)Z | 499851 | 329/05.09.08/EE(M)-II | M/s Ganesh Entp. | 16.08.09 | 18.11.08 | 499591
49 | 2008-08-26 | 14.07.08 | Dev of side berms on main road by pdg RMC from road no.66 to h.no.C-2/340 C-Block Yamuna vihar in C-256/SH(N)Z | 499850
50 | 2008-08-26 | 14.07.08 | Dev of side berms on main road by pdg RMC from h.no.C-2/340to Dividing road C-Block Yamuna vihar in C-256/SH(N)Z | 499850 | 337/05.09.08/EE(M)-II | M/s Ishika Entp. | 08.09.08 | 13.10.08 | 499524
51 | 2008-08-26 | 27.05.08 | Pdg Street Light Arrangement in Subhash Mohalla,Madhuvan Mohalla,Gangotri Vihar and Sanjay Mohalla in AC-51/SH(N) | 595855 | 153/31.12.08/EE(E)-VI | M/s Electra Fusion Technologies | 02.01.09 | 07.03.09 | 595122
52 | 2008-09-05 | 21.08.08 | P/O 12m pole in Shahid Bhagat Sing Park opp. Gurudwara C-9 Block Yamuna Vihar and gali no.5 k-Block Gangotri Vihar in AC-51 | 396168

## AC-52
S.No. | Date of Booking | Date of Consent | Name of Work | Amount Booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
| 2008-06-23 | 16.05.08 | P/L rmc from h.no.D-1 to D-6 on Karaval Ngr. road in c-270/SH(N)Zone | 219650 | 111/12.08.08/EE(M)-IV | M/s KK Const Co. | 14.08.08 | 29.08.08 | 219593
2 | 2008-05-30 | 15.05.08 | Pdg RMC and drain near h.no.53C,66,68 and 79 in Sadatpur Village in w.no.266/Sh(N)Zone | 428000 | 170/15.07.08/EE(M)-II | M/s Mahesh Bansal | 19.07.08 | P | 417490
3 | 2008-06-03 | 15.05.08 | Prg RMC and drain near along Kamlesh Swing Center in village Karawal Ngr Sh(N)Zone | 198000 | 158/19.06.08/EE(M)-II | M/s KK Const Co. | 14.08.08 | 29.08.08 | 219593
4 | 2008-07-15 | 15.05.08 | Pdg M/P and drain near Mahavir to Sanjay house in Sabeypur Village in C-271/AC-52 | 476000
5 | 2008-07-15 | 15.05.08 | Pdg M/P and drain near Praveen Rana to Shivani house in Sabeypur Village in C-271/AC-52 | 493531 | 195/08.08.08/EE(M)-II | M/s Moni builders | 11.08.08 | 20.12.08 | 492954
6 | 2008-07-15 | 15.05.08 | Pdg M/P and drain near Mahavir to Sanjay house in Sabeypur Village in C-271/AC-52 | 495870 | 281/01.09.08/EE(M)-II | M/s KS Aggarwal | 03.09.08 | 21.01.09 | 495335
7 | 2008-07-15 | 15.05.08 | Pdg M/P near Ratiram house to Rajesh house in Sabeypur Village in C-271/AC-52 | 493000 | 398/18.09.08/EE(M)-II | M/s Parveen & Co. | 26.09.08 | 06.12.08 | 492812
8 | 2008-07-15 | 15.05.08 | Pdg RMC and drain near Phatah Singh house to Mangal Singh house in Sabeypur Chauhan Patti in C-271/AC-52 | 493512 | 253/25.08.08/EE(M)-II | M/s Kushwaha Const Co. | 28.08.08 | 08.10.08 | 493123
9 | 2008-07-15 | 15.05.08 | Pdg RMC and drain near Umashankar Mishra to Karan Singh house in Sabeypur Chauhan Patti in C-271/AC-52 | 493000 | 280/01.09.08/EE(M)-II | M/s Adarsh Const Co. | 09.09.08 | 31.10.08 | 492629
10 | 2008-07-15 | 15.05.08 | Pdg M/P near Sh. Bijender Singh house to Alim house in Sabeypur Village in C-271/AC-52 | 498931 | 284/01.09.08/EE(M)-II | M/s Gajinder Kumar | 09.09.08 | 27.01.09 | 498921
11 | 2008-07-15 | 15.05.08 | Pdg RMC and drain near Ramphal house to Rajpal house in Sabeypur Chauhan Patti in C-271/AC-52 | 491998 | 283/01.09.08/EE(M)-II | M/s RA Assos. | 02.09.08 | 29.10.08 | 491544
12 | 2008-07-15 | 15.05.08 | Pdg RMC near Umesh Chand house to Ruchi Convent School in Sabeypur Chauhan Patti in C-271/AC-52 | 491895 | 193/08.08.08/EE(M)-II | M/s Vashistha Const Co. | 11.08.08 | 26.09.08 | 491457
13 | 2008-07-15 | 15.05.08 | Pdg RMC and drain near Virender Singh house and Chander Bhan in Sabeypur Chauhan Patti in C-271/AC-52 | 488000 | 267/25.08.08/EE(M)-II | M/s KP Entp. | 21.08.08 | 07.10.08 | 488000
14 | 2008-07-15 | 15.05.08 | Pdg M/P near Ratan house to Guptaji house in Sabeypur Village in C-271/AC-52 | 498931 | 277/01.09.08/EE(M)-II | M/s RS Const Co. | 26.11.08 | P | 493157
15 | 2008-07-15 | 15.05.08 | Pdg M/P near Kareef house to Ashok Gupta house in Sabeypur Village in C-271/AC-52 | 492742 | 282/01.09.08/EE(M)-II | M/s Ashwini Kumar Aggarwal | 02.09.08 | 27.11.08 | 492563
16 | 2008-07-15 | 15.05.08 | Pdg M/P near house of Sh. D.D.Binani to Ajit house in Sabeypur Village in C-271/AC-52 | 498758 | 272/01.09.08/EE(M)-II | M/s Parveen & Co. | 09.09.08 | 08.12.08 | 498758
17 | 2008-07-15 | 15.05.08 | Pdg M/P near Sh. Nirmla house to Mukesh house in Sabeypur Village in C-271/AC-52 | 491000 | 274/01.09.08/EE(M)-II | M/s Rajinder Const Co. | 10.09.08 | 08.12.08 | 490795
18 | 2008-07-15 | 15.05.08 | Pdg M/P near Anju Gupta house to Ch.Bharat Singh house in Sabeypur Village in C-271/AC-52 | 498931 | 489/10.10.08/EE(M)-II | M/s Vipin Const Co. | 13.10.08 | 19.01.09 | 498390
19 | 2008-07-15 | 15.05.08 | Pdg RMC and drian near Sh. Gopal house to near Rajender Singh house in Karawal Ngr.Village in C-271/AC-52 | 479542 | 278/01.09.08/EE(M)-II | M/s Love Kush Entp. | 06.09.08 | 04.12.08 | 479243
20 | 2008-07-15 | 15.05.08 | Pdg RMC and drian near Rame house and Rajender house in Karawal Ngr.Village in C-271/AC-52 | 482951 | 273/01.09.08/EE(M)-II | M/s Ishika Entp. | 03.09.08 | 30.10.08 | 482951
21 | 2008-07-15 | 15.05.08 | Pdg RMC and drian in link near Sandeep Kumar and Nagender in Sabaypur Chauhan Patti Village in C-271/AC-52 | 488610 | 275/01.09.08/EE(M)-II | M/s Arun Const Co. | 09.09.08 | 24.11.08 | 487512
22 | 2008-07-15 | 15.05.08 | Pdg RMC and drian in link near Bhim Singh house and near Mamta Cosmatic Shop in Sabaypur Chauhan Patti Village in C-271/AC-52 | 477000 | 276/01.09.08/EE(M)-II | M/s Adarsh Const Co. | 05.09.08 | 31.10.08 | 477000
23 | 2008-07-15 | 15.05.08 | Pdg RMC and drian near Shambhu and Ram Babu house in Sabaypur Chauhan Patti Village in C-271/AC-52 | 475812 | 279/01.09.08/EE(M)-II | M/s Dharam Const Co. | 09.09.08 | 18.11.08 | 475163
24 | 2008-07-28 | 17.07.08 | Dev of karawal Ngr. Road by pdg RMC near Salek Mkt. Khadi Gram Udhyog and Aggarwal Electrical in C-270/SH(N)Z | 280000 | 160/22.09.08/EE(M0-II | M/s KK Const Co. | 30.09.08 | 28.01.09 | 280000
25 | 2008-08-11 | 25.07.08 | Pdg RMC and drain near Ram Prakash house in Karawal Ngr. Village C-271/SH(N)Z | 222000 | 443/01.10.08/EE(M)-II | M/s Rajinder Const Co. | 10.10.08 | 10.11.08 | 222000
26 | 2008-09-23 | 05.07.08 | Pdg RMC near Sohail electricals to dev Medical in main road Karawal nagar w.no. 271 AC-52 Sh(N) | 491000 | 658/09.01.09/EE(M)-II | M/s Umang Const Co. | 12.01.09 | 25.02.09 | 489981
27 | 2008-09-23 | 05.07.08 | Pdg RMC near Badal Electronics to Super electronics main road Karawal nagar in w.no. 271/Sh(N) | 481000 | 660/09.01.09/EE(M)-II | M/s Moni builders | 12.01.09 | 26.02.09 | 480005
28 | 2008-09-23 | 05.07.08 | Pdg RMC near Khushi telecom to near Shri Ram readymate shop Karawal nagar village in w.no. 271/Sh(N) | 480000 | 664/09.01.09/EE(M)-II | M/s Jaina Assos. | 16.01.09 | 06.03.09 | 480000
29 | 2008-09-23 | 05.07.08 | Pdg RMC near Gupta pethology Lab to near Shalimar Foot wear shop Karawal nagar village in w.no. 271/Sh(N) | 490000 | 699/02.02.09/EE(M)-II | M/s KP Entp. | 11.02.09 | 20.03.09 | 489697
30 | 2008-09-23 | 05.07.08 | Pdg RMC and drain near Shambu house to h.no. A-14 in Shadatpur extn. in w.no. 271/Sh(N) | 492000 | 678/12.01.09/EE(M)-II | M/s Vashistha Const Co. | 16.01.09 | 25.02.09 | 490735
31 | 2008-09-23 | 05.07.08 | Pdg RMC and drain near gate of MC School near Rahul Bag house in Sabaypur Gujral village in w.no. 271/Sh(N) | 496000
32 | 2008-09-23 | 20.07.08 | Pdg RMC and drain near Smt Bimla Devi house sabaypur village in w.no. 271/Sh(N) | 485000 | 712/02.02.09/EE(M)-II | M/s Principle Const Co. | 11.02.09 | 08.05.09 | 485000
33 | 2008-09-23 | 05.07.08 | Pdg RMC and drain near gate of sr. Sec School to near Mohan Singh shop in Sabaypur gujral village in w.no. 271 Sh(N) | 498000
34 | 2008-09-23 | 20.07.08 | Pdg RMC and drain near Shri yogesh house in sabaypur village in w.no. 271/Sh(N) | 494000 | 702/02.02.09/EE(M)-II | M/s RA Assos. | 07.02.09 | 16.03.09 | 493096
35 | 2008-10-06 | 05.07.08 | Pdg RMC and drain near Laxmi Genreal store to Khanna Book shop Sabaypur gujral village in w.no. 271/Sh(N) | 496000 | 657/09.01.09/EE(M)-II | M/s Satish Kumar Goel | 15.01.09 | 28.06.09 | 495114
36 | 2008-10-06 | 05.07.08 | Pdg RMC and drain near h.no.21 to h.no.14 Sabaypur gujral village in w.no. 271/Sh(N) | 495000 | 687/16.01.09/EE(M)-I | M/s Garvit Const Co. | 24.01.09 | 07.03.09 | 495000
37 | 2008-10-06 | 05.07.08 | Pdg RMC and drain near Kishan house to near Bajrang Rolling centre in Sabaypur gujral village in w.no. 271/Sh(N) | 498000