## AC-37
S.No | DOB | DOC | Name of Works | Amount Booked | Work order no with date | Name of Agency | DOS | DOC | Amount Verified | Remarks
1 | 23.06.08 | 13.06.08 | Dev of lane by pdg drainage system and ccfrom h.no.481 to 500,small parl to 431,411 to 430,410 to 391,376 to small park,375 to small park, small park to 181,small park to 311,281 to 310 and /links in block-18 Trilok Puri AC-37/210 SH(S)Zone | 1213200 | 336/27.02.09 M-III | M/s Shahi Const co | 06.03.09 | 30.04.09 | 1185897 | Comp.
2 | 23.06.08 | 13.06.08 | Imp of lane by pdg drainage system and cc pav from h.no.310 to 281 360 to park 391 to 410 430 to 411 461 to 480 Block no.20 Trilokpuri w.no.209/Sh(S)Zone | 1964000 | 312/05/01/09 M-III | M/s Shahi Const co | 1900-01-01 00:44 | 14.05.09 | 1789468 | Comp.
3 | 2008-08-10 | 10.09.08 | Covering of drain by SFRC slab after raising of wall from block no. 112 to 117 and block no. 181 to 264 (Ganga marg) in pkt-I Mayur Vihar ph-1 w.no.203/37 Sh(S) Zone | 982200
4 | 23.06.08 | 13.06.08 | Dev of lane by pdg cc pavment from house no. 27/480 to 27/31, 27/186 to 110, 27/375 to 360 and near 141 in block no.27 Himatpuri w.no. 211/37 Sh(S) Zone | 995050
5 | 2008-08-10 | 10.09.08 | Dev of lane by pdg cc pavment from hno. 32/45 to 46, 32/60 to 31, 32/141 to 161 and near 31/265and near 30/411 to 430 in Trilokpuri/Himatpuri in w.no. 211/37 Sh(S) Zone. | 943700
6 | 2008-08-10 | 10.09.08 | Dev of lane by pdg cc pavment and covering of drain by pdg SFRC slab from hno. 21C to 17B near 11D, 27D to 35C 31A to 35D9-49A to 51D in Chilla Janta flats in w.no. 211/37 Sh(S) Zone. | 984200 | 332/18.02.09 M-III | M/s J.P. Mittal | 28.02.09 | 19.06.09 | 859789
7 | 2008-08-10 | 10.09.08 | P/o SHm light near MC Pry School Kotla village, chowk kotla vilaage and opp. Idgah Kotla road Mayur Vihar ph-I in AC-37/under Sh(S) | 598474 | 103/15.10.08 | M/s Sushma Electrical | 15.10.08 | 12.11.08 | 582020 | Comp.
8 | 10.10.08 | 27.06.08 | P/o SHM light opp. T-point main chowk block-13 Trilokpuri, near chowk block 139-25 Trilokpuri opp. Dev Complex Sanchar Mayur Vihar ph-I in AC-37/under Sh(S) | 598474 | 117/15.10.08 | M/s Tyagi Electircal | 15.10.08 | 23.11.08 | 559300 | Comp.
9 | 10.10.08 | 09.09.08 | Pdg lighting arrangement in Municipal park at Mayur Vihar part-I | 400000 | 140/02.02.09 | M/s Electra technologies | 02.02.09 | P | 29650 | Inprogress
10 | 23.06.09 | 13.06.08 | Dev of centrak works from block-13 Chowk to Kondli point Kotla road Trilok Puri AC-37/210/SH(S) | 1560000
11 | 11.06.09 | 02.09.08 | Dev of lane by pdg drainage system and cc from h.no.280 to 251,281 to 310,335 to 360 and 390 to 375 near School and links in block-6,Trilok Puri in AC-37/210/SH(S) | 1143200 | 17/11.06.09 M-III | M/s Shahi Const co | 05.06.09 | 08.07.09 | 1090473 | Comp.
a

## AC-38
S.No | DOB | DOC | Name of Works | Amount Booked | Work order no with date | Name of the Agency | DOS | DOC | Amount Verified | Remarks
1 | 19.06.08 | 16.05.08 | Dev of lane by pdg rmc M-20 from h.no.11/271 to 11/320 in block no.11 Kalyanpuri w.no.213/SH(South)Zone | 499514 | 197/29.08.08 | M/s M.K. Const co | 2009-08-09 | 2009-06-11 | 499514 | Comp.
2 | 19.06.08 | 16.05.08 | Dev of lane by pdg rmc M-20 from h.no.11/16 to 11/100 in block no.11 Kalyanpuri w.no.213/SH(South)Zone | 499897 | 201/4.09.09 | M/s Tomar Const Co | 14.09.08 | P | 449897 | Inprogress
3 | 19.06.08 | 16.05.08 | Dev of lane by pdg rmc M-20 from h.no.12/186 to 12/230 in block no.12 Kalyanpuri w.no.213/SH(South)Zone | 498666 | 198/29/08/08 | M/s Suraj Const Co | 2008-08-09 | P | 493666 | Inprogress
4 | 19.06.08 | 16.05.08 | Dev of lane by pdg rmc M-20 from h.no.12/271 to 12/320 in block no.12 Kalyanpuri w.no.213/SH(S)Zone | 499977 | 199/29/08/08 | M/s Alankar Builder | 2008-08-09 | 06.11.08 | 499907 | Inprogress
5 | 19.06.08 | 16.05.08 | Dev of lane by pdg rmc M-20 from h.no.14/110 to 14/125 in block no.14 Kalyanpuri w.no.213/SH(S)Zone | 499773 | 200/29.08.08 | M/s Suresh Enterp. | 2008-08-09 | 2008-10-10 | 499773 | Comp.
6 | 19.06.08 | 16.05.08 | Dev of lane by pdg rmc M-20 from h.no.11/96 to 11/260 in block no.11 Kalyanpuri w.no.213/SH(S)Zone | 498845 | 196/29/08/08 | M/s Rajesh Assoc | 2008-08-09 | 2008-10-11 | 498676 | Comp.
7 | 20.06.08 | 02.06.08 | Dev of road by dense carpetting from block no.1(Dispencary)to block no.6 Khicharipur in AC-38/SH(S)Zone | 2393000 | 86/15/10/08 | M/s Arjun Serfacing agency | 15.12.08 | 21.01.09 | 87106 | Comp.
8 | 20.06.08 | 02.06.08 | P/O semi high mast light at chowk between pkt. A and B,SFS Flats Mayur Vihar ph-III and MPL. park D-1 and D-2 Janta Flats in AC-38/SH(S)Zone | 652313 | 91/06.07.08 | M/s Perfect Elet. Const | 13.10.08 | 12.12.08 | 512599 | Comp.
9 | 20.06.08 | 14.05.08 | P/O 12m semi high mast light at 14 Block Kalyanpuri near gate of Lal bahadur Hospital Chowk 9,10 and 4 and chowk block no.5 Khicharipur near Transformer in AC-38/SH(S) | 651344 | 69/03.09.08 | M/s Perfect Elect. | 10.09.08 | 10.11.08 | 515966 | Comp.
10 | 20.06.09 | 12.05.08 | P/O 12m semi high mast light at MPL.park SFS flats between C and D Kondli road near State Bank of Patiyala and Block no.9 Khicharipur near h.no.9/215 in AC-38/SH(S) | 652513 | 113/15/10/08 | M/s Illuminater Circuit | 23.10.08 | 23.12.08 | 545320 | Comp.
11 | 20.06.08 | 07.05.08 | P/O 12m semi high mast light at Chowk block 9 and 2 near Sulabh Sauchalaya and A-1 and A-2 block Mayur vihar Ph-III in AC-38/SH(S) | 653682 | 68/3.09.08 | M/s Perfect Elect. | 11.09.08 | 10.11.08 | 505134 | Comp.
12 | 12.08.08 | 18.06.08 | Dev of road by pdg M/P from h.no.800 to 1257 (DDA Road End)Gharoli Dairy Farm A-Block in C-215/SH(S)Z | 496708 | 225/01.10.08 | M/s New Aditya Bldres | 05.12.08 | 15.05.08 | 496708 | Comp.
13 | 12.08.08 | 21.06.08 | Dev of road by pdg M/P from h.no.305 to 472 in Gharoli Dairy Farm A-Block in C-215/SH(S)Z | 499858 | 243/6/10/08 | M/s Shiv Bldres | 17/10/08 | 16/05/09 | 499858 | Comp.
14 | 12.08.08 | 19.06.08 | Dev of road by pdg M/P opp.park near h.no.6220 and 777 Ghorali Dairy Farm A-Block in C-215/SH(S)Z | 499467 | 237/6/10/08 | M/s Manishconst | 20.10.08 | P | 494467 | Inprogress
15 | 12.08.08 | 20.06.08 | Dev of road by pdg M/P from h.no.800 to 628 in Ghirali Dairy Farm A-Block in C-215/SH(S)Z | 498785 | 247/6/10/08 | M/s Vinay Const co | 2008-10-11 | 23/04/09 | 498785 | Comp.
16 | 12.08.08 | 21.06.08 | Dev of road by pfg M/P from h.no.76 to 160 in Ghorali Dairy Farm in A-Block C-215/SH(S)Z | 498751 | 242/6/10/08M-III | M/s Suraj Const Co | 19/11/08 | 25/05/09 | 498751 | Comp.
17 | 20.08.08 | 20.06.08 | Dev of Central park by Fancing of Wicket Gate opp.h.no.88 and 322 in Ghorali Dairy Farm in A-Block C-215/SH(S)Z | 498931 | 231/01/10/08M-III | M/s Tomar Const Co | 2008-10-11 | 2008-02-06 | 497225 | Comp.
18 | 4.09.08 | 30.08.08 | Dev of road by pdg RMC on dividing road of group X and XI in pkt.-A-2,from main gate to MC pry.School,MV Ph.III in C-216/AC-38/SH(S)Z | 499029 | 277/16/10/08 M_III | M/s Singlaji Const Co | 24/10/08 | 24/12/08 | 496679 | Comp.
19 | 4.09.08 | 30.08.08 | Dev of lanes by pdg RMC and drain from flat no.23A to 17B in dividing lanes around the park in pkt.-A-1 in MV Ph-III in C-216/AC-38/SH(S)Z | 499295 | 275/16/10/08M-III | M/s Bhagwan Dass | 24/10/08 | 28/11/08 | 496431 | Comp.
20 | 4.09.08 | 30.08.08 | Dev of lanes by pdg RMC around the park opp.flat no.98A and its adj qublanes of group-IV in pkt.-A-2 in MV Ph-III in C-216/AC-38/SH(S)Z | 499010 | 279/16/10/08M-III | M/s Singhla const Co | 25/10/08 | 17/12/08 | 499010 | Comp.
21 | 08.09.09 | 30.09.09 | Dev of lane by pdg RMC around the Park opp.flat no.174B and its nearly area in group-XIII pkt.A-3 MV ph.-III in C-216/AC-38/SH(S)Z | 487175 | 303/18/12/08 M-III | M/s Shiv Bhagwan | 28/12/08 | 23/03/09 | 486357 | Comp.
22 | 10.09.08 | 25.08.08 | Dev of road/lane from road of block no.10 Khicharipur to house of Rajpal Bharti in Village Khicharipur in AC-38/219/SH(S)Z imp by pdg RMC | 480000 | 211/02/12/08 M-IV | m/s Bhagwati Const co | 2008-11-12 | 14/02/09 | 477716 | Comp.
23 | 1.10.08 | 4.09.08 | Dev of lanes by pdg RMC (M-20) from F no. 182A to 173A in group -XIII pkt-A-3 Mayur Vihar ph-III, w.no.216/38 Sh(S) | 483500
24 | 1.10.08 | 4.09.08 | Dev of lanes by pdg RMC from F no. 107B to 113B around park and open surface near Dutbin in group-IV pkt-A-2 Mayur Vihar ph-III, w.no.216/38 Sh(S) | 642600
25 | 1.10.08 | 4.09.08 | Dev of lanes by pdg RMC from F no. 92B to 81B in group -IV pkt-A-2 Mayur Vihar ph-III, w.no.216/38 Sh(S) | 574500

## AC-39
S.No | DOB | DOC | Name of Works | Amount Booked | Work order no with date | Name of Agency | DOS | DOC | Amount Verified | Remarks
1 | 23.06.09 | 26.05.08 | Prov. of street light fitting HPSV 150 watt at Westm Vinod Ngr. w.no.72/AC-39/SH(S) | 199207 | 93/10.10.08 | M/s Illumination Circurt | 18/11/08 | P | 165000 | Inprog.
2 | 27.08.08 | 05.08.08 | Pdg cc pav.and c/o drain near Chaudary Dhiraj and Lakhi Public School in Mandawali Fazalpur in C-218/AC-39/SH(S)Z | 440302 | 169/25/09/08M-IV | M/s Man Mohan singh Washwa | 2008-04-10 | 2008-03-11 | 4400127 | Comp.
3 | 27.08.08 | 05.08.08 | Pdg cc pav and c/o drain in link gali from h.no.130 gali no.7 to gali no.1 in Sarpanchwara Mandawali Fazalpur in C-218/AC-39/SH(S)Z | 302417
4 | 27.08.08 | 05.08.08 | Pdg cc pav and c/o drain in link gali to Budha Marg Mandawali Fazalpur in C-218/AC-39/SH(S)Z | 255872 | 181/26/08/08 M-IV | M/s Sharma & Sharma const co | 2008-05-10 | 13/12/08 | 255724 | Comp.
5 | 03.09.08 | 31.07.08 | Dev of lanes by pdg cc pav. near h.no. 4-70,4/50 and 4/47 in Upadhaya Block in Shakarpur in C-224/AC-39/SH(S)Z | 405770 | 234/01/01/09M-IV | M/s Wadhwa | 2009-09-01 | 2009-09-03 | 399938 | Comp.
6 | 03.09.08 | 31.07.08 | Covering of Nalla near Mother Dairy Booth in School Block Shakarpur in C-224/AC-39/SH(S)Z | 690000 | 267/03/02/09 M-IV | M/s Bagwati Const Co | 2009-10-02 | 2009-11-05 | 605962 | Comp.
7 | 03.09.08 | 29.07.08 | Dev of lanes by pdg cc pav. near h.no.4-69 in Upadhaya Block Shakarpur in C-224/AC-39/SH(S)Z | 466470 | 235/01/01/09 M_III | M/s Rajesh Assicates | 2009-07-01 | 29/04/09 | 460836 | Comp.
8 | 03.09.08 | 31.07.08 | Dev of Gurudwara Wali gali by pdg cc. pav. in Upadhaya Block Shakarpur in C-224/AC-39/SH(S)Z | 499871 | 201/13/10/08 M-IV | M/s Kirit Assocat | 20.10.08 | 2009-07-08 | 498712 | Comp.
9 | 03.09.08 | 28.07.08 | Stg. of road from ROB side towards Bus stop by pdg mastic in Mandawali Fazalpur in w.no. 218/AC-39 Sh(S) | 697500
10 | 03.09.08 | 25.07.08 | Pdg cc pavment and drain to gali no.3 from .no. 228 Railway cly. to kalyan marg in Mandawali Fazalpur in w.no. 218/AC-39/Sh(S) | 499406 | 307/10.02.09 M-IV | M/s Bachan const Co | 19/02/09 | 16/05/09 | 499183 | Comp.
11 | 03.09.08 | 25.07.08 | Pdg cc pav. and drain in gali no.6 Shanker marg near h.no.215/4 and link in Mndawali Fazalpur w.no.218 Sh(S) | 404295
12 | 10.10.08 | 3.10.08 | Dev of approach road to Kalyan marg from Preet Vihar side upto gali no.9 by pdg cc pavment in Railway ly. Mandawali Fazalpur w.no.218 AC-39 | 497015
13 | 10.10.08 | 15.09.08 | Dev of lane by pdg cc pavment near Car workshop and J-I in East Vinod nagar in w.no.218 AC-39 | 340300 | 298/10/02/09 M_IV | M/s Vijay Const co | 25.02.09 | 18.04.09 | 336595 | Comp.
14 | 10.10.08 | 15.09.08 | Covering of nallah opp. Sr. Sec. school in School block Skarpur in w.no.224 Sh(S) | 821852 | 318/17/02/09 | M/s Singhla Const co | 20.02.09 | 15/05/09 | 809090 | Comp.
15 | 10.10.08 | 15.09.08 | C/o nallah near h.no. S-380 in School block Skarpur w.no.224/Sh(S) | 737616 | 317/17/02/09 M_III | M/s Singhla Const co | 19/2/09 | 23/05/09 | 7360335 | Comp.
16 | 10.10.08 | 15.09.08 | Covering of nallah near h.no. S-371 in School block Shakarpur in w.no. 224/Sh(S) | 560746 | 233/31.12.08 | M/s Singhla Const co | 06.01.09 | 1900-01-05 00:59 | 559261 | Comp.

## AC-40
S.No | DOB | DOC | Name of Works | Amount Booked | Work order no with date | Name of Agency | DOS | DOC | Amount Verified | Remarks
1 | 2008-06-23 | 24.05.08 | Prov. mastic asphalt on main road and intersection in gali no.4 I-Block w.no.221/AC-40 | 500000 | 230/21/08/09 M_I | M/s Bansal Const co | 29/08/09 | P | 488469 | Comp
2 | 2008-06-23 | 24.05.08 | Dev of lane prependicular to M.C. park by pdg rmc in Vishvkarma park in AC-40/221 | 449791 | 169/12.08.09 M-I | M/s JP Mittal | 18/08/08 | 30.09/08 | 449163 | Comp
3 | 2008-07-28 | 24.05.08 | Dev of lane adj to h.no.L-30 by pdg rmc and D/S in L-Block in AC-40/222 | 349632 | 176/12.08.08 M-I | M/s Jai Chanda Associate | 12.08.08 | 20.10.08 | 349632 | Comp
4 | 2008-07-28 | 24.05.08 | Dev of lane of H-Block near h.no.90 by pdg rmc in Garhwali Mohalla AC-40/221 | 485000 | 168/12.02.08 M-I | M/s K.K.Const | 18.08.08 | 30.09.08 | 483720 | Comp
5 | 2008-08-07 | 24.05.08 | Dev of lane of by pdg rmc and D/S near h.no.35 and 7 in Kishan Kunj Laxmi Ngr. AC-40/222 | 379500 | 177/12/08/08 M-I | M/s shiov Shakti Const | 13.08.08 | 25/09/08 | 379442 | Comp
6 | 2008-08-07 | 15.07.08 | Dev of lane by pdg rmc and D/S near h.no.689 and link in West ghuru Angad ngr. AC-40/222 | 299982 | 178/ 12.08.08 M-i | M/s Shakers Const co | 21.08.08 | 20.10.08 | 299982 | Comp
7 | 2008-08-11 | 15.07.08 | Dev of lane by pdg rmc and D/S near h.no.B-237 in B-Block PD Vihar AC-40/222 | 329792 | 179/12.08.08 M-I | M/s Shakers constco | 21.08.08 | 20.10.08 | 329792 | Comp
8 | 2008-08-11 | 07.07.08 | Pdg rmc in PP-block near h.no PP-7 in Laxmi Ngr. AC-40/222 | 179943 | 135/15/07/08 M-I | M/s Kapil Kumar puri | 14/07/08 | 30.08/08 | 179825 | Comp
9 | 2008-08-11 | 07.07.08 | Dev of drainage system and pdg rmc in lanr near h.no.9 Krishan Kunj Extn. part-II AC-40/221 | 199718 | 136/15.07/08 M-I | M/s Bhagwati Dass | 21/07/08 | 23/08/08 | 199172 | Comp
10 | 2008-08-11 | 07.07.08 | Dev of D/S of PD Vihar from LPS School to outfall drain AC-40/222 | 700000 | 229/21/08/08 M-I | M/s JP Mittal | 25/08/08 | 2008-08-11 | 588186 | Comp
11 | 2008-08-11 | 07.07.08 | P/o semi high mast light near underground water reservair,Bank Enclave and near School West Guru Angad Ngr. AC-40 | 497624 | 83/27/09/08 | M/s Illuminater& Circuters | 30.10.08 | P | 422247 | Comp
12 | 2008-08-21 | 11.07.08 | Pdg rmc and drain from h.no.2187 to 2197 and its link in RP-1 AC-229/40 | 400000 | 188/12/08/08 | M/s Manish Const Co | 14.08/.08 | 20.10.08 | 397621 | Comp
13 | 2008-08-21 | 11.07.08 | Pdg rmc and drain from h.no.2209 to 2218 and its link in RP-1 AC-229/40 | 270000 | 184/12.8.08 M_i | M/s Kapil Kumar puri | 14.08.08 | 26.09.08 | 267331 | Comp
14 | 2008-08-26 | 07.07.08 | Dev of lane infront of h.no.8A/44 Geeta Colony AC-229/40 | 250000 | 180/12.08.08 | M/s Dawer Assiciate | 14.08.08 | 10.10.08 | 250000 | Comp
15 | 2008-08-26 | 07.07.08 | DEv of lane infront of h.no.D-23 and links in jheel in AC-229/40 | 399017 | 183/12.08.08 | M/s Hari Kumar | 15.08.08 | 15.10.08 | 396826 | Comp
16 | 2008-08-26 | 15.07.08 | Covering of drain by pdg RCC slab in B block PD Vihar from Lovely Public sr.sec. School towards master plan road in AC-40 | 378100 | 228/4.09.08 M-I | M/s J.P.Mittal | 28.09.08 | 05.12.08 | 376105 | Comp
17 | 2008-09-29 | 02.08.08 | Dev of lane infront of Astha Public School Rani Garden in C-230/40 | 496372 | 347/810/08 M-I | M/s Guru Kirpa Enterp | 16.10.08 | 18.12.08 | 366112 | Comp
18 | 2008-08-11 | 02.08.08 | Dev of lane infront of h.no. 70A New Lahore Shastri Nagar in C-230/40 | 250000 | 346/8.10.08 | M/s Guru Kirpa Enterp | 17.10.08 | 18.12.08 | 196133 | Comp
19 | 2008-08-29 | 17.07.08 | Dev of lane infront of h.no. 12/70 Geeta colony in C-230/40 | 250000 | 320/29/09/08 M-I | M/s Guru Kirpa Enterp | 2008-07-10 | 2008-12-11 | 214078 | Comp
20 | 2008-08-29 | 19.07.08 | Dev of lane 1A and link in Aram park in C-230/40 | 416000 | 348/8/10/08 M-I | M/s Guru Kirpa Enterp | 17/10/08 | 18/12/08 | 314327 | Comp
21 | 2008-08-29 | 17.07.08 | Dev of lane along park near h.no. 16/80 Geeta colony in C-230/40 | 250000 | 319/29/09/08 M-I | M/s Guru Kirpa Enterp | 2008-07-10 | 2008-12-11 | 208855 | Comp
22 | 2008-08-29 | 19.07.08 | Dev of lane infront of h.no. 12/24 Geeta colony in C-230/40 | 262700 | 307/08/07/09 M-I | M/s Deepak | 29/10/08 | 18/12/08 | 212140 | Comp
23 | 2008-08-29 | 17.07.08 | Dev on culvert at different location in block 12 & 13 Geeta colny in C-230/40 | 197039 | 255/01/09/08 M-i | m/s Vijay Const | 10.09.08 | 09.11.08 | 195074 | Comp
24 | 2008-08-29 | 19.07.08 | Dev of lane infront of h.no. 12/137 Geeta colony in C-230/40 | 298300 | 310/23/09/08 M-I | M/s Riya Const | 30.09.08 | 01.12.08 | 240738 | Comp
25 | 2008-08-29 | 19.07.08 | Dev of lane infront of h.no.2/18 Geeta Colony in C-229/40 | 248200 | 436/09/12/08 M-I | M/s Parveen & Bor. | 26/12/08 | 18/04/09 | 208668 | Comp
26 | 2008-08-29 | 17.07.08 | Dev of Culver at police Station Geeta Colony and Raja Ram Kohli Marg in C-229/40 | 396600 | 468/19.01.09 M-I | M/s Saraswati Const co | 29.4.09 | 27.04.09 | 396600 | Comp
27 | 2008-09-04 | 17.07.08 | Dev of lane infront of h.no.92(along mastar plan road)in Sarojini Park in C-230/40 | 857000 | 403/17.12.08 M-I | M/s Bhagwati Dass | 31.12.08 | 27.02.05 | 629356 | Comp
28 | 2008-09-22 | 15.07.08 | Covering of drain by pdg SFRC slab in PD Vihar A block adj. to park near h.no. A-110 in AC-40 | 154391 | 437/19.12.08 M-I | M/s Sangala | 26.12.08 | 26.02.08 | 154352 | Comp
29 | 2008-09-22 | 15.07.08 | Dev of lane by pdg RMC adj. to h.no. J-3/141 and J-3/109 in J Extn. AC-40/221 | 219500 | 440/05.01.09 M-I | M/s Deepak | 12.01.09 | 09.03.09 | 180013 | Comp
30 | 2008-09-25 | 19.07.08 | Dev of lane by pdg RMC and D/S in lane adj. to h.no. F-66 in West Jwahar park AC-40/221 | 327500 | 431/19.12.08M-i | M/s Bachan Const Co | 27.12.08 | 08.04.09 | 264532 | Comp
31 | 2008-09-25 | 19.07.08 | Dev of lane by adj. to h.no. 51A to 124A in Kishan Kunj Extn. by pdg RMC in AC-40/221 | 395000 | 430/19/12/08 M-I | M/s Bachan Const Co | 26/12.08 | 27.03.09 | 321732 | Comp
32 | 2008-10-03 | 19.07.08 | Dev of road and adj. intersection by pdg mastic asphalt in the lane opp. transformer in Vishkarma park AC-40/221 | 700000
33 | 2008-07-28 | 02.08.08 | Dev of road by intersection by pdg mastic asphalt from Tikona park to Palwal road in F block Laxmi nagar in AC-40/221 | 695300
34 | 2008-07-28 | 02.08.08 | Dev of lane by pdg RMC near h.no. 58 and 21 in Vijay Block in Laxmi nagar in AC-40/221 | 230000 | 442/05.01.09 M-I | M/s Bachan Const Co | 19.01.09 | 19.03.09 | 190397 | Comp
35 | 2008-07-28 | 02.08.08 | Dev of lane by pdg RMC near 6-7 and 6-38 6 block Laxmi nagar AC-40/221 | 300000 | 439/05.01.09 M-i | M/s Deepak Const co | 14.01.09 | 24.03.09 | 248276 | Comp
36 | 2008-07-28 | 02.08.08 | Dev of road berms of Paliwal road by pdg interlocking tiles from h.no. F-190/663 to PP Ganj road in Laxmi nagar AC-40/221 | 550000 | 433/14.12.09 M-i | M/s Bachan Const Co | 27.12.08 | 26.03.09 | 364457 | Comp
37 | 2008-07-28 | 02.08.08 | Dev of lane by pdg RMC near Sanatan Dharam Mandir in F block Laxmi Nagar AC-40/221 | 299200 | 434/19.12.09 M-i | M/s Bachan Const Co | 30.12.08 | 26.03.09 | 224099 | Comp
38 | 2008-07-28 | 02.08.08 | Dev of D/S of Vishwkarma park L shpae lane and pdg RMC in link lane connecting SDm office and Vishkarma park in AC-40/221 | 199500 | 443/05.01.09 M-i | M/s Bachan Const Co | 12.01.09 | 12.03.09 | 166050 | Comp
39 | 2008-07-28 | 02.08.08 | Pdg Mastic ashpalt on Gurudwara road and intersaction in B block Guru Ram Das nagar in AC-40/w.no.222 | 628000
40 | 2008-07-28 | 02.08.08 | Dev of lane by pdg RMC on berms of road connecting Vishkarma park to Kishan Kunj road w.no.221 | 516404 | 204/12.08.08 M-i | M/s Bhgwati const co | 19.08.08 | 03.11.08 | 516404 | Comp
41 | 2008-07-28 | 02.08.08 | Dev of D/S of CR road from gali no.11 D block to main Lalita park road in w.no.221 | 683986 | 352/08.10.08 | M/s jai Bhagwan Const Co | 16.10.08 | p | 649787 | Comp
42 | 2008-07-28 | 02.08.08 | Dev of road berms by pdg RMC in Shastri gali and link in F block w.no.222 Sh(S) | 456865 | 206/12.8.08 m-I | M/S Bhagwati Const Co | 20.08.08 | 20.11.08 | 456865 | Comp
43 | 2008-07-28 | 02.08.08 | Dev of berms of old Thana road by pdg RMC in Laxmi nagar w.no. 222 Sh(S) | 467691 | 205/12.08.08M-I | M/S Bhagwati Const Co | 18.08.08 | 18.10.08 | 467961 | Comp
44 | 2008-07-28 | 02.08.08 | Dev of berms in the lane near h.no.214 and lane along MC Pry School Mangal Bazar by pdg RMC in w.no. 222 Sh(S) | 417206 | 267/04/09/08M-i | M/s Bhagwati Dass | 2008-05-09 | 06/011/08 | 417206 | Comp
45 | 2008-07-28 | 02.08.08 | P/o Semi HML in f block Laxmi Nagar AC_40 Sh (S) Zone. | 388096 | 154/06.02.09 | M/s Electra Eusion Technologies | 15.02.09 | 12.03.09 | 355356 | Comp
46 | 2008-07-28 | 02.08.08 | P/o SHML in PD Yehar lalita Park Laxmi Nagar AC-40 under Sh (S) Zone | 404714 | 154/06.02.09 | M/s Electra Eusion Technologies | 15.02.09 | 12.03.09 | 378984 | Comp
47 |  |  | P/o Lighting arrangement in Existing pall 150 w watt HPSV fitting in w No 230/AC-40 Sh (S) Zone | 399335 | 211/Krishan Electical | M/s Krishana Elect. | 10.04.09 | P | 304000 | Comp
48 | 2008-07-28 | 02.08.08 | P/o lighting arrangement in Existing pall 150 w watt HPSV fitting in AC-40 Sh (S) Zone | 621131 | 251/ 02.03.08 | M/s Illuminater& Circuters | 10.04.09 | 27.03.09 | 599964 | Comp
49 |  |  | P/o SHML in D& E block Lzxmi Nagar AC_40 Sh (S ) Zone | 388096 | 153/ 06.02.09 | M/s Electra Eusion Technologies | 15.02.09 | P | 305500 | Comp
Note on G86: xp:

## AC-41
S.No | DOB | DOC | Name of Works | Amount Booked | Work order no with date | Name of Agency | DOS | DOC | Amount Verified | Remarks
1 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and drainage system from h.no.4965 to 4972 in Kaushick Puri C-235/41 | 299953 | 136/01.09.08/(M)-II | M/s Jai Chanda Assos. | 02.09.08 | 09.11.08 | 299887
2 | 2008-06-20 | 21.05.08 | Pdg rmc and drainage system from h.no.5035 to 4091 in gali no.4 Kaushick Puri C-235/41 | 199885 | 119/26.08.08/EE(M)-II | M/s Bhati Const Co. | 27.08.08 | 24.10.08 | 199816
3 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and drainage system from h.no.5134 to 5137 in gali no.3 Kaushick Puri C-235/41 | 199977 | 67/29.07.08/EE(M)-II | M/s Kapil Const Co. | 01.08.08 | 07.10.08 | 199977
4 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and drainage system from h.no.5057 to 5084 Kaushick Puri C-235/41 | 299644 | 135/01.09.08/EE(M)-II | M/s Kapil Kumar Const. | 11.09.08 | 10.11.08 | 299610
5 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and drainage system from h.no.5084 to 5139 in gali no.1 Kaushick Puri C-235/41 | 399655 | 132/01.09.08/EE(M)-II | M/s KK Const. | 04.09.08 | 10.12.08 | 399649
6 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and drainage system from h.no.5025 to 5027 Kaushick Puri C-235/41 | 199828 | 118/26.08.08/EE(M)-II | M/s Nc & Assos. | 05.09.08 | 31.12.08 | 199816
7 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and drainage system near h.no.5099 in Kaushick Puri C-235/41 | 199968 | 95/13.08.08/EE(M)-II | M/s Goswami Aosos. | 14.08.08 | 18.10.08 | 199958
8 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and drainage system from h.no.X-3667A to h.no.3710 Shanti Mohalla C-236/41 | 199905 | 91/13.08.08/EE(M)-II | M/s Shiv Shaki Const Co. | 14.08.08 | 11.09.08 | 199873
9 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and drainage system from h.no.X-3666 to h.no.X-3664/C Shanti Mohalla C-236/41 | 199828 | 66/29.07.08/EE(M)-II | M/s Suresh Entp. | 30.07.08 | 13.08.08 | 199233
10 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and drainage system from h.no.X-3668 to h.no.3700B Shanti Mohalla C-236/41 | 199664 | 62/29.07.08/EE(M)-II | M/s Tomar Const Co. | 30.07.08 | 27.08.08 | 199664
11 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and drainage system from h.no.X-3700/3 to h.no.B-17/A Shanti Mohalla C-236/41 | 199516 | 94/13.08.08/EE(M)-II | M/s JP Mittal | 19.08.08 | 22.10.08 | 198978
12 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and drainage system from h.no.3911 to h.no.3904, Shanti Mohalla C-236/41 | 199565 | 104/13.08.08/EE(M)-II | M/s Rajesh builders | 14.08.08 | 22.10.08 | 199518
13 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and drainage system near h.no.3720/E1 and h.no.X-3774 Shanti Mohalla C-236/41 | 199752 | 58/29.07.08/EE(M)-II | M/s Dawar Assos. | 01.08.08 | 21.08.08 | 199694
14 | 2008-06-20 | 21.05.08 | Dev of Multani Mohalla road from Subhash road to Prem gali by pdg rmc in C-234/41 | 494903 | 261/03.09.08/EE(M)-II | M/s Prem Kumar | 06.09.08 | 20.10.08 | 486833
15 | 2008-06-20 | 21.05.08 | Dev of main road Gandhi Ngr. near Ser. Sec. School by pdg rmc in Kailash Ngr. in C-234/41 | 498827 | 195/12.08.08/EE(M)-II | M/s Sharwan Const Co. | 16.08.08 | 18.10.08 | 495540
16 | 2008-06-20 | 21.05.08 | Dev of gali no.9 Raghubarpura-II by pdg rmc in Dharampura C-233/41 | 499684 | 258/01.09.08/EE(M)-II | M/s Jindal builders | 04.09.08 | 20.10.08 | 494014
17 | 2008-06-20 | 21.05.08 | Dev of main road Ghandhi ngr. near Hanuman Mandir by pdg rmc in C-234/41 | 499386 | 196/12.08.08/EE(M)-II | M/s Goswami Aosos. | 20.08.08 | 17.09.08 | 496022
18 | 2008-06-20 | 21.05.08 | Dev pf lane near Shambhunath Building by pdg rmc in Ghandhi Ngr. C-234/41 | 435000 | 19/12.08.08/EE(M)-II | M/s Bhati Const Co. | 18.08.08 | 20.10.08 | 430569
19 | 2008-06-20 | 21.05.08 | Dev of Multani Mohalla road from P.O.road to Prem gali 3E by pdg rmc in C-234/41 | 499788 | 200/12.08.08/EE(M)-II | M/s Deepak Assos. | 18.08.08 | 13.10.08 | 491493
20 | 2008-06-20 | 21.05.08 | Dev of Dharampura Extn. road by pdg rmc in Ghandhi Ngr. C-234/41 | 497648 | 201/12.08.08/EE(M)-II | M/s Suresh Entp. | 18.08.08 | 07.10.08 | 490879
21 | 2008-06-20 | 21.05.08 | Dev of lane near Banarsidass Building by pdg rmc in Dharampura C-233/41 | 300000 | 189/12.08.08/EE(M)-II | M/s Vinay Conmsty Co. | 20.08.08 | 20.10.08 | 300000
22 | 2008-06-20 | 21.05.08 | Dev of Ajeet Ngr. gali no.9 by pdg rmc in Dharampura C-233/41 | 380278 | 197/12.08.08/EE(M)-II | M/s Prem Kumar | 14.08.08 | 17.10.08 | 374492
23 | 2008-06-20 | 21.05.08 | Dev of gali no.8 RAghubarpura-II by pdg rmc in C-233/41 | 497963 | 193/12.08.08/EE(M)-II | M/s Vijay Const | 14.08.08 | 10.10.08 | 492286
24 | 2008-06-20 | 21.05.08 | Dev of Subhash Mohalla gali no.4 by pdg rmc in C-233/41 | 481983 | 188/12.08.08/EE(M)-II | M/s Vinay Conmsty Co. | 16.08.08 | 20.10.08 | 477653
25 | 2008-06-20 | 21.05.08 | Dev of Jai Mata Wali gali by pdg rmc and D/S from h.no.549 to 5490 Raghubarpura-I C-236/41 | 199574 | 102/13.08.08/EE(M)-II | M/s PS Const Co. | 14.08.08 | 22.10.08 | 199503
26 | 2008-06-20 | 21.05.08 | Dev of Badi gali by pdg rmc and D/S from h.no.X-502 to X-499 and near h.no. X-551A Raghubarpura-I C-236/41 | 199846 | 60/29.07.08/EE(M)-II | M/s Bachu Lal Sharma | 08.08.08 | 07.10.08 | 199818
27 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and D/S from h.no.X-1183 to X-1189 Rajgarh Colony C-236/41 | 199388 | 56/24.09.08/EE(M)-II | M/s Y.P. Goel & Co. | 01.08.08 | 07.10.08 | 198978
28 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and D/S from h.no.X-970 to X-976 Chand Mohalla C-236/41 | 199944 | 70/29.07.08/EE(M)-II | M/s Shanker Assos. | 30.07.08 | 20.08.08 | 199844
29 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and D/S from h.no.X-64 and X-68 Raghubarpura-I C-236/41 | 199783 | 57/29.07.08/EE(M)-II | M/s Rajesh Assos. | 01.08.08 | 07.10.08 | 199771
30 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and D/S from h.no.11/191 to 163A Rajgarh Colony C-236/41 | 199764 | 93/13.08.08/EE(M)-II | M/s Vijay Const | 14.08.08 | 22.10.08 | 199498
31 | 2008-06-20 | 21.05.08 | Dev of lane by pdg rmc and D/S from h.no.A-69 to X-1510 Rajgarh Colony C-236/41 | 199728 | 99/13.08.08/EE(M)-II | M/s Naresh Dixit Assos. | 14.08.08 | 29.09.08 | 199661
32 | 2008-08-07 | 09.07.08 | Dev of lane by pdg RMC and drainage system from h.no.3911 to 3917 in gali no.13 Shanti Mohalla C-235/41 SH(S)Z | 199920 | 145/08.09.08/EE(M)-II | M/s PS Const Co. | 18.09.08 | 17.11.08 | 199769
33 | 2008-08-07 | 09.07.08 | Pdg RMC and drainage system from h.no.3921 to 3941 in Shanti Mohalla C-235/41SH(S)Z | 199920 | 142/08.09.08/EE(M)-II | M/s Shanker Assos. | 18.09.08 | 17.11.08 | 199913
34 | 2008-08-07 | 09.07.08 | Dev of lane pdg RMC and drainage system from h.no.4928/B-33 to drain in gali 4E Masjid Mohalla East of Seelampur in C-235/41 | 199876 | 230/15.10.08/EE(M)-II | M/s Bhagwati Const Co. | 16.10.08 | 24.12.08 | 199872
35 | 2008-08-26 | 09.07.08 | D/O lane by pdg RMC and drainage system from h.no.4928/A-26 to h.no.4928/A/35/1 in Masjid Mohalla East Old Seelampur C-235/AC-41/SH(S)Z | 299908 | 234/15.10.08/EE(M)-II | M/s Vijay Const | 25.10.08 | 24.12.08 | 299908
36 | 26.08.08 | 09.07.08 | Dev of lane by pdg RMC and drainage system from h.no. 3928 to 3921 in Shanti mohalla SH(S) | 199919 | 197/30.09.08/EE(M)-II | M/s United Const Co. | 01.10.08 | 09.12.08 | 199919
37 | 04.09.08 | 09.07.08 | Dev of lane by pdg RMC and drainage system from h.no. 3928/B-16 Hanuman Mandir in Masjid mohhala east old seelampur SH(S) | 299762 | 235/15.10.08/EE(M)-II | M/s MK Const Co. | 16.10.08 | 24.12.08 | 299622
38 | 04.09.08 | 09.07.08 | Dev of lane pdg RMC and drainage system from h.no.3928/6-B to 4928/B-20 in gali no.4-1 Masjid Mohalla East of Seelampur in C-235/41 | 399832 | 236/24.10.08/EE(M)-II | M/s Jagdamba Assos. | 03.11.08 | 02.01.09 | 399802
39 | 04.09.08 | 09.07.08 | Dev of lane by pdg RMC and drainage system from h.no. 4928/A/1 to drain in gali no.3 masjid mohalla in east old Seelampur Sh(S) | 397000 | 263/08.12.08/EE(M)-II | M/s NC & Co. | 18.12.08 | 28.08.08 | 395130
40 | 10.10.08 | 09.07.08 | Dev of gali no.9 and its link by pdg RMC and D/s Amar mohalla in Sh(S) | 478600
41 | 10.10.08 | 09.07.08 | Dev of main road by pdg RMC and drainage system in Amar Mohalla Sh(S) | 480000 | 407/26.02.09/EE(M)-II | M/s Manish Const. Co. | 08.03.09 | 07.05.09 | 478260
42 | 10.10.08 | 09.07.08 | Dev odf lane by pdg RMC and drainage system from h.no. 5310 to 7533Raghubarpura-II Sh(S) | 489600
43 | 10.10.08 | 09.07.08 | Dev of gali no./2 and its link by pdg CC pav. And dainage system in Nanak Basti in Sh(S) | 497700
44 | 10.10.08 | 09.07.08 | Dev of lane by pdg RMC and D/s nerar h.no. 3106 and 3111 to 3168 Raghubarpura 2 Sh(S) | 470000
45 | 10.10.08 | 09.07.08 | dev of lane pdg RMC and drainage system from h.no. 1280 to gali no.4 Raj Garh cly. Sh(S) | 454900
46 | 10.10.08 | 09.07.08 | Dev of lane by pdg and drainage system from h.no. 3044 Gurudwara Raghubarpura Sh(S) | 480300
47 | 10.10.08 | 09.07.08 | Dev of lane by pdg RMC and D/s near h.no. 2959 an h.no. 3050 and link between gali no.4 & 5 Sh(S) | 394000
48 | 10.10.08 | 09.07.08 | Dev of lane by pdg RMC and D/s near h.no.3775 3864 Shanti mohalla Sh(S) | 417000

## AC-42
S.No | DOB | DOC | Name of Works | Amount Booked | Work order no with date | Name of Agency | DOS | DOC | Amount Verified | Remarks
1 | 2008-06-23 | 24.05.08 | covering of drain at E-Block Krishna Ngr. by pdg rmc in C-229/42 | 497772 | 181/12.08.08/EE(M)-II | M/s Bachu Lala Sharma | 21.08.08 | 20.10.08 | 493797
2 | 2008-06-23 | 24.05.08 | Pdg rmc and drain in gali no.4 and 5 in A-Block krishna Ngr. C-229/42 | 498715 | 182/12.08.08/EE(M)-II | M/s Ahuja Const. | 18.08.08 | 15.10.08 | 498715
3 | 2008-07-28 | 24.05.08 | Stg. of road by pdg mastic asphalt from h.no. F-14/15 to desu office in F block Krishna NAgar in C-229/42 | 696400
4 | 2008-07-28 | 24.05.08 | Stg. of road by pdg mastic aspkalt from road no.57 to Hari Raj marg & J-5/7 in A block east Krishna Nagar in C-229/42 | 697400
5 | 2008-08-07 | 24.05.08 | Dev of lane by pdg RMC and drainage system in opp.lane of gali no.7 to gali no.10 Shankar Ngr.Extn. C-235/42 SH(S)Z | 199848 | 140/01.12.08/EE(M)-II | M/s Honda Assos. | 05.09.08 | 19.11.08 | 19843
6 | 2008-08-07 | 15.07.08 | Dev of lane by pdg RMC and drainage system in gali no.5 Eat of Azad Ngr.C-235/42 SH(S)Z | 199888 | 178/22.09.08/EE(M)-II | M/s NC & Co. | 02.10.08 | 31.12.08 | 199840
7 | 2008-08-11 | 15.07.08 | Stg of road by pdg mastic asphalt from h.no.23 to 34 and its link in Gyan Park in C-231/42 | 632000 | 504/09.02.09/EE(M)-II | M/s Y.K. builders | 02.03.09 | 16.05.09 | 631749
8 | 2008-08-11 | 07.07.08 | Dev of lane by pdg RMC and its link along h.no.A-21 and C-4 in Rashid Mkt.in C-231/42 SH(S)Z | 399600 | 469/19.01.09/EE(M)-II | M/s Bachu Const Co. | 04.02.09 | 13.03.09 | 325697
9 | 2008-08-11 | 07.07.08 | Stg of road by pdg mastic asphalt near h.no.63 and 96 in Radheypuri Extn.-II in C-232/42 | 996000 | 515/17.02.09/EE(M)-I | M/s Maman Singh Wadhwa | 20.02.09 | P | 995902
10 | 2008-08-11 | 07.07.08 | Stg of road by pdg mastic asphalt near h.no.A-20 and 74A in 33 in Radheypuri Extn.-II in C-232/42 | 993300 | 483/30.01.09/EE(M)-I | M/s Pawan Bros. | 13.02.09 | P | 943635
11 | 2008-08-11 | 07.07.08 | Stg of road by pdg mastic asphalt near h.no.A-11 and B-5/28 in B-Block Krishna ngr. in C-229/42 SH(S)Z | 789900
12 | 2008-08-21 | 11.07.08 | Stg of road by pdg mastic asphalt near h.no.48 pandit park to h.no.244/19 Ghondi in C-231/42 | 718600 | 481/30.01.09/EE(M)-I | M/s M.G. Goel Const Co. | 08.02.09 | 18.04.09 | 716103
13 | 2008-08-21 | 11.07.08 | Stg of lane no.5 and its link by pdg mastic asphalt in Rashid Mkt.in C-231/42 | 754500 | 502/09.02.09/EE(M)-I | M/s Maman Chand Bansal | 02.03.09 | 16.05.09 | 754167
14 | 2008-08-26 | 07.07.08 | Dev of lane by pdg RMC and D/S in gali no.10 Shankar Ngr.Extn.C-235/AC-42/SH(S)Z | 199775 | 186/30.09.08/EE(M)-II | M/s Wadhwa & Co. | 01.10.08 | 09.12.08 | 199770
15 | 2008-08-26 | 07.07.08 | Stg.of road by pdg Mastic Asphalt on main road Lal Mandir and gali no.3 and 4 Radheypuri in C-229/AC-42/SH(S)Z | 999657 | 477/30.01.09/EE(M)-I | M/s Maman Chand Bansal | 06.02.09 | P | 983643
16 | 2008-08-26 | 15.07.08 | Stg.of road by pdg Mastic Asphalt from h.no.K-63 to K-75 in C-229/AC-42/SH(S)Z | 560600 | 453/12.01.09/EE(M)-I | M/s Roshan Lal Volra & Sons. | 20.01.09 | P | 510431
17 | 2008-09-29 | 02.08.08 | Imp. of d/s and covering of drain from h.no. B-1 to B-48 in Jittar Nagar in B block AC-42/232 Shah(S) | 689600 | 459/26.01.09/EE(M)-I | M/s S.G. Goel & Co. | 06.02.09 | 23.04.09 | 665286
18 | 2008-08-11 | 02.08.08 | Stg of road by pdg mastic asphalt near h.no. A-20 and A-24 in A-Block Jagatpuri in AC-42/232 | 694620 | 387/01.12.08/EE(M)-II | M/s Maman Chand Bansal | 18.02.09 | 30.04.09 | 666060
19 | 2008-08-29 | 17.07.08 | Imp of D/S and covering of drain near h.no. A-1 to A-46 in A-Block Jittar Ngr. in AC-42/232 | 693200 | 506/09.02.09/EE(M)-I | M/s Bachan Const Co. | 24.02.09 | 04.05.09 | 693072
20 | 2008-08-29 | 19.07.08 | Stg of road by pdg mastic asphalt near h.no. A-5 and A-22 in Jagatpuri in AC-42/232/SH(S)Z | 997015 | 507/09.02.09/EE(M)-I | M/s Hans Kumar Jain | 26.02.09 | 24.04.09 | 995900
21 | 2008-08-29 | 17.07.08 | Stg of lane no.1 by pdg mastic asphalt in Shyam Ngr.in AC-42/231 | 685000 | 463/16.01.09/EE(M)-I | M/s Maman Chand Bansal | 23.01.09 | P | 482981
22 | 2008-08-29 | 19.07.08 | Stg of Bhagat Singh road by pdg mastic asphalt from h.no.6 Satnam Park from h.no.108 Ram Ngr.Ext. in C-231/42 | 610000 | 464/16.01.09/EE(M)-I | M/s Bansal Const Co. | 24.02.09 | 17.04.09 | 609457
23 | 2008-08-29 | 17.07.08 | Stg of main road by pdg mastic asphalt from h.no.110 Ram Ngr.Ext. to link road in C-231/42 | 792500 | 510/16.02.09/EE(M)-I | M/s Maman Chand Bansal | 02.03.09 | 23.05.09 | 792496
24 | 2008-08-29 | 19.07.08 | Stg of main road by pdg mastic asphalt from h.no.E-24 East Chandar Ngr. to h.no. H-11 in East Chandar Ngr. in C-231/42 | 983500 | 503/09.02.09/EE(M)-I | M/s Maman Chand Bansal | 27.02.09 | P | 934194
25 | 2008-08-29 | 19.07.08 | Stg of lane no.2 by pdg mastic asphalt in Old Govindpura Ext.in C-231/42 | 653400 | 462/16.01.09/EE(M)-I | M/s Pradeep Kumar Goel | 04.02.09 | 24.04.09 | 653039
26 | 2008-08-29 | 17.07.08 | Stg of lane no.4 and lane along Ser.Sec. School in Old Govindpura Ext.in C-231/42 | 666000 | 505/09.02.09/EE(M)-I | M/s Man Mohan Singh Wadhwa | 26.02.09 | 16.05.09 | 665671
27 | 2008-09-04 | 17.07.08 | Dev of lane by pdg RMC and drainage system in gali no.7 Kanti Ngr.Ext.C-235/AC-42/SH(S)Z | 399942 | 264/08.12.08/EE(M)-II | M/s NC & Co. | 18.12.08 | 17.02.09 | 399925
28 | 2008-09-22 | 15.07.08 | Dev of lane by pdg RMC and drainage system in gali no. 9 Krishna nagar extn. 235/Shah(S) Zone | 373800 | 277/16.12.08/EE(M)-II | M/s Hans Kumar Jain | 22.12.08 | 25.12.08 | 373712
29 | 2008-09-22 | 15.07.08 | Stg. of road by pdg mastic asphalt from h.no. B-9/24 to B-17/8 in B block Krishna Nagar w.no.229/Sh(S) | 660450
30 | 2008-09-25 | 19.07.08 | Stg. of road by pdg mastic asphalt from Chhochi Bldg Chowk to main road Raghubarpura in C-229/AC-42 | 556000
31 | 2008-09-25 | 19.07.08 | Stg. of road by pdg mastic asphalt from A-Block Park to B-11/10 in B-Block Krishna Ngr. in C-229/42/SH(S)Z | 700000 | 511/16.02.09/EE(M)-I | M/s Y.K. builders | 23.02.09 | 23.04.09 | 700000
32 | 2008-10-03 | 19.07.08 | Stg. of road by pdg mastic asphalt from h.no. F-24/1 to F-6/24 F block Krishna nagar ni w.no. 229/Sh(S) | 900000
33 | 2008-07-28 | 02.08.08 | Stg of road by pdg mastic asphalt in galoi no.1 and 3 old Arjun nagar in w.no.229 | 776014 | 490/04.02.09/EE(M)-II | M/s Maman Chand Bansal | 27.02.09 | P | 762481

## AC-43
S.No | DOB | DOC | Name of Works | Amount Booked | Work order no with date | Name of Agency | DOS | DOC | Amount Verified | Remarks
1 | 2008-06-17 | 19.05.08 | Imp of road in G-Block Preet vihar C-228 | 2407000 | 203/30.09.08/EE(M)-II | M/s Suresh Kumar Goel | 09.10.08 | P | 2185403
2 | 2008-06-17 | 19.05.08 | Imp of road in C and D Block Preet vihar and Gagan Vihar h.no.82 to 98, 100 to 1061 C-228 | 2475000 | 202/30.09.08/EE(M)-II | M/s Suresh Kumar Goel | 09.10.08 | 08.12.08 | 2267706
3 | 2008-06-17 | 19.05.08 | Imp/Stg of road in G-Block Preet vihar (H.no.G-22 G-53) Chitra Vihar and Shanker Vihar w.no.228 | 2485000 | 204/30.09.08/EE(M)-II | M/s Suresh Kumar Goel | 09.10.08 | P | 1671340
4 | 2008-06-18 | 23.05.08 | P/O semi high mast pole near choupal in MPL. park opp.h.no.125/2 Kakardooma Vill. AC-43/225 | 446034 | 66/03.09.08/EE(E)-V | M/s Perfect Elect Works | 11.10.08 | 19.09.08 | 349040
5 | 2008-06-18 | 23.05.08 | P/O semi high mast pole near h.no.B-43 Preet vihar AC-43/225 | 242937 | 70/03.09.08/EE(E)-V | M/s Perfect Elect Works | 08.09.08 | 06.10.08 | 168164
6 | 2008-06-18 | 23.05.08 | P/O semi high mast pole near h.no.99 and h.no.289 in Mpl.prak AGCR Enclave AC-43 | 439866 | 65/03.09.08/EE(E)-V | M/s Perfect Elect Works | 11.10.08 | 18.09.08 | 339232
7 | 2008-06-18 | 23.05.08 | P/O semi high mast pole opp. Kala Niketan School In Gazipur Vill. AC-43 | 248319 | 63/03.09.08/EE(E)-V | M/s Perfect Elect Works | 08.09.08 | 06.10.08 | 169123
8 | 2008-06-18 | 23.05.08 | P/O semi high mast pole nar in Municipal park opp. h.no. 225 Karkardooma Village AC-43 | 237748 | 61/03.09.08/EE(E)-V | M/s Perfect Elect Works | 11.10.08 | 19.09.08 | 172045
9 | 2008-06-18 | 23.05.08 | P/O semi high mast pole at behind Mother dairy in central park C block Nirman Vihar and corner of gali no.3 GAzipur in Ac-43/Sh(S) | 470529 | 67/03.09.08/EE(E)-V | M/s Perfect Elect Works | 12.09.08 | P | 336951
10 | 2008-06-20 | 29.04.08 | Dev of Vishwas naghar c/o road by pdg cc and drainage of gali no.6 and half (KDS) in vishwas nagar c-226/AC-40 | 300000 | 50/15.07.08/EE(M)-II | M/s Guru Kripa Entp. | 23.07.08 | 23.09.08 | 223574
11 | 2008-06-20 | 30.05.08 | C/o road by pdg RMC from h.no. 131, 107 and 148 back lane to h.no. 158 in saini enclave in C-225/AC-43 | 297300 | 147/08.09.08/EE(M)-II | M/s Sarawati Const Co. | 08.09.08 | P | 279053
12 | 2008-06-20 | 02.06.08 | C/o road by pdg mastic carpeting in back side of delhi Administrative flats in Karkardooma village in C-225/AC-43 | 566913 | 110/13.08.08/EE(M)-II | M/s Sona Const. | 03.09.08 | P | 561913
13 | 2008-06-20 | 02.06.08 | C/o road by pdg RMC and drain in lane no. 13,12 and link in Karkardooma village w.no. C-225/AC-43 | 389307 | 47/15.07.08/EE(M)-II | M/s Niranjan Singh | 24.07.08 | 24.10.08 | 389193
14 | 2008-06-26 | 29.04.08 | Prov.of lighting arrangement in Kasturba Gandhi Park New vihwas Ngr. AC-43 | 389723 | 112/15.10.08/EE(E)-V | M/s Maanu Elect. | 22.10.08 | 21.11.08 | 353153
15 | 2008-06-26 | 29.04.08 | Dev/Stg of road by pdg mastic asphalt in gali no.2,4,6 and 8 in New Govindpura in C-228/AC-43 | 1643000 | 158/10.09.08/EE(M)-II | M/s Sona Const. | 18.08.08 | P | 1607622
16 | 2008-08-05 | 29.04.08 | P/L cc pav.and dev of sw drain in lane no.B-6 to B-16,A-15 to A-18 in East Arjun Ngr.Visvash Ngr.C-226 | 531100 | 299/16.12.08/EE(M)-II | M/s Bhagwati Const Co. | 26.12.08 | P | 391279
17 | 2008-08-05 | 29.04.08 | P/F Name Boards in Anand Vihar AC-43 Visvash Ngr.in C-225 | 500000 | 320/26.12.08/EE(M)-II | M/s Bhagwati Const Co. | 04.01.09 | P | 478261
18 | 2008-08-05 | 29.04.08 | P/L cc pav.and dev of sw drain in lane from h.no.C-25 to C-16,D-23 in East Arjun Ngr.Visvash Ngr.C-226 | 263100 | 300/16.12.08/EE(M)-II | M/s Bhagwati Const Co. | 26.12.08 | P | 194559
19 | 2008-08-05 | 29.04.08 | Dev of approved colony- Stg and dev of drainage system from h.no.46 to 62 and 161 to 174 and 233b to 214,215 to 232 in Surya Niketan C-225 | 760078 | 348/27.01.09/EE(M)-II | M/s Aspiration builders | 05.02.09 | P | 713173
20 | 2008-08-26 | 29.04.08 | I/S of road in A and B Block Preet Vihar C-228/AC-43/SH(S)Z | 2275245
21 | 2008-08-26 | 29.04.08 | I/S of road in Gagan Vihar by pdg mastic asphalt from h.no. 36 to 41,73 to 69,66 to 59,54 to 47,BSES Office to 349,348 to 333 and 343 to 308 in C-228/AC-43/SH(S)Z | 2473000
22 | 2008-08-26 | 29.04.08 | I/S of road in Gagan Vihar by pdg mastic asphalt in East Guru Angad Ngr. and East Laxmi Mkt. in C-228/AC-43/SH(S)Z | 2278963 | 382/16.02.09/EE(M)-II | M/s Sona Const. | 02.03.09 | P | 2203518
23 | 2008-06-26 | 29.04.08 | C/O road by pdg mastic carpetting of Kunti Marg from gali no.4 to gali no.10 in Vishwas Ngr. in C-226/AC-43/SH(S)Z | 625778 | 159/10.09.08/EE(M)-II | M/s Sona Const. | 15.10.08 | P | 590778
24 | 2008-09-02 | 10.04.08 | Covering and development of Nallah from gali no. 4 Pandav road side Vishwas nagar in w.no.226/Sh(S) | 443600 | 334/19.01.09/EE(M)-II | M/s Sanjay Kumar Gupta | 21.01.09 | 18.04.09 | 443600
25 | 2008-09-02 | 02.06.08 | Covering and development of Nallah from gali no. 4 and 8 Pandav road side Vishwas nagar in w.no.226/Sh(S) | 443600 | 333/19.01.09/EE(M)-II | M/s Sanjay Kumar Gupta | 23.01.09 | 28.02.09 | 443355
26 | 2008-09-02 | 03.07.08 | Dev. of 60" road Vishwas nagar by constructing foot path on covering of existing nallah in w.no226/Sh(S) from gali no. 13 to gali no.17 (KDS) | 499707 | 190/30.09.08/EE(M)-II | M/s Ahuja Const. | 08.10.08 | 08.12.08 | 499707
27 | 2008-06-26 | 03.07.08 | C/o road by pdg mastic carpeting in Daksh road (PRS) in Vishwas nagar in w.no.226/Sh(S) | 684645 | 160/10.09.08/EE(M)-II | M/s Maman Chand Bansal | 19.09.08 | P | 675187
28 | 2008-06-26 | 03.07.08 | C/O road by pdg cc and imp to drainage to gali no.8,9 half(RHS) in Vishwas Ngr. in C-226/AC-43/SH(S)Z | 311000 | 49/15.07.08/EE(M)-II | M/s Guru Kripa Entp. | 24.07.08 | 20.09.08 | 231627
29 | 2008-06-26 | 03.07.08 | C/O road by pdg mastic carpetting of Kunti Marg from gali no.15 to gali no.17 in Vishwas Ngr. in C-226/AC-43/SH(S)Z | 579398 | 107/13.08.08/EE(M)-II | M/s Sona Const. | 09.10.08 | P | 554398
30 | 2008-06-26 | 10.04.08 | C/O road by pdg mastic carpetting in gali no.12(KDS)Vishwas Ngr. in C-226/AC-43/SH(S)Z | 560267
31 | 2008-06-26 | 10.04.08 | C/O road by pdg mastic carpetting in Siddharth Gali, gali no.10(PRS)in Vishwas Ngr. in C-226/AC-43/SH(S)Z | 466376 | 111/13.08.08/EE(M)-II | M/s Sona Const. | 22.08.08 | P | 456242
32 | 2008-06-26 | 10.04.08 | C/O road by pdg mastic carpetting in Nehru Gali (PRS) in Vishwas Ngr.in C-226/AC-43/SH(S)Z | 542253 | 106/13.08.08/EE(M)-II | M/s Sona Const. | 15.09.08 | P | 524772
33 | 2008-06-26 | 08.07.08 | C/O road by pdg mastic carpetting in Karan Gali in (KDS)Vishwas Ngr.in C-226/AC-43/SH(S)Z | 573421 | 108/13.08.08/EE(M)-II | M/s Sona Const. | 24.09.08 | P | 556898
34 | 2008-06-26 | 04.07.08 | C/O road by pdg mastic carpetting from gali no.10 to gali no.15 in Vishwas Ngr.in C-226/AC-43/SH(S)Z | 598462 | 105/13.08.08/EE(M)-II | M/s Sona Const. | 09.10.08 | P | 315198
35 | 2008-06-26 | 24.07.08 | C/O road by pdg mastic carpetting in gali no.2 (KDS) in Vishwas Ngr.in C-226/AC-43/SH(S)Z | 671218 | 157/10.09.08/EE(M)-II | M/s Sona Const. | 10.10.08 | P | 654202
36 | 2008-09-02 | 24.07.08 | Dev of Vishwas Ngr. by covering of existing drain along 60 feet road and c/o footpath from Arjun gali to gali no.2 Vishwas Ngr.in C-226/AC-43/SH(S)(KDS) | 489707 | 241/24.10.08/EE(M)-II | M/s Shiv Shakti Const Co. | 03.01.08 | 01.01.09 | 489707
37 | 2008-09-02 | 24.07.08 | P/L RMC m-20 grade and d/o SW drain in gali no.6,10(small gali)in Bhisham Singh Colony Vishwas Ngr.in C-226/AC-43/SH(S) | 463399 | 312/26.12.08/EE(M)-II | M/s Manish Const Co. | 01.01.09 | 09.02.09 | 462603
38 | 2008-09-03 | 24.07.08 | Dev of approved colony stg. of road along DMRC wall from h.no.40 to 73 jagriti Enclave in C-225/AC-43/SH(S)Z | 470372 | 242/24.10.08/EE(M)-II | M/s Kapil Kumar Puri | 20.10.08 | 28.03.09 | 458648
39 | 2008-09-03 | 24.07.08 | Stg. of road along DAV Public School Sresththa Vihar C-225/AC-43/SH(S)Z | 479700 | 226/07.10.08/EE(M)-II | M/s Swaraj Const Co. | 15.10.08 | P | 390022
40 | 2008-10-10 | 10.10.08 | P/O street light fitting at various cly. in AC-43/under Sh(S) (Anand Vihar, rishab vihar, jagrati enclave, Bahubali enclave, priya enclave, Saini enclave, Shri Ram enclave, Suraj vihar, vivek vihar etc.0 | 273965 | 236/02.03.09/EE(E)-V | M/s Repair Shop | 02.03.09 | 25.03.09 | 244453
41 | 2008-10-10 | 20.08.08 | C/o road by pdg mastic carpet from h.no.82 to 92 in Vigyan vihar w.no.225/AC-43 Sh(S)_ | 597600
42 | 2008-10-10 | 06.09.08 | covering of drain in dayanand vihar from School to h.no. 270 and 183 in w.no.228 sh(S) | 599175 | 393/19.02.09/EE(M)-II | M/s Bachu Lala Sharma | 25.02.09 | 26.05.09 | 354875

## AC-44
S.No | DOB | DOC | Name of Works | Amount Booked | Work order no with date | Name of Agency | DOS | DOC | Amount Verified | Remarks
1 | 2008-06-20 | 29.04.08 | Prov. of Tubewell at park J and K h.no.104 Dilshad Garden w.no.240/AC-44 | 136577 | 279/23.07.08/EE(E)Hort | M/s Bharat Elect. & Elect. | 29.07.08 | 29.08.08 | 127312
2 | 2008-06-20 | 29.04.08 | Prov. of Tubewell at park J and K h.no.88 Dilshad Garden w.no.240/AC-44 | 135648 | 278/23.07.08/EE(E)Hort | M/s Sury Lite Entp. | 30.08.08 | 06.11.08 | 133499
3 | 2008-06-20 | 29.04.08 | Prov. of Tubewell at park J and K h.no.42 Dilshad Garden w.no.240/AC-44 | 135968 | 280/23.07.08/EE(E)Hort | M/s Moni Elect. | 31.07.08 | 29.08.08 | 135646
4 | 2008-06-20 | 22.05.08 | P/L rmc in lane near railway line in Bhihari Colony w.no.237/AC-44 | 95633 | 86/13.08.08/EE(M)-II | M/s Shiv Bhan Sharma | 14.08.08 | 27.09.08 | 95580
5 | 2008-06-20 | 22.05.08 | P/L rmc in lane near Hari Mandir gali in Jawala Ngr. in w.no.238/AC-44 | 193946 | 81/23.08.08/EE(M)-II | M/s M.K. Const Co. | 14.08.08 | 27.09.08 | 193855
6 | 2008-06-20 | 22.05.08 | P/L rmc in lane adj to Prop. no. 455 in Jawala Ngr. w.no.238/AC-44 | 197000 | 83/13.08.08/EE(M)-II | M/s Jai Bhawani Assos. | 18.08.08 | 21.09.08 | 197000
7 | 2008-06-20 | 22.05.08 | P/L rmc in in gali no.8 Bhaihari Colony in w.no.237/AC-44 | 195705 | 82/13.08.08/EE(M)-II | M/s Jindal builders | 14.08.08 | 07.10.08 | 195688
8 | 2008-06-20 | 22.05.08 | P/L rcc culvert and MS jalls at different drain crossing in w.no./44 | 182234 | 79/13.08.08/EE(M)-II | M/s Vinay Const/. | 20.08.08 | 20.10.08 | 182151
9 | 2008-06-20 | 22.05.08 | P/L rmc in lane portion from Prop.no.221 towards prop.no. 740 in jawala Ngr.C-238/44 | 494000 | 207/07.10.08/EE(M)-II | M/s guru Kripa Entp. | 10.10.08 | 15.01.09 | 376759
10 | 2008-06-20 | 22.05.08 | P/L rmc in gali no.3 bhihari colony in w.no.237/AC-44 | 394000 | 113/25.08.08/EE(M)-II | M/s Vijay Const. | 26.08.08 | 15.10.08 | 392971
11 | 2008-06-20 | 22.05.08 | P/L rmc in lane near flat no.227 and 236 in Shiva Khand in Vishvkarma Ngr. in w.no.238/AC-44 | 197000 | 218/07.10.08/EE(M)-II | M/s Naresh Dixit Assos. | 08.10.08 | 08.11.08 | 194087
12 | 2008-06-20 | 22.05.08 | P/L rmc in lane adj to prop.no.346 in Bhola Nath Ngr. in w.no.237/AC-44 | 199423 | 89/13.08.08/EE(M)-II | M/s Rajesh Assos. | 16.08.08 | 06.10.08 | 199408
13 | 2008-06-20 | 22.05.08 | P/L rmc in lane behind Gaushala in Bhola Nath Ngr. in w.no.237/AC-44 | 199000 | 84/13.08.08/EE(M)-II | M/s Jai Chanda Assos. | 16.08.08 | 06.10.08 | 199000
14 | 2008-06-20 | 22.05.08 | P/L rmc in lane and link adj to prop.no.202 in Mohalla Gudai in Shahdra Vill. in w.no.237/AC-44 | 370600 | 171/17.09.08/EE(M)-II | M/s Saraswati Const Co. | 28.09.08 | P | 300071
15 | 2008-06-20 | 22.05.08 | P/L rmc at Church road adj to St. John school in jawala Ngr.in w.no.238/AC-44 | 585200 | 169/17.09.08/EE(M)-II | M/s Saraswati Const Co. | 18.09.08 | P | 469055
16 | 2008-06-20 | 22.05.08 | P/L rmc at Church road starting from Shiv Mandir chowk in jawala Ngr.in w.no.238/AC-44 | 591600 | 183/30.09.08/EE(M)-II | M/s Saraswati Const Co. | 01.10.08 | 29.12.08 | 466457
17 | 2008-06-20 | 22.05.08 | P/L rmc in lane from Kali Mata Mandir chowk to gali no.6 in jawala Ngr.in w.no.238/AC-44 | 477000 | 170/17.09.08/EE(M)-II | M/s Saraswati Const Co. | 18.09.08 | 25.11.08 | 384344
18 | 2008-07-08 | 22.05.08 | P/l RMC in gali masjid wali in Jwala nagar C-238/44 | 356000 | 338/19.01.09/EE(M)-II | M/s guru Kripa Entp. | 22.01.09 | 24.04.09 | 355579
19 | 2008-07-08 | 22.05.08 | P/l RMC in lane adj. to MC Pry School in Jwala nagar C-238/44 | 522000 | 340/19.01.08/EE(M)-II | M/s Aspiration builders | 23.01.09 | 28.05.08 | 522000
20 | 2008-07-25 | 23.07.08 | P/O tube well at 251 Shiva khurd w.no. 238 | 139363 | 426/07.08.08/EE(E)-Hort. | M/s Kahiraan Elect. | 25.08.08 | 13.09.08 | 138737
21 | 2008-08-29 | 17.07.08 | P/L RMC in lane adj to Property no.4/2265 in Behari Colony in C-237/AC-44/SH(S)Z | 196828 | 197/30.09.08/EE(M)-II | M/s Vijay Const. | 06.10.08 | 01.12.08 | 196828
22 | 2008-08-29 | 17.07.08 | P/L RMC in gali no.12 Mahabir Block Bholanath Ngr.in C-237/AC-44/SH(S)Z | 376000 | 196/30.09.08/EE(M)-II | M/s Rajesh Assos. | 03.10.08 | 11.11.08 | 375327
23 | 2008-08-29 | 17.07.08 | P/L RMC in gali no.11 adj to house of Devi Sahey in Bholanath Ngr.in C-237/AC-44/SH(S)Z | 567000 | 339/19.01.09/EE(M)-II | M/s guru Kripa Entp. | 22.01.09 | P | 419252
24 | 2008-08-29 | 17.07.08 | P/L RMC in gali no.4 Property no.4/2755 in Behari Colony in C-237/AC-44/SH(S)Z | 498000 | 185/30.09.08/EE(M)-II | M/s Jai Rishab Const & Elect. | 01.10.08 | 12.12.08 | 496994
25 | 2008-08-29 | 17.07.08 | P/L cc in lane adj to Property no.278,299 in Mohalla Doorga in Shahdra Village in C-237/AC-44/SH(S)Z | 296000 | 337/19.01.09/EE(M)-II | M/s Guru Kripa Entp. | 21.01.09 | 19.02.09 | 295842
26 | 2008-09-03 | 19.07.08 | Dev of Chowraha/lane adj to flat no.126 to 130,144,197,etc by pdg cc pav in J and K Block Poohit Dilshad Garden in AC-44/SH(S)Z | 347561 | 325/19.09.08/EE(M)-III | M/s Vikas Jain | 24.09.08 | 21.11.08 | 346322
27 | 2008-09-03 | 21.07.08 | Dev to lane by cc pav near h.no. 181,185,192 in E-Pkt.Dilshad Garden in C-239/AC-44/SH(S)Z | 499807 | 328/19.09.08/EE(M)-III | M/s SK Assos. | 25.09.08 | 16.01.09 | 499807
28 | 2008-09-03 | 16.06.08 | Dev to drainage system by perfaraled slab from L-111 to L-95 in L-Pkt.Dilshad Garden in AC-44/SH(S)Z | 479980 | 334/19.09.08/EE(M)-III | M/s Ashwini Kumar Agg. | 24.09.08 | 26.11.08 | 478902
29 | 2008-09-03 | 16.06.08 | Dev to road by m/premixing from Factory no.2 to 29 DSIDC Sheds in A-Block Jhilmil Industrial Area in AC-44/SH(S)Z | 499647 | 323/19.09.08/EE(M)-III | M/s Lalit Sharma | 26.09.08 | P | 479616
30 | 2008-09-03 | 16.06.08 | Dev ot drainage system adj flat no.133,153,27,43,etc by perfarcoted slab in H-Pkt. Dilshad Garden in AC-44/SH(S)Z | 499686 | 324/19.09.08/EE(M)-III | M/s Mahesh Bansal | 27.09.08 | 16.01.09 | 497454
31 | 2008-09-03 | 17.07.08 | P/L RMC in gali no.10 (Rly.line side)in Bihari Colony in C-237/AC-44/SH(S)Z | 193369 | 227/15.10.08/EE(M)-II | M/s Rajesh Assos. | 17.10.08 | 28.11.08 | 192777
32 | 2008-09-03 | 17.07.08 | P/L RMC in gali no.9 and 10(from Idgah Road)in Bholanath Ngr. in C-237/AC-44/SH(S)Z | 197482 | 211/07.10.08/EE(M)-II | M/s Sharma Assos. | 11.10.08 | 10.11.08 | 196605
33 | 2008-09-03 | 17.07.08 | P/L RMC in gali no.6(adj to property no.251/2A)in Bholanath Ngr. in C-237/AC-44/SH(S)Z | 198218 | 228/15.10.08/EE(M)-II | M/s PS Const Co. | 18.10.08 | 17.12.08 | 197951
34 | 2008-09-05 | 17.07.08 | P/L RMC in lanes adj to property no.P-10 and P-28 in Shri Ram Colony, Bihari Colony in C-238/AC-44 | 439000 | 223/07.10.08/EE(M)-II | M/s Bachu Lal Sharma | 08.11.08 | 10.12.08 | 438280
35 | 2008-09-05 | 17.07.08 | P/L RMC in lane adj to property no. 4/2720 and P-71 in Shri Ram Colony Bihari Colony in C-238/SH(S)Z | 463000
36 | 2008-09-19 | 17.07.08 | P/L RMC in Narrow laneadj to Baburam School in Gajju Katra in C-237/AC-44 | 184394 | 271/16.12.08/EE(M)-II | M/s Shejada Const | 17.12.08 | 14.01.09 | 184329
37 | 2008-10-06 | 17.07.08 | P/L RMC in lane adj to property no. E-127 and E-129 in jhilmil cly. in w.no. 238 Sh(S) | 200000 | 269/16.12.08/EE(M)-II | M/s Prem Const Co. | 23.12.08 | 07.02.09 | 200000
38 | 2008-10-08 | 17.07.08 | P/l RMC in lane adj to property no. E-84 jhilmil cly. w.no.238/Sh(S) | 499000 | 286/16.12.08/EE(M)-II | M/s Shiv Bhan Sharma | 17.12.08 | 24.03.09 | 498871
39 | 2008-10-08 | 17.07.08 | P/L RMC in lane adj to property no. 27/96 and 27/61 in jwala nagar in w.no.238/Sh(S) | 278853 | 257/08.12.08/EE(M)-II | M/s Naresh Dixit Assos. | 15.12.08 | 12.02.08 | 278659
40 | 2008-10-08 | 17.07.08 | P/l RMC in lane adj to property no. 28/18A/72 Bholanath nagar w.no.237/Sh(S) | 196365 | 270/16.12.08/EE(M)-II | M/s KK Const. | 18.12.08 | 27.01.09 | 196365
41 | 2008-10-10 | 09.09.08 | P/l RMC in lane adj to property no. P-102 and A-23 in Shri ram cly., Bhihari cly. w.no.237/Sh(S) | 495000 | 355/10.02.09/EE(M)-II | M/s Nareender Const Co. | 12.02.09 | P | 369286
42 | 2008-10-10 | 09.09.08 | P/l RMC in lane adj to property no. 4/1644 in Mahavir block w.no.237/Sh(S) | 460000 | 366/16.02.09/EE(M)-II | M/s Jindal builders | 24.05.09 | 14.04.09 | 460000
43 | 2008-10-10 | 09.09.08 | Dev of road by Pdg m/p in Shri ram cly., Bhihari cly. w.no.237/Sh(S) | 398000