## AC-08
S.no. | Date of Booking | Date of consent | Name of work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified
1 | 2008-07-09 | 2008-05-23 | Imp of back lane by P/l interlocking tiles from h.no. B-34 to B-43 at Sarvodya Enclave in w.no. 161/Sz | 199631 | 70/08.08.08/EE(M)-II | M/s Kwality Entp. | 18.08.08 | 15.10.08 | 199631
2 | 2008-07-09 | 2008-05-23 | Imp of road berms by P/l interlocking tiles from entrance gate no. 3 to opp. B-25 at Sarvodya Enclave in w.no.161/SZ | 197607 | 91/25.08.08/EE(M)-II | M/s Gya Dass Const. Co. | 02.09.08 | 23.12.08 | 196963
3 | 2008-07-09 | 2008-05-23 | Imp of road berm by P/l interlocking tiles from h.no. D-13 to D-23 at Geetanjali Enclave in w.no.161/SZ | 198000 | 90/25.08.08/EE(M)-II | M/s Ramkesh | 10.09.08 | 31.10.08 | 198000
4 | 2008-07-09 | 2008-05-23 | Imp of B/wall and walkway infront of 10 b/k Malviya nagar in w.no.161 SZ | 199000 | 66/25.08.08/EE(M)-II | M/s Pooja Entp. | 21.08.08 | 17.10.08 | 198980
5 | 2008-07-09 | 2008-05-23 | Imp. of road by P/L intrelocking tiles from Entrance Gate no.2 to opp.h.no.B-24 at Sarvodya Enclave in C-161/SZ | 199000 | 92/25.08.08/EE(M)-II | M/s Tanwar Const. | 15.09.08 | 30.10.08 | 198779
6 | 2008-07-09 | 2008-05-23 | Imp.of back lane by P/L intrelocking tiles from h.no.B-51 to B-44 at Sarvodya Enclave in C-161/SZ | 197762 | 88/25.08.08/EE(M)-II | M/s Kuldeep Const. Co. | 28.08.08 | 10.10.08 | 197762
7 | 2008-07-09 | 2008-05-23 | Imp of foothpath adj. to gate no. 3 opp. Mothers International School by p/l interlocking tiles and kerb stone at Sarvodya Enclave in C-161/SZ | 198000 | 89/25.08.08/EE(M)-II | M/s Sunil Kumar | 02.09.08 | P | 194868
8 | 2008-07-09 | 2008-05-23 | Dev ogf lane from h.no.25/3 to 13B and adj to h.no.27 at Adchini Village in w.no 161/SZ | 199629
9 | 2008-07-24 | 2008-07-16 | Const and raising of B/wall of park in appart. Panchshil enclave in w.no.191/SZ | 199958 | 123/07.10.08/EE(M)-II | M/s Sadhara Assos. | 17.10.08 | 12.12.08 | 165603
10 | 2008-07-25 | 2008-07-17 | Pdg and laying interlocking tiles in parking area C-4 in pkt.-C Sheikh Sarai SFS-1 in w.no.191/SZ | 460000 | 162/21.10.08/EE(M)-II | M/s Pappu Seth | 30.10.08 | P | 450000
11 | 2008-07-25 | 2008-07-17 | Pdg and laying interlocking tiles in parking area C-6 in pkt.-C Sheikh Sarai SFS-1 in w.no.191/SZ | 490000 | 161/21.10.08/EE(M)-II | M/s Kuldeep Const. Co. | 30.10.08 | P | 480000
12 | 2008-07-25 | 2008-07-17 | Pdg and laying interlocking tiles in parking area B-1 and B-5 in pkt.-B Sheikh Sarai SFS-1 in w.no.191/SZ | 400000 | 152/13.10.08/EE(M)-II | M/s Pappu Seth | 22.10.08 | P | 390000
13 | 2008-08-28 | 2008-05-23 | Pdg cc from h.no. E-2/10 to E-2/16 in E block Malviya nagar in w.no.161/SZ | 174609
14 | 2008-08-28 | 2008-05-23 | Pdg cc from Balmiki temple to Sr. Sec School and h.no. 70-B in village Hauz Rani in w.no.162/SZ | 199478
15 | 2008-08-28 | 2008-05-23 | Pdg cc from h.no.282 Baba dairy to 226 to near MC Pry. School in village Hauz Rani in w.no.162/SZ | 177952
16 | 2008-08-28 | 2008-05-23 | Pdg cc from Kabab Corner to H U Khan Sherwani house and near Gandhi park in village Hauz Rani in w.no.162/SZ | 199929
17 | 2008-08-28 | 2008-05-23 | Pdg cc from h.no. 74 to Press enclave road, h.no.79 to Chaudhary Mamchan house and h.no.77 to Mamchand in village Hauz Rani in w.no.162/SZ | 199241
18 | 2008-08-28 | 2008-05-23 | Pdg cc from h.no.262 to 267/1 (Ammu) and near h.no. 148 in village Hauz Rani in w.no.162/SZ | 178391
19 | 2008-08-28 | 2008-05-23 | P/L CC in back lane of h.no.M-7913 and B-1/155 in Malviya Ngr. in C-162/SZ | 199794 | 206/19.01.09/EE(M)-II | M/s Harsha Const. | 17.02.09 | 16.06.09 | 160407
20 | 2008-08-28 | 2008-05-23 | P/L CC in back lane of h.no.B-1/1 in Malviya Ngr.in C-162/SZ | 144308
21 | 2008-08-28 | 2008-05-23 | P/L CC in back lane of h.no.1/6 in Malviya Ngr. in C-162/SZ | 147030
22 | 2008-08-28 | 2008-05-23 | P/L CC in back lane of h.no.E-3/7 to E-2/8 in E-Block Malviya Ngr. in C-162/SZ | 173343 | 198/09.01.09/EE(M)-II | M/s Harsha Const. | 16.02.09 | 18.06.09 | 139292
23 | 2008-08-28 | 2008-08-11 | Dev of road berms by pdg RMC adj park from h.no.F-11/1 to Gol Chukkar in F-Block Malviya Ngr. in C-162/SZ | 499393
24 | 2008-08-28 | 2008-08-11 | Dev of road by pdg RMC between h.no.F-11/6 and oark in F-Block Malviya Ngr. in C-162/SZ | 495049
25 | 2008-08-28 | 2008-08-11 | Dev of lane by pdg RMC between h.no.F-7/12 and F-8/12 in F-Block Malviya Ngr. in C-162/SZ | 260133
26 | 2008-08-28 | 2008-08-11 | Dev of road by pdg RMC between h.no.F-3/1 and F-4/1 in F-Block Malviya Ngr. in C-162/SZ | 254375
27 | 2008-08-28 | 2008-08-11 | Dev of road by pdg RMC between h.no.F-3/1 and F-1/4 in F-Block Malviya Ngr. in C-162/SZ | 269378
28 | 2008-08-28 | 2008-08-11 | Dev of road berm by pdg RMC between gate adj h.no.F-11/12 and Gurudwara in F-Block Malviya Ngr. in C-162/SZ | 181513
29 | 2008-10-07 | 2008-09-29 | dev of internal roads pdg RMc from h.no. 33 to 34, 25 to 26, 18 to 25, 58 to 59, 57 to 58 and around park in Kailash Kunj in w.no. 192/CZ | 367050 | 264/12.01.09/EE(M)-II | M/s Suman Assos. | 21.01.09 | 17.03.09 | 341613
30 | 2008-10-07 | 2008-09-29 | Dev of back lane by pdg RMC from h.no. M-2 to M-32 in M block GK-I i w.no. 192/CZ | 558900
31 | 2008-10-07 | 2008-09-25 | Dev of back lane by pdg interlocking tiles fromh.no. E-185 to E-203, E-286 to E-264, E-109 to E-133 in E block in GK-I in w.no. 192/CZ | 586100 | 260/05.01.09/EE(M)-II | M/s Gopal Goyal | 14.01.09 | 08.04.09 | 586100
|  |  |  | 8404553 |  |  |  |  | 4097998

## AC-09
S.no. | Date of Booking | Date of consent | Name of work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified
1 | 2008-06-23 | 2008-05-26 | Covering of drain by RCC slab near h.no.C-12 in Green Park in C-163/SZ | 499708 | 162/08.08.08/EE(M)-I | M/s Chajju Ram Bedwal | 01.10.08 | 22.12.08 | 491469
2 | 2008-06-23 | 2008-05-23 | Dev to park by prov. walkway with interlocking pavers near h.no. B-2/63 in S.j. Enclave in C-163/SZ | 199805 | 199/22.08.08/EE(M)-I | M/s Vinod Prakash Entp. | 29.08.08 | 15.01.09 | 199805
3 | 2008-06-23 | 2008-05-23 | Covering of drian by RCC slab near h.no.A-6 in Green Park in C-163/SZ | 499887 | 163/08.08.08/EE(M)-I | M/s Ravi Gupta | 14.08.08 | 28.02.09 | 499887
4 | 2008-06-23 | 2008-05-30 | P/O semi high mast light at park opp. kalu Sarai Village Sarvpriya vihar w.no.161 under SZ | 233885 | 290/20.01.09/EE(M)-I | M/s Perfect Elect. Works | 29.01.09 | 22.05.09 | 199695
5 | 2008-08-12 | 2008-07-25 | P/L interlocking tiles and RMC in lane from h.no.45 to Gurudwara and infront of Masjid at Kalu sarai in C-161/SZ | 319689
6 | 2008-08-12 | 2008-07-25 | P/L RMC in lane of Vijay Mandal janta Flats in C-161/SZ | 470317
7 | 2008-08-12 | 2008-07-25 | P/L RMC in lane of Sarvpriya Vihar Janta Flats in C-161/SZ | 247091
8 | 2008-08-25 | 2008-08-11 | P/O semi high mast light in B-1 Safdarjang Enclave in C-163/SZ | 213694 | 195/24.12.08/EE(E)-IV | M/s Electra Fusion Techn. | 02.01.09 | 01.02.09 | 203576
9 | 2008-08-28 | 2008-08-11 | P/O semi high mast light in Hauz Khas Village in C-163/SZ | 215280 | 380/26.02.09/EE(E)-IV | M/s Saturn Elect. | 26.02.08 | P | 166702
10 | 2008-08-25 | 2008-08-11 | P/O semi high mast light in park infront of h.no.285 Gulmohar Enclave in C-164/SZ | 213176 | 254/26.12.08/EE(E)-IV | M/s Pragati Engg. | 03.01.09 | 02.02.09 | 206815
11 | 2008-08-25 | 2008-08-11 | P/O semi high mast light at Sudarshan Road Gautam Ngr.in C-164/SZ | 209669 | 201/24.12.08/EE(E)-IV | M/s Maya Elect. | 01.01.09 | 30.01.09 | 193246
12 | 2008-09-16 | 2008-08-07 | Dev. of street lane by pdg cc near h.no. 34 in Hauz Khas village in C-163 SZ | 275400 | 405/30.01.09/EE(M)-I | M/s Jitender Kumar | 10.02.09 | P | 220890
13 | 2008-09-16 | 2008-08-07 | Dev of back lane by pdg cc behind S-II in Greeen park in E-163/SZ | 346550
14 | 2008-09-16 | 2008-08-07 | Stg. of road by pdg dense carpeting from X-63 to X-49 in Green park in C-163/SZ | 309800
15 | 2008-09-16 | 2008-08-07 | Dev top back lane by pdg interlocking pavers behind D-27 in Green park at C-163/SZ | 447500
16 | 2008-09-16 | 2008-08-25 | Stg. of road by pdg dense carpeting from h.no. B-6/23 to B-6/46 and near B-6/47 in SJ enclave in C-163/SZ | 568200
17 | 2008-09-16 | 2008-08-25 | Dev of street lane by pdg cc near h.no. 49/B-2 in Arjun nagar in C-163/SZ | 522700
18 | 2008-09-16 | 2008-08-25 | Dev of street lane by pdg cc near h.no. 186F in Arjun nagar in C-163/SZ | 406850
19 | 2008-09-16 | 2008-08-25 | Dev of street lane by pdg cc near h.no. 142 in Arjun nagar in C-163/SZ | 437750
20 | 2008-09-16 | 2008-08-25 | Dev of street/lane by pdg cc near h.no. 70/3 in Humayunpur in C-163/SZ | 398850 | 450/20.02.09/EE(M)-I | M/s Kuldeep Const Co. | 27.02.09 | 21.07.09 | 334703
21 | 2008-09-18 | 2008-08-25 | Dev of street/lane by pdg. cc near h.no. 62R in Humayunpur in C-163/SZ | 341650
22 | 2008-09-25 | 2008-08-22 | Dev. of pavment of main mkt. at Green park in C-163/SZ | 5000000
23 | 2008-06-18 | 2008-05-19 | Stg.of road by dense carpetting from H-47 to H-35 in Green Park Extn. in C-163/SZ | 499813 | 303/13.10.08/EE(M)-I | M/s Dhingra Const Co. | 13.11.08 | P | 2373223
24 | 2008-06-18 | 2008-05-21 | Stg. of road by dense carpetting from gate no.1 to gate no.3 in SFS Flats Kalu Sarai Vijay Mandal Enclave in C-164/SZ | 499955 | 303/13.10.08/EE(M)-I | M/s Dhingra Const Co. | 13.11.08 | P
25 | 2008-06-18 | 2008-05-13 | Stg. of road by dense carpetting from U-23 to U-13 in Green Park Extn.in C-163/SZ | 499822 | 303/13.10.08/EE(M)-I | M/s Dhingra Const Co. | 13.11.08 | P
26 | 2008-06-18 | 2008-05-13 | Stg. of road by prov. dense carpetting from U-8 to V-26 in Green Park main in C-163/SZ | 499629 | 303/13.10.08/EE(M)-I | M/s Dhingra Const Co. | 13.11.08 | P
27 | 2008-06-18 | 2008-05-15 | Stg. of road by dense carpetting from V-1 to U-12 in Green Park Extn. in C-163/SZ | 499632 | 303/13.10.08/EE(M)-I | M/s Dhingra Const Co. | 13.11.08 | P
28 | 2008-06-18 | 2008-05-15 | Dev. to road berms by prov. cc along B/Wall of DDA SFS Flats Kalu Sarai in C-164/SZ | 499764 | 191/22.08.08/EE(M)-I | M/s Aay Kay Const Co. | 12.09.08 | P | 479764
29 | 2008-06-23 | 2008-05-24 | Dev.to parking area by prov. red sand stone in DDA SFS Flats Kalu Sarai in C-164/SZ | 499950
|  |  |  | 15876016 |  |  |  |  | 5569775

## AC-10
S.no. | Date of Booking | Date of consent | Name of work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified
1 | 2008-07-04 | 2008-05-30 | P/F kota stone in open space in Sect-9 Mkt. in R.K. Puram in w.no.167/SZ | 499900 | 226/10.09.08/EE(M)-I | M/s Bahadur Singh Contct. | 11.09.08 | P | 474784
2 | 2008-07-04 | 2008-05-30 | P/F interlocking tiles from h.no.142 to h.no.1105 Sect-12,R.K. Puram w.no.167/SZ | 299600 | 227/10.09.08/EE(M)-I | M/s M.K. Entp. | 12.09.08 | 29.10.08 | 299360
3 | 2008-07-04 | 2008-05-30 | P/L RMC in side berm of Satya Sai Bal Vihar to h.no.533 Sect-5, R.K.Puram in w.no.167/SZ | 199628 | 228/10.09.08/EE(M)-I | M/s P.C. Mehraf Co. | 13.09.08 | 04.11.08 | 199628
4 | 2008-07-29 | 2008-07-09 | Dev of Bank Street by P/L RMC from Community Hall to C-211 Shop no.in Munirka Village in C-166/SZ | 199668 | 224/05.09.08/EE(M)-I | M/s Pappu Seth | 05.09.08 | 13.10.08 | 199564
5 | 2008-09-04 | 2008-08-19 | P/F Red Sand Stone on Walkway in park front of h.no.D-121 in Anand Niketan in C-168/SZ | 199550 | 276/06.10.08/EE(M)-I | M/s Pupinder Pal Singh | 13.10.08 | 30.12.08 | 199550
6 | 2008-09-05 | 2008-08-25 | Dev of lane by p/l RMC from h.no.332 to 314,321 to 326 and adj area in Munirka Village in C-166/SZ | 498942
7 | 2008-09-05 | 2008-08-25 | Dev of parking area along Mother Dairy by p/l interlocking tile of parki in mkt.infront of R.K.Puram Sec.-3 C-166/SZ | 199860 | 444/20.02.09/EE(M)-I | M/s Shalab Gupta | 29.02.09 | 31.03.09 | 179675
8 | 2008-06-02 | 2008-05-28 | Stg. of internal roads by dense carpetting near community centre Sec-6 R.K.Puram/SZ | 499371 | 113/20.08.08/EE(Pr.)/South | M/s Mukesh Assos. Pvt. Ltd. | 27.08.08 | 27.08.08 | 498370
9 | 2008-06-20 | 2008-05-28 | Dev of road by P/L RMC from Pump House to Guest House in Air India Colony Vasant Vihar w.no.165/SZ | 312324 | 208/26.08.08/EE(M)-I | M/s Sonu Const. Co. | 05.09.08 | P | 307778
10 | 2008-06-20 | 2008-05-28 | Dev of lanes by P/L RMC in Indian Airlines Colony Block no.A1/121 to 160 and A1/161 to 200 Vasant Vihar in w.no.165/SZ | 266073 | 207/26.08.08/EE(M)-I | M/s Ravi builders | 09.09.08 | 08.12.08 | 266073
11 | 2008-06-20 | 2008-05-28 | Dev of lane by P/L RMC from A32/497 to A1/8 and B10/109 in Air India Colony Vasant Vihar w.no.165/SZ | 257905 | 206/26.08.08/EE(M)-I | M/s Lalit Kumar | 10.10.08 | 23.10.08 | 257905
12 | 2008-06-20 | 2008-05-28 | Dev of road berms by P/L interlocking tiles from outer ring road to Taxi Stand in Vasant Appt. w.no.165/SZ | 261205 | 209/26.08.08/EE(M)-I | M/s H.G. Assos. | 02.09.08 | 16.10.08 | 261205
13 | 2008-06-20 | 2008-05-28 | Dev of road by P/L RMC from road connecting Samshan Bhoomi to Vasant Appt. in w.no.165/SZ | 143069 | 183/22.08.08/EE(M)-I | M/s Happy Const. | 09.09.08 | 10.10.08 | 141692
14 | 2008-06-20 | 2008-05-28 | Dev of road by Pdg dense carpet from Flat no. 103 to gate no.9 Vasant Enclave w.no.165/SZ | 261933 | 338/13.10.08/EE(M)-I | M/s Dhingra Const Co. | 17.11.08 | P | 259876
15 | 2008-06-23 | 2008-05-30 | P/F cc interlocking tiles from h.no.637 to community Centre and upto h.no.771 in Sec-6 R.K. Puram in C-168/SZ | 492245 | 160/06.08.08/EE(M)-I | M/s Shalabh Gupta | 27.08.08 | P | 472245
16 | 2008-06-23 | 2008-05-30 | P/L cc interlocking tiles on road berm along h.no.958 to h.no.1046 in Sec-8 R.K.puram C-168/SZ | 463910 | 159/06.08.08/EE(M)-I | M/s Dinesh Kumar | 08.08.08 | 20.09.08 | 463910
17 | 2008-06-23 | 2008-05-30 | P/L cc interlocking tiles on road berm along h.no.913 to h.no.646 in Sec-8 R.K.puram C-168/SZ | 378535 | 158/06.08.08/EE(M)-I | M/s Balbir Singh Tanwar & Co. | 23.09.08 | 18.11.08 | 378535
18 | 2008-06-23 | 2008-05-30 | P/F cc interlocking tiles along Electric Sub Stn. opp. Nanak Pura Mkt. in c-168/SZ | 249424 | 157/06.08.08/EE(M)-I | M/s Sonu Const. Co. | 22.09.08 | P | 234424
19 | 2008-06-23 | 2008-05-30 | Const. of Toe Wall from Mother Dairy Booth to toward urinal block front of Sec-6 R.K.Puram Mkt.in C-168/SZ | 197973 | 161/06.08.08/EE(M)-I | M/s R.K. Const. Co. | 22.08.08 | 11.11.08 | 197973
|  |  |  | 5881115 |  |  |  |  | 5292547

## AC-32
S.no. | Date of Booking | Date of consent | Name of work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified
1 | 2008-06-20 | 2008-05-21 | Remodeling of different crossings/drains in Village Chattarpur in ward 174/SZ | 199584
2 | 2008-06-20 | 2008-05-21 | Prov. RMC and drain in Suresh and adj lane in Village Chattarpur in ward 174/SZ | 150157 | 104/29.09.08/EE(M)-IV | M/s Sushil Kumar Gupta | 15.10.08 | 08.12.08 | 150038
3 | 2008-06-20 | 2008-05-21 | covering of drain along and infront of Rampal SI house,60 feet wide road Chattarpur in ward 174/SZ | 192655 | 103/29.09.08/EE(M)-IV | M/s Mangal Singh | 01.03.09 | 30.04.09 | 192377
4 | 2008-06-20 | 2008-05-21 | Pdg RMC from Ranveer house to Subash house in Village Chattarpur in ward 174/SZ | 499188 | 120/30.09.08/EE(M)-IV | M/s National Const Co. | 30.09.08 | 30.10.08 | 498842
5 | 2008-06-20 | 2008-05-21 | Pdg RMC in lane from Goenka Traders to Dinesh Khari house in Village Sultanpur in ward 174/SZ | 197830 | 122/30.09.08/EE(M)-IV | M/s Sachin Gupta | 06.10.08 | 26.11.08 | 196656
6 | 2008-07-07 | 2008-05-21 | Pdg RMC and drain in lane among Devendre hs and Kiran Singh hs in Village Asola in C-176/SZ | 288310 | 132/30.09.08/EE(M)-IV | M/s Ravi Gupta | 05.12.08 | 02.04.09 | 287831
7 | 2008-07-07 | 2008-05-21 | Pdg RMC from Chahat hs towards Begraj hs in Village Asola in C-176/SZ | 495374 | 131/30.09.08/EE(M)-IV | M/s Kuldeep Const Co. | 01.12.08 | 16.01.09 | 494997
8 | 2008-07-07 | 2008-05-21 | Pdg RMC and drain from Cheta shop to Rajpal hs in Village Mandi in C-175/SZ | 499008 | 116/30.09.08/EE(M)-IV | M/s J.P. Const Co. | 21.10.08 | 24.12.08 | 499008
9 | 2008-07-07 | 2008-05-21 | Pdg Premixing Carpet on road approaching to Jawahar Colony in Village Mandi in C-175/SZ | 493053
10 | 2008-07-07 | 2008-05-21 | Pdg Premixing from main road towards Sr.Sec.School Zorapur in Village Zorapur in C-175/SZ | 485550
11 | 2008-07-07 | 2008-05-21 | Pdg Premixing from Rishipal Ambawata Farm towards Mandi road in Village Zorapur in C-175/SZ | 490484
12 | 2008-07-07 | 2008-05-21 | Pdg cc from Ram Singh Shop,Rupi Pehalwan,Dharam Singhhouse upto Chowk near Pratap Singh house in Village Mandi in C-175/SZ | 333918 | 133/30.09.08/EE(M)-IV | M/s Jha & Jha & Const Co. | 11.10.08 | 03.12.08 | 333182
13 | 2008-07-07 | 2008-05-21 | Pdg RMC and drain from Dharamveer house,Leelu Ram house and lane infront of Rajender house to Bangali house in Village Zorapur in C-175/SZ | 497306 | 119/30.09.08/EE(M)-IV | M/s M.K. Entp. | 11.10.08 | 12.12.08 | 496831
14 | 2008-07-07 | 2008-05-21 | C/O drain and pdg RMC from Mangal Bhagat house to LLate Leelay Pradhan house and Charna house to Raju house in Village Asola in C-176/SZ | 340335 | 121/30.09.08/EE(M)-IV | M/s Hawks Const Co. | 13.10.08 | 02.12.08 | 339833
15 | 2008-07-07 | 2008-05-21 | Pdg RMC and drain from Radhey house to Rajpal house,Bega house,Jodha house,Balram house in Village Bhatti Kalan in C-176/SZ | 355398 | 130/30.09.08/EE(M)-IV | M/s Hira Const. Co. | 11.10.08 | 20.12.08 | 354960
16 | 2008-07-07 | 2008-05-21 | Pdg RMC and drain in lane from Parmanand Sharma house to Mandir in Village Zorapur in C-175/SZ | 199027 | 102/29.09.08/EE(M)-IV | M/s Bansal Brothers | 11.10.08 | 12.12.08 | 198908
17 | 2008-07-07 | 2008-05-21 | Pdg RMC from Sunil Genral Store to Zilley Singh Farm in Village Mandi in C-175/SZ | 499107 | 118/30.09.08/EE(M)-IV | M/s Amar Engg. & Contct. | 25.10.08 | 06.01.09 | 498799
18 | 2008-07-07 | 2008-05-21 | Pdg RMC and drain from Chopal to Narendra house in Village Zorapur in C-175/SZ | 163919 | 99/29.09.08/EE(M)-IV | M/s Shalab Gupta | 22.10.08 | 05.12.08 | 163116
19 | 2008-07-07 | 2008-05-21 | Pdg RMC in lane from Ramesh Sharma shop to Aruna Public School and Devia pradhan house to Rishipal house in Village Zorapur in C-175/SZ | 499791 | 117/30.09.08/EE(M)-IV | M/s Ramkesh | 22.10.08 | 09.07.09 | 498821
20 | 2008-07-07 | 2008-05-21 | Remodeling of different Crossing/drain in Village Aya Ngr.in C-175/SZ | 195940 | 101/29.09.08/EE(M)-IV | M/s R.K. Const Co. | 17.11.08 | 03.02.09 | 195528
21 | 2008-08-28 | 2008-08-12 | Pdg RMC from Masjid to gali infront of Naresh Sharma house in Village Chattarpur in C-174/SZ | 197179
22 | 2008-08-28 | 2008-08-12 | Pdg Premixing Carpet near Dharamshala E-Turnning of 60ft road at 100ft wide road in Village Chattarpur in C-174/SZ | 199459 | 157/13.10.08/EE(M)-IV | M/s R.D. Const. Co. | 03.11.08 | 20.12.08 | 199103
23 | 2008-09-18 | 2008-09-01 | Pdg RMC from Chaupal to Tejpal and Rishi house in village Fatehpur Beri in w.no.176/SZ | 446982
|  |  |  | 7919554 |  |  |  |  | 5598830

## AC-33
S.no. | Date of Booking | Date of consent | Name of work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified
1 | 2008-06-20 | 2008-05-20 | P/L cc adj Kh.no.396,Devli Village w.no.178/SZ | 188250 | 81/25.07.08/EE(M)-III | M/s Gyan Dass Const Co. | 07.08.08 | 28.09.09 | 188200
2 | 2008-06-20 | 2008-05-20 | P/L cc from h.no.600 to 610 and 600 to 466 in Devli Village w.no.178/SZ | 199950 | 80/25.07.08/EE(M)-III | M/s Deepak Kumar | 06.08.08 | 02.09.08 | 199034
3 | 2008-06-20 | 2008-05-20 | P/L culverts adj h.no.491 and Gram Mkt. Nai Basti,Devli village w.no.178/SZ | 85000 | 64/07.07.08/EE(M)-III | M/s S.K. Const Co. | 17.07.08 | 12.02.09 | 85000
4 | 2008-06-23 | 2008-04-18 | P/O street lighting arrangement in various colonies in Saket And Pushp vihar under SZ | 448493 | 140/16.12.08/EE(E)-IV | M/s Illuminator & Cont. | 25.12.08 | 22.01.09 | 447938
5 | 2008-06-23 | 2008-04-18 | P/O street lighting arrangement in various colonies Deoli road,Raju Park, krishna Park, Khanpur Extn.,Tigri etc under SZ | 449873
6 | 2008-07-07 | 2008-05-20 | P/L RMC from h.no.692/2 to 677/22 Nai Basti Devli Village in C-178/SZ | 478670 | 138/18.08.08/EE(M)-III | M/s Heera Const Co. | 28.08.08 | 15.10.08 | 477001
7 | 2008-07-07 | 2008-05-20 | P/L RMC from h.no.554 to 540/2 Devli Village in C-178/SZ | 498600 | 139/18.08.08/EE(M)-III | M/s R.,K. Const Co. | 08.09.08 | 24.10.08 | 402173
8 | 2008-07-07 | 2008-05-20 | P/L RMC adj h.no.592 Devli Village in C-178/SZ | 404290 | 137/18.08.08/EE(M)-III | M/s M.K. Entp. | 26.09.08 | 13.10.08 | 498475
9 | 2008-07-30 | 2008-07-04 | Dev of road berm along RHS of road opp.M-Block Saket from Amity international to h.no. M-I in C-169/SZ | 483800
10 | 2008-07-30 | 2008-07-15 | Dev of back lane by pdg interlocking tiles from D-94 to D-106 in D-Block Saket in C-169/SZ | 334500 | 183/05.0109/EE(M)-IV | M/s Sadhna Assos. | 20.01.09 | 23.02.09 | 330768
11 | 2008-07-30 | 2008-07-15 | C/O Projection Wall along M-Block Nallah Saket opp. M-7 to M-10 in C-169/SZ | 378200 | 184/05.01.09/EE(M)-IV | M/s Sadhna Assos. | 13.02.09 | 28.03.09 | 313810
12 | 2008-07-30 | 2008-07-02 | Dev of lane in L-Block Saket by pdg cc and drain from h.no.83 to h.no.96 in C-169/SZ | 344200 | 186/05.01.09/EE(M)-IV | M/s Sadhna Assos. | 16.02.09 | 15.04.09 | 288285
13 | 2008-07-30 | 2008-07-02 | Dev of lane in L-Block Saket by pdg cc and drain from h.no.76B to h.no.66B,51A to 47A and upto Chowk in C-169/SZ | 366700 | 182/05.01.09*/EE(M)-IV | M/s Sadhna Assos. | 16.02.09 | 26.04.09 | 306584
14 | 2008-07-30 | 2008-07-02 | Dev of lane in L-Block Saket by pdg cc and drain from h.no.43A to h.no.42B,21A to Chowk,9 to 12 and near gate in C-169/SZ | 391900
15 | 2008-07-30 | 2008-06-22 | Pdg RMC for development of front lane fron J-165 to J-38 in J-Block Saket in C-169/SZ | 375300 | 185/05.01.09/EE(M)-IV | M/s Sadhna Assos. | 11.02.09 | 09.03.09 | 339400
16 | 2008-07-30 | 2008-06-22 | Dev of backlane by pdg interlocking tiles from J-152 to J-168 in J-Block Saket in C-169/SZ | 199860 | 153/13.10.08/EE(M)-IV | M/s Sadhna Assos. | 27.01.09 | 04.03.09 | 199786
17 | 2008-07-30 | 2008-06-22 | Dev of backlane by pdg interlocking tiles frpm J-124 to J-136 in J-Block Saket in C-169/SZ | 303300 | 188/05.01.09/EE(M)-IV | M/s Sadhna Assos. | 27.01.09 | 04.03.09 | 303280
18 | 2008-07-30 | 2008-06-22 | Dev of front lane in D-Block Saket from D-30 to D-37 by pdg interlocking tiles and dev of the drainage system in C-169/SZ | 489200 | 180/05.01.09/EE(M)-IV | M/s Gopal Goyal | 14.01.09 | 23.02.09 | 489200
19 | 2008-07-30 | 2008-06-22 | Dev of front lane in D-Block Saket from D-46 to D-53 by pdg interlocking tiles and dev of the drainage system in C-169/SZ | 477400 | 187/05.01.09/EE(M)-IV | M/s Sadhna Assos. | 19.01.09 | 23.03.09 | 301081
20 | 2008-07-30 | 2008-06-22 | Dev of back lane by pdg interlocking tiles from D-30 to D-37 in D-Block Saket in C-169/SZ | 199100 | 152/13.10.08/EE(M)-IV | M/s Goel Const Co. | 08.12.08 | 20.01.09 | 199100
21 | 2008-07-30 | 2008-06-22 | Dev of back lane by pdg interlocking tiles from D-38 to D-45 in D-Block Saket in C-169/SZ | 199428 | 155/13.10.08/EE(M)-IV | M/s Mangal Singh | 21.11.08 | 20.12.08 | 198517
22 | 2008-08-20 | 2008-07-18 | Dev of park in L-Block Saket by pdg Walking Track in C-169/SZ | 175500 | 155/13.10.08/EE(M)-IV | M/s Uttam Const Co. | 04.11.08 | 21.12.08 | 175464
23 | 2008-08-26 | 2008-08-08 | C/O B/Wall of park adj to h.no.337 in DDA Flat Tigri in C-179/SZ | 469300 | 199/19.09.08/EE(M)-III | M/s Sushil Kumar Gupta | 30.09.08 | 28.12.08 | 469232
24 | 2008-08-26 | 2008-08-08 | pdg RMC and its drainage system from h.no.34 to 27 in DDA Flats Tigri in C-179/SZ | 491200 | 281/07.01.09/EE(M)-III | M/s M.K. Entp. | 17.01.09 | 18.03.09 | 491197
25 | 2008-08-26 | 2008-08-08 | Pdg paralel storm water pipe line from Kumhar Mohalla Deoli to Hanuman Temple in C-181/SZ | 498650 | 340/17.02.09/EE(M)-III | M/s Naresh builders | 27.02.09 | 20.05.09 | 498605
26 | 2008-08-26 | 2008-08-08 | Pdg paralel storm water pipe line from Masjid to A-Block Raja Park in C-181/SZ | 497400 | 101/05.06.09/EE(M)-III | M/s Deepak Kumar | 15.06.09 | 12.08.09 | 346671
27 | 2008-08-26 | 2008-08-06 | P/L RMC in lane Chowk near Block no.65 Sec.-I Pushp Vihar C-184/SZ | 199680 | 191/16.12.08/EE(M)-II | M/s Mukesh Jorwal | 18.01.09 | 07.02.09 | 164723
28 | 2008-08-26 | 2008-08-06 | Remodeling of drain along park Sec.-I Pushp Vihar in C-184/SZ | 199707 | 188/16.12.08/EE(M)-II | M/s Mukesh Jorwal | 18.12.08 | 30.01.09 | 182302
29 | 2008-08-26 | 2008-08-06 | Remodeling of drain along Sarvodya Vidhyalaya Sec.-I Pushp Vihar in C-184/SZ | 199659 | 184/16.12.08/EE(M)-II | M/s Mukesh Jorwal | 22.12.08 | 06.02.09 | 184387
30 | 2008-08-26 | 2008-08-06 | Remodeling of drain near block no.52 to main road opp.Sarvodya Vidhayalaya Sec.-I Pushp Vihar in C-184/SZ | 199659 | 186/16.12.08/EE(M)-II | M/s Mukesh Jorwal | 20.12.08 | 18.01.09 | 184481
31 | 2008-08-26 | 2008-08-06 | Remodeling of drain from Mother Dairy Booth to opp.Old Police Chowki Sec.-IV Pushp Vihar in C-184/SZ | 199395 | 192/16.12.08/EE(M)-II | M/s Mukesh Jorwal | 18.12.08 | 20.01.09 | 184569
32 | 2008-08-26 | 2008-08-06 | Remodeling of drain block no.53 to near block no.57 Sec.-I Pushp Vihar in C-184/SZ | 199094 | 190/16.12.08/EE(M)-II | M/s Mukesh Jorwal | 18.12.08 | 21.01.09 | 184829
33 | 2008-09-10 | 2008-07-11 | P/o SHM light at G block Saket and E block Saket under SZ | 415088 | 103/16.12.08/EE(E)-IV | M/s Sri Balaji Elect. | 16.12.08 | 15.01.09 | 403851
34 | 2008-10-10 | 2008-07-11 | P/o SHM light at D block Saket near Bansi Lal house and D block near Tanya park Saket under SZ | 414153 | 154/16.12.08/EE(E)-IV | M/s Illuminator & Cont. | 25.12.08 | 23.01.09 | 404191
35 | 2008-10-10 | 2008-07-11 | P/o SHM light at main park opp. L block Saket and main gate press Enclave cly. under SZ | 413685 | 158/16.12.08/EE(E)-IV | M/s Best Elect. & Electro. | 16.12.08 | 14.01.09 | 400432
36 | 2008-09-10 | 2008-07-11 | P/o SHM light at main gate opp. college of Pharmacy MB road Khanpur and at main gate Carriappa marg Khirki extn. near Bangkok under SZ | 425142 | 152/16.12.08/EE(E)-IV | M/s Vivek Elect. | 16.12.08 | 12.01.09 | 413613
37 | 2008-09-10 | 2008-07-11 | P/o SHM light at park Pushp vihar sec-2 c/o/ K.K. Rathore and c/o N.R. Patnaik Pushp Vihar section SZ | 409243 | 206/24.12.08/EE(E)-IV | M/s Electra Fusion Techn. | 02.01.09 | 30.01.09 | 362370
38 | 2008-09-10 | 2008-07-11 | P/o SHM light at Block L part-I gali no.7 chowk near Jai Bhagwan STD Deoli and at M-III block DJB T/well temple Deoli under SZ | 412282 | 155/16.12.08/EE(E)-IV | M/s Illuminator & Cont. | 25.12.08 | 23.01.09 | 401978
39 | 2008-09-10 | 2008-07-11 | P/o SHM light at Police post chowki near Dr. Sahib Singh Vishnu marg and New Tiraha Police booth Durga Vihar Deoli under SZ | 414854 | 54/17.10.08/EE(E)-IV | M/s Unique Elect. | 17.10.08 | 25.11.09 | 402701
40 | 2008-09-10 | 2008-07-11 | P/o SHM light at infront of Savitri barat Ghar Deoli and Asthal mandi road Entrance Deoli under SZ | 415789 | 91/16.12.08/EE(E)-IV | M/s Illuminator & Cont. | 25.12.08 | 23.01.09 | 404904
41 | 2008-09-10 | 2008-07-11 | P/o SHM light at Creamation ground complex Deoli and Asthal Mandir Complex Deoli under SZ | 411815 | 102/16.12.08/EE(E)-IV | M/s Sri Balaji Elect. | 16.12.08 | 15.01.09 | 400487
42 | 2008-09-10 | 2008-07-11 | P/o SHm light at DDA flat Tigri and at C-1211 Tigri cly. under SZ | 413685 | 87/16.12.08/EE(E)-IV | M/s Technoview Electricals | 16.12.08 | 05.01.09 | 402506
43 | 2008-09-10 | 2008-07-11 | P/o SHM light at near h.no. 865 Mangal Bazar road Deoli and naer Tiraha entrance Mangal Bazar road near F-3 corner Deoli under SZ | 411815 | 264/29..12.08/EE(E)-IV | M/s Perfect Electricals Works | 07.01.09 | 06.02.09 | 401214
44 | 2008-09-10 | 2008-07-11 | P/o SHM light at G block Tiraha near Rohtas goel shop Holi chowk Deoli and L-1011 gali no. 15 Shiv Balaji temple Deoli under SZ | 411347 | 171/16.12.08/EE(E)-IV | M/s Technoview Electricals | 16.12.08 | 16.01.09 | 400786
45 | 2008-09-10 | 2008-07-11 | P/o SHM light at entrance of Pramod Mahajan marg from MB road Saket and at main gate Duggal colony Deoli road near Devinder Bansal Property under SZ | 411347 | 135/16.12.08/EE(E)-IV | M/s Forward Engg. | 25.12.08 | 24.01.09 | 401147
46 | 2008-09-10 | 2008-07-11 | P/o SHM light at Pushp Vihar sector-I Central park under SZ | 409009 | 157/04.12.08/EE(E)-IV | M/s Grover Eclect. | 13.12.08 | 12.01.09 | 397699
47 | 2008-06-20 | 2008-05-20 | P/L cc from h.no.677/22 to 677/09,677/22 to 677/24 and 677/08 to 677/09 Nai Basti, Devli Village w.no.178/SZ | 193900 | 76/23.07.08/EE(M)-III | M/s Salabh Gupta | 07.08.08 | 01.10.08 | 193783
|  |  |  | 16608412 |  |  |  |  | 14425754

## AC-34
S.no. | Date of Booking | Date of consent | Name of work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified
1 | 2008-06-23 | 2008-06-05 | C/O culvert near School and Community Centre and dev. of road berms near Church by P/L cc in Block no.18 Dakshinpuri Extn. in C-183/SZ | 199760 | 103/25.07.08/EE(M)-III | M/s Amar Engg. & Contractor | 04.08.08 | 15.09.08 | 198873
2 | 2008-07-03 | 2008-06-05 | C/O road surface by P/L RMC from M.C. Pry.School Madangir Village to Raja Ram marg in Madangir Village in C-180/SZ | 498793 | 148/18.08.08/EE(M)-III | M/s J.P. Const. | 28.08.08 | 24.09.08 | 498696
3 | 2008-07-03 | 2008-06-05 | C/O B/Wall of park near h.no.18 in CPO-Block Madangir Ph-I in C-183/SZ | 464382 | 147/18.08.08/EE(M)-III | M/s Sadh na Assos. | 28.08.08 | 24.09.08 | 463079
4 | 2008-07-23 | 2008-05-26 | C/O drainage system from Durbal Nath Mandir to F-37 Dakshinpuri in C-182/SZ | 454200 | 275/07.01.09/EE(M)-III | M/s Jha & Jha Const. | 14.01.09 | 27.02.09 | 450320
5 | 2008-07-23 | 2008-04-09 | C/O Park in L-Block Madangir PH.-II C-182/SZ SH: B/Wall,grit wash plaster and M.S. grills etc. | 199945 | 191/08.09.08/EE(M)-III | M/s Bahadur Singh Contractor | 10.09.08 | 03.11.08 | 198879
6 | 2008-09-22 | 2008-09-04 | Dev of lanes by p/l RMC from h.no. 199 to 220 in D-1 Madangiri in C-183/SZ | 599800 | 253/15.12.08/EE(M)-III | M/s Sadh na Assos. | 24.12.08 | 23.03.09 | 553845
7 | 2008-09-22 | 2008-09-04 | Dev of lanes by p/l RMC from h.no. 67 to 88, 23 to 44, 111 to 132 and 155 to 176 in D-I MadangiriC-183/SZ | 599900 | 255/15.12.08/EE(M)-III | M/s Sadh na Assos. | 25.12.08 | 30.03.09 | 552888
8 | 2008-09-26 | 2008-09-04 | C/o drain from F-600 to RPS Nallah in Dakshinpuri in w.no. 182/SZ | 499600 | 271/29.12.08/EE(M)-III | M/s Jagdish | 31.12.08 | 05.02.09 | 466220
|  |  |  | 3516380 |  |  |  |  | 3382800