## Sheet1
Status Report of MLA, Sh. Anil Bhardwaj (AC-17), 2008-09
S.No. | Date of Booking | Date of consent | Name of Work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount Verified | Present Position
1 | 2008-06-23 | 23.05.08 | Dev. of lane by pdg. CC from gate no.2 entry to h.no.62 in Ashoka Park in C-62/RZ | 498731 | 114/17.07.08/EE(M)-II | M/s MK Gupta | 24.07.08 | 25.03.09 | 498297 | Work Completed
2 | 2008-06-23 | 23.05.08 | Dev. of road by pdg. CC from h.no.2550(Vardhman Vatika) corner to h.no.2546(Super Bazar) along Vardhman vatika in Tri Nagar in C-61/RZ | 426911 | 120/17.07.08/EE(M)-II | M/s Supreme const. | 25.07.08 | 24.11.08 | 426638 | Work Completed
3 | 2008-06-23 | 23.05.08 | Dev. of lane by CC pav. from h.no.13 to h.no.30 in Ashoka Park in C-62/RZ | 462428 | 115/17.07.08/EE(M)-II | M/s Singhal Builders | 18.07.08 | 06.03.09 | 462428 | Work Completed
4 | 2008-06-23 | 23.05.08 | Dev. of lane by P/L CC in gali no.3,4,6,Onkar Nagar-B Tri NAgar in C-61/RZ | 438437 | 118/17.07.08/EE(M)-II | M/s JMD Const.Co. | 25.07.08 | 10.10.08 | 433658 | Work Completed
5 | 2008-06-23 | 23.05.08 | Dev. of lane by P/L CC in gali no.6 Kanhiya Nagar in C-61/RZ | 497782 | 119/17.07.08/EE(M)-II | M/s DB Ent. | 25.07.08 | 25.11.08 | 496310 | Work Completed
6 | 2008-06-23 | 22.05.08 | Dev. of road by CC pav. from h.no.53 to h.no.60 in Ashoka Park in C-62/RZ | 448506
7 | 2008-06-23 | 22.05.08 | Dev. of lane by P/L CC from h.no.4649 to h.no.4645 gali no. 15 Jai Mata Mkt. Tri Ngr. C-61/RZ | 499603 | 129/22.07.08/EE(M)-II | M/s Vivek Associates | 25.07.08 | 25.11.08 | 498725 | Work Completed
8 | 2008-06-23 | 22.05.08 | Dev. of lane by Pdg CC from gate no.1 entry to h.no.52 in Ashoka Park in C-62/RZ | 495425 | 127/22.07.08/EE(M)-II | M/s R.S. buiding material supp. | 29.07.08 | 31.12.08 | 495425 | Work Completed
9 | 2008-06-23 | 22.05.08 | Dev. of road P/L CC in gali no. 95,105 and 166 in Ganesg Pura Tri Ngr. C-61/RZ | 381124 | 125/22.07.08/EE(M)-II | M/s Satyam Const. | 29.07.08 | 18.02.08 | 379518 | Work Completed
10 | 2008-07-24 | 21.05.08 | P/o lighting arrangement in Mpl park opp. Mother dairy C-7, keshav Puramin C-61/RZ | 264827 | 79/12.09.08/EE(E)-VII | M/s Super Shine Assos. | 17.09.08 | 10.10.08 | 249838 | Work Completed
11 | 2008-08-01 | 17.05.08 | P/O semi high mast lights at Char Khamba Chowk Shakurpur Village in C-62/RZ | 215636 | 161/17.10.08/EE(E)-VII | M/s Forward Engg. | 16.12.08 | 23.01.09 | 215487 | Work Completed
12 | 2008-08-01 | 19.05.08 | P/O semi high mast pole with lights in Lawrance Road Industrial State in C-62/RZ | 213004 | 154/17.10.08/EE(E)-VII | M/s Malhotra Elect. | 17.12.08 | 14.01.09 | 210419 | Work Completed
13 | 2008-08-01 | 15.05.08 | P/O semi high mast pole with lights in MPL Park opp. SDM office Rampura in C-62/RZ | 437034 | 153/17.10.08/EE(E)-VII | M/s Shri Om Traders | 16.12.08 | 30.12.08 | 406012 | Work Completed
14 | 2008-08-20 | 08.08.08 | C/o Bairam Khan Marg by P/L cc in Tri nagar in C_61 RZ | 479002 | 227/18.09.08/EE(M)-II | M/s Tokas & Co. | 24.09.08 | 12.01.09 | 478252 | Work Completed
15 | 2008-08-20 | 08.08.08 | C/o gali no.5 by P/L cc in Jai Mata Mkt. Tri nagar in C_61 RZ | 406472 | 223/18.09.08/EE(M)-II | M/s Har Const Co. | 15.12.08 | 06.03.09 | 404739 | Work Completed
16 | 2008-08-26 | 20.05.08 | P/o 100 nos HPSV street light arrangement in Sri nagar, Shakurpur village Rampura in w.no.66/RZ | 513951
17 | 2008-08-27 | 14.08.08 | C/o School by P/L cc from SDM office road to park corner at Rampura in C-62/RZ | 338428 | 262/13.10.08/EE(M)-II | M/s Nishant Const Co. | 18.10.08 | 29.12.08 | 337415 | Work Completed
18 | 2008-08-27 | 18.08.08 | C/o B/wall along Shkur Basti drain near Janta flats MAndir from Tranformer to Mandir corner in Rampura in C-62/RZ | 489798
19 | 2008-08-27 | 18.08.08 | Dev of road by P/L cc from MIG flats gate to park corner on School road Rampura in C-62/RZ | 409010 | 261/31.10.08/EE(M)-II | M/s Har Const Co. | 21.10.08 | P | 406810 | In Prog.
20 | 2008-08-27 | 18.08.08 | Dev of footpath along MIG flats B/wall from SDM park gate to Rampura drain in Rampura in C-62/RZ | 356244
21 | 2008-08-27 | 08.08.08 | C/o gali no.221 by P/L cc in Chander Nagar w.no.61/Tri nagar RZ | 427167
22 | 2008-08-27 | 08.08.08 | C/o lane by P/L cc in gali no.14 (Mandir Side) Jai Mata mkt. Tri nagar w.no.61/RZ | 198635 | 239/29.09.08/EE(M)-II | M/s Shri Balaji Const Co. | 03.10.08 | 06.01.09 | 197950 | Work Completed
23 | 2008-08-27 | 08.08.08 | C/o gali no.164 by P/L cc at Ganeshpura in Tri nagar w.no.61/RZ | 455033 | 230/18.09.08/EE(M)-II | M/s Tokas & Co. | 26.09.08 | 26.12.08 | 385115 | Work Completed
24 | 2008-09-01 | 08.08.08 | C/O gali no.185 and gali no.87(Gsnesh Pura)by P/L cc in Tri Ngr. in C-61/RZ | 360400 | 275/13.10.08/EE(M)-II | M/s Naresh Entp. | 24.10.08 | 23.01.09 | 360004 | Work Completed
25 | 2008-09-22 | 14.08.08 | C/o drain (Builtup section) from LIG flats gate no.1 to gate no.4 in Rampura in w.no.62/RZ | 496800 | 416/02.03.09/EE(M)-II | M/s Rajeev Kumar Gupta | 10.03.09 | 06.05.09 | 463566 | Work Completed
26 | 2008-09-22 | 14.08.08 | C/o lane by P/L cc from Ram Rikh Yadav School corner to Char Khamba Chowk Phirni road in shakurpur at Rampura w.no.62/RZ | 498406 | 322/23.12.08/EE(M)-II | M/s Ajit Dabas | 01.01.09 | 30.03.09 | 498272 | Work Completed
27 | 2008-09-30 | 15.09.08 | P/L cc road from h.no.1537 to gali no.113 at Anaj Mandi in Tri Ngr. in C-61/RZ | 472750 | 357/10.02.09/EE(M)-II | M/s Dinesh Sethi | 14.02.09 | P | 322960 | In Prog.
28 | 2008-09-30 | 15.09.08 | P/L cc in gali no.7, Jai Mata Mkt. in Tri Ngr. in C-61/RZ | 565300
29 | 2008-09-30 | 15.09.08 | P/L cc road in gali no.8, Jai Mata Mkt. in Tri Ngr. in C-61/RZ | 404000
30 | 2008-09-30 | 15.09.08 | P/L cc road in Anaj Mandi from gali no.160 to Tota Ram Bazar in Tri Ngr. in C-61/RZ | 406000
31 | 2008-09-30 | 15.09.08 | P/L cc road in Anaj Mandi road from Aggarsen Marg to gali no.160(h.no.2040) in Tri Ngr. in C-61/RZ | 420800
32 | 2008-09-30 | 15.09.08 | P/L cc road at Anaj Mandi road from gali no.113 to Parsuram Marg in Tri Ngr. in C-61/RZ | 519275 | 358/10.02.09/EE(M)-II | M/s Dinesh Sethi | 14.02.09 | 09.06.09 | 366370 | Work Completed
33 | 2008-10-08 | 07.10.08 | Imp to road behind UCO bank near C-7 block Lawrance road Industrial area w.no. 62/RZ | 1350000 | 65/12.01.09/EE(Pr.)/RZ | M/s Manoj Kumar Gupta | 19.01.09 | P | 1211161 | In Prog.
|  |  |  | 14846919 |  |  |  |  | 10205369

## Sheet2
Status Report of MLA, Dr. S.C. Vats (AC-18), 2008-09
S.No. | Date of Booking | Date of consent | Name of Work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount Verified | Present Position
1 | 2008-06-23 | 16.05.08 | P/O lighting arrangememt near G-300, J.j.Colony Shakur Pur under Rohini Zone | 98871 | 194/16.12.08/EE(E)-VII | M/s Amit Electric Service | 17.12.08 | 22.01.09 | 93594 | Work Completed
2 | 2008-06-23 | 16.05.08 | P/O lighting arrangement in Ram Lila Park in G-Block j.j.colony Shakur Pur under Rohini Zone | 99695 | 159/17.10.08/EE(E)-VII | M/s S.T. Electric Co. | 17.10.08 | 23.12.08 | 92841 | Work Completed
3 | 2008-06-23 | 16.05.08 | P/O lighting arrangement in Phoola Ram Park in Rishi Ngr.under Rohini Zone | 477461 | 109/06.10.08/EE(E)-VII | M/s Bansal Electric Store | 06.10.08 | 15.10.08 | 352248 | Work Completed
4 | 2008-06-23 | 16.05.08 | P/O lighting arrangement in Municipal Park near h.no.49 in Sandesh vihar under Rohini Zone | 184222 | 111/06.10.08/EE(E)-VII | M/s Bansal Electric Store | 06.10.08 | 15.10.08 | 134553 | Work Completed
5 | 2008-06-23 | 16.05.08 | P/O lighting arrangement in Municipal Park near h.no.64 in Rohit Kunj under Rohini Zone | 206829 | 108/06.10.08/EE(E)-VII | M/s Master Electric Store | 06.10.08 | 15.10.08 | 152148 | Work Completed
6 | 2008-06-23 | 16.05.08 | P/O Tubewell with sub.pump set at Jan Suvidha Parisar at E-Block J.J. Colony Shakurpur under Rohini Zone | 173539 | 136/13.10.08/EE(E)-VII | M/s Electra Fusion Tech. | 16.12.08 | 24.12.08 | 168234 | Work Completed
7 | 2008-07-18 | 27.06.08 | C/o foot path park near h.no. B-18 Pushpanjali Enclave in C-60/RZ | 257430 | 264/10.09.08/EE(M)-I | M/s Bhatia & Co. | 20.09.08 | 08.11.08 | 255373 | Work Completed
8 | 2008-07-18 | 27.06.08 | C/o foothpath of park along vidhya vihar near CNG filling station Saraswati Vihar in w.no. 60/RZ | 323350 | 220/29.08.08/EE(M)-I | M/s Singal builders | 09.09.08 | 18.02.09 | 323350 | Work Completed
9 | 2008-07-18 | 27.06.08 | Dev of back lane from h.no. 199 to 139 at Anand Vihar, w.no. 60/RZ | 499074 | 267/10.09.08/EE(M)-I | M/s Har Const. | 20.09.08 | 16.12.08 | 497026 | Work Completed
10 | 2008-07-18 | 27.06.08 | Dev of back lane from h.no. 24 to 31 in Deepali in w.no. 60/RZ | 214426 | 221/29.08.08/EE(M)-I | M/s Mahesh Entp. | 06.09.08 | 14.11.08 | 213860 | Work Completed
11 | 2008-07-23 | 27.06.08 | Dev of lane from Gurudwara to 1052 in Rani bagh in C-59/RZ | 205810 | 201/18.08.08/EE(M)-I | M/s Laxman Const Co. | 13.08.08 | 15.10.08 | 205750 | Work Completed
12 | 2008-07-23 | 24.06.08 | P/o lighting arrangement in the Mpl park near C-450, Saraswati Vihar C- /RZ | 215419 | 129/13.10.08/EE(E)-VII | M/s Kamal Electricals | 13.10.08 | 17.10.08 | 207796 | Work Completed
13 | 2008-07-28 | 24.06.08 | Installation of tubewell at Pitampura Chopal in C-66/RZ | 173539 | 137/13.10.08/EE(E)-VII | M/s Modern Electricals | 16.12.08 | 20.01.09 | 168801 | Work Completed
14 | 2008-07-28 | 28.06.08 | P/o lighting arrangement in mpl park near h.no. 179, Harsh Vihar C- /RZ | 281757 | 134/13.10.08/EE(E)-VII | M/s Bindra Motors & Eletricals | 15.10.08 | 24.10.08 | 267821 | Work Completed
15 | 2008-07-28 | 28.06.08 | P/o lighting arrangement in mpl park near h.no.207, Harsh Vihar. | 195522 | 133/13.10.08/EE(E)-VII | M/s Saksham Electricals & Electronics | 13.10.08 | 17.10.08 | 188029 | Work Completed
16 | 2008-07-28 | 30.06.08 | P/o lighting arrangement in mpl park near h.no.D-816, HSaraswati Vihar C-66/RZ | 697934 | 189/16.12.08/EE(E)-VII | M/s M.J. Electricals & Electronics | 17.12.08 | 07.01.09 | 691514 | Work Completed
17 | 2008-07-28 | 30.06.08 | P/o lighting arrangement in mpl park near h.no.129, Engineers enclave C-/RZ | 223372 | 150/17.10.08/EE(E)-VII | M/s Shri Balaji Elect. | 17.12.08 | 24.12.08 | 220773 | Work Completed
18 | 2008-07-28 | 30.06.08 | P/o lighting arrangement in mpl park near h.no.91, Engineers enclave C-/RZ | 320600 | 163/17.10.08/EE(E)-VII | M/s U.V. Entp. | 17.12.08 | 23.04.09 | 305708 | Work Completed
19 | 2008-07-28 | 30.06.08 | p/o lighting arrangement in the MPL. park near H no. 303 rajdhani enclave C- /RZ | 320295 | 135/13.10.08/EE(E)-VII | M/s Ankur Entp. | 22.12.08 | 19.01.09 | 306724 | Work Completed
20 | 2008-07-28 | 21.07.08 | P/o lighting arrangement in Kor nala park in Pitampura village C-/RZ | 97222 | 130/13.10.08/EE(E)-VII | M/s S.K. Entp. | 13.10.08 | 17.11.08 | 94017 | Work Completed
21 | 2008-07-28 | 30.06.08 | P/o lighting arrangement in the park near h.no.72, Deepali enclave C-60/RZ | 98871 | 250/03.02.09/EE(E)-VII | M/s Perfect Elct. Works | 09.02.09 | 19.06.09 | 92092 | Work Completed
22 | 2008-07-31 | 10.05.08 | Dev of lane by pdg cc pav.in Chaupal in Pitempura Village in C-63/RZ | 412493 | 262/10.09.08/EE(M)-I | M/s JMD Const | 13.09.08 | 09.10.08 | 412493 | Work Completed
23 | 2008-08-13 | 10.06.08 | Dev of SW drain from h.no. 74 to 91 in Sandesh Vihar in C-63/RZ | 564700 | 435/26.12.08/EE(M)-I | M/s Sherawat Const Co,. | 05.01.09 | 03.03.09 | 408741 | Work Completed
24 | 2008-08-13 | 10.06.08 | C/O Umbrella in park in N.H.8 in Kapila Vihar in C-63/RZ | 239104
25 | 2008-08-13 | 10.06.08 | Dev of SW drain from Samrat Enclave to h.no. 64 in Samrat Enclave in C-63/RZ | 498745 | 314/07.10.08/EE(M)-I | M/s Ajit Dabas | 17.10.08 | 20.04.09 | 498700 | Work Completed
26 | 2008-08-13 | 10.06.08 | Dev of road by pdg cc from h.no. 194 to 207 in Harsh Vihar in C-63/RZ | 433790
27 | 2008-08-13 | 28.05.08 | Dev of backlane from h.no. 89 to 106 in Chandar Lok in C-63/RZ | 474362
28 | 2008-08-26 | 30.05.08 | P/o lighting arrangement in Municipal park in Vidya vihar w.no.60/RZ | 600000 | 164/17.10.08/EE(E)-VII | M/s Sachdeva Electricals | 22.12.08 | 19.01.09 | 598895 | Work Completed
29 | 2008-08-26 | 30.06.08 | P/o lighting arrangement in Municipal parks of Maharana Pratap Enclave in w.no.63/RZ | 600000 | 142/13.10.08/EE(E)-VII | M/s Kawatra Elec. Works | 13.10.08 | 20.03.09 | 598419 | Work Completed
30 | 2008-08-26 | 20.07.08 | p/o lighting arrangement in NHP Central park, Kapil Vihar in w.no.60/RZ | 600000 | 116/06.10.08/EE(E0-VII | M/s Master Electric Store | 14.10.08 | 10.02.09 | 599451 | Work Completed
31 | 2008-08-29 | 11.08.08 | Stg existing Lav.Block near Rang Mahal Socity Cluster CTC at Saraswati Vihar in C-60/RZ | 105813
32 | 2008-08-29 | 11.08.08 | Dev of backlane from E-934 to E-945 in Saraswati Vihar in C-60/RZ | 448340 | 304/07.1008/EE(M)-I | M/s SAS Const CO. | 17.10.08 | 12.04.09 | 448230 | Work Completed
33 | 2008-08-29 | 11.08.08 | Dev of backlane from E-946 to E-961 in Saraswati Vihar in C-60/RZ | 331624 | 302/07.10.08/EE(M)-I | M/s SS contractors | 17.10.08 | 20.12.08 | 330855 | Work Completed
34 | 2008-09-10 | 04.09.08 | C/O Flower bed and Satties at main Mkt. E-Block Park Saraswati Vihar in C-60/RZ | 79783 | 335/15.10.08/EE(M)-I | M/s Singhal builders | 17.10.08 | 20.11.08 | 79501 | Work Completed
35 | 2008-09-18 | 20.08.08 | P/O Lighting arragment in the Mpl Park near F. Block Mandir J.J colony shakurpur in C-63/RZ. | 98871 | 253/03.02.09/EE(E)-VII | M/s Repair Shop | 03.02.09 | 11.02.09 | 92795 | Work Completed
36 | 2008-09-18 | 21.08.08 | P/o lighting arrangemt in the Municipal park near E block Mandir JJ cly. Shakurpur in w.no. 64/RZ | 98871 | 252/03.02.09/EE(E)-VII | M/s Sheela Electric Works | 03.02.09 | 12.02.09 | 91738 | Work Completed
37 | 2008-06-20 | 02.05.08 | C/O Walkway in park back of h.no.38 in Rajdhani Enclave C-63/RZ | 205994 | 145/21.07.08/EE(M)-I | M/s Parkash Khanna | 31.07.08 | 17.10.08 | 205906 | Work Completed
|  |  |  | 11157728 |  |  |  |  | 9397976

## Sheet6
Status Report of MLA, Sh. Mange Ram Garg (AC-53), 2008-09
S.No. | Date of Booking | Date of consent | Name of Work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount Verified | Present Position
1 | 2008-06-23 | 08.05.08 | P/O two semi high mast lights with pole near E-73 Ashok vihar Ph-1 w.no.68/RZ | 450707 | 143/13.10.08/EE(E)-VII | M/s Ram Gopal & Co. | 13.10.08 | 17.10.08 | 384751 | Work Completed
2 | 2008-06-23 | 08.05.08 | P/O lighting arrangement in park of Nimri Colony w.no.68/RZ | 568148 | 131/13.10.08/EE(E)-VII | M/s Sheela Electric Works | 15.10.08 | 12.02.09 | 554818 | Work Completed
3 | 2008-06-23 | 08.05.08 | P/O semi high mast lights with pole in the park of Satyawati Colony w.no.66/RZ | 217515 | 184/EE(E)-VII | M/s Sudhir Electricals | 17.12.08 | 22.01.09 | 193490 | Work Completed
4 | 2008-06-23 | 08.05.08 | P/O two semi high mast lights with pole in the park of Ashok vihar Ph-3 w.no.66/RZ | 213560 | 249/03.02.09/EE(E)-VII | M/s Prince Engg. Works | 10.02.09 | 02.03.09 | 180774 | Work Completed
5 | 2008-06-23 | 08.05.08 | P/O semi high mast lights with pole in the park of Ashoka vihar ph.-II,C-66/RZ | 217515
6 | 2008-06-23 | 08.05.08 | P/o lighting arrangement in mpl park of Ashok Vihar ph-I, JJ cly Wazirpur, Nimri cly, Bharat Nagar Ashok Vihar ph-II/RZ | 566078 | 222/31.12.08/EE(E)-VII | M/s Sachdeva Electricals | 05.01.09 | 04.02.09 | 565592 | Work Completed
7 | 2008-06-23 | 08.05.08 | P/o lighting arrangement in Radhey-Radhey park Ashok Vihar ph-I under RZ | 287537 | 62/27.08.08/EE(E)-VII | M/s Unique Elect. | 04.09.08 | 03.10.08 | 210050 | Work Completed
8 | 2008-06-23 | 08.05.08 | P/o lighting arrangement in mpl park near Jain MAndir F block Ashok Vihar ph-I/under RZ | 261787 | 132/13.10.08/EE(E)-VII | M/s Sheela Electric Works | 13.10.08 | 18.10.08 | 219275 | Work Completed
9 | 2008-06-23 | 08.05.08 | P/o lighting arrangement in mpl park infornt of house no. H-57 in Ashok Vihar ph-I/under RZ | 279052 | 85/24.09.08/EE(E)-VII | M/s Sri Balaji Elect. | 24.09.08 | 16.10.08 | 252245 | Work Completed
10 | 2008-06-23 | 08.05.08 | P/o lighting arrangement in mpl park infornt of house no. B-160 in Ashok Vihar ph-I C-68/under RZ | 283396 | 86/24.09.08/EE(E)-VII | M/s Saksham Electric & Elect. | 24.09.08 | 10.10.08 | 246231 | Work Completed
11 | 2008-06-23 | 08.05.08 | P/o lighting arrangement in mpl park infornt of house no. B-222 in Ashok Vihar ph-I C-68/under RZ | 202023 | 75/12.09.08/EE(E)-VII | M/s Ram Gopal & Co. | 17.09.08 | 09.10.08 | 149551 | Work Completed
12 | 2008-06-23 | 08.05.08 | P/o semi high mast light with pole near green belt, F block Ashok Vihar ph-I under RZ | 215898 | 356/27.02.09/EE(E)-VII | M/s Utsav Engineers | 27.02.09 | 03.04.09 | 186944 | Work Completed
13 | 2008-06-23 | 28.05.08 | Covering of drain at red light of Mont Ford School Gulab Singh marg w.no. 67/RZ | 499350 | 163/04.08.08/EE(M)-II | M/s Sanjay Gupta | 05.08.08 | 08.09.08 | 499208 | Work Completed
14 | 2008-06-23 | 28.05.08 | wid. of road by pdg RMC at red light of Mont Ford School Gulab Singh marg w.no. 67/RZ | 278200 | 220/18.09.08/EE(M)-II | M/s Singhal builders | 09.09.08 | 30.10.08 | 274768 | Work Completed
15 | 2008-06-23 | 22.05.08 | dev of lane by cc flooring from WP-427 to 426, 545 to 203, 150 to 172, 160 to 164, 156 to 158, 146 to 49, 118 to 116, 128 to 134 in Wazirpur village C-67/RZ | 497610 | 176/02.09.08/EE(M)-II | M/s Har Const Co. | 12.09.08 | P | 159500 | In Prog.
16 | 2008-06-23 | 22.05.08 | P/l cc pav. on berms along B/wall of park C-1 block near h.no. c-1/76 Ashok Vihar ph-II C-66/RZ | 350038 | 121/17.07.08/EE(M)-II | M/s Bhatia & Co. | 22.08.08 | 25.09.08 | 350000 | Work Completed
17 | 2008-06-23 | 22.05.08 | C/o footpath and P/F MS grills in park near C-2/24 in C-2 block Ashok Vihar ph-II C-66/RZ | 255944 | 122/17.07.08/EE(M)-II | M/s Ajit Dabas | 26.08.08 | 24.10.08 | 255858 | Work Completed
18 | 2008-06-23 | 22.05.08 | P/l cc pavment in back lane and side berms and front side from h.no. A-2/21 to A-2/14 Shakti nagar Extn. c-66/RZ | 389172 | 123/17.07.08/EE(M)-II | Laxman Const Co. | 17.07.08 | 06.10.08 | 388015 | Work Completed
19 | 2008-06-23 | 22.05.08 | C/o open surface drain from h.no. 1 to 60 in HArijan basti Sawan park w.no. 66/RZ | 417100 | 192/02.09.08/EE(M)-II | M/s Gujral Const. | 09.09.08 | 08.12.08 | 310927 | Work Completed
20 | 2008-06-23 | 22.05.08 | P/l cc pavment in back lane from h.no. B-1 to B-16 in Shakti nagar Extn. C-66/RZ | 412806 | 113/17.07.08/EE(M0-II | M/s Ishwar Singh | 04.08.08 | 02.12.08 | 408760 | Work Completed
21 | 2008-06-23 | 22.05.08 | P/l mastic wearing course on road around park from h.no. A-80 to A-86, h.no. 79 to 71 and from h.no 58 to 70 in A block Ashok vihar ph-III C-66/RZ | 504800 | 201/02.09.08/EE(M)-II | M/s Ashok Kumar Gupta | 07.11.08 | 14.11.08 | 454240 | In Prog.
22 | 2008-06-23 | 22.05.08 | P/l mastuic wearing course on T point near C-1/1 in Ashok Vihar ph-II C-66/RZ | 440600 | 195/02.09.08/EE(M)-II | M/s Ashok Kumar Gupta | 21.10.08 | 18.11.08 | 440027 | Work Completed
23 | 2008-06-23 | 22.05.08 | P/l mastuic wearing course at the entrance of Shakti Apptt. in Shakti NAgar Extn.C-66/RZ | 451100 | 179/02.09.08/EE(M)-II | M/s Ashok Kumar Gupta | 21.10.08 | 14.11.08 | 450853 | Work Completed
24 | 2008-06-23 | 22.05.08 | C/o open surface drain from h.no. 64 to 31, 56A to 44A connecting to main drain of Sawan park in Sawan park extn C-66/RZ | 528700 | 191/02.09.08/EE(M)-II | M/s Jasvinder Gulati | 03.1.08 | 15.12.08 | 418030 | Work Completed
25 | 2008-06-23 | 22.05.08 | P/l cc pav. in back lane from h.no. B-2/49 to B-2/59 and along B-2/50 in B-2 block Ashok Vhar ph-II C-66/RZ | 407176 | 177/02.09.08/EE(M)-II | M/s Har Const Co. | 04.12.08 | P | 404365 | In Prog.
26 | 2008-06-23 | 22.05.08 | P/l mastic wearing course at T-point near LB College and Radha Swami Satsang Bhawan in Satyawati Mkt. Ashok Vihar ph-III C-66/Rz | 468100 | 194/02.09.08/EE(M)-II | M/s Bansal Const Co. | 05.11.08 | 20.11.08 | 466558 | Work Completed
27 | 2008-07-14 | 19.04.08 | C/o of walkway in the park opp. h.no. H-57 in H block in Ashok Vihar ph-I w.no.68/RZ | 199900 | 136/30.07.08/EE(M)-II | M/s S. Kumar Const. Co. | 07.08.08 | 06.10.08 | 199878 | Work Completed
28 | 2008-07-25 | 10.05.08 | C/o of back lane from h.no. C-106 to C-114 in Ashok Vihar ph-I w.no.68/RZ | 299790 | 189/02.09.08/EE(M)-II | M/s Tokas & Co. | 10.09.08 | 18.03.09 | 298335 | Work Completed
29 | 2008-07-25 | 10.05.08 | C/o cc from C-58 back lane in Ashok Vihar ph-I w.no.68/RZ | 485000 | 188/02.09.08/EE(M)-II | M/s Har Const Co. | 03.09.08 | P | 471484 | In Prog.
30 | 2008-07-25 | 10.05.08 | C/o of nallah from h.no. C-114 to C-106 in Ashok Vihar ph-I w.no.68/RZ | 394980 | 187/02.09.08/EE(M)-II | M/s Bhatia & Co. | 02.09.08 | 10.1.08 | 394601 | Work Completed
31 | 2008-05-25 | 10.05.08 | C/o of nallah from B-120 to B-102 in Ashok Vihar ph-I w.no.68/RZ | 481704
32 | 2008-07-25 | 10.05.08 | C/o of nallah from B-130 to B-147 in Ashok Vihar ph-I w.no.68/RZ | 480000 | 190/02.09.08/EE(M)-II | M/s Laxman Const Co. | 15.09.08 | 30.10.08 | 479529 | Work Completed
33 | 2008-07-25 | 10.05.08 | C/o of nallah from B-148 to mkt corner in Ashok Vihar ph-I w.no.68/RZ | 494870
34 | 2008-07-25 | 10.05.08 | C/o of nallah from A-91 to A-104 in Ashok Vihar ph-I w.no.68/RZ | 459000 | 197/02.09.08/EE(M)-II | M/s S.S. Contractor | 08.09.08 | P | 450770 | In Prog.
35 | 2008-07-25 | 10.05.08 | C/o of walkway infront of h.no. H-46, park in Ashok Vihar ph-I w.no.68/RZ | 199607 | 185/02.09.08/EE(M)-II | M/s Bhatia & Co. | 14.09.08 | 29.10.08 | 199417 | Work Completed
36 | 2008-08-04 | 28.07.08 | Dev of front open compound of community hall Ashok Vihar ph-II by pdg kota stone flooring in w.no.66 RZ | 587950 | 45/26.09.08/EE(Pr.)RZ | M/s Manish Const Co. | 05.01.08 | P | 300353 | In Prog.
37 | 2008-08-04 | 28.07.08 | C/o B/wall infront of community hall Ashok Vihar ph-II in w.no.66 RZ | 584600 | 46/26.09.08/EE(Pr.)RZ | M/s Manish Const Co. | 05.10.08 | P | 356515 | In Prog.
38 | 2008-09-05 | 08.08.08 | /o of walkway in the park of central park in H-block in Ashok Vihar Ph-I in C-68/RZ. | 495067 | 333/24.12.08/EE(M)-II | M/s SAS Const. | 12.01.09 | 31.03.09 | 495067 | Work Completed
39 | 2008-09-10 | 11.08.08 | C/O road by mastic asphalt wearing course from Budh Mandir to Ram Dev Mandir in J.J.Colony Wazirpur in C-65/RZ | 605700
40 | 2008-09-10 | 11.08.08 | C/O road by mastic asphalt wearing course from J-2 Dalao to J-2 Mandir and L-113 to L-462 in J.J.Colony Wazirpur in C-65/RZ | 625000
41 | 2008-09-10 | 11.08.08 | C/O road by mastic asphalt wearing course from near D-1 to C-280 in J.J.Colony Wazirpur in C-65/RZ | 442000 | 346/24.12.08/EE(M)-II | M/s Ashok Kumar Gupta | 16.03.09 | P | 433162 | In Prog.
42 | 2008-09-10 | 11.08.08 | C/O road by mastic asphalt wearing course from Gurudwara to Sanatan Dharam Mandir in J.J.Colony Wazirpur in C-65/RZ | 480550 | 90/12.06.09/EE(M)-II | M/s Ashok Kumar Gupta | 12.06.09 | 24.06.09 | 475324 | Work Completed
43 | 2008-09-10 | 11.08.08 | C/O road by mastic asphalt wearing course from near H-237 to G-258 in J.J.Colony Wazirpur in C-65/RZ | 440500 | 345/24.12.08/EE(M)-II | M/s Ashok Kumar Gupta | 09.02.09 | 14.03.09 | 440500 | Work Completed
44 | 2008-09-10 | 11.08.08 | C/O road by mastic asphalt wearing course from Mehak Restuarent to Corner of Central Park near DDA Mkt. in J.J.Colony Wazirpur in C-65/RZ | 596540 | 347/24.12.08/EE(M)-II | M/s Ashok Kumar Gupta | 09.02.09 | 14.03.09 | 536540 | Work Completed
45 | 2008-09-10 | 11.08.08 | C/O road by mastic asphalt wearing course from Sanatan Dharam Mandir to Police Chowki in J.J.Colony Wazirpur in C-65/RZ | 449700 | 344/24.12.08/EE(M)-II | M/s Ashok Kumar Gupta | 09.02.09 | 19.04.09 | 449700 | Work Completed
|  |  |  | 18466370 |  |  |  |  | 14406005

## Sheet3
Status Report of MLA, Sh. R.N. Bansal (AC-19), 2008-09
S.No. | Date of Booking | Date of consent | Name of Work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount Verified | Present Position
1 | 2008-07-11 | 28.05.08 | Dev of lane and drainage system from h.no. 24/5 to Gupta Glass, main orad to h.no. 56, h.no. SP-10 to SP-8 in Solapur village in Shalimar bagh in C-55/RZ | 348000 | 286/25.09.08/EE(M)-I | M/s Mahinder Singh | 25.09.08 | 22.01.09 | 303656 | Work Completed
2 | 2008-07-11 | 28.05.08 | Dev of lane from h.no. 60 to main road and side berms from Police station road to Kababi shop (along NDPL office) in Shahipur village in Solapur village in Shalimar bagh in C-55/RZ | 587500
3 | 2008-07-11 | 08.07.08 | Dev of walkway of park opp. h.no. 179 in BU block Pitampura (North) in C-54/RZ | 306120
4 | 2008-07-15 | 11.07.08 | Dev of side lane by pdg drainage of RMC along flat no. 6, 19, 28, 48, and 61 in AC block in Shalimar BAgh (South) in C-56/RZ | 496700 | 192/18.08.08/EE(M)-I | M/s J.M.D Const Cio. | 25.08.08 | 16.01.09 | 495902 | Work Completed
5 | 2008-07-15 | 11.07.08 | Dev of side lane by pdg drainage from h.no. 69 to 78 and 139 to 148 and berms near flat no. 98 to 119 in block BK-I in Shalimar BAgh (South) in C-56/RZ | 575500 | 366/08.12.08/EE(M)-I | M/s Singhal builders | 15.12.08 | 14.03.09 | 499700 | Work Completed
6 | 2008-07-15 | 11.07.08 | Dev of lane and berms pdg RMC and drainage along h.no. 24 to 19, 27 to 25, 25 to 30 and 31 to 34 in AC block in Shalimar BAgh (South) in C-56/RZ | 593000 | 357/08.12.08/EE(M)-I | M/s Singhal builders | 15.12.08 | 30.06.09 | 499996
7 | 2008-07-17 | 15.07.08 | Remodling to drainage system along the B/wall of Guru Govind Singh College of Commerce on TV Tower road i Pitam Pura (south) in C-53/RZ | 387300 | 320/10.10.08/EE(M)-I | M/s Kuhar Const Co. | 17.10.08 | 20.01.09 | 293218 | Work Completed
8 | 2008-07-18 | 05.07.08 | Dev of back lane by pdg RMC and drainage from h.no. 1 to 6 and 7 to 16 in AE block in Shalimar bagh C- /RZ | 597700 | 368/08.12.08/EE(M)-I | M/s Singhal builders | 15.12.08 | 16.03.09 | 592184 | Work Completed
9 | 2008-07-28 | 07.07.08 | P/o street lighting arrangment in MCD park in B block 9west0 to CA block Shaimar bagh C- /RZ | 449607 | 155/17.10.08/EE(E0-VII | M/s Pee Kay Elect. Works | 17.12.08 | 24.12.08 | 422017 | Work Completed
10 | 2008-07-28 | 09.07.08 | P/o strret lighting arrangemt in MCD park opp. 69/A in BW block Shalimar bagh in C /RZ | 306898 | 279/20.02.09/EE(E)-VII | M/s Amit Elevator Services | 25.02.09 | 24.03.09 | 256669 | Work Completed
11 | 2008-07-28 | 19.05.08 | P/o lighting arrangment in MCD park situated in KU and HU block in Pitam pura w.no. /RZ | 483227 | 138/13.10.08/EE(E)-VII | M/s Gyan Entp. | 14.10.08 | 10.11.08 | 437684 | Work Completed
12 | 2008-08-04 | 05.07.08 | Dev of lane by pdg RMC and drain in the lane of h.no.100 to 109 in AE-block in Shalimar Bagh(South) in C-56/RZ | 805500
13 | 2008-08-04 | 11.07.08 | Dev of lane by RMC and drain from h.no.11 to 21 and 22 to 32 in AE-Block in Shalimar Bagh (South) in C-56/RZ | 993200
14 | 2008-08-08 | 18.07.08 | Dev of park B/Wall from flat no.36A to 37A and 69A to 73A in U and V -Block in Shalimar Bagh(North)in C-56/RZ | 688960
15 | 2008-08-26 | 30.07.08 | P/o lighting arangement in MCD park opp. h.no. 82 to 83 BU block Pitam pura w.no.53 RZ | 99968 | 193/16.12.08/EE(E)-VII | M/s Modern Electricals | 17.12.08 | 22.01.09 | 98646 | Work Completed
16 | 2008-08-26 | 15.07.08 | P/o SHM pole with lights infront of Gurudwara in BC- block (west), Shalimar bagh w.no.56/RZ | 219824 | 220/31.12.08/EE(E)-VII | M/s Paras Const.Co. | 29.12.08 | 12.01.09 | 190925 | Work Completed
17 | 2008-08-26 | 29.07.08 | P/o 50 nos. MS Tube poles in Shalimar Bagh and Pitampura w.no. 56/RZ | 447690 | 165/17.10.08/EE(E)-VII | M/s Forward Engineers | 17.12.08 | 19.02.09 | 427853 | Work Completed
18 | 2008-08-26 | 29.07.08 | P/o 100 nos HPSV street lights arrangement in Shalimar Bagh in pitam Pura in C-56/RZ | 513764 | 166/17.10.08/EE(E)-VII | M/s Sri Balaji Electricals | 16.12.08 | 22.01.09 | 499608 | Work Completed
19 | 2008-08-28 | 22.07.08 | Pdg RMC in the front portion of CU-Block Mkt.opp.EU-Block in Pitampura (North)in C-54/RZ | 489275 | 307/07.10.0/EE(M)-I | M/s Bhatia & Co. | 17.10.08 | 26.12.08 | 420195 | Work Completed
20 | 2008-08-28 | 28.07.08 | Pdg Red Sand Stone on the Planters(Front Portion)of CU-Block Mkt. in Pitampura(North)in C-54/RZ | 246958 | 313/07.10.08/EE(M)-I | M/s Tokas & Co. | 15.10.08 | 14.01.09 | 246866 | Work Completed
Addl. | 2008-09-10 | 09.09.08 | C/O hall, under ground Water Tank, Septic Tank, Plaing Courts and Passage etc. in MC Pry School Sahipur Village Shalimar Bagh in C-55/RZ | 2367000 | 50/10.10.08/EE(Pr.)/RZ | M/s Sarthak Const Co. | 15.10.08 | 18.04.09 | 2358008 | Work Completed
21 | 2008-09-24 | 19.09.08 | P/P lighting arrangement in MCD Park in B-I-Block, Salimar Bagh, in RZ | 149177 | 171/17.10.08/EE(E)-VII | M/s Sheela Elect. Works | 18.12.08 | 31.12.08 | 124332 | Work Completed
|  |  |  | 12152868 |  |  |  |  | 8167459

## Sheet4
Status Report of MLA, Sh. Jai Bhagwan Aggarwal (AC-20), 2008-09
S.No. | Date of Booking | Date of consent | Name of Work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount Verified | Present Position
1 | 2008-06-23 | 25.05.08 | Dev of lane from Chajju Pardhan hs. to Banni Singh hs. in Siraspur Vill. in C-18/CLZ | 354400 | 146/25.08.08/EE(M)-IV | M/s Gaurav Mehta | 01.09.08 | 05.12.08 | 351917 | Work Completed
2 | 2008-08-07 | 04.08.08 | Dev of lane by pdg RMC near h.no.60 to 71 in pkt.A-1 Sec-8 in C-51/RZ | 194970
3 | 2008-08-07 | 04.08.08 | C/O Umbrella in park of pkt.A-1 near plot no.73 of Sec-8 in C-51/RZ | 494750
4 | 2008-08-12 | 03.07.08 | Imp of road side berms by pdg interlocking tiles from h.np.1 to 249 and cc in parking area infront of h.no.495 and main entry gate in Millanium Appartment in Sec-18 and backlane from C-9/31 to C-9/36 in Sec-15 C-49/RZ | 320767 | 413/19.09.0/EE(M)-IV | M/s J.D. Const Co. | 30.09.08 | 26.12.08 | 318954 | Work Completed
5 | 2008-08-12 | 03.07.08 | P/F barbad wire fancing on the B/Wall from h.no.426 along Canal side in C-Block Sec-18 in Millanium Appartment in C-49/RZ | 198935
6 | 2008-08-14 | 25.07.08 | C/O passage near h.no.417,434 to 307,312,418,433,580,596 by pdg chequered terrazo tiles floring in pkt.C-8 Sec-8 in C-51/RZ | 499350
7 | 2008-08-14 | 04.08.08 | C/O walkway in park near h.no.80 in pkt.A-1 Sec-8 in C-51/RZ | 296450 | 564/13.01.09/EE(M)-IV | M/s Shri Bhagwan Const Co. | 28.01.09 | 29.04.09 | 184983 | Work Completed
8 | 2008-08-14 | 25.07.08 | C/O lane by pdg RMC and O/S drain from h.no.1 to 26 in pkt.D-12 Sec-8 C-51/RZ | 499500 | 627/24.02.09/EE(M)-IV | M/s Birender Singh Dabas | 24.02.09 | 06.04.09 | 498445 | Work Completed
9 | 2008-08-14 | 25.07.08 | D/O lane by pdg RMC from h.no.31 to 120 in pkt.B-4 Sec-8 C-51/RZ | 488000 | 583/28.01.09/EE(M)-IV | M/s Shri Bhagwan Const Co. | 07.02.09 | 06.05.09 | 462246 | Work Completed
10 | 2008-08-14 | 25.07.08 | D/O lane by pdg RMC from h.no.91 to 120 in pkt.B-4 Sec-8 C-51/RZ | 329000 | 546/13.01.09/EE(M)-IV | M/s Birender Singh Dabas | 15.01.09 | 30.03.09 | 314040 | Work Completed
11 | 2008-08-14 | 25.07.08 | C/O B/Wall and path in park near h.no.F-19/24 Sec-8 C-51/RZ | 360000 | 563/13.01.09/EE(M)-IV | M/s Shri Bhagwan Const Co. | 23.01.09 | 05.05.09 | 260725 | Work Completed
12 | 2008-08-14 | 25.07.08 | Dev of lane by pdg RMC from h.no.361 to 390 in Pkt.B-4 Sec-8 in C-51/RZ | 349000 | 547/13.01.09/EE(M)-IV | M/s Birender Singh Dabas | 16.01.09 | 31.03.09 | 332035 | Work Completed
13 | 2008-08-14 | 25.07.08 | Dev of lane by pdg RMC from h.no.121 to 210 in Pkt.B-4 Sec-8 in C-51/RZ | 478000 | 596/03.02.09/EE(M)-IV | M/s Shri Bhagwan Const Co. | 12.02.09 | 29.04.09 | 435341 | Work Completed
14 | 2008-08-14 | 25.07.08 | Dev of lane by pdg RMC from h.no.121 to 210 in Pkt.B-6 Sec-8 in C-51/RZ | 444000 | 582/28.01.09/EE(M)-IV | M/s Shri Bhagwan Const Co. | 07.02.09 | 04.05.09 | 416917 | Work Completed
15 | 2008-08-14 | 25.07.08 | C/O Ahatas by pdg interlocking prefeb pavers from h.no.140 to 146,147 to 154,155 to 16,169 to 178 and 181 to 198 in pkt.E-16,Sec-8 in C-51/RZ | 499960
16 | 2008-08-14 | 25.07.08 | Imp to drainage system and lane by pdg cc pav.near h.no.F-138 and near C-270 in Prashant Vihar in C-51/RZ | 348000 | 416/19.09.08/EE(M)-IV | M/s J.D. Const Co. | 29.09.08 | 24.12.08 | 348000 | Work Completed
17 | 2008-08-14 | 25.07.08 | Dev of park by pdg marble washed plaster etc near h.no.26,361,369 and 324 in pkt.B-5 Sec-8 in C-51/RZ | 439950
18 | 2008-08-14 | 25.07.08 | Dev of park by pdg marble washed plaster etc near h.no.20 and side wall towards School in pkt.B-5 Sec-8 in C-51/RZ | 371000 | 590/28.01.09/EE(M)-IV | M/s Subash Chander_III | 06.02.09 | 29.04.09 | 368132 | Work Completed
19 | 2008-08-14 | 25.07.08 | Dev of park by pdg marble washed plaster etc near h.no.134,174,238 and 91 in pkt.B-5 Sec-8 in C-51/RZ | 439950
20 | 2008-08-20 | 04.08.08 | C/O Chatrinuma Shelter in C-Block Park Millanium Appartment in Sec-18 in C-49/RZ | 239900 | 556/13.01.09/EE(M)-IV | M/s Vikas Bansal | 20.01.09 | 18.03.09 | 237728 | Work Completed
21 | 2008-08-20 | 03.07.08 | Imp of road side berms by pdg interlocking tiles from h.no.175 to 531,531 to 426,426 to 410 and 410 to 316(One Side)in C-Block Millanium Appartment Sec-18 in C-49/RZ | 498887 | 412/19.09.08/EE(M)-IV | M/s Tokas & co. | 14.10.08 | 03.02.09 | 498250 | Work Completed
22 | 2008-08-20 | 19.08.08 | C/O road side berms (both sides)and parking area by pdg cc pav from h.no.pkt.3/2 to DESU Office,DESU Office to Mkt.(near shop no.4),pkt.3/1 to 3/23 and parking area infront of pkt.5/42 in E-2 Block Sec-15 in C-49/RZ | 497803 | 414/19.09.08/EE(M)-IV | M/s Ram Kishore Bairwa | 16.02.09 | 15.05.09 | 497567 | Work Completed
23 | 2008-08-20 | 19.08.08 | Imp of parking area by pdg cc pav.at infront of h.no.1/17,2/17,2/57,3/34 and near (shop no.16)in pkt. 1,2 and 3 in E-2 Block Sec-15 in C-49/RZ | 448000 | 421/19.09.08/EE(M)-IV | M/s S.S. builders & Contractors | 28.09.08 | 01.12.08 | 447960 | Work Completed
24 | 2008-09-08 | 02.09.08 | C/O road by pdg dense carpetting in H-19 pkt. from h.no. H-19/120 to H-19/136 and H-19/86 to H-19/102 in Sec-7 in C-52/RZ | 400000
25 | 2008-09-08 | 02.09.08 | C/O road by pdg dense carpetting in B-6 pkt. from h.no.B-6/31 to B-6/182 and B-6/91 to B-6/290 in Sec-7 C-52/RZ | 442700
26 | 2008-09-08 | 02.09.08 | C/O road by pdg dense carpetting in H-19 pkt. from h.no.H-19/17 to H-19/154 in Sec-7 in C-52/RZ | 346000
27 | 2008-09-16 | 12.09.08 | P/O lighting arrangement in the MPL Parks of A and B Block Sec-7, C and D Block of Sec-8, near New Swastick Appartment Sec-9, D-Block Prashant Vihar, near Jung Appartment Sec-13,B and C-Block Park Sec-15, B-Block Park Sec-18 in C-50 and 51/RZ | 496826 | 117/06.10.08/EE(E)-VII | M/s S.T. Electric Co. | 06.10.08 | 15.10.08 | 481960 | Work Completed
28 | 2008-09-18 | 10.09.08 | C/O Road By RMC in the lane of Gulab singh house And Pujari hs. and jai kishan hs. in village Naharpur in C-52/RZ. | 399176
29 | 2008-09-18 | 10.09.08 | C/O Road by RMC in the lane of lala Narayan singh hs. gali and apporach and adj. lane in village Naharpur in C-/52/RZ. | 398316 | 476/13.10.08/EE(M)-IV | M/s Ram Swaroop | 17.10.08 | 16.12.08 | 396454 | Work Completed
30 | 2008-09-18 | 10.09.08 | Raising of road from main road to Rani Satee Mandir and adj lane in village Naharpur in w.no.52/RZ | 299882 | 464/13.10.08/EE(M)-IV | M/s Ishwar Singh | 10.11.08 | 04.12.08 | 297465 | Work Completed
31 | 2008-09-25 | 18.09.08 | P/O lighting arrangement in the MPL. Park in G-6 Sec-16,A-Block Sec-17,B-Block Sec-15,A-Block Sec-18,C-Block Sec-19 in C-21/RZ | 489968 | 128/13.10.08/EE(E)-VII | M/s Kawatara Elect. Works | 13.10.08 | 21.10.08 | 488166 | Work Completed
32 | 2008-09-25 | 17.09.08 | P/O lighting arrangement at the Chowk and Park of C,D,E, Block, Sec-7 Rohini, B-Block Sec-5, A-1 Block Sec-6, D-Block Prashant Vihar in C-22/RZ | 479616 | 126/13.10.08/EE(E)-VII | M/s Prince Engg. Works | 13.10.08 | 21.10.08 | 465923 | Work Completed
33 | 2008-09-25 | 20.09.08 | P/O 2 nos. semi high mast lights with poles at Chowk near C-Block Sec-19 Rohini and near Chowk at Arawali Kunj Sec-13 in C-49,50 RZ | 419688 | 124/13.10.08/EE(E)-VII | M/s Aman Elect. | 17.12.08 | 23.01.09 | 394955 | Work Completed
34 | 2008-09-29 | 02.09.08 | Imp of Boundary/Walkway in park opp. DAV Public School in E-4 Pkt.in Sec-7 in C-52/RZ | 499000 | 512/13.10.08/EE(M)-IV | M/s JMD Const Co. | 24.10.08 | 20.01.09 | 498995 | Work Completed
35 | 2008-09-29 | 02.09.08 | C/O Ahata by Pdg RMC in B-5 Pkt.h.no.59 to 67 in Sec-7 in C-52/RZ | 98000 | 510/13.10.08/EE(M)-IV | M/s Tokas & co. | 15.12.08 | 19.01.09 | 83784 | Work Completed
36 | 2008-09-29 | 26.09.08 | C/O road by pdg RMC from J.K.Tailor to near Shiv Charan Saini hs in Village Naharpur in C-52/RZ. | 491638 | 499/13.10.08/EE(M)-IV | M/s Rameshwar Dayal | 24.10.08 | P | 366946 | In pro
37 | 2008-09-29 | 26.09.08 | C/O road by pdg RMC near Rohini Public School to Yadav Mkt.(near road)and main road in Village Naharpur in C-52/RZ. | 488915
38 | 2008-09-29 | 26.09.08 | Dev of Chaupal in Village Naharpur in C-52/RZ. | 95963 | 500/13.10.08/E(M)-IV | M/s Rameshwar Dayal | 16.10.08 | 18.12.08 | 95054 | Work Completed
39 | 2008-06-06 | 05.05.08 | C/O B/Wall of park infront of F-1/12 in F-Block,Sec-15 in w.no.49/Rohini | 190759 | 269/31.07.08/EE(M)-IV | M/s Dee Pee Entp. | 21.08.08 | 08.10.08 | 190669 | Work Completed
40 | 2008-06-06 | 05.05.08 | C/O B/Wall of park infront of F-2/28 in F-Block,Sec-15 in w.no.49/Rohini Zone | 193122 | 268/31.07.08/EE(M)-IV | M/s Ishwar Singh | 14.11.08 | 18.02.09 | 192744 | Work Completed
41 | 2008-06-06 | 05.05.08 | C/o B/WAll of park infront of F-2/20 Sec-15,in w.no.49/Rohini Zone | 191101 | 270/31.07.08/EE(M)-IV | M/s Sanjay Gupta | 26.08.08 | 08.10.08 | 191024 | Work Completed
42 | 2008-06-06 | 05.05.08 | C/o B/Wall of park infront of G-1/51 in G-Block,Sec-15 in w.no.49/Rohini Zone | 197356
43 | 2008-06-18 | 21.05.08 | C/O Ahatas by pdg interlocking prefeb.pavers in D-11 Pkt h.no.9 to 22 and 151 to 164 in Sec-7 w.no.52/Rohini Zone | 324100 | 348/08.08.08/EE(M)-IV | M/s Ishwar Singh | 07.10.08 | 10.11.08 | 323594 | Work Completed
44 | 2008-06-18 | 21.05.08 | C/O road by pdg RMC in E-4 pkt. h.no.134 to 150 and infront of park in Sec-7 w.no.52/Rohini Zone | 465400 | 289/01.08.08/EE(M)-IV | M/s Satyam Const. | 21.10.08 | 10.11.08 | 459087 | Work Completed
45 | 2008-06-18 | 21.05.08 | C/O road by pdg RMC from Shiv Chran Sharma to Ramavtar yadav and Bishan Yaday to Bhopal Yadav wali gali in Naharpur village w.no.52/Rohini Zone | 485750 | 287/01.08.08/EE(M)-IV | M/s Sanjay Gupta | 12.09.08 | 10.10.08 | 474527 | Work Completed
46 | 2008-06-18 | 21.05.08 | C/o Ahatas by pdg interlocking prefeb. pavers in B-6 pkt. h.no.69-82,127 to 144,199 to 210, 267-284 in Sec-7 w.no.52/Rohini Zone | 498600 | 410/09.09.08/EE(M)_IV | M/s Sanjay Gupta | 10.09.08 | 20.11.08 | 498506 | Work Completed
47 | 2008-06-18 | 21.05.08 | C/O backlane from E-4/82 to 90 in Sec-7 w.no.52/Rohini Zone | 227550 | 285/01.08.08/EE(M)-IV | M/s Nisant Const Co. | 11.0.08 | 11.12.08 | 227370 | Work Completed
48 | 2008-06-18 | 21.05.08 | C/O Backlane by pdg RMC in E-4 pkt. h.no.139 to 146 and 138 to 135 along park in Sec-7 w.no.52/Rohini Zone | 270000 | 286/01.08.08/EE(M)-IV | M/s Vivek Assos. | 08.08.08 | 29.09.08 | 269284 | Work Completed
49 | 2008-06-18 | 21.05.08 | C/O ahatas by pdg interlocking prefeb pavers in B-4 pkt. h.no.30 to 38,39 to 58 and 59 to 67 in Sec-7 w.no.52/Rohini Zone | 456000 | 290/01.08.08/EE(M)-IV | M/s Vinod Const co. | 05.08.08 | 10.04.09 | 453874 | Work Completed
50 | 2008-06-18 | 21.05.08 | C/O backlane by pdg RMC in E-4 pkt. h.no.121 to 134 in Sec-7 w.no.52/Rohini Zone | 227500 | 288/01.08.08/EE(M)-IV | M/s Har Const Co. | 10.11.08 | P | 226296 | In pro
51 | 2008-06-18 | 28.05.08 | Dev of drain in Prashant Vihar from A-219 to B-208 And C-257 to C-247 in w.no.51/Rohini Zone | 441150
52 | 2008-06-18 | 28.05.08 | Dev to drain from h.no.56 to 23, 61 to 70, 71 to 80 in pkt. A-1 in Sec-8 w.no.51/Rohini Zone | 385450
53 | 2008-06-18 | 28.05.08 | Dev to drain from h.no.93 to 107 and 53 to 57 in pkt.A-1 in Sec-8 w.no.51/Rohini Zone | 348100
54 | 2008-06-18 | 28.05.08 | C/O backlane from h.no.1 to 10 in Block C-3 in Prashant Vihar w.no.51/Rohini Zone | 256328 | 275/01.08.08/EE(M)-IV | M/s Birender Singh Dabas | 11.08.08 | 26.11.08 | 247256 | Work Completed
55 | 2008-06-18 | 28.05.08 | Dev to road berms from h.no.238 to 239 pkt.C-9, Sec-7 Rohini And ahatas from h.no.1 to 8, 384 to 390,pkt.B-4,Sec-8 from h.no.61 to 72 pkt.A-3,Sec-7 by interlocking tiles in w.no.51/Rohini Zone | 364250 | 274/01.08.08/EE(M)-IV | M/s M.K. Gupta | 10.09.08 | 10.10.08 | 364226 | Work Completed
56 | 2008-06-18 | 28.05.08 | Dev to ahatas by pdg interlocking tiles from h.no.1 to 9, 10 to 18, 71 to 82, 134 to 145, 188 to 196 and 209 to 217 in pkt.A-2 Sec-8 w.no.51/Rohini Zone | 480800 | 276/01.08.08/EE(M)-IV | M/s Parkash Khanna | 20.08.08 | 10.10.08 | 476659 | Work Completed
57 | 2008-06-18 | 23.05.08 | Dev to road by pdg RMC And open surface drain from A-1/39 to A-1/52 in Sec-8 w.no.51/Rohini Zone | 499234 | 277/01.08.08/EE(M)-IV | M/s Har Const Co. | 09.09.08 | P | 461446 | In pro
58 | 2008-06-18 | 23.05.08 | Dev to lane by pdg RMC from h.no.A-1/12 to A-1/22 in Sec-8 w.no.51/Rohini Zone | 452300 | 278/01.08.08/EE(M)-IV | M/s Dee Pee Entp. | 09.09.08 | 08.11.08 | 449892 | Work Completed
59 | 2008-06-18 | 23.05.08 | Dev to park near Ram Mandir in D-Block Prashant Vihar by pdg walkway and raising of B/Wall in w.no.51/Rohini Zone | 179183 | 283/01.08.08/EE(M)-IV | M/s Ram Kishore Bairwa | 25.09.08 | 20.10.08 | 179183 | Work Completed
60 | 2008-06-18 | 23.05.08 | Dev to lane of pkt. A-1 Sec-7 Rohini by pdg RMC from h.no.42 to 81, 81 to 82 to 41, 41 to 17, 81 to 101, 10 to 1, 121 to 113 in w.no 51/Rohini Zone | 446520 | 280/01.08.08/EE(M)-IV | M/s Rameshwar Dayal | 23.09.08 | 10.11.08 | 423960 | Work Completed
61 | 2008-06-18 | 23.05.08 | Dev to lane by pdg RMC from h.no.c-269 to C-283 in Prashant Vihar w.no.51/Rohini Zone | 342465 | 303/02.08.08/EE(M)-IV | M/s Vinod Const co. | 11.08.08 | 29.10.08 | 342465 | Work Completed
62 | 2008-06-18 | 23.05.08 | Dev to lane in Prashant Vihar from h.no.B-208 to B-183 by pdg RMC and open surface drain in w.no.51/Rohini Zone | 498187 | 279/01.08.08/EE(M)-IV | M/s Mukesh Kumar Bansal | 11.08.08 | 27.01.09 | 497753 | Work Completed
63 | 2008-06-18 | 23.05.08 | Dev to lane in prashant Vihar from h.no.A-190 to A-136 by pdg RMC open surface drain in w.no.51/Rohini Zone | 498187 | 282/01.08.08/EE(M)-IV | M/s Ram Kishore Bairwa | 11.08.08 | 09.02.09 | 490039 | Work Completed
64 | 2008-06-18 | 23.05.08 | Dev of lane in Prashant Vihar from h.no.A-274 to B-260by pdg RMC and open surface drain in w.no.51/Rohini Zone | 498187 | 281/01.08.08EE(M)-IV | M/s Vivek Assos. | 11.08.08 | 22.01.09 | 496501 | Work Completed
|  |  |  | 24353839 |  |  |  |  | 17479297 | 0

## Sheet5
Status Report of MLA, Sh. Kulwant Rana (AC-21), 2008-09
S.No. | Date of Booking | Date of consent | Name of Work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount Verified | Present Position
1 | 2008-06-23 | 12.05.08 | P/O HPSV street light arrangement at vill. Rithala(west Portion)C-22/RZ | 595830 | 243/31.12.08/EE(E)-VII | M/s Sant Gian Corp. | 31.12.08 | 12.01.09 | 444411 | Work Completed
2 | 2008-06-23 | 12.05.08 | P/O HPSV street light arrangement at vill. Mangolpur Khurd(East Portion)C-47/RZ | 595091 | 427/02.03.09/EE(E)-VII | M/s Saturn Elect. | 08.05.09 | 22.05.09 | 500433 | Work Completed
3 | 2008-06-23 | 12.05.08 | P/O HPSV street light arrangement at vill. Mangolpur Khurd(West Portion)C-47/RZ | 595506 | 264/03.02.09/EE(E)-VII | M/s Ankur Entp. | 03.02.09 | P | 396900 | In Prog.
4 | 2008-06-23 | 12.05.08 | P/O HPSV street light arrangement at vill. Mangolpur Khurd(South Portion)C-47/RZ | 595091 | 188/16.12.08/EE(E)-VII | M/s Super Shine Assos. | 16.12.08 | 19.12.08 | 494732 | Work Completed
5 | 2008-06-23 | 12.05.08 | P/O HPSV street light arrangement at vill. Rithala (North Portion)C-22/RZ | 595091 | 452/02.03.09/EE(E)-VII | M/s Utsav Engineers | 08.05.09 | 04.06.09 | 498252 | Work Completed
6 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.84 to 559 in pkt.C Sec-1,in C-24/RZ | 473000 | 341/07.08.08/EE(M)-IV | M/s D.B. Entp. | 11.08.08 | 05.01.09 | 472540 | Work Completed
7 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.01 to 642 in pkt.D Sec-1,in C-24/RZ | 499300 | 336/07.08.08/EE(M)-IV | M/s Vinod Const Co. | 03.11.08 | 08.01.09 | 499236 | Work Completed
8 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.01 to 82 in pkt.D Sec-1,in C-24/RZ | 499300 | 335/07.08.08/EE(M)-IV | M/s Vinod Const Co. | 03.11.08 | 17.12.08 | 497393 | Work Completed
9 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.01 to 84 in pkt.C Sec-1,in C-24/RZ | 496800 | 372/20.08.08/EE(M)-IV | M/s Sanjay Gupta | 08.09.08 | 26.02.09 | 496735 | Work Completed
10 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.255 to 336 in pkt.D Sec-1,in C-24/RZ | 492900 | 332/07.08.08/EE(M)-IV | M/s JMD Const Co. | 10.11.08 | 18.12.08 | 491201 | Work Completed
11 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.253 to 334 in pkt.C Sec-1,in C-24/RZ | 485700 | 338/07.08.08/EE(M)-IV | M/s M.K. Gupta | 25.08.08 | 15.11.08 | 485667 | Work Completed
12 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.1041 to 1122 in pkt.B Sec-1,in C-24/RZ | 441550 | 339/07.08.08/EE(M)-IV | M/s M.K. Gupta | 20.08.08 | 29.12.08 | 441060 | Work Completed
13 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.10 to 56 in pkt.E Sec-1,in C-24/RZ | 467550 | 333/07.08.08/EE(M)-IV | M/s Ishwar Singh | 25.08.08 | 26.11.08 | 443290 | Work Completed
14 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.33 to 44 in pkt.E Sec-1,in C-24/RZ | 400850 | 370/20.08.08/EE(M)-IV | M/s Ram Kishore Bairwa | 27.10.08 | 16.01.09 | 400326 | Work Completed
15 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.69 to 83 in pkt.E Sec-1,in C-24/RZ | 453650 | 330/07.08.08/EE(M)-IV | M/s Ishwar Singh | 18.08.08 | 02.04.09 | 453588 | Work Completed
16 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.60 to 68 in pkt.E Sec-1,in C-24/RZ | 367200 | 371/20.08.08/EE(M)-IV | M/s GargEntp. | 29.09.08 | 27.11.08 | 366250 | Work Completed
17 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.30 to 159,202 to 368,664 to 721,31 to 154 and along park in pkt.B Sec-1,in C-24/RZ | 492300 | 340/07.08.08/EE(M)-IV | M/s Parkash Khanna | 03.11.08 | 29.12.08 | 490521 | Work Completed
18 | 2008-06-23 | 28.05.08 | P/L RMC and dev.of drainage system from h.no.01 to 20, to 11 in pkt.E Sec-1,in C-24/RZ | 427450 | 334/07.08.08/EE(M)-IV | M/s Sanjay Gupta | 18.09.08 | 10.11.08 | 421069 | Work Completed
19 | 2008-06-23 | 28.05.08 | Dev of Ahatas infront of/adj. to h.no. 292,477,330,436,426,414,336,382,628,534,526,693,708,792,in pkt-B Sec-1 C-24/RZ | 497050 | 337/07.08.08/EE(M)-IV | M/s Har Const Co. | 26.11.08 | P | 305346 | In Prog.
20 | 2008-06-23 | 28.05.08 | Dev of Ahatas infront of/adj. to h.no. 745,945,935,901,896,1015,876,1026,1027,1038,1044,1053,in Block-B and C-26.C-51 in block-C Sec-1 C-24/RZ | 495350 | 329/07.08.08/EE(M)-IV | M/s Ram Kishore Bairwa | 03.10.08 | 31.12.08 | 491724 | Work Completed
21 | 2008-06-23 | 28.05.08 | Dev of Ahatas infront of/adj. to h.no.C-64,78,108,13,33,217,213,307,382,409,437,474,576,476,in pkt-C Sec-1 C-24/RZ | 483650 | 342/07.08.08/EE(M)-IV | M/s Birender Singh Dabas | 20.08.08 | P | 258744 | Work Completed
22 | 2008-08-18 | 14.08.08 | P/o HPSV Street light arrangement along approach road from Cremation ground Avantika to Khanzhawla road w.no.24/RZ | 594255 | 426/03.02.09/EE(E)-VII | M/s Amit Elevator Services | 08.05.09 | 27.05.09 | 590020 | Work Completed
23 | 2008-08-18 | 14.08.08 | P/o Semi High Mast light/Pole at park between pkt-23 and 24 Sec -24 w.no.24 RZ | 279580
24 | 2008-08-18 | 14.08.08 | P/o HPSV Street light arrangement from village Pansoli to Karala road w.no.26/RZ | 593555
25 | 2008-08-23 | 14.08.08 | P/o lighting arrangement at village Shahbad Daulatpur from Ochandi road to Sec-17 water filling points w.no.26/RZ | 593555 | 312/20.02.09/EE(E)-VII | M/s Seth Const Co. | 20.02.09 | 04.03.09 | 593555 | Work Completed
26 | 2008-08-18 | 14.08.08 | P/o lighting arrangement from Prahladpur Boys School to Khera Khurd road upto Triple bend in C-26/RZ | 593905 | 451/02.03.09/EE(E)-VII | M/s Forward Engineers | 08.05.09 | 27.05.09 | 593270 | Work Completed
27 | 2008-08-18 | 14.08.08 | P/o Street light arrangement from main Ochandi road to Sec-26 JJ Rc cly. sent St. Zaviour School Shahbad Daulatpur w.no.26/RZ | 593909
28 | 2008-08-18 | 14.08.08 | P/o lighting arrangement along Supplementary drain on Bed road from Sec-24, 60mtr vide road to sec-26 bridge w.no.26/RZ | 594255 | 428/02.03.09/EE(E)-VII | M/s Ram Gopal & Co. | 02.03.09 | 10.04.09 | 585330 | Work Completed
29 | 2008-09-04 | 11.08.08 | C/O Common area of Shaft near/adjoining h.no.723,707,708,691,724,738,776,747,625,627,611,643,563,674 in Pkt.6-II in Sec-3 Rohini in C-45/RZ | 584000
30 | 2008-09-04 | 11.08.08 | C/O Common area of Shaft near/adjoining h.no.145,243,274,763,778 in Pkt.6-I and h.no.547,531,562,595,580,594,467, in Pkt.6-II in Sec-2 Rohini in C-45/RZ | 587750
31 | 2008-09-04 | 11.08.08 | C/O Common area of Shaft near/adjoining h.no.1,3,17,20,33,83,113,186,170,155,197,154,129,115 in Pkt.-III Sec-2 Rohini in C-45/RZ | 587750
32 | 2008-09-04 | 11.08.08 | C/O Common area of Shaft near/adjoining h.no.211,227,228,260,842,851,859,867,875,786,818,819,804,762 in Pkt.6-I in Sec-2 Rohini in C-45/RZ | 586000
33 | 2008-09-04 | 11.08.08 | C/O Common area of Shaft near/adjoining h.no.100,67,65,52,49,187,202 in Pkt.-III and 412,403,371,369 in Pkt.-IV and h.no.211,20,195 in Pkt.-VII in Sec-2 Rohini in C-45/RZ | 587750
34 | 2008-09-04 | 11.08.08 | C/O Common area of Shaft near/adjoining h.no.394,212,244,258,260,275,306,292,322,324,353,355,363 in Pkt.-IV in Sec-2 Rohini in C-45/RZ | 587750
35 | 2008-09-04 | 11.08.08 | C/O Common area of Shaft near/adjoining h.no.129,170,116,171,179,99,98,114,131,66,67,35,34,18 in Pkt.-VII in Sec-2 Rohini in C-45/RZ | 586000
36 | 2008-09-10 | 24.07.08 | C/O lane by cc from Dharampal hs to Meghraj hs and Shiv hs to Bheecha hs in Village Rithala in C-22/RZ | 199986 | 470/13.10.08/EE(M)-IV | M/s JMD Const Co. | 14.10.08 | 15.06.09 | 199986 | Work Completed
37 | 2008-09-10 | 24.07.08 | C/O lane by cc from Shrichand hs to Thakur uday Singh Rana hs in Village Rithala in C-22/RZ | 211167
38 | 2008-09-10 | 24.07.08 | C/O lane by cc from Ramesh Kumar hs to Rameshwar Singh Rana hs and Pt.Bhagwan Dayal Sharma hs to Dhola Pandit hs in Village Rithala in C-22/RZ | 276022 | 459/13.10.08/EE(M)-IV | M/s Ishwar Singh | 28.10.08 | 14.01.09 | 276022 | Work Completed
39 | 2008-09-10 | 24.07.08 | P/F MS Sign Boards in Village Rithala, Sec-5 and 6 in Rohini in C-22/RZ | 175032
40 | 2008-09-16 | 24.07.08 | C/O lane by cc from Ganga Ram hs to Temple and Kalu Ram hs to Dharam Kanta in Village Rithala in C-22/RZ | 493000 | 490/13.10.08/EE(M)-IV | M/s Tokas & Co. | 20.10.08 | 19.03.09 | 488127 | Work Completed
41 | 2008-09-16 | 24.07.08 | C/O lane by cc from Hansraj hs to Bharampal Singh hs, Shukla hs to Satpal Singh hs and Satpal hs to Sateesh hs in Village Rithala in C-22/RZ | 277000 | 460/13.10.08/EE(M)-IV | M/s Ishwar Singh | 24.10.08 | 15.01.09 | 274521 | Work Completed
42 | 2008-09-16 | 24.07.08 | Dev of drain and C/O berms from Supplementry drain to kasra no.1108/h.no.27/2 in Village Rithala in C-22/RZ | 479000
43 | 2008-09-16 | 24.07.08 | C/O drain from PWD road to gali no.18 infront of Hero honda Showroom in Village Rithala in C-22/RZ | 484900
44 | 2008-09-16 | 24.07.08 | C/O lane by cc drainage system from main Rithala road to Baba Begraj hs in Village Rithala in C-22/RZ | 320000 | 457/13.10.08/E(M)-IV | M/s Ram Swaroop | 23.10.08 | 16.01.09 | 319314 | Work Completed
45 | 2008-09-16 | 24.07.08 | Covering of drain from gali no.15 to gali no.18 in Village Rithala in C-22/RZ | 304900 | 666/26.02.09/EE(M)-IV | M/s Shiv Shanker Gupta | 16.03.09 | 30.04.09 | 223245 | Work Completed
46 | 2008-09-22 | 19.09.08 | C/o lane by RMC from outer Phirni to jai Prakash house in village Rithala in C-22/RZ | 451150
47 | 2008-09-22 | 19.09.08 | C/o lane by RMC from outer Phirni to Hukam singh house in village Rithala in C-22/RZ | 451400 | 456/13.10.08/EE(M)-IV | M/s Ram Swaroop | 23.10.08 | 17.01.09 | 451400 | Work Completed
48 | 2008-09-22 | 19.09.08 | C/o lane by RMC from Suresh house to Kali Ram MAster house along nallah in village Rithala in C-22/RZ | 495610 | 469/13.10.08/EE(M)-IV | M/s JMD Const Co. | 03.11.08 | 25.03.09 | 495610 | Work Completed
|  |  |  | 23019390 |  |  |  |  | 14439818