## AC-11
S.no. | Date of booking | Date of consent | Name of wrok (AC-11) | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-09-03 | 2008-08-09 | P/F of steel benches for various park in Nangal Raya in C-110/WZ | 484700 | 465/13.10.08/EE(M)-I | M/s Bajrang Engineers | 2008-10-29 | 2008-12-03 | 482221
2 | 2008-09-26 | 2008-09-15 | Pdg and fixing MS steel benches in satya niketan w.no.168/SZ | 198300 | 340/17.10.08/EE(M)-I | M/s Neel Const | 2008-11-25 | 2008-11-22 | 198300
680521

## AC-12
S.no. | Date of booking | Date of consent | Name of wrok (AC-12) | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-06-23 | 2008-05-21 | C/O drain and pdg RMC behind A-2 Mkt.(park side)along park opp.A-2/45 in A-2 Block Janakpuri C-117/WZ | 438927 | 280/14/04/08/EE(M)-III | M/s Manish Nayar | 2008-08-23 | 2008-12-30 | 433104 | Work Comp.
2 | 2008-06-23 | 2008-05-21 | Pdg RMC opp. Rich Harvest School park to 235,park to 230,and along Rich Harvest School A-1 Block Janakpuri WZ | 494125 | 305/14.08.08/EE(M)-III | M/s A. B builders | 2008-08-18 | 2008-11-06 | 492133 | Work Comp.
3 | 2008-06-23 | 2008-05-12 | Pdg RMC from h.no.188 to 200 in C-Block C-117/WZ | 439100 | 319/28.08.08/EE(M)-III | M/s Star Const | 2008-08-29 | P | 439100 | In Prog.
4 | 2008-06-23 | 2008-05-12 | Pdg RMC from h.no.60 to 76 in C-1 Block janakpuri C-117/WZ | 548900 | 319/28.08.08/EE(M)-III | M/s Star Const | 2008-08-29 | P | 522600 | In Prog.
5 | 2008-06-23 | 2008-05-12 | Pdg RMC from h.no.201 to 208 in C-1 Block janakpuri C-117/WZ | 557200 | 319/28.08.08/EE(M)-III | M/s Star Const | 2008-08-29 | P | 522600 | In Prog.
6 | 2008-06-23 | 2008-05-12 | Pdg RMC from h.no.152 to Hardwari lal pank and side in A-5A Block janakpuri C-117/WZ | 644400 | 319/28.08.08/EE(M)-III | M/s Star Const | 2008-08-29 | P | 606100 | In Prog.
7 | 2008-06-23 | 2008-05-12 | Pdg RMC from WZ-30 to WZ-24,WZ-24 to WZ-24A in Harijan Basti Aslapur, Janakpuri C-117/WZ | 684200 | 310/28.08.08/EE(M)-III | M/s Mahesh Const. | 2008-09-04 | P | 518912 | In Prog.
8 | 2008-06-23 | 2008-05-12 | Pdg RMC in becklane from h.no.1 to 15 in A-1 block in Janakpuri C-117/WZ | 696300 | 329/12.09.08/EE(M)-III | M/s Star Const | 2008-09-15 | P | 600351 | In Prog.
9 | 2008-06-23 | 2008-05-12 | Pdg RMC in becklane from h.no.15 to 61 in A-1 Block Janakpuri C-117/WZ | 696300 | 329/12.09.08/EE(M)-III | M/s Star Const | 2008-09-15 | P | 600351 | In Prog.
10 | 2008-06-23 | 2008-05-12 | Pdg RMC in becklane from h.no.110 to 128 in A-1 Block Janakpuri C-117/WZ | 696300 | 329/12.09.08/EE(M)-III | M/s Star Const | 2008-09-15 | P | 600351 | In Prog.
11 | 2008-06-23 | 2008-05-12 | Pdg RMC in frontlane from h.no.15 to 298 in A-1 Block Janakpuri C-117/WZ | 691400 | 318/28.08.08/EE(M)-III | M/s Star Const | 2008-09-04 | P | 627426 | In Prog.
12 | 2008-06-23 | 2008-05-12 | Pdg RMC in frontlane from h.no.283 to 277 in A-1 Block Janakpuri C-117/WZ | 694100 | 318/28.08.08/EE(M)-III | M/s Star Const | 2008-09-04 | P | 627426 | In Prog.
13 | 2008-06-23 | 2008-05-12 | Pdg RMC in from h.no.297 to 284(front side0 in A-1 Block Janakpuri C-117/WZ | 688700 | 318/28.08.08/EE(M)-III | M/s Star Const | 2008-09-04 | P | 627426 | In Prog.
14 | 2008-06-23 | 2008-06-06 | Defv of lane by pdg RMC and drain from A-69 to D-127 becklane in D-Block in East Uttam Ngr. in WZ | 448223 | 298/14.08.08/EE(M)-III | M/s Sahil builders | 2008-08-23 | 2008-12-15 | 442975 | Work Comp.
15 | 2008-06-23 | 2008-06-06 | Dev of lane by pdg RMC and drain from F-46 to F-43 in F-Block in Milap Ngr. C-119,WZ | 296121
16 | 2008-06-23 | 2008-06-06 | Dev of lane by pdg RMC and drain from B-13 to B-11 in B-Block in Milap Ngr. C-119,WZ | 295425 | 304/14.08.08/EE(M)-III | M/s Manish Nayar | 2008-08-14 | 2009-01-31 | 208850 | Work Comp.
17 | 2008-06-23 | 2008-06-06 | Dev of lane by RMC and drain from A-24 to A-18 becklane in A-Block East Uttam Ngr. C-119/WZ | 225273 | 324/12.09.08/EE(M)-III | M/s Balaji Const. | 2008-09-21 | 2009-04-02 | 224410 | Work Comp.
18 | 2008-06-23 | 2008-06-06 | Dev of lane by RMC and drain from D-13 to D-6 in D-Block East Uttam Ngr. Milap Ngr.in WZ. | 262428 | 291/14.08.08/EE(M)-III | M/s Prince Entp. | 2008-08-22 | 2008-12-30 | 149914 | Work Comp.
19 | 2008-06-23 | 2008-06-06 | Dev of lane by RMC and drain from A-51 to A-57 in A-Block East Uttam Ngr.in WZ. | 440474 | 289/14.08.08/EE(M)-III | M/s Mahesh Kumar Const. | 2008-08-22 | 2009-01-14 | 390432 | Work Comp.
20 | 2008-06-23 | 2008-06-06 | Dev of lane by RMC and drain from A-38 to A-50 (becklane) in A-Block East Uttam Ngr.in WZ. | 373914 | 270/14.08.08/EE(M)-III | M/s L.Gee Const. | 2008-08-16 | 2008-12-19 | 373246 | Work Comp.
21 | 2008-06-23 | 2008-06-06 | Dev of lane by RMC and drain from A-51 to A-57 becklane in A-Block East Uttam Ngr.in WZ. | 336759 | 292/14.08.08/EE(M)-III | M/s Jatin Jaggi | 2008-08-26 | P | 332759 | Work Comp.
22 | 2008-07-14 | 2008-06-30 | Dev of becklane from 1 to 26, 26 to 24 in C-4B block C-118 Janakpuri in WZ. | 499423 | 300/14.08.08/EE(M)-III | M/s Sahil builders | 2008-08-23 | 2008-11-29 | 499345 | Work Comp.
23 | 2008-07-14 | 2008-06-30 | Dev to pavment/road side berms from 20 to 8 and 26 in C-2D Block in C-118 in Janakpuri. | 475775 | 293/14.08.08/EE(M)-III | M/s Money Const. | 2008-08-23 | 2008-12-02 | 474799 | Work Comp.
24 | 2008-07-14 | 2008-06-30 | Dev to road side berms and pavment from 1 to 12, 70 to 72, 30 to 40 in C-4D C-117 in Janakpuri in WZ. | 499080 | 303/14.08.08/EE(M)-III | M/s Som Const. | 2308.08 | P | 447921 | In Prog.
25 | 2008-07-14 | 2008-06-30 | Dev of becklane from 93 to 94, 10 to 107 in C-4G block in Janakpuri in WZ. | 478308
26 | 2008-07-14 | 2008-06-30 | Dev of road side berms from main gate to h.no.10 and 18 to 95 in C-6A in C-118 Janakpuri in WZ. | 374900 | 275/14.08.08/EE(M)-III | M/s Ghan Shyam Dass | 2008-08-23 | 2008-11-17 | 373816 | Work Comp.
27 | 2008-07-14 | 2008-06-30 | Dev of pavment/road side berms from 26 to 36,21 to 25,37 to 45,46 to 50 in C-2D in C-118 in Janakpuri. | 429591
28 | 2008-07-14 | 2008-06-30 | Dev to becklane from 127 to 132,51 to 65 in C-6B block in C-118 WZ Janakpuri. | 302871
29 | 2008-07-14 | 2008-06-06 | P/F SFRC slab on drain from h.no.A-69 to D-127 becklane in East Uttam Ngr. and from B-24 to A-18 becklane in East Uttam Ngr. and from h.no.D-13 to D-6 in East Uttam Ngr. and from h.no.A-51 to A-57 in East Uttam Ngr. in C-119/WZ in Milap Ngr. WZ. | 346900 | 566/13.10.08/EE(M)-III | M/s Star Const | 2008-11-25 | 2008-12-05 | 199594 | Work Comp.
30 | 2008-07-14 | 2008-06-06 | P/F SFRC slab on drain from h.no.A-38 to A-50 becklane in East Uttam Ngr. and from 9A-51 to A-57 becklane in East Uttam Ngr. and from h.no.A-7,A-13 in East Uttam Ngr. and from G-111 to G-106 in G-Block Uttam Ngr. in C-119/WZ in Milap Ngr. WZ. | 358500 | 568/13.10.08/EE(M)-III | M/s Star Const | 2008-11-27 | 2008-10-12 | 199094 | Work Comp.
31 | 2008-07-14 | 2008-06-06 | P/F SFRC slab on drain from h.no.F-46 to F-43 in Milap Ngr.and from B-13 to B-11 in Milap Ngr.and from h.no.D-111 to D-115 in Uttam Ngr. and h.no.D-154 to D-170 in Uttam Ngr.and from A-79 to A-70 in Uttam Ngr. and from h.no.J-72 to J-96 in Uttam Ngr. in C-119/WZ in Milap Ngr. WZ. | 399000 | 565/13.10.08/EE(M)-III | M/s Amit Const | 2008-10-22 | 2008-06-10 | 233546 | Work Comp.
32 | 2008-07-14 | 2008-06-06 | Dev of lane by RMC of drain from h.no.J-72 to J-96 in J-Block Uttam Ngr. WZ | 282299 | 279/14.08.08/EE(M)-III | M/s Ashok Bansal | 2008-08-14 | 2008-10-20 | 282140 | Work Comp.
33 | 2008-07-14 | 2008-06-06 | Dev of lane by RMC of drain from h.no.A-79 to A-70 in A-Block Uttam Ngr. WZ | 276303 | 273/14.08.08/EE(M)-III | M/s Om Mark builders | 2008-08-23 | 2008-11-26 | 276303 | Work Comp.
34 | 2008-07-14 | 2008-06-06 | Dev of lane by RMC of drain from h.no.D-154 to D-170 in D-Block Uttam Ngr. WZ | 293780 | 274/14.08.08/EE(M)-III | M/s V.K. Sahni | 2008-08-23 | 2008-02-26 | 170807 | Work Comp.
35 | 2008-07-14 | 2008-06-06 | Dev of lane by RMC of drain from h.no.D-111 to D-15 in D-Block Uttam Ngr. WZ | 293780 | 296/14.08.08/EE(M)-III | M/s Bhutani Entp. | 2008-08-23 | 2009-01-07 | 293781 | Work Comp.
36 | 2008-07-14 | 2008-06-06 | Dev of lane by RMC of drain from h.no.G-111 to G-106 in G-Block Uttam Ngr. WZ | 282299 | 251/13.08.08/EE(M)-III | M/s Vijay Kumar jha | 2008-08-14 | 2008-12-08 | 276317 | Work Comp.
37 | 2008-07-18 | 2008-06-30 | Dev of open space on site of C-4E Mkt. opp. Govt. School in C-118 Janakpuri | 499000 | 302/14.08.08/EE(M)-III | M/s Prince Entp. | 2008-12-26 | 2009-06-20 | 498713 | Work Comp.
38 | 2008-07-23 | 2008-06-30 | Dev of different park of C-2 Block in C-118 Janakpuri WZ. | 421812
39 | 2008-07-23 | 2008-06-30 | Dev of road side berms from 1 to 46 and 27 to 325 in C-4B block C-118 Janakpuri WZ | 311705
40 | 2008-07-23 | 2008-06-06 | Dev of lane by RMC of drain from A-7 to A-13 in A-Block in East Uttam Ngr. | 336759 | 417/13.10.8/EE(M)-III | M/s Sahil builders | 2008-10-12 | 2009-03-24 | 336693 | Work Comp.
41 | 2008-07-23 | 2008-06-06 | Dev of drainage system from h.no.M-78 to h.no.12,13 in M-Block in Uttam Ngr. WZ | 441841 | 593/13.10.08/EE(M)-III | M/s Kriti Assos. | 2008-10-22 | 2009-01-17 | 441146 | Work Comp.
42 | 2008-07-25 | 2008-07-12 | C/O hut/Rain Sheleter in park opp h.no.67 in Narang Colony in C-117/WZ | 484000
43 | 2008-07-25 | 2008-07-12 | C/O hut/Rain Sheleter in park opp h.no.201 in A-2 Block Janakpuri in C-117/WZ | 484000 | 286/14.08.08/EE(M)-III | M/s Mahesh Const. | 2008-08-23 | 2009-06-06 | 382109 | Work Comp.
44 | 2008-08-01 | 2008-06-30 | Dev of open space infront of C-4E Mkt. on Ram Mandir marg in C-118 Janakpuri in C-118/WZ | 769000
45 | 2008-08-01 | 2008-06-30 | Dev of open space ground/space and Parking space in C-2C Block Pkt.2 Mkt. in C-118/in Janakpuri in WZ | 704100
46 | 2008-05-23 | 2008-05-21 | Pdg RMC from h.no.85 to 82,85 to 47,46 to 47,23to 15,64 to 59 in C-1A Block Janak Puri in w.no.117/WZ | 694300 | 313/28.08.08/EE(M)-III | M/s Star Const | 2008-09-04 | P | 625630 | In Prog.
47 | 2008-05-23 | 2008-05-21 | Pdg RMC from h.no.1 to 12 and along B/Wall from Pankha Road to Parking C-1A Block Janakpuri in w.no.117/WZ | 699700 | 313/28.08.08/EE(M)-III | M/s Star Const | 2008-09-04 | P | 625630 | In Prog.
48 | 2008-05-23 | 2008-05-21 | Pdg RMC from 115 to 111,111 to 104,103 to 96 and 94 to 80 in A-1B Block Janakpuri in w.no.117/WZ | 693300 | 320/10.09.08/EE(M)-III | M/s Star Const | 2008-09-05 | P | 651308 | In Prog.
49 | 2008-05-23 | 2008-05-21 | Pdg RMC from h.no.184 to 187,166 to 169,81 to 92,74 to 69,47 to 52 and oppsite 18A in A-5B and A-5C in Janakpuri w.no.117/WZ | 695900 | 320/10.09.08/EE(M)-III | M/s Star Const | 2008-09-05 | P | 651308 | In Prog.
50 | 2008-05-23 | 2008-05-21 | Pdg RMC from h.no.351 to 383 in A-5A Block in Janakpuri in w.no.117/WZ | 699700 | 320/10.09.08/EE(M)-III | M/s Star Const | 2008-09-05 | P | 651308 | In Prog.
51 | 2008-09-30 | 2008-09-12 | Const /imp of road side berms from 259 to 288, 203 to 230, 75 to 102 in C-4B block Janakpuri C-118 WZ | 499000 | 635/13.10.08/EE(M)-III | M/s Babbar Entp. | 2008-10-22 | P | 470511 | In Prog.
52 | 2008-09-30 | 2008-09-12 | Const/imp of road side berms from 308 to 202, 173 to 147, 27 to 326 in C-4B block Janakpuri in WZ | 499000 | 627/07.01.09/EE(M)-III | M/s Rohit Const. | 2008-10-22 | 2009-01-07 | 462323 | Work Comp.
53 | 2008-09-30 | 2008-09-12 | Cont/ Imp of road side berms from 16 to 25, 41 to 45, 30 to 40 in C-4 D block Janakpuri in w.no.118/WZ | 493000
54 | 2008-09-30 | 2008-09-12 | Pdg MS grill and tiles at intersaction of Janakpuri marg and Dabri road in w.no.118/Wz | 444800
55 | 2008-09-30 | 2008-09-12 | Pdg MS grill and tiles at intersaction of Janakpuri marg and b-2 marg opp. mahila college inw.no.118/Wz | 454000
56 | 2008-09-30 | 2008-09-12 | Const/Imp of back lane from 116 to 153 in C-4 F block janakpuri w.no.118/WZ | 672000 | 957/02.03.09/EE(M)-II | M/s Rohit Const. | 2009-03-02 | P | 670000 | In Prog.
57 | 2008-09-30 | 2008-09-12 | Const/imp of road side berms from 19 to 45, 9 to 79, 46 to 79 and 46 to 1 in c-6 b block in janakpuri in w.no.118/WZ | 499000 | 622/13.10.08/EE(M)-III | M/s Rohit Const. | 2008-10-22 | 2008-12-21 | 462453 | Work Comp.
58 | 2008-09-30 | 2008-09-12 | Const/imp of back lane from 19 to 25, in C-5 A block in janakpuri in w.no.118/WZ | 425000 | 630/13.10.08/EE(M)-III | M/s R.K. Entp. | 2008-10-12 | P | 410509 | In Prog.
59 | 2008-09-30 | 2008-09-12 | Const/imp of road side berms from 123 to 118 in C-4 E block in janakpuri in w.no.118/WZ | 499000
60 | 2008-09-30 | 2008-09-12 | Const/imp of park B/wall opp h.no. 329 in C-4 E block in janakpuri in w.no.118/WZ | 498000 | 121/13.10.08/EE(M)-III | M/s Babbar Entp. | 2008-10-22 | 2009-06-08 | 595955 | Work Comp.
61 | 2008-09-30 | 2008-09-12 | Const/imp of park B/wall opp h.no. 21, 68 and 130 in C-3 b block in janakpuri in w.no.118/WZ | 496000 | 620/13.10.08/EE(M)-III | M/s Babbar Entp. | 2009-10-26 | 2009-06-08 | 481139 | Work Comp.
62 | 2008-09-30 | 2008-09-12 | Const/imp of drainage system and road side berms from near 115 to 126, 120 to 192, 14 to 198 in C-6 B block in janakpuri in w.no.118/WZ | 451000 | 628/13.10.08/EE(M)-III | M/s Rohit Const. | 2008-10-22 | 2008-12-21 | 451000 | Work Comp.
63 | 2008-09-30 | 2008-09-12 | Const/imp of road side berms from infront of h.no. 330 to 340 in C-2 block in janakpuri in w.no.118/WZ | 320000 | 642/13.10.08/EE(M)-III | M/s Shri Sharma Const. | 2008-10-22 | 2009-01-21 | 299553 | Work Comp.
64 | 2008-09-30 | 2008-09-12 | Const/imp of lane and drainage system and road side berms from C-3 (SFS) 286 to 289 in janakpuri in w.no.118/WZ | 676900 | 645/13.10.08/EE(M)-III | M/s Shivam Const. | 2008-10-22 | 2009-02-21 | 576419 | Work Comp.
65 | 2008-09-30 | 2008-09-12 | Const/imp of drainage system and road side berms from 100 to 147 in C-3 block in janakpuri in w.no.118/WZ | 498000 | 644/13.10.08/EE(M)-III | M/s Shivam Const. | 2008-10-22 | P | 464923 | In Prog.
66 | 2008-10-03 | 2008-09-12 | Pdg RMC from Prof joginder singh marg to CSF office in janakpuri w.no.117 | 461000 | 536/13.10.08/EE(M)-III | M/s Metric Engineering | 2008-10-11 | 2008-12-20 | 461000 | Work Comp.
67 | 2008-10-03 | 2008-09-12 | Imp of road side berms and const of drain opp. Mandir in A-2 block and pdg interlocking tiles opp. Vardhman mkt. in Janakpuri in w.no.117/WZ | 244000 | 534/13.10.08/EE(M)-III | M/s Eagle Entp. | 2008-10-16 | 2009-01-16 | 243988 | Work Comp.
68 | 2008-10-03 | 2008-09-12 | Pdg RMC from WZ-22 to 10b to 10 to WZ-34 to chopal in village Asalatpur in Janakpuri w.no.117/Wz | 519000 | 531/13.10.08/EE(M)-III | M/s Star Const | 2008-10-22 | P | 515792 | In Prog.
69 | 2008-10-03 | 2008-09-12 | Pdg RMC from 80 foot ROW road to A-5A block Janakpuri w.no.117/Wz | 467000 | 539/13.10.08/EE(M)-III | M/s Shiv Kumar Gupta | 2008-10-22 | 2009-01-09 | 463519 | Work Comp.
70 | 2008-10-03 | 2008-09-12 | Imp of road side berms and const of drain park to h.no. 196 in A-3 block in janakpuri in w.no.117/WZ | 404200 | 527/13.10.08/EE(M)-III | M/s Pawan Kumar | 2008-10-22 | P | 361166 | In Prog.
71 | 2008-10-03 | 2008-09-12 | Imp to side berms and const of drain from h.no. 270 to 261 A-1 block in janakpuri w.no.117/WZ | 332000 | 529/13.10.08/EE(M)-III | M/s Pawan Kumar | 2008-10-22 | P | 297105 | In Prog.
72 | 2008-10-03 | 2008-09-12 | C/o drian from B-1 marg to A-5A Double storey block Janakpuri w.no.117/Wz | 508000 | 537/13.10.08/EE(M)-III | M/s Devender Kumar | 2008-10-21 | P | 504000 | In Prog.
73 | 2008-10-03 | 2008-09-12 | pdg RMC and const f drain in back lane from h.no. 114 to 126 in Chander nagar w.no.117/Wz | 570000 | 538/13.10.08/EE(M)-III | M/s Shiv Kumar Gupta | 2008-10-22 | P | 530102 | In Prog.
74 | 2008-10-03 | 2008-09-12 | C/o of drain from h.no.16 to gate no.2 in A-1 block janakpuri w.no. 117/Wz | 500000 | 532/13.10.08/EE(M)-III | M/s Star Const | 2008-10-22 | 2009-07-27 | 500000 | Work Comp.
75 | 2008-10-03 | 2008-09-12 | Imp to side berms and const of drain from mojor deepak tyagi marg to h.no. 270 in A-1 block Janakpuri wno. 117 WZ | 428000 | 528/13.10.08/EE(M)-III | M/s Pawan Kumar | 2008-10-16 | P | 377114 | In Prog.
76 | 2008-10-03 | 2008-09-12 | Pdg RMC opp. PNT block at B-1 marg in janakpuri w.no.117/Wz | 446000 | 530/13.10.08/EE(M)-III | M/s Star Const | 2008-10-15 | P | 443965 | In Prog.
77 | 2008-10-03 | 2008-09-12 | Imp to road by pdg RMC and drain from J-74 to J-77 in J block Uttam nagar w.no.119/Wz | 437000 | 576/13.10.08/EE(M)-III | M/s Rohit Const. | 2008-10-22 | 2008-12-21 | 374419 | Work Comp.
78 | 2008-10-03 | 2008-09-12 | Imp to road by pdg RMC and drain from E-1 to E-13 in E block Uttam nagar w.no. 119/Wz | 534000 | 569/13.10.08/EE(M)-III | M/s Rohit Const. | 2008-10-22 | 2008-12-21 | 493242 | Work Comp.
79 | 2008-10-03 | 2008-09-12 | Imp to road by pdg RMc and drain from h.no. RZ-39 to RZ-33 in South extn-I Uttam nagar w.no. 119/WZ | 466000
80 | 2008-10-03 | 2008-09-12 | Imp to road by pdg RMC and drain from J-74 to J-91 in J block Uttam nagar w.no.119/Wz | 436000 | 579/13.10.08/EE(M)-III | M/s Manheet Const Co. | 2008-10-23 | P | 399262 | In Prog.
81 | 2008-10-03 | 2008-09-12 | Imp to road by pdg RMc and drain from b-9 to B-20 gali no.34 in B block Uttam nagar w.no. 119/WZ | 352000 | 816/05.02.09/EE(M)-III | M/s Eagle Entp. | 2009-02-14 | P | 269037 | In Prog.
82 | 2008-10-03 | 2008-09-12 | Imp to road by pdg RMC and drain from b-8A to B-8B in B block in Uttam nagar w.no. 119/WZ | 300300 | 815/05.02.09/EE(M)-III | M/s Eagle Entp. | 2009-02-14 | P | 229111 | In Prog.
83 | 2008-10-03 | 2008-09-12 | Imp to road by pdg RMC and drain from A-86 to A-83 in A block Uttam nagar w.no. 119/WZ | 507800
84 | 2008-10-03 | 2008-09-12 | Imp to road by pdg RMC and drain from D-96 to D-101 in D block back lane Uttam nagar w.no. 119/WZ | 569000 | 570/13.10.08/EE(M)-III | M/s Rohit Const. | 2008-10-22 | P | 495312 | In Prog.
85 | 2008-10-03 | 2008-09-12 | Imp to road by pdg RMC and drain from Z-106 to Z-77, 78 in Z block Uttam nagar w.no. 119/WZ | 591000
86 | 2008-10-03 | 2008-09-12 | Imp to road by pdg RMC and drain from Z-111 to Z-96 in Z block Uttam nagar w.no. 119/WZ | 413000 | 574/13.10.08/EE(M)-III | M/s Nikhil Const. | 2008-10-22 | 2008-12-18 | 365946 | Work Comp.
87 | 2008-10-03 | 2008-09-12 | pdg RMC from WZ-44 to WZ-43, 66 to 70, 7 to 79 and opp 71 in village Possangipur in w.no. 117/WZ | 467000 | 692/02.12.08/EE(M)-III | M/s Shiv Kumar Gupta | 2008-12-11 | 2009-05-16 | 467000 | Work Comp.
88 | 2008-10-03 | 2008-09-12 | pdg RMC and const of SW drain from A-3/70 to 82 in A3 block janakpuri w.no.117 WZ | 699800
89 | 2008-10-03 | 2008-09-12 | Imp to road side berms and c/o drain from h.no. 188 to 196 in A3 block janakpuri w.no. 117 WZ | 500000
31067639

## AC-13
S.no. | Date of booking | Date of consent | Name of Work (AC-13) | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-05-27 | 2008-05-26 | P/O lighting arrangement at different main chowk and main points of assambly C-no.13 under WZ | 598801 | 185/10.10.08/EE(E)-III | M/s Perfect Electrical works | 2008-10-15 | 2008-12-15 | 587063 | Work Comp.
2 | 2008-06-11 | 2008-06-04 | C/O yoga hall in 654 MIG Maya Puri in C-111/WZ | 1066800
3 | 2008-06-18 | 2008-05-04 | Dev of road from Mangal Pandey road to CB-18 along Deen Dayal Hospital in Hari Ngr. C-111/WZ | 1174900 | 425/30.09.08/EE(M)-I | M/s Cheena builders | 2008-10-16 | P | 1005131 | In Prog.
4 | 2008-06-23 | 2008-05-06 | Prov. of 1X400 watt flood light arrangement in the Mini Stadium Hari Ngr. under WZ | 258610 | 144/08.09.08/EE(E)-III | M/s Aman Elec. Const. | 2008-09-15 | 2008-10-25 | 253362 | Work Comp.
5 | 2008-06-23 | 2008-05-06 | Prov. of Cascade Fountain in 17 Block Subhash Ngr. in w.no.112/WZ | 180422
6 | 2008-06-23 | 2008-05-05 | Prov.of post top lantern fitting from Cambridge School to Arya Samaj Mandir on Arya Samaj road Subhash Ngr. in w.no.112/WZ | 475415
7 | 2008-06-23 | 2008-05-16 | Prov. of post top, lantern fitting from 4 block chowk to T-point 3 Block Arya Samaj road Subhash Ngr. in w.no.112/WZ | 555581
8 | 2008-06-23 | 2008-05-26 | Dev of road by pdg drainage and RMC from h.no.B-217 to B-225 in BE-block in Hari Ngr. C-111/WZ | 498633 | 85/24.07.08/EE(M)-I | M/s Sahil builders | 2008-08-02 | 2009-02-24 | 496142 | Work Comp.
9 | 2008-06-23 | 2008-05-26 | Dev of lane by RMC from h.no.M-68 to M-61,WZ-173 to A-247 and WZ-176 to M-39 in M-block Hari Ngr. WZ | 452818 | 77/24.07.09/EE(M)-I | M/s Mahesh Kumar Const. | 2008-11-06 | 2009-06-03 | 449483 | Work Comp.
10 | 2008-06-23 | 2008-05-26 | Dev of lane by RMC from h.no.M-23 to M-30 and 15 M-15 to M-22 in M-Block Hari Ngr. WZ | 344305 | 88/24.07.09/EE(M)-I | M/s Om Mark builders | 2008-12-19 | 2009-02-25 | 441190 | Work Comp.
11 | 2008-06-23 | 2008-05-26 | Dev of road by pdg RMC and drainage system from road.no.32 to DE-216 in BE-block in Hari Ngr.C-111/WZ | 499376 | 117/25.07.08/EE(M)-I | M/s Praveen Kumar Const. | 2008-08-01 | 2009-01-27 | 497400 | Work Comp.
12 | 2008-06-23 | 2008-05-26 | Dev of road by pdg RMC and drainage system from B-228 to B-224 in BE-block in Hari Ngr.C-111/WZ | 368694 | 82/24.07.09/EE(M)-I | M/s Ghan Shyam Dass | 2008-07-30 | P | 358343 | In Prog.
13 | 2008-06-23 | 2008-05-26 | Dev to lane by RMC from h.no.M-46 to M-60 in M-Block in Hari Ngr.C-111/WZ | 428035 | 94/24.07.09/EE(M)-I | M/s Arjun Entp. | 2008-07-28 | P | 287981 | In Prog.
14 | 2008-06-23 | 2008-05-26 | Dev to lane by RMC from h.no.C-157 to CB-17 in C-Block in Hari Ngr.C-111/WZ | 364869 | 86/24.07.09/EE(M)-I | M/s Som Const. | 2008-07-28 | P | 239880 | In Prog.
15 | 2008-06-23 | 2008-05-26 | Dev to lane by RMC from h.no.BE-260 to BE-249,BE-40 to BE-64 and BE-197 to Be-191 in BE-Block in Hari Ngr.C-111/WZ | 464021 | 87/24.07.09/EE(M)-I | M/s Y.K. Saini | 2008-07-28 | P | 434169 | In Prog.
16 | 2008-07-04 | 2008-05-26 | Dev to lane by RMC from h.no.C-175 to C-183 in C-Block in Hari Ngr. C-111/WZ | 414920 | 289/18.08.08/EE(M)-I | M/s M.P. Assos | 2008-08-27 | 2008-01-23 | 414900 | Work Comp.
17 | 2008-07-09 | 2008-05-19 | Dev of road by RMC from h.no.MS 10 to 470/JI in MS Block C-110/WZ | 498486 | 69/22.07.08/EE(M)-I | M/s Chittarmal | 2008-07-23 | 2008-12-19 | 498400 | Work Comp.
18 | 2008-07-09 | 2008-05-19 | Dev of road by RMC from h.no.DB-68 to DB-74 in DB Block in Hari Ngr. C-110/WZ | 498326 | 68/22.07.08/EE(M)-I | M/s Mukesh Kumar Const | 2008-10-14 | 2009-07-03 | 498330 | Work Comp.
19 | 2008-07-09 | 2008-05-19 | Dev of road by RMC from DB-82 to DB-87 in DB-Block Hari Ngr. C-110/WZ | 499206 | 67/22.07.08/EE(M)-I | M/s Rohit Const | 2008-07-31 | 2008-10-30 | 499181 | Work Comp.
20 | 2008-07-17 | 2008-06-30 | C/O B/Wall and pdg Senetery fitting to Library at Hari Enclave in C-111/WZ | 426966 | 290/18.08.08/EE(M)-I | M/s Y.K. Saini | 2008-08-18 | 2009-02-12 | 371062 | Work Comp.
21 | 2008-07-17 | 2008-05-06 | Dev of lane by RMC from h.no.C-195 to C-185 in C-Block Hari Ngr. C-111/WZ | 491293 | 288/18.08.08/EE(M)-I | M/s Prince Entp. | 2008-08-27 | 2009-03-30 | 483268 | Work Comp.
22 | 2008-07-31 | 2008-06-11 | C/O main gate at Mini Stadium Shyam Vatika in Hari Ngr. in C-111/WZ | 230000 | 354/28.08.08/EE(M)-I | M/s Rajveer Gupta | 2008-08-28 | 2008-09-26 | 199892 | Work Comp.
23 | 2008-07-31 | 2008-06-11 | Face lifiting og wall at VIP Plateform at Mini Stadium Shyam Vatika Hari Ngr. C-111/WZ | 177000 | 754/11.02.09/EE(M)-I | M/s Rajveer Gupta | 2009-02-11 | 2009-02-26 | 79237 | Work Comp.
24 | 2008-07-31 | 2008-06-11 | Pdg False Ceiling at VIP Plateform at Mini Stadium Shyam Vatika Hari Ngr. C-111/WZ | 343800 | 579/17.12.08/EE(M)-I | M/s Pankaj builders | 2008-12-17 | P | 176792 | In Prog.
25 | 2008-08-29 | 2008-06-30 | Pdg Drainage flooring and Wall Lining at Mini Stadium Shyam Vatika in Hari Ngr.in C-111/WZ | 496000 | 401/19.09.08/EE(M)-I | M/s Vashisth Const | 2008-09-19 | 2008-10-27 | 452305 | Work Comp.
26 | 2008-09-30 | 2008-09-05 | Pdg openable gate at Mini stadium Shyam Vatika in Hari Nagar C-111 in WZ | 188200 | 684/31.01.09/EE(M)-I | M/s Bajrang Engg. | 2009-01-31 | P | 146412 | In Prog.
27 | 2008-10-10 | 2008-05-19 | Pdg RMC from h.no. 52 to park in CD blocck Hari Nagar IN C-109/WZ | 578800 | 810/04.02.09/EE(M)-III | M/s L. Gee Const. | 2009-02-05 | P | 573704 | In Prog.
28 | 2008-10-10 | 2008-09-20 | C/o drainage & foothpath from h.no. 8A to B-65 in Asha park w.no.109/WZ | 529000
29 | 2008-10-10 | 2008-09-20 | C/o drainage & foothpath from h.no. 9A to B-66 in Asha park in C-109/WZ | 501600
30 | 2008-10-10 | 2008-09-20 | C/o designer gate in park opp. CD-42 in Hari nagar C-109/WZ | 284100 | 842/10.02.09/EE(M)-III | M/s R.N. builders | 2009-02-19 | P | 277527 | In Prog.
31 | 2008-10-10 | 2008-09-20 | C/o drain from K block Fateh nagar to Ashok nagar road at Suhag Banquet road in C-109/WZ | 697900
32 | 2008-10-10 | 2008-09-20 | C/o drain and RMC from CD-42 to Major Rajeev Lal road in CD block Hari nagar in C-109/WZ | 511200 | 813/04.02.09/EE(M)-I | M/s Bansal Const. | 2009-02-05 | 2009-04-12 | 498812 | Work Comp.
33 | 2008-10-10 | 2008-09-05 | P/O Electri installed and post top latern fittings in mini stadoum in Hari nagar w.no.109/WZ | 411000 | 380/04.02.09/EE(E)-III | M/s Aman Elec. Const. | 2009-02-10 | P | 245838 | In Prog.
34 | 2008-10-10 | 2008-09-05 | P/o SHM light in mini Stadium Hari Nagar in w.no.111/WZ | 483278
35 | 2008-07-31 | 2008-06-11 | Dev of roof of VIP platform at mini stadium Shyam Vatika Hari nagar C-111/WZ | 78293 | 581/17.12.08/EE(M)-I | M/s Pankaj builders | 2008-12-17 | 2009-01-18 | 68428 | Work Comp.
10534232

## AC-14
S.no. | Date of booking | Date of consent | Name of work (AC-14) | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 02.5.008 | 2008-03-04 | Prov. of posttop lantern light fittings in park Vikas Puri area WZ | 569427 | 99/14.08.08/EE(E)-III | M/s Dev Engineers | 2008-08-15 | 2008-09-20 | 559256 | Work Comp.
2 | 2008-05-02 | 2008-03-04 | Prov. of posttop lantern light fittings in park between Kangra Niketan and Vikas Kunj w.no.113/WZ | 281000 | 112/29.08.08/EE(E)-III | M/s Paras Const Co. | 2008-09-01 | 2008-09-29 | 280701 | Work Comp.
3 | 2008-06-06 | 2008-05-26 | Prov. of lighting arrangement at tilak Ngr. area w.no.113/WZ | 399658 | 190/16.10.08/EE(E)-III | M/s Neeraj Entp. | 2008-10-16 | 2008-11-01 | 361477 | Work Comp.
4 | 2008-06-06 | 2008-05-26 | Prov. of street light with pole at tilak Ngr. area w.no.113/WZ | 170000 | 79/25.07.09/EE(E)-III | M/s Ram Gopal & Co. | 2008-08-01 | 2008-09-01 | 162779 | Work Comp.
5 | 2008-06-18 | 2008-04-25 | C/O B/S/D in lane from BA-23 to BA-253 in Tagore Garden in AC-14/WZ | 309108 | 204/04.07.08/EE(M)-III | M/s Vashishth Const. | 2008-07-14 | P | 275178 | In Prog.
6 | 2008-06-18 | 2008-04-25 | C/O B/R/S berms of lane of BA block Tagore garden from BA-328 to BA-340 by interlocking tiles on both sides in Tagore Garden in AC/WZ | 350440 | 205/07.07.08/EE(M)-III | M/s Ravinder Const. | 2008-07-16 | P | 332132 | In Prog.
7 | 2008-06-18 | 2008-04-25 | C/O B/S/D in lane from BA-292 to BA-306 in Tagore Garden in AC/WZ | 309108 | 203/04.07.08/EE(M)-III | M/s Vashishth Const. | 2008-07-14 | P | 276402 | In Prog.
8 | 2008-06-18 | 2008-04-25 | C/O B/S/D in lane from BA-275 to BA-289 in Tagore Garden in AC/WZ | 311518
9 | 2008-06-18 | 2008-04-25 | C/O B/S/D in lane from BA-328 to BA-340 in Tagore Garden in AC/WZ | 313892
10 | 2008-06-18 | 2008-05-28 | C/O road berms by prov. tiles infront of KG-III/1 to KG-III/33 in Vikas Puri AC-14/WZ | 297260 | 223/13.08.08/EE(M)-III | M/s A.K. Entp. | 2008-08-14 | 2008-10-22 | 295901 | Work Comp.
11 | 2008-06-20 | 2008-05-28 | C/O lane by pdg RMC opp. A-24 to A-25 along B/Wall of MCD store and BSES office in Sankar Garden AC-14/WZ | 199600 | 258/13.08.08/EE(M)-III | M/s Ashok Bansal | 2008-08-23 | 2008-11-04 | 198404 | Work Comp.
12 | 2008-06-20 | 2008-05-28 | C/O lane by pdg RMC from 16/18 to 16/25 in Tilak Ngr.AC-14/WZ | 397760 | 256/13.08.08/EE(M)-III | M/s M.P. Assos. | 2008-08-14 | 2008-10-11 | 392187 | Work Comp.
13 | 2008-06-20 | 2008-05-28 | C/O lane by pdg rmc in gali no. 2 and 3 New Mahabeer Ngr.in AC/WZ | 498346 | 235/13.08.08/EE(M)-III | M/s Arjun Entp. | 2008-08-22 | 2008-12-05 | 497522 | Work Comp.
14 | 2008-06-20 | 2008-05-28 | C/O becklane by pdg rmc from 13/1 to 13/5 Tilak Ngr.in AC-14/WZ | 200000 | 240/13.08.08/EE(M)-III | M/s Om Mark builders | 2008-08-23 | 2008-10-16 | 200000 | Work Comp.
15 | 2008-06-20 | 2008-05-28 | C/O becklane by pdg rmc from 13/3 to 13/23 Tilak Ngr.in AC-14/WZ | 496963 | 229/13.08.08/EE(M)-III | M/s Neel Traders | 2008-08-22 | 2008-11-14 | 493365 | Work Comp.
16 | 2008-06-20 | 2008-05-28 | C/O lane by pdg RMC from h.no.1 to h.no.20 and 31 to 50 in Tihar Camp Ajay Enclave Ext. AC-14/WZ | 398929 | 228/13.08.08/EE(M)-III | M/s Neel Traders | 2008-08-13 | 2008-08-11 | 397790 | Work Comp.
17 | 2008-06-20 | 2008-05-28 | C/O lane by pdg RMC from D-23 to D-40 gali no.4 Krishna Park AC-14/WZ | 200000 | 263/13.08.08/EE(M)-III | M/s Om Mark builders | 2008-08-23 | 2008-10-22 | 199498 | Work Comp.
18 | 2008-06-20 | 2008-05-28 | C/O both side road side berms on service lane by pdg interlocking tile fron 1/6 Tilak Ngr. near Vishal Mega Mart to Tilak Ngr. Metro Station near shop no. 36 New Mkt. Tilak Ngr. in AC-14/WZ | 499365 | 232/1308.08/EE(M)-III | M/s Mahesh Const. | 2008-08-13 | 2009-01-31 | 499365 | Work Comp.
19 | 2008-06-20 | 2008-05-28 | C/O lane by pdg RMC from S-3/76 to S-3/69 Old Mahabeer Ngr. AC-14/WZ | 200000 | 248/13.08.08/EE(M)-III | M/s A.K. Entp. | 2008-08-22 | p | 193207 | In Prog.
20 | 2008-06-20 | 2008-05-28 | C/O lane by pdg RMC from S-3/62 to S-3/68 Old Mahabeer Ngr. AC-14/WZ | 200000
21 | 2008-06-20 | 2008-05-28 | C/O lane by pdg RMC from S-3/55 to D-54 Old Mahabeer Ngr. AC-14/WZ | 198582 | 264/13.08.08/EE(M)-III | M/s A.B. builders | 2008-08-22 | 2008-11-28 | 198425 | Work Comp.
22 | 2008-06-20 | 2008-05-28 | C/O lane by pdg RMC from A-104 to A-99 and A-105 to A-111 Ganesh Ngr. AC-14/WZ | 399494 | 231/13.08.8/EE(M)-III | M/s A.B. builders | 2008-08-22 | 2008-11-26 | 395285 | Work Comp.
23 | 2008-06-20 | 2008-05-28 | C/O lane by pdg RMC in gali no.20 opp. W-20/1 to Iqbal Singh Chakki Wala in New Mahabeer Ngr. AC-14/WZ | 399611 | 265/13.08.08/EE(M)-III | M/s L. Gee Const Co. | 2008-10-23 | 2008-12-20 | 395380 | Work Comp.
24 | 2008-06-20 | 2008-05-28 | C/O lane by pdg RMC from 17/12 to 17/16 Tilak Ngr. AC-14/WZ | 200000 | 252/13.08.08/EE(M)-III | M/s Hankhelen Singh | 2008-08-25 | 2008-10-22 | 200000 | Work Comp.
25 | 2008-06-20 | 2008-05-28 | C/O road by MP from A-1A to BN-39B,B-25A to A-18A in DDA flat opp. 12-Block Tilak Ngr. AC-14/WZ | 199823 | 242/13.08.08/EE(M)-III | M/s Umda Const. | 2008-08-20 | 2009-01-28 | 199261 | Work Comp.
26 | 2008-06-20 | 2008-05-25 | C/O service lane along Najafgarh road by pdg RMC from Janakpuri East Metro Station to B-120 Ganesh Ngr. AC-14/WZ | 499553 | 227/13.08.08/EE(M)-III | M/s Sahil builders | 2008-08-22 | 2008-12-30 | 498581 | Work Comp.
27 | 2008-06-20 | 2008-06-01 | C/O rain shelter in AC-Block park Tagore Garden C-105/WZ | 376400 | 585/17.12.08/EE(M)-III | M/s Mahesh Const. | 2008-12-16 | 2009-03-07 | 374186 | Work Comp.
28 | 2008-06-20 | 2008-06-01 | C/O rain shelter in AD-Block park Tagore Garden C-105/WZ | 376400
29 | 2008-06-20 | .1.06.08 | C/O designer gate in AC-b lock park Tegore Garden in C-105/WZ | 224000 | 540/13.10.08/EE(M)-III | M/s Mukesh Const Co. | 2008-10-22 | 2009-04-04 | 220402 | Work Comp.
30 | 2008-06-20 | 2008-06-01 | C/O designer gate in AD-block park opp.AD-77 Tegore Garden in C-105/WZ | 312400
31 | 2008-07-09 | 2008-06-01 | C/O designer gate in AD-block on main road side near Urinal Tegore Garden in C-105/WZ | 312400
32 | 2008-07-25 | 2008-05-28 | C/O park B/Wall with both side marble wash plaster on East side B/Wall of Distt. park,New Krishna park adj to Vikas kunj Society in AC-14/WZ | 473500 | 375/01.10.08/EE(M)-III | M/s Manish Const Co. | 2008-10-11 | 2008-12-10 | 399353 | Work Comp.
33 | 2008-07-25 | 2008-05-28 | C/O B/Wall with railing in ground from 20B/11 to 20B/22 in Tilak Ngr.AC-14/WZ | 300000 | 379/01.10.08/EE(M)-III | M/s Om Mark builders | 2008-10-10 | 2009-01-07 | 266358 | Work Comp.
34 | 2507.08 | 2008-05-28 | C/O 50 no.cc benches for verious park of ward no.C-113,C-114,in AC-14/WZ | 284600 | 482/13.10.08/EE(M)-III | M/s Om Mark builders | 2009-10-22 | 2009-01-21 | 228881 | Work Comp.
35 | 2008-07-25 | 2008-05-28 | C/O 50 no. p.c.c.benches for verious park of ward C-105,C-106 in AC-14/wz | 284600 | 481/13.10.08/EE(M)-III | M/s Om Mark builders | 2008-10-22 | 2009-01-21 | 227759 | Work Comp.
36 | 2008-07-25 | 2008-05-28 | C/O 2 no. Ornamental gates in Green Belt Park out side Shanker Garden on Nej road in AC-14/WZ | 500000 | 469/13.10.08/EE(M)-III | M/s Gaurav Const Co.-II | 2008-10-22 | 2009-03-06 | 417129 | Work Comp.
37 | 2008-07-25 | 2008-05-28 | C/O Ornamental gates in Park infrontof F-215 Raghubeer Ngr. in AC-14/WZ | 300000
38 | 2008-07-25 | 2008-05-28 | C/O Ornamental gates in Park infront of KG-II/190 Vikaspuri in AC-14/WZ | 300000 | 370/01.10.08/EE(M)-III | M/s Gaurav Const Co.-II | 10.10..08 | 2009-01-09 | 255953 | Work Comp.
39 | 2008-07-25 | 2008-05-28 | C/O Ornamental hut in Park near Ramlila Ground opp. MCD Staff Qtr. in 32 Block in Ashok Ngr. in AC-14/WZ | 388000
40 | 2008-07-25 | 2008-07-07 | C/O 2 no.Ornamental gate each in Park near Sanskrit Mahavidhyalya and TC-1150 in T.C. Camp Raghubeer Ngr.in AC-14/WZ | 374200
41 | 2008-07-25 | 2008-07-09 | C/O 2 no.Ornamental gates in 608 Qtr. in Tegore Garden Ext.in AC-14/WZ | 374200
42 | 2008-07-29 | 2008-07-28 | P/O Tubewell in park infront of 1/1 Mall Road in Tilak Ngr. under AC-14/WZ | 165387 | 385/06.08.08/EE(E)-Hort. | M/s Seth Const. | 2008-08-07 | 2008-08-28 | 164431 | Work Comp.
43 | 2008-08-11 | 2008-05-28 | C/O Wall with ornamental grill on Island on Ngj Road at Subhash Ngr. Red Light near Subhash Ngr. drain in Ajay Enclave in AC-14/WZ | 276600
44 | 2008-08-11 | 2008-05-28 | C/O Chowk behind Bata Showroom and 5/6 Block D.S.Tilak Ngr. in AC-14/WZ | 499818 | 852/22.09.08/EE(M)-I | M/s Honey Const. | 2008-09-23 | 2008-11-15 | 499109 | Work Comp.
45 | 2008-08-11 | 2008-05-28 | C/O service lane along N.G. road by pdg RMC from K-10 New Mahavir Ngr. to M.I. New Mahavir Ngr. Mandir on main Ngj Road opp.New Mahavir Ngr. red light in AC-14/WZ | 499600 | 416/03.10.08/EE(E)-III | M/s Shree Ji Const Co. | 2008-10-04 | 2008-11-10 | 484581 | Work Comp.
46 | 2008-08-11 | 2008-07-09 | C/O backlane by pdg RMC from h.no. WZ-29 to WZ-100 in Sant Ngr. Extn. in AC-14/WZ | 301800 | 374/11.10.08/EE(M)-I | M/s Manjeet Const Co. | 2008-10-06 | 2008-12-01 | 363441 | Work Comp.
47 | 2008-08-11 | 2008-07-09 | C/O lane by pdg RMC from 8/9 to 8/30,8/31 to 8/33 in Tilak Ngr. in AC-14/WZ | 350000 | 419/03.10.08/EE(M)-I | M/s Manjeet Const Co. | 2008-10-03 | 2009-03-12 | 318988 | Work Comp.
48 | 2008-08-11 | 2008-07-09 | C/O lane by pdg RMC from 24/1 to 24/6 in Ashok Vihar in AC-14/WZ | 350000 | 487/13.10.08/EE(M)-I | M/s Sabarwal Const Co. | 2008-10-13 | 2008-12-15 | 350000 | Work Comp.
49 | 2008-08-14 | 2008-07-09 | C/O road by pdg RMC from Harijan Colony(80yds)culvert over Subhash Ngr.drain near WZ-179 Sant Ngr. to WZ-14 Sant Ngr.Extn. in AC-14/WZ | 495000 | 489/13.10.08/EE(M)-I | M/s Shree Ji Const Co. | 2008-10-14 | 2008-11-21 | 487575 | Work Comp.
50 | 2008-08-14 | 2008-07-09 | C/O lane by pdg RMC from 20B/96 to 20B/105 in Tilak Ngr. in AC-14/WZ | 400000 | 484/13.10.08/EE(M)-I | M/s Maa Durga Const Co. | 2008-10-15 | 2008-01-29 | 394222 | Work Comp.
51 | 2008-08-19 | .07.07.08 | C/O Toilet Block outside in Ganesh Ngr. Mkt. on N.G.road near Ganesh Ngr. Subway in C-114/WZ | 179300
52 | 2008-08-19 | 2008-08-18 | C/O Rawndom Stone Masonary Wall with grills along Subhash Ngr. drain in 134 Allternative plot Chaukhandi in AC-14/WZ | 463300 | 610/13.10.08/EE(M)-I | M/s Rakesh Entp. | 2008-10-13 | 2008-12-21 | 432038 | Work Comp.
53 | 2008-06-20 | 2008-05-25 | C/O road by MP from A-18A to B-39A in DDA Flat opp.12-Block Tilak Ngr. AC-14/WZ | 199823
54 | 2008-06-20 | 2008-05-25 | C/O Service lane along Neg road by pdg RMC from Ganesh Ngr.Subway to WZ-1 Ganesh Ngr. in AC-14/WZ | 499877 | 222/13.08.08/EE(M)-III | M/s Parveen Kumar Const. | 2008-08-18 | 2008-11-07 | 499877 | Work Comp.
55 | 2008-06-20 | 2008-05-25 | C/O road side berms by pdg interlocking tiles from C-15 to Mother Dairy Both in New Krishna Park in AC-14/WZ | 199800 | 325/12.09.08/EE(M)-III | M/s Ghan Shyam Dass | 2008-09-12 | 2008-11-19 | 196987 | Work Comp.
56 | 2008-06-20 | 2008-05-25 | C/O lane by pdg RMC from shop no.48 to 5/57 D.S.Tilak Ngr. AC-14/WZ | 200000 | 339/13.08.08/EE(M)-III | M/s M.P. Assos. | 2008-08-22 | 2008-10-21 | 199205 | Work Comp.
57 | 2008-06-20 | 2008-05-25 | C/O Chowk by pdg RMC from 20A-27 to 20A/37 in Tilak Ngr.in AC-14/WZ | 396823 | 225/13.08.08/EE(M)-III | M/s Gupta Engg. Cost. | 2008-08-14 | 2008-10-03 | 396791 | Work Comp.
58 | 2008-08-29 | 2008-08-24 | C/O lane by pdg RMC from 20A/11 to 20A/17 Tilak Ngr.in AC-14/WZ | 199000 | 486/13.10.08/EE(M)-III | M/s Maa Durga Const Co. | 2008-10-15 | 2008-11-24 | 183872 | Work Comp.
59 | 2008-08-29 | 2008-05-28 | C/O walkway in park behind B-52 Shanker Garden in AC-14/WZ | 198935 | 448/13.10.08/EE(M)-III | M/s Devender Kumar | 2008-10-22 | 2009-01-14 | 198430 | Work Comp.
60 | 2008-08-29 | 2008-08-29 | C/O lane by pdg RMC from 11/48 to 11/53 Tilak Ngr.in AC-14/WZ | 198400 | 485/13.10.08/EE(M)-III | M/s Maa Durga Const Co. | 2008-10-20 | 2008-11-25 | 193299 | Work Comp.
61 | 2008-09-03 | 2008-08-24 | C/O backlane by pdg RMC from 22/1 to 22/7 and 22/35 to 22/38 in Tilak Ngr.in AC-14/WZ | 375000 | 483/13.10.08/EE(M)-III | M/s Shree Maa Durga Const | 2008-12-22 | 2008-12-11 | 350613 | Work Comp.
62 | 2008-09-03 | 2008-07-09 | C/O Ornamental Hut in A-Block Park opp.A-79 Shanker Garden in AC-14/WZ | 350000 | 490/13.10.08/EE(M)-III | M/s Manish Const | 2008-10-13 | 2008-01-17 | 349254 | Work Comp.
63 | 2008-09-03 | 2008-07-09 | C/o lane by pdg RMC infront of lane WZ-29 to WZ-44 Sant nagar Extn. Ac-14/WZ | 339000 | 762/19.12.08 | M/s Shiv Kumar gupta | 2008-12-28 | 2009-04-15 | 335922 | Work Comp.
|  |  |  | 20818513 |  |  |  |  | 16290752

## AC-15
S.no. | Date of booking | Date of consent | Name of work (AC-15) | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks | ac-15
1 | 2008-05-23 | 2008-05-12 | Prov. of Tubewell in park at C-Block Raghubir Ngr.(25Gaj)under WZ | 198000 | 368/06.08.08/EE(E)-III(Hort.) | M/s Modern Elect. | 2008-09-12 | 2008-12-10 | 197965 | Work Comp.
2 | 2008-05-30 | 2008-05-22 | Prov.of post top lantern fitting in park of F-9 Block Rajori Garden in C-105 under WZ | 399852 | 66/11.07.08/EE(E)-III | M/s S. Gee Entp. | 2008-07-18 | 2008-08-19 | 387698 | Work Comp.
3 | 2008-05-30 | 2008-04-11 | Prov.of post top lantern fitting in park at RED Appartment infrontof h.no.176-A, Rajori Garden in C-105 under WZ | 228809 | 98/12.08.08/EE(E)-III | M/s Ankur Entp. | 2008-08-18 | 2008-10-16 | 224978 | Work Comp.
4 | 2008-05-30 | 2008-05-22 | Prov.of post top lantern fitting in park infrontof Sanatan Dharam Mandir J-3 and G-19 Rajori Garden in C-105 under WZ | 339950 | 97/12.08.08/EE(E)-III | M/s Rai Elect. | 2008-08-18 | 2008-10-17 | 326146 | Work Comp.
5 | 2008-06-23 | 2008-05-23 | Prov.of post top lantern fitting arrangement in Chameli park Raghubir Ngr.under WZ | 563107 | 127/EE(E)-III | M/s Super Shine Assos. | 2008-09-13 | 2008-09-12 | 549484 | Work Comp.
6 | 2008-07-23 | 2008-05-09 | Prov.of lighting fitting arrangement in park of J-3 Rajori Garden in C-105 under WZ | 109635
7 | 2008-07-31 | 2008-05-19 | Pdg cc pav. from Ghodi Wala Mandir to Subhash Toilet and K-60 to K-11 in Raghubir Ngr. at C-101/WZ | 199394 | 371/28.08.08/EE(M)-I | M/s Parveen Kumar Garg | 2008-09-05 | 2008-11-03 | 197556 | Work Comp.
8 | 2008-07-31 | 2008-05-19 | Pdg cc pav. from K-101 to K-372 in Raghubir Ngr. at C-102/WZ | 197895 | 370/28.08.08/EE(M)-I | M/s Gupta Engg. | 2008-09-03 | 2008-11-03 | 197828 | Work Comp.
9 | 2008-07-31 | 2008-06-05 | P/L RMC from h.no.WZ-76 to WZ-63 in phirni Road Basai Dharapur at C-101/WZ | 477589 | 664/30.01.09/EE(M)-I | M/s Devender Ved | 2009-01-30 | 2009-02-27 | 454480 | Work Comp.
10 | 2008-07-31 | 2008-05-19 | Pdg cc pav. from K-21 to K-343 in Raghubir Ngr. at C-102/WZ | 198521 | 368/28.08.08/EE(M)-I | M/s M.P. Assos | 2008-09-05 | 2009-01-24 | 198092 | Work Comp.
11 | 2008-07-31 | 2008-05-19 | Pdg cc pav. from K-41 to K-61 in Raghubir Ngr. at C-102/WZ | 92757 | 372/28.08.08/EE(M)-I | M/s Aman Const. | 2008-09-03 | 2008-10-30 | 91856 | Work Comp.
12 | 2008-07-31 | 2008-06-05 | C/O Hut in Madhav Parl in Rajori Garden at C-105/WZ | 285600
13 | 2008-07-31 | 2008-06-05 | C/O Designer gate in park opp.h.no.B-270 in Raghubir Ngr.in C-101/WZ | 299500 | 575/17.12.08/EE(M)-I | M/s R.P. Garg Const. | 2008-12-19 | 2008-03-24 | 299500 | Work Comp.
14 | 2008-07-31 | 2008-06-05 | C/O Designer gate in park near h.no.A-1/1 in Bhagat Singh Colony in C-101/WZ | 276300 | 576/17.12.08/EE(M)-I | M/s R.P. Garg Const. | 2009-01-07 | 2009-02-25 | 276300 | Work Comp.
15 | 2008-07-31 | 2008-06-05 | P/L RMC from h.no.WZ-80 to WZ-76 and WZ-480 to WZ-47A in Phirni Raod Basai Dharapur at C-101/WZ | 477316 | 658/30.01.09/EE(M)-I | M/s Devender Ved | 2009-01-30 | 2009-02-27 | 456068 | Work Comp.
16 | 2008-08-26 | 2008-05-19 | Stg of road by pdg dense carpetting from WZ-494 to Ramesh Ngr.drain in basai Darapur in C-101/WZ | 598200
17 | 2008-08-26 | 2008-05-19 | Stg of road by pdg dense carpetting from Shitla Mata mandir to N.G.Road in Basai Darapur in C-101/WZ | 598000
18 | 2008-08-26 | 2008-05-19 | Stg of road by pdg dense carpetting from WZ-271 to WZ-407A/1 and 508 to WZ-523/10 in Basai Darapur in C-101/WZ | 597200
19 | 2008-08-26 | 2008-05-19 | Stg of road by pdg dense carpetting from WZ-523/24 to WZ-485/1 in Basai Darapur in C-101/WZ | 593700
20 | 2008-08-26 | 2008-07-17 | P/L RMC from C-246 to Barat Ghar Raghubir Ngr. 80 Sq,Yard in C-101/WZ | 653500 | 772/12.02.09/EE(M)-I | M/s L.Gee Const. | 2009-02-14 | 2009-05-19 | 594850 | Work Comp.
21 | 2008-08-26 | 2008-07-17 | P/L RMC from C-137 to C-228 in D/Story in Raghubir Ngr.in C-101/WZ | 657200 | 771/12.02.09/EE(M)-I | M/s L.Gee Const. | 2009-02-14 | 2009-05-19 | 592952 | Work Comp.
22 | 2008-08-26 | 2008-08-07 | P/L RMC from A-15 to A-31 in Rajori Garden in C-105/WZ | 595700
23 | 2008-08-26 | 2008-08-07 | P/L RMC infront of Mother Dairy Road MIG Rajori Garden in C-105/WZ | 317100
24 | 2008-08-26 | 2008-08-07 | Stg of road by dense carpetting from J-11 to Desu Office Rajori Garden in C-105/WZ | 489500
25 | 2008-08-26 | 2008-08-07 | P/L RMC from A-36 to A-44 and A-39 to A-42 in Rajori Garden in C-105/WZ | 496100
26 | 2008-08-26 | 2008-08-07 | P/L RMC from J-3/70 to J-3/76D and J-3/74 to Arya Samaj Mandir in Rajori Garden in C-105/WZ | 461800 | 638/29.12.08/EE(M)-I | M/s Shri Ji Const. | 2008-01-07 | 2009-04-02 | 445672 | Work Comp.
27 | 2008-08-26 | 2008-08-07 | P/L RMC from J-3/16 to J-3/21 and J-3/52 to J-3/57,J-3/64 to J-3/69 in Rajori Garden in C-105/WZ | 573800
28 | 2008-08-26 | 2008-08-07 | P/L RMC from A-62 to A-65 and A-65 to A-71 in Rajori Garden in C-105/WZ | 390500 | 677/30.01.09/EE(M)-I | M/s Shri Ji Const. | 2009-02-09 | 2009-08-03 | 364619 | Work Comp.
29 | 2008-08-26 | 2008-08-07 | Stg of road by pdg dense carpetting from D-1/19 to D-1/9 and D-1/8 to D-1/1 in Rajori Garden in C-105/WZ | 503900
30 | 2008-08-26 | 2008-08-07 | P/L cc pav. from R-43 to R-40,S-55 to S-37 and J-3/137A to J-3/137A(back lane)in Rajori Garden in C-105/WZ | 411400 | 805/29.12.08/EE(M)-I | M/s Vashisth Const. | 2009-01-07 | 2009-06-06 | 322011 | Work Comp.
31 | 2008-08-26 | 2008-07-22 | Stg of road from A-120 to A-28,A-104 to A-111 and A-74 to A-84 in Vishal Enclave in C-101/WZ | 749400
32 | 2008-08-26 | 2008-07-22 | Stg of road from Bhagwan Ram Park to A-195 ion Sudarshan Park at C-101/WZ | 757400
33 | 2008-08-26 | 2008-07-22 | P/L RMC from C-219 to C-245 in Raghubir Ngr.80 Sq,Yard at C-101/WZ | 657000
34 | 2008-08-26 | 2008-08-01 | C/O Designer gate in Park of LIG Flats main Road at Rajori Garden in C-105/WZ | 299300
35 | 2008-08-26 | 2008-08-01 | C/O Designer Gate in J-Block Park near Super Bazar at Rajori Garden in C-105/WZ | 299100 | 544/13.10.08/EE(M)-I | M/s Vashisth Const. | 2008-10-21 | 2009-04-15 | 296164 | Work Comp.
36 | 2008-08-26 | 2008-08-01 | C/O Designer Gate in Park of Red MIG Flats N.G.Main Road at Rajori Garden in C-105/WZ | 296000 | 590/17.12.08/EE(M)-I | M/s Vashisth Const. | 2009-01-06 | 2009-03-24 | 293044 | Work Comp.
37 | 2008-08-26 | 2008-08-01 | C/O Designer Gate in J-3 Block(Tikona)Park at Rajori Garden in C-105/WZ | 299200 | 542/13.10.08/EE(M)-I | M/s Vashisth Const. | 2008-10-20 | 2009-05-18 | 296268 | Work Comp.
38 | 2008-08-26 | 2008-08-01 | C/O Hut in park opp.Arya Samaj mandir J-3 Block at Rajori Garden in C-105/WZ | 291100
39 | 2008-08-26 | 2008-08-01 | C/O Hut in park opp.h.no.25A Red MIG Flats at Rajori Garden in C-105/WZ | 292800
40 | 2008-08-26 | 2008-08-01 | C/O Designer Gate in Park opp.h.no.92A Red MIG Flats at Rajori Garden in C-105/WZ | 279500 | 543/13.10.08/EE(M)-I | M/s Vashisth Const. | 2008-10-22 | 2009-04-23 | 274943 | Work Comp.
41 | 2008-08-26 | 2008-08-01 | C/O Hut in Park opp.h.no.90 Red MIG Flats at Rajori Garden in C-105/WZ | 289500 | 594/29.12.08/EE(M)-I | M/s R.P. Garg Const. | 2009-01-05 | 2009-06-21 | 289500 | Work Comp.
42 | 2008-08-26 | 2008-08-01 | C/O Hut in Park J-3 Block Road Jhoda Singh Park at Rajori Garden in C-105/WZ | 287600
43 | 2008-09-01 | 2008-07-01 | P/O Post Top Lentern Fitting in the Park of Shivaji Enclave under WZ | 526128
44 | 2008-09-30 | 2008-07-30 | Stg. of road by pdg dense carpeting J-13/1 to T-69 in Rajouri garden C-105/WZ | 991800
|  |  |  | 18597653 |  |  |  |  | 7627974

## AC-16
S.no. | Date of booking | Date of consent | Name of wrok (AC-16) | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-05-30 | 2008-05-26 | Dev of road by pdg RMC from h.no.1/49 to 15/49 on road no.49 West Punjabi Bagh C-103/WZ | 498972 | 171/29.07.08/EE(M)-I | M/s A.B. builders | 2008-08-07 | 2008-10-31 | 498594 | Work Comp.
2 | 2008-05-30 | 2008-05-26 | Dev of lane by pdg cc pav. from h.no.WZ-206 to 207,171A to 171, 244 to 233, 511 to 513, 327 to 575, 321A to 324, 524 to 529, 529 to 528, 310 to 308, 285 to 285A and infront of 293A in Modipur Village in C-103/WZ | 497010 | 152/28.03.08/EE(M)-I | M/s Arjun Entp. | 2008-08-06 | P | 222346 | In Prog.
3 | 2008-05-30 | 2008-05-26 | Dev of B/Wall of park infront of flat no. B-6A and B-23A in New Slum Outer Punjabi Bagh C-103/WZ | 197563 | 173/25.07.08/EE(M)-I | M/s A.B. builders | 2008-08-07 | 2008-12-29 | 197297 | Work Comp.
4 | 2008-05-30 | 2008-05-26 | Dev of road by pdg RMC from h.no.1/48 to 15/48 on road no.48 and h.no.15/49 to 19/49 on road no.49 West Punjabi Bagh C-103/WZ | 499082 | 261/11.08.08/EE(M)-I | M/s Honey Const. | 2008-08-21 | 2008-11-07 | 496351 | Work Comp.
5 | 2008-05-30 | 2008-05-26 | Dev of road by pdg RMC from corner of Dairy yo WZ-257,WZ-257 to Shiv Mandir Road,WZ-249A to 270 and WZ-249 to corner of Dairy in Modipur Village C-103/WZ | 498343 | 218/06.08.08/EE(M)-I | M/s M.P. Assos | 2008-08-15 | 2008-12-24 | 488269 | Work Comp.
6 | 2008-05-30 | 2008-05-26 | Pdg RMC infront of flat no. A-40A,A-1A,B-6A,A-23A,B-24A,A-22A,B-26A,B-18A and Chowk in New Slum Outer Punjabi Bagh C-103/WZ | 497488 | 229/06.08.08/EE(M)-I | M/s Praveen Kumar Const. | 2008-08-16 | P | 454044 | In Prog.
7 | 2008-06-20 | 2008-05-26 | Dev of B/Wall of park infront of flat no.A-1A,A-40A,A-22A and B-24A in New Slum Qtrs. Punjabi Bagh C-103/WZ | 497892
8 | 2008-06-20 | 2008-05-28 | C/O flower space in beck side of flat no. 55,77,73,57,61,13,17,25,41,121,125,133,129,109,105,81,149 and 137 in SFS Flats Modipur C-103 | 366438
9 | 2008-06-20 | 2008-05-28 | Pdg RMC infront of flat no. 73 to 77 in SFS Flat Modipur C-103 | 199207 | 256/11.08.08/EE(M)-I | M/s Neel Const. | 2008-08-20 | 2008-11-12 | 198097 | Work Comp.
10 | 2008-06-20 | 2008-05-28 | Pdg RMC in lane around park infront of flat no. 9 to 29,9 to 49, 49 to 69 and 29 to 69 in SFS Flat Modipur C-103 | 373192 | 25/11.08.08/EE(M)-I | M;/s Manish Nayar | 2008-08-11 | 2008-11-19 | 261350 | Work Comp.
11 | 2008-06-20 | 2008-05-28 | Pdg RMC in lane around park infront of flat no. 121 to 125,89 to 109 and 109 to 129 in SFS Flat Modipur C-103 in WZ | 295455 | 172/29.07.08/EE(M)-I | M/s Lee Gee Const. | 2008-08-07 | 2008-11-04 | 294712 | Work Comp.
12 | 2008-06-20 | 2008-05-28 | Pdg RMC in lane around park infront of flat no. 81 to 85,89 to 149 and 129 to 149,41 to 45 in SFS Flat Modipur WZ | 399464 | 158/28.07.08/EE(M)-I | M/s Bhutani Entp. | 2008-08-06 | 2008-10-24 | 392951 | Work Comp.
13 | 2008-06-20 | 2008-05-26 | Pdg MS grill on chabutra near h.no.D-159 and missing grills in B to F Block chabutra in R/C Madipur C-104/WZ | 171090
14 | 2008-06-20 | 2008-05-26 | C/O drain from h.no.A-1A to Community Center and side of Pump house and park in A-Block of Shivaji Kunj Madipur C-104/WZ | 197900 | 214/06.08.08/EE(M)-I | M/s M.P. Assos | 2008-08-18 | 2008-10-08 | 195938 | Work Comp.
15 | 2008-06-20 | 2008-05-26 | Dev of lane around the park of colont nallah and adj lanes in A and B Block of Shivaji Kunj Madipur C-104/WZ | 450800 | 287/18.08.08/EE(M)-I | M/s Aman builders | 2008-08-27 | 2008-10-06 | 448062 | Work Comp.
16 | 2008-06-20 | 2008-05-26 | Dev to lane by pdg RMC between flat no. 19 and 54 in D/S of Pkt.-II Pachimpuri C-104/WZ | 199413 | 220/06.08.08/EE(M)-I | M/s A.K. & co | 2008-09-05 | 2008-10-01 | 195931 | Work Comp.
17 | 2008-06-20 | 2008-05-26 | Dev to lane by pdg RMC between flat no. 1 to 59 and park in D/S of Pkt.-II Pachimpuri C-104/WZ | 199255 | 244/11.10.08/EE(M)-I | M/s Harinder Singh | 2008-08-20 | 2008-12-10 | 197825 | Work Comp.
18 | 2008-08-06 | 2008-07-28 | Dev of drainage system from h.no.WZ-217 to 193 Janta Flat and 193 to 513 on Main Road in Janta Flat in Madipur C-103/WZ | 198259 | 316/22.08.08/EE(M)-I | M/s Rajan builders | 2008-09-01 | 2009-05-20 | 197525 | Work Comp.
19 | 2008-08-08 | 2008-08-04 | Covering of drain infront of St.martin School on Major Ashwani Marg in A-2 Block Paschim Vihar C-57/WZ | 507100 | 182/13.08.08/EE(M)-II | M/s J.M. Const | 2008-10-22 | 2009-05-26 | 493686 | Work Comp.
20 | 2008-08-08 | 2008-08-04 | Dev of B/Wall of park between BG-7 and Desu Service Station on Outer Periphenal Road in C-57/WZ | 452500 | 174/10.10.08/EE(M)-II | M/s Som Const | 2008-10-19 | 2009-04-06 | 452372 | Work Comp.
21 | 2008-08-08 | 2008-08-04 | Dev of backlane by pdg cc pav.in back lane from h.no.302 to 311,185 to 201 and 168 to 180 in A-4 Block Paschim Vihar in C-58/WZ | 502100 | 183/13.10.08/EE(M)-II | M/s Nayar Bros. | 2008-10-22 | 2009-06-12 | 341836 | Work Comp.
22 | 2008-08-08 | 2008-08-04 | Dev to park by pdg walkway between B-2 and B-4 Block Remaining Portion in Paschim Vihar C-57/WZ | 494200 | 329/22.12.08/EE(M)-II | M/s J.P. Const | 2009-01-01 | 2009-02-16 | 343652 | Work Comp.
23 | 2008-08-08 | 2008-08-04 | Dev of raod by pdg RMC from h.no.265 to Corner of park near B-1/271 in B-1 Block in Paschim Vihar | 502800
24 | 2008-08-12 | 2008-07-03 | P/O post top lantern fitting in Ram Lila Park Madipur J.J.Colony under WZ | 345830 | 195/17.010.08/EE(E)-III | M/s MS Trading Co. | 2008-10-17 | 2008-11-12 | 334426 | Work Comp.
25 | 2008-08-12 | 2008-07-28 | Pdg Marbel Wash and Sand Stone along ring road side and along WA Road side of Sant Harchand Gangwal Park in W.P.Bagh in C-103/WZ | 262355 | 501/13.10.08/EE(M)-I | M/s Ram Const. | 2008-10-22 | P | 151968 | In Prog.
26 | 2008-08-12 | 2008-07-28 | Pdg Marbel Wash and Sand Stone along Station side and al;ong road no.41 of Sant Harchand Gangwal Park in W.P.Bagh in C-103/WZ | 397580
27 | 2008-09-12 | 2008-07-28 | Pdg cc interlocking tiles on berms on road by precast rcc salb on drain from plot no.6A to 107A in LIG Plots in Madipur C-103/WZ | 433400 | 812/23.02.09/EE(M)-I | M/s LG Const | 2009-03-04 | 2009-06-01 | 398773 | Work Comp.
28 | 2008-08-14 | 2008-08-01 | C/O footpath from flat no.C-10A New Slum Qtrs.to Murti Sweets Pkt.-III Paschimpuri C-104/WZ | 484300
29 | 2008-08-14 | 2008-08-01 | C/O road berm by pdg interlocking tiles from flat no.C-10A New Slum Qtrs.to Mutti Sweets in Pkt.-III Paschimpuri C-104/WZ | 391100 | 70/30.05.09/EE(M)-I | M/s Shanti builders | 2009-06-08 | 2009-07-27 | 346712 | Work Comp.
30 | 2008-08-14 | 2008-08-01 | C/O drain by Razing and Covering from New Slun Qtrs. to Park near Murty Sweets in Pkt.-III Pachimpuri C-104/WZ | 499200
31 | 2008-08-14 | 2008-08-01 | C/O drain and imp to road berm from infront of Murti Sweets to prk in PKt.-III Paschimpuri C-104/WZ | 499000 | 606/29.12.08/EE(M)-I | M/s Vashisth const | 2009-01-07 | 2009-04-08 | 414607 | Work Comp.
32 | 2008-08-28 | 2008-08-27 | Dev of lane by pdg RMC between SBI and Meera Bagh B-Block C-57/WZ | 502400 | 273/13.10.08/EE(M)-II | M/s Som Const | 2008-10-22 | 2009-04-06 | 476918 | Work Comp.
33 | 2008-08-28 | 2008-08-27 | C/O B/Wall of open space in A-6 Block janta Flat C-58/WZ | 198100 | 305/13.10.08/EE(M)-II | M/s Praveen Kumar Const. | 2008-10-23 | 2008-12-22 | 155133 | Work Comp.
34 | 2008-08-28 | 2008-08-27 | Dev to park of h.no.175 and side of h.no.175 in A-5B Block C-58/WZ | 519700
35 | 2008-09-23 | 2008-09-25 | Dev to park by pdg marble wash and ms grill infront of h.no.36 ti BG-5A block Pashchim Vihar C-57/WZ | 198300 | 359/31.12.08/EE(M)-II | M/s Som Const | 2009-01-09 | 2009-03-02 | 198112 | Work Comp.
36 | 2008-09-23 | 2008-09-20 | Dev of road from h.no.86 to BSES office J block RBI cly. Pashchim Vihar C-57/WZ | 499700 | 377/09.01.09/EE(M)-II | M/s Som Const | 2009-01-16 | 2009-03-31 | 488156 | Work Comp.
9335643

## AC-26
S.no. | Date of booking | Date of consent | Name of wrok (AC-26) | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-08-28 | 2009-08-28 | Dev of lane by pdg relaying Kota Stone from Plot.no.382 to 384 and Plot no.324 to 328 in Chand Ngr.in C-107/WZ | 457857 | 140/15.09.08/EE(M)-II | M/s Prince Entp. | 2008-09-24 | 2008-02-11 | 457800 | Work Comp.
2 | 2008-08-28 | 2009-08-28 | Dev of lane by pdg cc from Plot.no.404 to 406 and Plot no.1 to 10 in Chand Ngr.in C-107/WZ | 460505 | 147/15.09.08/EE(M)-II | M/s Sahil builders | 2008-09-16 | 2008-11-28 | 459159 | Work Comp.
3 | 2008-08-28 | 2009-08-28 | Dev of lane by pdg relaying Kota Stone from 41 to 50 backlane in Chand Ngr.in C-107/WZ | 199378
4 | 2008-08-28 | 2009-08-28 | Dev of lane by pdg relaying Kota Stone from 272 to 278 back lane in Chand Ngr.in C-107/WZ | 139851 | 136/15.09.08/EE(M)-II | M/s A.K. Entp. | 2008-09-29 | 2008-11-21 | 139738 | Work Comp.
5 | 2008-08-28 | 2009-08-28 | Dev of lane by pdg cc from Plot.no.410 to 413 and Plot no.348 to 361 in Chand Ngr.in C-107/WZ | 447997 | 146/15.09.08/EE(M)-II | M/s Manish Nayar | 2008-09-24 | 2009-03-31 | 447997 | Work Comp.
6 | 2008-08-28 | 2009-08-28 | Dev of lane by pdg relaying Kota Stone from 101 to 109 and Plot no.12 to 20 in Chand Ngr.in C-107/WZ | 199850 | 161/15.09.08/EE(M)-II | M/s Balaji Const. | 2008-09-25 | 2009-03-25 | 198297 | Work Comp.
7 | 2008-08-28 | 2009-08-28 | Dev of lane by pdg cc from h.no.III-B/25 to III-B/60 and F-60 to F-58 in Vishnu Garden in C-107/WZ | 493475 | 149/15.09.08/EE(M)-II | M/s L.Gee Const. | 2008-09-29 | 2008-12-03 | 493475 | Work Comp.
8 | 2008-08-28 | 2009-08-28 | Dev of lane by pdg cc from h.no.III-B/5 to III-B/40 and 111/6 to F-60 in Vishnu Garden in C-107/WZ | 434163 | 156/15.09.08/EE(M)-II | M/s Amar Const Co. | 2008-09-25 | 2009-02-16 | 434100 | Work Comp.
9 | 2008-08-29 | 2009-08-28 | Dev of lane by pdg cc from h.no.III-B/120 to III-B/132 in Vishnu Garden in C-107/WZ | 357008 | 160/15.09.08/EE(M)-II | M/s Vijay Kumar Jha | 2008-09-24 | 2009-01-09 | 356462 | Work Comp.
10 | 2008-08-29 | 2009-08-28 | Dev of lane by pdg cc from h.no.WZ-16A to WZ-76/1 Navyug Block and C-3 to C-36 in Vishnu Garden in C-107/WZ | 496568 | 155/15.09.08/EE(M)-II | M/s Pawan Kumar Garg | 2008-09-20 | 2008-12-05 | 496568 | Work Comp.
11 | 2008-08-29 | 2009-08-28 | Dev of lane by pdg relaying Kota Stone from h.no.WZ-145 to WZ-42 in Ram Ngr.in C-107/WZ | 299813
12 | 2008-08-29 | 2009-08-28 | Dev of lane by pdg cc from h.no.Balaknath Mandir to III-B/14 and III-B/15 to III-B/7A in Vishnu Garden in C-107/WZ | 494939 | 148/15.08.08/EE(M)-II | M/s Rajan builders | 2008-09-25 | 2009-02-13 | 493160 | Work Comp.
13 | 2008-08-29 | 2009-08-28 | Dev of lane by pdg relaying Kota Stone from WZ-70/A to WZ-15/A and N-15 to N-11 Navyug Block Vishnu Garden in C-107/WZ | 456246
14 | 2008-08-29 | 2009-08-28 | Dev of lane by pdg relaying Kota Stone from E-3 to E-16 in Vishnu Garden in C-107/WZ | 243491 | 154/15.09.08/EE(M)-II | M/s Rohit Const. | 2008-09-24 | 2008-11-21 | 243396 | Work Comp.
15 | 2008-08-29 | 2009-08-28 | Dev of lane by pdg relaying Kota Stone from h.no.III-B/60 to III-B/75 and F-173 to F-179 Vishnu Garden in C-107/WZ | 498709
16 | 2008-09-04 | 2009-08-28 | Dev of lane by pdg cc from h.no.283/30 to 283/21 in Vishnu Garden in C-108/WZ | 496530 | 215/13.10.08/EE(M)-II | M/s Sahil builders | 2008-10-14 | 2008-11-28 | 495512 | Work Comp.
17 | 2008-09-04 | 2009-08-28 | Dev of lane by pdg cc from h.no.283/81 to B-19 in Vishnu Garden in C-108/WZ | 497279 | 198/13.10.08/EE(M)-II | M/s Rohit Const. | 2008-12-22 | 2008-12-10 | 497277 | Work Comp.
18 | 2008-09-04 | 2009-08-28 | Dev of lane by pdg cc from h.no.283/267 to 283/276 gali no.8 in Vishnu arden in C-108/WZ | 432659 | 208/13.10.08/EE(M)-II | M/s Jatin Jaggi | 2008-10-17 | 2008-12-15 | 431735 | Work Comp.
19 | 2008-09-04 | 2009-08-28 | Dev of lane by pdg cc from h.no.B-1/184 to B-1/75 and B-1/83 to B-1/103 in Vishnu Garden in C-108/WZ | 497786
20 | 2008-09-04 | 2009-08-28 | Dev of lane by pdg cc from Gurudwara Wali gali to III-B/143 in Vishnu Garden in C-107/WZ | 357008
21 | 2008-09-04 | 2009-08-28 | Dev of lane by pdg cc from h.no.III-A/53 to III-A/52 in Vishnu Garden in C-107/WZ | 411615 | 216/13.10.08/EE(M)-II | M/s Mukesh Kumar -II | 2008-10-23 | 2009-05-15 | 411600 | Work Comp.
22 | 2008-09-04 | 2009-08-28 | Dev of lane by pdg cc from h.no.III-A/53 to III-A/7 in Vishnu Garden in C-108/WZ | 414116 | 199/13.10.08/EE(M)-II | M/s Harvinder Singh | 2008-10-23 | 2009-03-13 | 410639 | Work Comp.
23 | 2008-09-04 | 2009-08-28 | Dev of lane by pdg relaying Kota Stone from F-137 to F-143 and F-240 to F-110 in Vishnu Garden in C-107/WZ | 499656
24 | 2008-09-04 | 2009-08-28 | Dev of lane by pdg relaying Kota Stone from III-A-12/1 to III-A-11/7 to III-A-12/1 and III-A-8 in Vishnu Garden in C-108/WZ | 454653
25 | 2008-09-04 | 2009-08-28 | Dev of lane by relaying kota Stone from h.no.283/285 to 283/88 gali no.7 in Vishnu Garden in C-108/WZ | 382169 | 214/13.10.08/EE(M)-II | M/s Ashok Bansal | 2008-11-10 | 2009-01-21 | 381327 | Work Comp.
26 | 2008-09-04 | 2009-08-28 | Dev of lane by relaying kota Stone from h.no.283/124 to 283/138 gali no.7 in Vishnu Garden in C-108/WZ | 499648 | 197/13.10.08/EE(M)-II | M/s Umda Const Co. | 2008-10-24 | 2008-12-10 | 497282 | Work Comp.
27 | 2008-09-04 | 2009-08-28 | Dev of lane by relaying kota Stone from h.no.283/351 to 283/267 gali no.11 in Vishnu Garden in C-108/WZ | 387636 | 201/13/.10.08/EE(M)-II | M/s A.K. Const. | 2008-10-21 | 2009-02-24 | 387500 | Work Comp.
28 | 2008-09-04 | 2009-08-28 | Dev of lane by relaying kota Stone from h.no.283/338 to 283/351 in Vishnu Garden in C-108/WZ | 496859 | 190/13.10.08/EE(M)-II | M/s Rajan builders | 2008-10-24 | 2008-12-29 | 494242 | Work Comp.
29 | 2008-09-05 | 2009-08-28 | Dev of lane by relaying kota Stone from h.no.283/276 to B-1/103 gali no.9 in Vishnu Garden in C-108/WZ | 498598
30 | 2008-09-05 | 2009-08-28 | Dev of lane by pdg relaying kota Stone from h.no.283/16 to 283/27 in Vishnu Garden in C-108/WZ | 301364
31 | 2008-09-05 | 2009-08-28 | Dev of lane by pdg cc from h.no.WZ-95 to WZ-217 Khyala Village in Vishnu Garden in C-108/WZ | 364195 | 218/13.10.08/EE(M)-II | M/s A.B. builders | 2008-10-24 | 2008-01-12 | 363859 | Work Comp.
32 | 2008-09-05 | 2009-08-28 | Dev of lane by pdg cc from h.no.WZ-48/8A to WZ-83 Khyala Village in Vishnu Garden in C-108/WZ | 372044
33 | 2008-09-05 | 2009-08-28 | Dev of lane by pdg cc from h.no.WZ-125 to WZ-125B Khyala Village in Vishnu Garden in C-108/WZ | 369372
34 | 2008-09-30 | 2009-08-18 | P/o SHM light at Subash nagar more near Police booth and Sr. Sec School Khayala no.1 in w.no. 108/WZ | 382589
35 | 2008-09-30 | 2008-09-20 | P/o SHM light at park Chaukhandi near A-465/in w.no.107/WZ | 390402
8591125

## AC-27
S.no. | Date of booking | Date of consent | Name of wrok (AC-27) | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-06-20 | 2008-05-26 | Pdg RMC in lane from S-5A to S-1A in S-Block Parampuri C-127/WZ | 499408 | 135/25.07.08/EE(M)-IV | M/s Jatin Jaggi | 2008-08-03 | P | 486309 | In Prog.
2 | 2008-06-20 | 2008-05-26 | Pdg RMC in lane from S-7 to S-30 in S-Block Parampuri C-127/WZ | 494138 | 136/25.07.08/EE(M)-IV | M/s Parveen Kumar Garg | 2008-08-08 | 2008-09-10 | 493925 | Work Comp.
3 | 2008-06-20 | 2008-05-26 | Pdg RMC and drainage system on both side from RZ-A1 to RZ-A151 in Prajapati Colony C-127/WZ | 461034 | 138/25.07.08/EE(M)-IV | M/s Neel Const & Co. | 2008-08-03 | 2008-11-20 | 460807 | Work Comp.
4 | 2008-06-20 | 2008-05-26 | Pdg RMC and drainage system on both side from RZ-127 to RZ-88 in Santosh Park C-127/WZ | 461690 | 133/25.007.08/EE(M)-IV | M/s Chitter Mal | 2008-08-03 | 2008-11-25 | 461528 | Work Comp.
5 | 2008-06-20 | 2008-05-26 | Pdg RMC and drainage system on both side from RZ-1 to RZ-21 in Santosh Park C-127/WZ | 498631 | 143/25.07.08/EE(M)-IV | M/s Prince Entp. | 2008-08-04 | 2008-12-10 | 497797 | Work Comp.
6 | 2008-06-20 | 2008-05-26 | Pdg drainage system and cc from RZ-98 to G-56 in Panjabi Colony C-127/WZ | 497704 | 139/25.07.08/EE(M)-IV | M/s L. Gee Const. | 2008-08-03 | 2008-10-31 | 496683 | Work Comp.
7 | 2008-07-23 | 2008-05-26 | Pdg drainage system on both side and RMC from RZA-59 to RZA-64 in Prajapati Colony C-127/WZ | 424188 | 137/25.07.09/EE(M)-IV | M/s Jatin Jaggi | 2008-08-03 | 2008-11-01 | 423940 | Work Comp.
8 | 2008-06-23 | 2008-05-26 | Pdg drainage system on both side and RMC from RZ-178 to A-300 in Prajapati Colony C-127/WZ | 404475 | 142/25.07.08/EE(M)-IV | M/s Parveen Kumar Garg | 2008-08-03 | 2008-10-23 | 404409 | Work Comp.
9 | 2008-06-23 | 2008-05-26 | Pdg drainage system on both side and RMC from G-166 to RZB-23 in Prajapati Colony C-127/WZ | 403872 | 132/25.07.08/EE(M)-IV | M/s Aman Entp. | 2008-08-04 | 2009-01-05 | 402140 | Work Comp.
10 | 2008-06-23 | 2008-05-26 | Pdg drainage system on both side and RMC from RZ-145 to RZ-160 in Prajapati Colony and RMC from RZ-106 to RZ-155 in Santosh Park C-127/WZ | 477377 | 126/25.07.08/EE(M)-IV | M/s Manish Nayar | 2008-09-24 | 2009-01-28 | 477078 | Work Comp.
11 | 2008-06-23 | 2008-05-26 | Pdg drainage system on both side and RMC from RZ-139 to RZ-96 in Santosh Park C-127/WZ | 460679 | 140/25.07.08/EE(M)-IV | M/s Mukesh Kumar Const. | 2008-08-03 | 2008-11-19 | 460076 | Work Comp.
12 | 2008-06-23 | 2008-05-29 | Pdg drainage system on both side and RMC from A-26 to A-14 in Subhash Park in C-127/WZ | 499403 | 130/25.07.08/EE(M)-IV | M/s Som Const. | 2008-08-03 | 2009-01-23 | 499239 | Work Comp.
13 | 2008-06-23 | 2008-05-29 | Pdg RMC in lane from S-23 to S-47 gali no.9 in Parampuri in c-127/WZ | 496638 | 131/25.07.08/EE(M)-IV | M/s Gupta Engg. & Const. | 2008-08-03 | 2008-09-10 | 496616 | Work Comp.
14 | 2008-06-23 | 2008-05-29 | Pdg drainage system on both side and RMC from B-25 to B-37 in Subhash Park in C-127/WZ | 498791 | 127/25.07.08/EE(M)-IV | M/s L.Gee Const | 2008-08-03 | p | 491852 | In Prog.
15 | 2008-06-23 | 2008-05-29 | Pdg RMC in lane from S-11 to S-16 gali no.3 in Parampuri in C-127/WZ | 196624 | 129/25.07.08/EE(M)-IV | M/s Harvinder Singh | 2008-08-03 | 2008-10-11 | 196624 | Work Comp.
16 | 2008-06-23 | 2008-05-29 | Pdg drainage system on both side and RMC in lane gali no.8 from S-21 to S-32 in Parampuri in C-127/WZ | 439965 | 134/25.070.08/EE(M)-IV | M/s Manish Nayar | 2008-08-03 | 2009-01-19 | 439405 | Work Comp.
17 | 2008-06-23 | 2008-05-29 | Pdg RMC in lane from S-9 to S-5 gali no.2 in Parampuri in C-127/WZ | 199388 | 128/25.07.08/EE(M)-IV | M/s Honey Const. | 2008-08-03 | 2008-09-08 | 198015 | Work Comp.
18 | 2008-06-23 | 2008-05-26 | Pdg RMC in lane from S-34 to S-53 in S-Block in Parampuri in C-127/WZ | 495402 | 141/25.07.08/EE(M)-IV | M/s Gupta Engg. & Const. | 2008-08-03 | 2008-09-24 | 495383 | Work Comp.
19 | 2008-07-23 | 2008-05-19 | Pdg RMC in lane from A-1 Sanjay Enclave to RZ-50 T-Extn.on Bindapur matiayala Road in C-127/WZ | 494447 | 285/26.08.08/EE(M)-IV | M/s Mahesh Const. | 2008-09-04 | 2008-11-14 | 493798 | Work Comp.
20 | 2008-07-23 | 2008-05-19 | Dev of drainage system from RZ-27 Subhash Park Extn.-II to RZ-T-214 in T-Block Uttam Ngr.(both sides) on Bindapur to Matiayala Road in C-127/WZ | 431017 | 293/26.08.08/EE(M)-IV | M/s L.Gee Const | 2008-09-04 | 2009-01-19 | 429889 | Work Comp.
21 | 2008-06-23 | 2008-05-19 | Pdg RMC in lane from U-121 Subhash Park to near T-28 Bindapur to Matiayala Road in C-127/WZ | 493271 | 284/26.08.08/EE(M)-IV | M/s Arujn Entp. | 2008-09-04 | 2009-01-23 | 492858 | Work Comp.
22 | 2008-07-23 | 2008-05-19 | Dev of drainage system from S-156,Parampuri to RZ-14,Subhash Park Extn.-II(both side)on Bindapur to Matiayala Road in C-127/WZ | 493628 | 287/26.08.08/EE(M)-IV | M/s Sahil builders | 2008-09-04 | 2008-12-03 | 493557 | Work Comp.
23 | 2008-07-23 | 2008-05-19 | Pdg RMC in lane from RZ-73-T Extn.U-12 Subhash Park on Bindapur to Matiayala Road in C-127/WZ | 496505 | 288/26.08.08/EE(M)-IV | M/s Gupta Engg. & Const. | 2008-09-04 | 2008-10-24 | 496500 | Work Comp.
24 | 2008-07-23 | 2008-05-19 | Pdg RMC in lane from U-13 Subhash Park U-6 Subhash Park on Bindapur to Matiayala Road in C-127/WZ | 493232 | 289/26.08.08/EE(M)-IV | M/s Chitter Mal | 2008-09-04 | p | 480013 | In Prog.
25 | 2008-07-23 | 2008-05-19 | Pdg RMC on road from T-3 to T-12 in T-Block Sukar Bazar Uttam Ngr.C-127/WZ | 386851 | 295/26.08.08/EE(M)-IV | M/s Kushal Kumar Bhatia | 2008-09-04 | 2008-10-30 | 386839 | Work Comp.
26 | 2008-07-24 | 2008-05-20 | Dev of U/R Colony in C-127/WZ SH: Pdg drasinage system on both side and cc from RZ-A74 to RZ-A133 in Prajapati Colony C-127/WZ | 494760 | 212/26.08..08/EE(M)-IV | M/s Amar Const. | 2008-09-04 | p | 481103 | In Prog.
27 | 2008-07-24 | 2008-05-20 | Dev of U/R Colony in C-127/WZ SH: Pdg drasinage system on both side and RMC from RZ-A31 to RZ-A36 in Prajapati Colony C-127/WZ | 499820 | 291/26.08.08/EE(M)-IV | M/s Rajan builders | 2008-09-04 | p | 486686 | In Prog.
28 | 2008-07-24 | 2008-05-20 | Dev of U/R Colony in C-127/WZ SH: Pdg drasinage system on both side and cc from RZ-A108 to RZ-A135 in Prajapati Colony C-127/WZ | 490141 | 290/26.08.08/EE(M)-IV | M/s Vijay Kumar Jha | 2008-09-04 | 2008-10-22 | 490120 | Work Comp.
29 | 2008-07-30 | 2008-06-30 | Pdg RMC on road from B-45 to B-1/57 in Sewak Park in C-127/WZ | 468982 | 286/26.08.08/EE(M)-IV | M/s Rohit Const | 2009-09-04 | 2008-10-23 | 468898 | Work Comp.
30 | 2008-07-30 | 2008-06-30 | Pdg RMC on road from Durga MAndir to C-5 in Sewak Park in C-127/WZ | 274861 | 294/26.08.08/EE(M)-IV | M/s Gupta Engg. & Const. | 2008-09-04 | p | 264860 | In Prog.
31 | 2008-07-30 | 2008-06-30 | P/F Streert Name Board in Uttam Ngr. C-127/WZ | 197536 | 186/26.08.08/EE(M)-IV | M/s Manish Nayar | 2008-08-29 | 2008-10-28 | 197536 | Work Comp.
32 | 2008-08-27 | 2008-07-22 | Dev of lane by pdg RMC from RZ-135 to RZ-142 in Manas Kunj in C-128/WZ | 199190 | 386/13.10.08/EE(M)-IV | M/s Chitter Mal | 2008-10-22 | 2008-12-21 | 198685 | Work Comp.
33 | 2008-08-28 | 2008-07-22 | Dev of lane by pdg RMC from A-106 to A-111 Nand Ram Park n C-128/WZ | 199409 | 385/13.10.08/EE(M)-IV | M/s Manish Nayar | 2008-11-09 | 2008-11-22 | 198154 | Work Comp.
34 | 2008-09-05 | 2008-07-22 | Dev of lane by pdg RMC from h.no.RZ-81 to RZ-87,RZ-89 to RZ-96 and RZ-134 to RZ-128 Manas Kunj in C-128/WZ | 484875 | 358/01.10.08/EE(M)-IV | M/s Bhutani Entp. | 2008-10-10 | 2008-12-08 | 484591 | Work Comp.
35 | 2008-09-05 | 2008-07-22 | Dev of lane by pdg RMC from h.no.RZ-116 to RZ-80 and RZ-81 to RZ-87 in Manas Kunj C-128/WZ | 498925 | 346/01.10.08/EE(M)-IV | M/s Harinder Singh | 2008-10-10 | 2008-12-08 | 497417 | Work Comp.
36 | 2008-09-05 | 2008-07-22 | Dev of lane by pdg RMC from N-66 to N-56 in Vijay Vihar in C-128/WZ | 350036 | 347/01.10.08/EE(M)-IV | M/s Pawan Kumar Garg | 2008-10-10 | 2008-11-27 | 349842 | Work Comp.
37 | 2008-09-05 | 2008-07-22 | Dev to road by Pdg RMC from h.no.RZ-6 to RZ-92 in Rajapuri Road in Manav Kunj in C-128/WZ | 498818 | 350/01.10.08/EE(M)-IV | M/s Neel Traders | 2008-10-10 | 2008-12-03 | 498522 | Work Comp.
38 | 2008-09-05 | 2008-07-22 | Dev to road by pdg RMC from h.no.RZ-50 to RZ-36 in New Uttam Ngr.in C-128/WZ | 499605 | 353/01.10.08/EE(M)-IV | M/s Balaji Const. | 2008-10-10 | 2008-12-08 | 497417 | Work Comp.
39 | 2008-09-05 | 2008-07-22 | Dev of lane by pdg RMC from h.no.RZ-69 to RZ-82 and RZ-68 to RZ-64 in New Uttam Ngr.C-128/WZ | 478745 | 352/01.10.08/EE(M)-IV | M/s Y.K. Sahni | 2008-10-10 | 2009-01-16 | 478303 | Work Comp.
40 | 2008-09-05 | 2008-07-22 | Dev of lane by pdg RMC from h.no.RZ-16 to RZ-28 and RZ-16 to RZ-13 in New Uttam Ngr.in C-128/WZ | 424491 | 359/01.10.08/EE(M)-IV | M/s Y.K. Sahni | 2008-10-10 | 2009-03-09 | 423471 | Work Comp.
41 | 2008-09-05 | 2008-07-22 | Dev of lane by pdg RMC from h.no.RZ-17 to RZ-19,RZ-28 to RZ-26 and RZ-1 to RZ-6 in New Uttam Ngr.in C-128/WZ | 499431 | 345/01.10.08/EE(M)-IV | M/s Harinder Singh | 2008-11-09 | 2008-11-22 | 499059 | Work Comp.
42 | 2008-09-05 | 2008-07-22 | Dev of road by pdg RMC from h.no.RZ-13 to RZ-69 in Rajapuri Road in New Uttam Ngr.in C-128/WZ | 499883 | 351/01.10.08/EE(M)-IV | M/s Honey Const. | 2008-10-10 | 2008-12-09 | 499470 | Work Comp.
43 | 2008-09-05 | 2008-07-22 | Dev of road by pdg RMC from h.no.RZ-93A to RZ-98 in New Uttam Ngr.in C-128/WZ | 318032 | 354/01.10.08/EE(M)-IV | M/s Y.K. Sahni | 2008-10-10 | 2008-12-04 | 317297 | Work Comp.
44 | 2008-09-05 | 2008-07-22 | Dev of lane by pdg RMC from h.no.RZ-84 to RZ-92 and RZ-83 to RZ-85 in New Uttam Ngr.in C-128/WZ | 354415 | 348/01.10.08/EE(M)-IV | M/s Aman builders | 2008-10-10 | 2008-12-08 | 353487 | Work Comp.
45 | 2008-09-05 | 2008-07-22 | Dev of road by pdg RMC from h.no.RZ-83 to RZ-92 in New Uttam Ngr.in C-128/WZ | 499106 | 349/01.10.08/EE(M)-IV | M/s G.Pee Const | 2008-10-10 | 2008-12-10 | 498904 | Work Comp.
19339102

## AC-65
S.no. | Date of booking | Date of consent | Name of wrok (AC-65) | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-06-20 | 2008-05-26 | Pdg Rmc in Chowk opp.E-133 Jain Mandir in Karampura C-100/WZ | 495289 | 139/25/07/08EEM-I | M/s parveen kumar Garg | 2008-08-01 | 2008-10-08 | 494779 | Comp
2 | 2008-06-20 | 2008-05-26 | Pdg drainage system from E-243 to E-299 in E-Block and Shop no.73 to Shop no.52 in Bhyana Mkt.in Karampura C-100/WZ | 450201 | 136/25/07/08/EEM-I | M/s A.K & Const | 2008-08-20 | 2009-01-02 | 450200 | Comp
3 | 2008-06-20 | 2008-05-26 | Pdg Rmc in Chowk opp.E-239 to Hanuman Mandir in Karampura C-100/WZ | 494544 | 130/25/07/08/EEM-I | M/s Som const | 2008-10-03 | 2008-12-08 | 495521 | Comp
4 | 2008-06-20 | 2008-05-26 | Pdg Rmc in lane from I-397 to I-455 in I-Block in Karampura C-100/WZ | 499687 | 129/25/07/08/EEM-I | M/s Khusal Kumar Bhatia | 2008-08-04 | 2008-10-28 | 497947 | Comp
5 | 2008-06-20 | 2008-05-26 | Pdg Rmc from shop no.14 to Koyla Depot and shop no.73 to shop no.52 in Bhyana Mkt. in Karampura C-100/WZ | 499513 | 140/25/07/08/EEM-I | M/s Y.K Saheney | 2008-02-02 | 2008-04-10 | 498408 | Comp
6 | 2008-06-20 | 2008-05-26 | Pdg Rmc in lane from F-443 to F-419 in F-Block in Karampura C-100/WZ | 198508 | 199/04/08/08/EEM-I | M/s Parveen kumar Contract | 2008-08-08 | 2008-09-08 | 198175 | Comp
7 | 2008-06-20 | 2008-05-26 | Pdg drainage system from H-277 to H-347 in H-Block in Karampura C-100/WZ | 498256 | 128/25/07/08/EEM-I | M/s Ghanshyam Dass | 2008-08-01 | 2009-01-20 | 496948 | Comp
8 | 2008-06-20 | 2008-05-26 | Pdg RMC in lane from E-131 to E-85 and E-49 to E-83 in Karampura C-100/WZ | 498112 | 135/25.07.08/EE(M)-I | M/s M.P. Assos | 2008-08-02 | 2008-08-29 | 498100 | Comp
9 | 2008-06-20 | 2008-05-26 | Pdg drainage system from H-229 to H-272 in H-Block in Karampura C-100/WZ | 194985 | 143/25.07.08/EE(M)-I | M/s M.P. Assos | 2008-08-03 | 2008-09-30 | 194900 | Comp
10 | 2008-06-23 | 2008-04-15 | C/O Recreatoin Center (F.F) for Senior Citizen at Ramesh Ngr.WZ SH: Pdg marble wash in external wall | 99500 | 06/11.07.08/EE(M)-I | M/s Manoj Kumar Gupta | 2008-07-14 | 2008-07-28 | 98273 | Comp
11 | 2008-06-23 | 2008-04-15 | P/F aluminium door and misc.work at recreation center at Ramesh Ngr.WZ | 500000 | 08/11.07.08/EE(M)-I | M/s Shanker bulinder | 2008-07-12 | 2008-07-31 | 499740 | Comp
12 | 2008-06-23 | 2008-04-15 | C/O U.G.S.tank and dev of toilet,back kitchen and compound at recreation center in Ramesh Ngr.WZ | 499800 | 07/11.07.08/EE(M)-I | M/s Manoj Kumar Gupta | 2008-07-12 | 2008-07-30 | 498677 | Comp
13 | 2008-07-03 | 2008-05-20 | Pdg RMC in lane around park from G-14 to G-26 in G-Block Extn.in Kirti Ngr. C-97/WZ | 498276 | 134/25.07.08/EE(M)-I | M/s L. Gee Const Co. | 2008-08-03 | 2008-10-14 | 498083 | Comp
14 | 2008-07-03 | 2008-05-20 | Pdg premix carpetting on road along park from C-5 to C-20 and C-22 to C-40 in C-Block in Kirti Ngr.and from C-3/27 to C-3/18 in C-Block Rajori Garden in C-97/WZ | 496454 | 122/25.07.08/EE(M)-I | M/s Ghanshyam Dass | 2008-07-26 | 01.011.08 | 495877 | Comp
15 | 2008-07-03 | 2008-05-20 | Pdg premix carpetting on Chowk and adj road infront of B-87,B-105,B-117 in B-Block D/S Ramesh Ngr.and from L-85 to L-100 around park in L-Block in Kirti Ngr.C-97/WZ | 499657 | 124/25.07.08/EE(M)-I | M/s Honey Const | 2008-08-03 | 2008-10-15 | 499504 | Comp
16 | 2008-07-03 | 2008-05-20 | Pdg RMC in lane from C-43 to C-52 and C-33 to C-42 in C-Block in M.S.Garden in C-98/WZ | 499380 | 119/25.07.08/EE(M)-I | M/s Parveen Kumar Garg | 2008-08-28 | 2008-09-04 | 498988 | Comp
17 | 2008-07-03 | 2008-05-20 | Pdg RMC in lane from D-46 to D-52 and D-42 to D-33 and D-5 to B-12 in Saraswati Garden in C-97/WZ | 499658
18 | 2008-07-03 | 2008-05-20 | Pdg premix carpetting on road and chowk infront of I-80 to I-94 in I-Block in Kirti Ngr.chowk infront of H-54 in H-Block in Kirti Ngr.C-97/WZ | 335337 | 133/25.07.08/EE(M)-I | M/s Som const | 2008-08-03 | p | 330009 | In Prog.
19 | 2008-07-03 | 2008-05-20 | Pdg RMC in lane from B-53 to B-72 and B-57 to B-101 in B-Block Shardapuri C-98/WZ | 499384
20 | 2008-07-03 | 2008-05-20 | P/F M/S grill on Central Verge of 80 ROW road from F-1 Man Sarovar Garden to E-Block Saraswati Garden C-97/WZ | 495570 | 311/22.08.08/EE(M)-I | M/s Rohit Const. | 2008-08-23 | p | 495500 | In Prog.
21 | 2008-07-03 | 2008-05-20 | Pdg premix carpeting on road from G-14 to G-1 in G-Block Extn.in Kirti Ngr.and from around park from A-53 to A-71 and Chowk infront of A-76 in A-Block Kirti Ngr.C-97/WZ | 499232 | 181/29.07/.08EE(M)-I | M/s Aman builders | 2008-08-07 | 2008-10-08 | 499200 | COMP
22 | 2008-07-03 | 2008-05-20 | P/F M/S grill on Central Verge of 80 ROW road from E-Block Saraswati Garden to SBI Man Sarovar Garden C-97/WZ | 493351 | 109/24.02.08/EE(M)-I | M/s L.Gee Const Co. | 2008-08-03 | p | 260723 | In Prog.
23 | 2008-07-10 | 2008-06-27 | W/O road by pdg interlocking tiles and pdg of drainage system from 9/36 to M.C.Pry.School 9-Block Moti Ngr.C-99/WZ | 199661 | 204/04.08.08/EE(M)-I | M/s Ashok Bansal | 2008-08-11 | 2008-09-25 | 199121 | COMP
24 | 2008-07-10 | 2008-06-27 | Pdg drainage system and side berms by interlocking tiles from 5/3 to 5/9 Moti Ngr.C-99/WZ | 194708 | 205/04.08.08/EE(M)-I | M/s Parveen Kumar Garg | 2008-08-07 | 2008-10-10 | 194700 | COMP
25 | 2008-07-16 | 2008-05-15 | C/o Chhatri in B-Block park karampura in C-100/WZ | 258000
26 | 2008-07-16 | 2008-05-15 | Pdg RMC in lane from F-71 to F-37 in karampura C-100/WZ | 482674 | 319/22.08.08/EE(M)-I | M/s Baba Ji Const | 2008-10-20 | p | 475414 | In Prog.
27 | 2008-07-16 | 2008-05-15 | Pdg RMC in lane from F-119 to F-97 in karampura C-100/WZ | 198191 | 386/04.09.08/EE(M)-I | M/s Neel Traders | 2008-09-11 | 2008-11-12 | 197925 | COMP
28 | 2008-07-16 | 2008-05-15 | Pdg RMC in lane from F-37 to F-35 in karampura C-100/WZ | 198418 | 203/04.08.08/EE(M)-I | M/s Vijay Kumar Jha | 2008-10-23 | 2008-11-28 | 198386 | COMP
29 | 2008-09-26 | 2008-09-26 | C/o B/wall of park infront of h.no. H-3 at Kailash park in w.no. 99/WZ | 462984 | 582/17.12.08/EE(M)-I | M/s A.B. builders | 2008-12-26 | 2009-02-20 | 462199 | COMP
30 | 2008-10-10 | 2008-09-03 | P/L RMC from h.no. D-126 to C-131 in D block Mansarovar GArdenn at C-98 WZ | 263600 | 648/30.01.09/EE(M)-I | M/s Bajrang Engg. Components | 2009-02-09 | 2009-03-25 | 262317 | COMP
31 | 2008-10-10 | 2008-09-13 | C/o designer gate and P/f grill in park of F block Moti nagar along h.no.34 road in w.no.99/WZ | 199000
32 | 2008-10-10 | 2008-09-13 | Stg. of rioad by pdg mastic from 9/9 to 9/36 in Moti nagar w.no.99/WZ | 496900 | 600/29.12.08/EE(M)-I | M/s Ashok Kumar Gupta | 2009-01-07 | P | 467551 | In Prog.
33 | 2008-10-10 | 2008-09-13 | Stg. of road by pdg mastic from 4/28 to 4/36 in Moti nagar w.no.99/WZ | 498600 | 601/29.12.08/EE(M)-I | M/s Ashok Kumar Gupta | 2009-01-07 | P | 474292 | In Prog.
34 | 2008-10-10 | 2008-09-13 | Pdg interlocking tiles infront of D-39 moti nagar in w.no.99/WZ | 397838
35 | 2008-10-10 | 2008-09-13 | Imp of road by pdg premix from 4/1 to 5/6 Moti nagar in w.no.99/WZ | 199800
36 | 2008-10-10 | 2008-09-13 | C/o Chhatri in park of D block infront of block no.18 Moti nagar w.no.99/WZ | 198900 | 758/11.02.09 | M/s Vikas Builders | 2009-02-12 | 2009-05-19 | 198742 | COMP
37 | 2008-10-10 | 2008-09-13 | C/o Chatrri in park infront of h.no.C-152 moti nagar w.no.99/WZ | 198900 | 757/11.02.08 | M/s Vikas Builders | 2009-02-12 | 2009-05-19 | 198652 | COMP
38 | 2008-10-10 | 2008-09-13 | Pdg RMC from 1/56 Moti nagar to 1/6 Moti nagar in w.no.99/WZ | 199900 | 759/11.02.09 | M/s Vikas Builders | 2009-02-19 | 2009-03-30 | 197234 | COMP
39 | 2008-10-10 | 2008-09-13 | Pdg RMC from C-108 to C-103 Moti nagar in w.no.99/WZ | 199500 | 700/4.02.09 | M/s Divine Const | 2009-02-05 | 2009-03-17 | 197800 | COMP
40 | 2008-10-10 | 2008-09-13 | Imp of covering drainage system from C-110 to C-124 Moti nagar w.no.99/WZ | 198023 | 729/05.02.09CC | M/s Raj Const | 2009-02-09 | 2009-03-25 | 197369 | COMP
|  |  |  | 14790291 |  |  |  |  | 12421254