## AC-22
S.No. | Date of Booking | Date of Consent | Name of Work | Amount Booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-06-17 | 09.04.08 | Pdg cc and c/o drain in lane Baljit, Rajinder Jile and Ramphal in Village Daryapur | 472000 | 47/05.09.08/EE(Pr.) | M/s Anand Mathur mpl Contractor | 12.09.08 | P | 350939
2 | 2008-06-17 | 27.05.08 | Pdg brick florring from Surrte house/flat to Cannal in village Nangal Thagran | 160000
3 | 2008-07-08 | 12.06.08 | Pdg brick flooring in lane Tarif , sri Bhagwan , Lak Ram and Rameshwar in village Sultanpur | 359800 | 48/05.09.08/EE(Pr.) | M/s A.R. Entp. | 08.09.08 | P | 298007
4 | 2008-07-08 | 12.06.08 | Pdg brick floring in the lane Tarif Sri Bhagwan,Lekhram and Rameshwar in Village Sultqanpur Dabas | 341600
5 | 2008-07-08 | 12.06.08 | Pdg cc from Dayanand Dharamshala to Sat narayan house in Village Pooth Khurd | 230000 | 49/05.09.08/EE(Pr.) | M/s V.R. Const. | 08.09.08 | 24.03.09 | 194589
6 | 2008-07-15 | 16.06.08 | Pdg cc pav.and drain from Raj Singh house to Randhir house and Kartar Singh house to Mukhtyar Singh house in Village Boodanpur Majra Dabas in C-27/NZ | 491700 | 97/19.09.08/EE(M)-II | M/s Satish Const Co. | 29.09.08 | 16.03.09 | 404914
7 | 2008-07-15 | 16.06.08 | Pdg cc pav.from Satish house to Jaipal house in Jat Khore in C-27/NZ | 132400 | 105/26.09.08/EE(M)-II | M/s Atul Gupta | 10.10.08 | 27.11.08 | 108010
8 | 2008-07-29 | 09.07.08 | Pdg cc pav.from Mandir to Sardar house in Village Nangal Thakran in C-28/NZ | 499680 | 48/22.08.08/EE(M)-II | M/s Dharam Pal Gupta | 06.09.08 | 10.12.08 | 499536
9 | 2008-07-29 | 09.07.08 | Pdg cc pav.from Bridge to Deshraj house and along park in Village Nangal Thakran in C-28/NZ | 364088 | 47/22.08.08/EE(M)-II | M/s Vidya Const Co. | 25.08.08 | 20.10.08 | 363938
10 | 2008-07-29 | 09.07.08 | Pdg cc pav.and c/o o/s drain from Hari Singh house to Dalbir house in Village Bajitpur in C-28/NZ | 210800 | 96/19.09.08/EE(M)-I | M/s A.R. Entp. | 15.09.08 | 27.11.08 | 186281
11 | 2008-07-29 | 09.07.08 | Pdg cc pav.and c/o o/s drain from Pappu Shop to Prem house in Village Bawana in C-28/NZ | 425500 | 107/30.09.08/EE(M)-I | M/s Surender Kumar Verma | 08.10.08 | 30.12.08 | 353466
12 | 2008-07-29 | 09.07.08 | Pdg cc pav.and c/o o/s drain from Meer Singh house to Prakash house and side lane in Village Bawana in C-28/NZ | 434500 | 101/26.09.08/EE(M)-I | M/s Surender Kumar Verma | 04.10.08 | 31.12.08 | 366959
13 | 2008-07-29 | 09.07.08 | Pdg cc pav.and drain from Tek Chand house to Krishan house and side lane in Village Bawana in C-28/NZ | 383200 | 177/10.10.08/EE(M)-II | M/s Prem Bros. | 16.10.08 | 05.03.09 | 316588
14 | 2008-08-27 | 05.08.08 | Pdg cc pav.and drain from Tek Chand house to Mangeram house and Sukhvir house to Delhi road in Village Pooth Khurd in C-27/NZ | 99800 | 112/10.10.08/EE(M)-II | M/s Vidya Const Co. | 16.10.08 | 29.11.08 | 99652
15 | 2008-09-29 | 16.06.08 | Pdg cc pav. & drain from Rajinder Singh Joon house to Bijor park in village Pooth khurd w.no27 Narela | 254000 | 176/10.10.08/EE(M)-II | M/s Om Conmst Co. | 18.10.08 | 18.12.08 | 215198
16 | 2008-09-04 | 02.09.08 | Dev of lane by pdg b/f from main road to Randhir house in village Mangeshpur in Narela Zone | 199800 | 62/25.09.08/EE(M)-VI | M/s Bhardwaj Const Co. | 30.09.08 | 24.11.08 | 192788
17 | 2008-09-04 | 02.09.08 | Dev to lane by pdg b/f from Lakki house to Prem Patwari house in village Mangeshpur in narela | 199700 | 61/25.09.08/EE(M)-VI | M/s Shiv Narain | 30.09.08 | 24.11.08 | 193063
18 | 2008-09-04 | 02.09.08 | Dev of lane by pdg b/f from drain to Balwan house in village Mangeshpur in Narela Zone | 199700 | 60/25.09.08/EE(M)-VI | M/s Shiv Narain | 30.09.08 | 24.11.08 | 193745
19 | 2008-09-04 | 29.08.08 | Making easy spead breaker and culvet from bawana chowk to Bawana in C-28 Narela Zone | 191684 | 110/30.09.08/EE(M)-II | M/s Anand Mathur mpl Contractor | 04.10.08 | 20.12.08 | 191555
20 | 2008-09-04 | 29.08.08 | making easy spead benches and culvert from Rajiv Gandhi Stadium Auchandi Border in C-28 Narela Zone | 450000 | 111/30.09.08/EE(M)-II | M/s Raj Roop Mathur mpl Contractor | 04.10.08 | 21.12.08 | 449895
21 | 2008-10-06 | 17.09.08 | pdg lighting arrangement in village Bawana under AC-22 Narela Zone | 80000 | 275/04.02.09/EE(E)-II | M/s A.K. Elect. | 13.02.09 | 04.03.09 | 69364
22 | 2008-06-17 | 09.04.08 | Dev of lane from Rajvir Ramchander NAresh Nanak and Rambir by pdg cc and drain in village Katewara | 419919 | 38/22.08.08/EE(Pr.) | M/s D&G Const Co. | 22.10.08 | P | 416924
23 | 2008-06-17 | 09.04.08 | Dev of lane Prem chand Rampat Sukhbir Dharam Ishwar Mange and Sher singh by pdg cc pavment and drain in village Katewara | 314742 | 33/22.08.08/EE(Pr.) | M/s D&G Const Co. | 09.01.09 | 09.03.09 | 291183
24 | 2008-06-17 | 09.04.08 | Pdg cc and and c/o drain in lane Tek Chand and Ram kumar in village Nangal Thakran w.no.28 | 324998 | 32/22.08.08/EE(Pr.) | M/s D&G Const Co. | 29.08.08 | 29.12.08 | 319822
25 | 2008-06-17 | 09.04.08 | Pdg cc and and c/o drain in lane Dhare and Rohtas in in village Nangal Thakran w.no.28 | 383865 | 31/22.08.08/EE(Pr.) | M/s D&G Const Co. | 06.10.08 | P | 377191
26 | 2008-06-17 | 09.04.08 | Pdg cc pav and c/o drain from main road to Rajesh house in village Mangeshpur | 419985 | 46/03.09.08/EE(Pr.) | M/s Raj Roop Mathur mpl Contractor | 12.09.08 | 22.01.09 | 370946
27 | 2008-06-17 | 09.04.08 | Pdg cc pav and c/o drain in lane Jaswant house to Rajesh house and side lanes Raj Joginder Rampal Ajit in village Mangeshpur w.no.28/ | 396183 | 37/22.08.08/EE(Pr.) | M/s D&G Const Co. | 29.08.08 | 02.02.09 | 351052
28 | 2008-06-17 | 09.04.08 | Pdg cc pav and c/o drain in lane Dalip Hawa singh Ram phal and Jai chand in village Mangeshpur w.no.28/ | 295314 | 39/22.08.08/EE(Pr.) | M/s D&G Const Co. | 29.08.08 | 17.02.09 | 261117
29 | 2008-06-17 | 09.04.08 | Dev of side berms by Pdg RMC from transformer to Bhushan house and lane Ramphal in village Daryapur w.no.28/ | 442444 | 36/22.08.08/EE(Pr.) | M/s A.K. builders | 29.08.08 | 20.10.08 | 441363
30 | 2008-06-17 | 09.04.08 | Pdg cc pav and c/o drain in lane Sahib and Anup in village Daryapur w.no.28/ | 246994 | 35/22.08.08/EE(Pr.) | M/s D&G Const Co. | 27.08.08 | 15.10.08 | 246198
31 | 2008-06-17 | 09.04.08 | dev of road/lane by pdg RMC Ajit Ramchander Anil and Jagdish in village Chandpur w.no.28 | 453960 | 34/22.08.08/EE(Pr.) | M/s Anand Mathur mpl Contractor | 08.10.08 | 22.12.08 | 441884
32 | 2008-07-15 | 09.06.08 | C/o o/s drain from Hari Pradhan house to MC Pry School in village Harevli w.no.28 | 317167 | 59/05.09.08/EE(Pr.) | M/s D&G Const Co. | 11.09.08 | 12.12.08 | 315341
33 | 2008-07-15 | 09.06.08 | Pdg cc pavment from Dharam house to hari Pradhan house Ram Prasad house to Hari har house and side lane and Ganga Dutt wali gali in village harevali w.no.28 | 485177 | 60/05.09.08/EE(Pr.) | M/s Shyam Lal Gupta | 12.09.08 | 12.12.08 | 474308
34 | 2008-07-15 | 09.06.08 | Pdg cc pav from Manful house to Chadngi house Prabhu to Balbir house Bhim singh to Hari chand house and Run singh to khazana house in village Nangal Thakran w.no.28 | 361357 | 64/05.09.08/EE(Pr.) | M/s Shyam Lal Gupta | 15.09.08 | 12.12.08 | 359167
35 | 2008-07-15 | 09.06.08 | Pdg cc pav from Jai singh house to Pratap house and side lanes and chopal to Dharmvit=r house in village Nangal Thakran w.no.28 | 264373 | 61/05.09.08/EE(Pr.) | M/s Devender Kumar | 10.09.08 | 12.12.08 | 250088
36 | 2008-07-15 | 09.06.08 | Pdg cc pav from Ram kishan houase to chopal in village Bajitpur in w.no.28 | 251849 | 63/05.09.08/EE(Pr.) | M/s Devender Kumar | 11.09.08 | 13.12.08 | 231891
37 | 2008-07-15 | 09.06.08 | Pdg cc pav from Vijender house to Hari singh Baljit house to Anil house and Mandir to Mahavir wali gali in village Bajitpur in w.no.28 | 243299 | 62/05.09.08/EE(Pr.) | M/s Devender Kumar | 12.09.08 | 10.12.08 | 234393

## AC-54
S.No. | Date of Booking | Date of Consent | Name of Work | Amount Booked | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-06-06 | 29.05.08 | Pdg cc pav and O/S drain from Sh. Om Prakash house to Ram Phal house in Village Khera Khurd in w.no.3/Narela Zone | 578200 | 111/26.09.08/EE(M)-I | M/s Gupta Assos. | 07.11.08 | 22.01.09 | 477430
2 | 2008-07-21 | 08.05.08 | Pdg cc pav. from Pandit Mahender to Jai Bhagwan and krishan to om rao singh and sh. Kartar singh to Bake house in Naya Baans C-3 | 334300 | 94/23.09.08/EE(M)-I | M/s D&G Const. | 19.03.09 | 15.05.09 | 274198
3 | 2008-07-21 | 08.05.08 | C/o B/wall from Mukhtyar Singh to Surender house in Kherakalan C-3 | 399900 | 90/23.09.08/EE(M)-I | M/s Rakesh Kumar | 08.10.08 | 02.01.09 | 296879
4 | 2008-07-21 | 08.05.08 | C/o open surface drain from Tara Chand house (Harijan Chopal) to Railway crossing in Kherakalan C-3 | 486600 | 88/23.09.08/EE(M)-I | M/s Surender Kumar Verma | 30.10.08 | 17.12.08 | 413831
5 | 2008-07-21 | 08.05.08 | Pdg cc pav from Rajinder to Sushil Saini house and adj lane in village Holambi kalan C-3 | 378500 | 40/26.09.08/EE(M)-I | M/s D&G Const. | 10.12.08 | 05.01.09 | 311343
6 | 2008-07-21 | 08.05.08 | Pdg cc pav from Mata Chowk to Shri Bhagwan house in village Holambi kalan C-3 | 394700 | 109/26.09.08/EE(M)-I | M/s D&G Const. | 05.12.08 | 04.01.09 | 316712
7 | 2008-07-21 | 08.05.08 | Pdg cc pav in the lane of Shri. mahesh tyagi house in village Holambi kalan C-3 | 235000
8 | 2008-07-21 | 08.05.08 | Pdg cc pav in internal lane in Harijan Basti in Khera Khurd C-3 | 473500 | 108/26.09.08/EE(M)-I | M/s D&G Const. | 16.01.09 | 06.04.09 | 377809
9 | 2008-07-21 | 08.05.08 | Pdg cc pav and open surface drain from umeed singh to Jai Narain, Jile singh to Ajit, Suresh to Jairam and Ram singh Balmiki in Khera Khurd C-3 | 460900 | 105/26.09.08/EE(M)-I | M/s Khatri Const Co. | 07.10.08 | 26.06.09 | 370289
10 | 2008-07-21 | 08.05.08 | Pdg cc pav and open surface drain from Shri Raghuvir singh house to Chopal Raj singh to Basle in Holambi khurd C-3 | 186700 | 178/10.10.08/EE(M)-I | M/s Atul Gupta | 10.11.08 | 25.11.08 | 152678
11 | 2008-07-30 | 08.05.08 | Pdg cc pav and open surface drain from Raghuvir house to Dhamvir Son of Late Muktyar singh house in village Bakner in C-2 | 620000 | 76/19.09.08/EE(M)-I | M/s Shyam Lal Gupta | 20.09.08 | 13.12.08 | 518475
12 | 2008-07-30 | 08.05.08 | Pdg cc pav and open surface drain from Lampur road to Ramphal house landless cly. in village Bakner C-2 | 498800 | 78/19.09.08/EE(M)-I | M/s Khatri Const Co. | 30.09.08 | 27.12.08 | 398343
13 | 2008-07-30 | 08.05.08 | Pdg cc pav and open surface drain from Ramphal house Kartar singh plot and Balwan house to Ramkishan house in landless cly. in village Bakner C-2 | 479900 | 79/19.09.08/EE(M)-I | M/s Khatri Const Co. | 05.10.08 | 28.02.09 | 349297
14 | 2008-07-30 | 08.05.08 | Pdg cc pav and open surface drain from Hariram house to main lane and Lampur road to Ramchander house in landless cly. in village Bakner C-2 | 499000 | 80/19.09.08/EE(M)-I | M/s Khatri Const Co. | 05.10.08 | 28.02.09 | 379021
15 | 2008-07-30 | 08.05.08 | Pdg cc pav and open surface drain from Dharampal house to Lampur road in landless cly. in village | 493600 | 82/19.09.08/EE(M)-I | M/s Khatri Const Co. | 29.09.08 | 27.11.08 | 345033
16 | 2008-07-30 | 08.05.08 | Pdg cc pav and open surface drain in left out portion in landless cly. in village | 360000 | 81/19.09.08/EE(M)-I | M/s Khatri Const Co. | 24.09.09 | 28.02.09 | 271126
17 | 2008-07-30 | 08.05.08 | Pdg m/p from main Lampur road to both side higher Sec. School in village Bakner and side lane in viilage Bakner in C-2 Narela | 480000 | 75/19.09.08/EE(M)-I | M/s Satish Const Co. | 26.09.08 | 20.04.09 | 455083
18 | 2008-07-30 | 08.05.08 | Pdg cc pav and open surface drain from Chander bhan Khatri house to Via well in village Bakner C-2 | 497679 | 69/01.09.08/EE(M)-I | M/s Raj Assos. | 05.09.08 | P | 496622
19 | 2008-07-30 | 08.05.08 | Dev of lane by Pdg cc pav and open surface drain from Randhi house to back lane Surender house to Mai wala road and back lane in village Bakner C-2 | 499700 | 83/19.09.08/EE(M)-I | M/s Khatri Const Co. | 29.09.08 | 27.11.08 | 297475
20 | 2008-08-01 | 22.07.08 | Pdg cc pav and drain from Sandeep bhawan to Jagat Singh house and Karan Singh house to garden in village Ramjaan pur C-2 | 598200 | 101/26.09.08/EE(M)-I | M/s Shyam Lal Gupta | 02.10.08 | 30.03.09 | 488424
21 | 2008-08-01 | 22.07.08 | Pdg and laying b/p Surajbhan to Karamvir house infront of Chopal in Pachalla Pana in village Tajpur C-4 | 643300 | 97/26.09.08/EE(M)-I | M/s Rakesh Kumar | 10.10.08 | 20.12.08 | 589043
22 | 2008-08-01 | 22.07.08 | C/o drain from Chanderoop to Chothe house house in Panchalla Pana in village Tajpur in C-4 | 346300 | 99/26.09.08/EE(M)-I | M/s Atul Gupta | 08.10.08 | 28.11.08 | 289971
23 | 2008-08-01 | 22.07.08 | dev of lane by pdg cc pav darin from Rama to Prem Parkash to Lek Ram Kaptan Singh to Taken , Gyan house and its adj lanes in village Bakhtawarpur in C-4 | 599000 | 142/03.10.08/EE(M)-I | M/s A.K. Const Co. | 08.10.08 | 14.12.08 | 489932
24 | 2008-08-11 | 08.05.08 | C/o drain from park (Lampur road) in Bawana road in back lane of Swatantra nagar C-2 | 816900
25 | 2008-09-09 | 08.05.08 | Dev of lane by pdg B/P and OS drain from Joginder to Gowdown, Sunder to Ramphal and Ram kishan to Devi Singh house in village Harridpur in w.no. 4 Narela | 694600 | 312/09.01.09/EE(M)-I | M/s Shyam Lal Gupta | 15.01.09 | 30.03.09 | 588696
26 | 2008-10-08 | 08.05.08 | Dev of Lampur road (damaged portion) from Bakner railway xing to lampur road in C-2 Narela Zone | 499834 | 177/10.10.08/EE(M)-I | M/s A.R. Entp. | 13.10.08 | 17.12.08 | 499834
27 | 2008-07-21 | 08.05.08 | Pdg cc pavment and o/s suface drain from Sunder to Karan Singh house and Shri Nafe singh to Ajit singh house in Naya Baans in C-3 | 283000 | 112/26.09.08/EE(M)-I | M/s Kamal Const. | 30.10.08 | 20.01.09 | 233814