## Sheet1
Status Report of MLA, Sh. Ramakant Goswami (AC-66), 2008-09
S.No. | Date of Booking | Date of Consent | Name of Work | Amount booked | Work order no. with date i/c division | Name of agency | D.O.S | D.O.C | Expenditure | Present Position
1 | 2008-05-01 | 01.04.2008 | Dev of lane by pdg cc in lane no.1 Transit camp in Pandav nagar w.no. 150/KBZ | 199700 | 16/02.02.07/EE(M)-I | M/s Vikas Const. Co. | 2.05.08 | 24.12.08 | 199700 | Work Completed
2 | 2008-07-22 | 01.07.2008 | Dev of lane by pdg cc and drain from Katputly Colony flyover to JE store in Pandav Nagar in C-150/KBZ. | 498591 | 317/10.10.08/EE(M)-I | M/s S.P. Const. | 19.10.08 | 13.02.08 | 498517 | Work Completed
3 | 2008-05-01 | 01.04.08 | Dev of lane by pdg cc in lane no.2 Transit camp PAndav Nagar C-150/KBZ | 199400 | 18/13.05.08/EE(M)-I | M/s Sandeep Kapoor | 22.05.08 | 21.03.09 | 198912 | Work Completed
4 | 2008-05-01 | 01.04.08 | Dev of Dhobi Ghat by pdg cc in PAndav Nagar C-150/KBZ | 199600
5 | 2008-07-31 | 28.07.08 | C/o lanes and by lanes by pdg CC and drainage under Stair case D block in New Ranjeet nagar w.no.96/KBZ | 198000 | 305/10.10.08/EE(M)-I | M/s Sonu builders | 24.10.08 | 16.01.09 | 197843 | Work Completed
6 | 2008-08-12 | 28.07.08 | C/o lanes and by lanes by pdg CC and drainage in Munshi Ram Bagh in New Ranjeet nagar w.no.96/KBZ | 499000 | 308/10.10.08/EE(M)-I | M/s Nikhil builders | 20.10.08 | 18.01.09 | 498421 | Work Completed
7 | 2008-08-12 | 28.07.08 | C/o lanes pdg cc and drainage in D block in New Ranjeet nagar w.no.96/KBZ | 298000 | 306/10.10.08/EE(M)-I | M/s P.R. Const Co. | 19.10.08 | 19.01.09 | 297406 | Work Completed
8 | 2008-08-28 | 01.08.08 | C/O lanes and bylanes by pdg cc and drainage, D-Block in new Ranjit Ngr. C-96/KBZ | 410000 | 307/10.10.08/EE(M)-I | M/s Welcome Assos. | 19.10.08 | 02.01.09 | 409823 | Work Completed
9 | 2008-10-10 | 22.08.08 | C/o lane and by lanes of gali no.18B by pdg.CC pav. and drainage in Prem Nagar in C-94/KBZ. | 499000 | 324/13.10.08/EE(M)-I | M/s Kuldeep Singh | 24.01.08 | 09.01.09 | 499000 | Work Completed
10 | 2008-10-08 | 22.08.08 | C/o lane and by lanes of gali Sthanak wali and its adj.lanesand gali Shiv Nanak wali in Prem Nagar in C-94/KBZ. | 498000 | 329/13.10.08/EE(M)-I | M/s Sanjay builders | 24.10.08 | 19.01.09 | 498000 | Work Completed
11 | 2008-10-08 | 22.08.08 | C/o lane and by lanes of gali no.19B and C by pdg.CC pav.and drainage(upper side)in Prem Nagar C-94/KBZ. | 496818 | 325/03.10.08/EE(M)-I | M/s Deepak Const. Co. | 05.11.08 | 02.12.08 | 495467 | Work Completed
12 | 2008-10-08 | 22.08.08 | C/o lane and bylanes of gali no.20B(upper side)by pdg.CC and drainage in Prem Nagar in C-94/KBZ. | 497871 | 330/13.10.08/EE(M)-I | M/s Fabcon Engineers | 16.10.08 | 01.12.08 | 497034 | Work Completed
13 | 2008-10-08 | 22.08.08 | C/o lane and bylanes of gali no.22A,B by pdg.CC and drainage in Prem Nagar in C-94/KBZ. | 498000 | 326/13.10.08/EE(M)-I | M/s Aggarwal Assos. | 05.11.08 | 16.01.09 | 498000 | Work Completed
14 | 2008-10-08 | 22.08.08 | C/o gali from h.no.533 to gali no.1 by pdg.CC pav.and drainage in Prem Nagar in C-94/KBZ. | 498677 | 333/13.10.08/EE(M)-I | M/s Sarthak Const Co. | 30.10.08 | 05.01.09 | 497151 | Work Completed
15 | 2008-10-08 | 22.08.08 | C/o lane and bylanes along h.no.2126/2N/78 in gali no.4 and gali no.5 by pdg.CCand drainge in Prem Nagar in C-94/KBZ. | 499000 | 331/13.10.08/EE(M)-I | M/s Fren Const Co. | 30.10.08 | 29.12.08 | 499000 | Work Completed
16 | 2008-10-08 | 22.08.08 | C/o B/Wall of park in gali no.23 and Tikona park in Prem Nagar in C-94/KBZ. | 298800 | 353/16.12.08/EE(M)-I | M/s Ragini | 16.01.09 | 20.03.09 | 298007 | Work Completed
17 | 2008-10-08 | 22.08.08 | C/o lane and bylanes of gali no.23 by pdg.CC and drainge in Prem Nagar in C-94/KBZ. | 497000 | 332/13.10.08/EE(M)-I | M/s Chinmay Const Co. | 24.10.08 | 25.11.08 | 497000 | Work Completed
18 | 2008-10-08 | 22.08.08 | C/o lane and by lanes of gali no.9 & 10 (Upper site ) by pdg.CC and drainge in Prem Nagar in C-94/KBZ. | 497000 | 327/13.10.08/EE(M)-I | M/s J.D. Const Co. | 24.10.08 | 02.01.09 | 497000 | Work Completed
19 | 2008-10-08 | 22.08.08 | C/o gali no.15B called Mandir wali(upper side) by pdg.CC pav.and drainage in Prem Nagar in C-94/KBZ. | 498755 | 328/13.10.08/EE(M)-I | M/s Jolly Const Co. | 05.11.08 | 17.10.08 | 497049 | Work Completed
20 | 2008-10-08 | 01.09.08 | C/o lane and bylanes by pdg.CC and drainage from V-1to V-14 inWest Patel Nagar in C-94/KBZ. | 199800 | 349/16.12.08/EE(M)-I | M/s Balaji Const. | 16.01.09 | 17.02.09 | 198320 | Work Completed
21 | 2008-10-08 | 01.09.08 | C/o lane and bylanes by pdg. CC and drainage from 29/113 to 29/158 in West Patel Nagar in C-94/KBZ. | 498000 | 354/16.12.08/EE(M)-I | M/s Naresh Kumar | 05.01.09 | 25.02.09 | 497522 | Work Completed
22 | 2008-10-08 | 01.09.08 | C/O back courtyard and lanes along 28/8 to28/16 to 28/128 in West Patel Nagar in C-94/KBZ. | 499000 | 358/16.12.08/EE(M)-I | M/s Sanjay builders | 05.01.09 | 20.03.09 | 499000 | Work Completed
23 | 2008-10-08 | 01.09.08 | C/o side lane by pdg.CC and drainage along 34/1 to 34/9 in West Patel Nagar in C-94/KBZ. | 198900 | 359/16.12.08/EE(M)-I | M/s Rakesh Entp. | 26.12.08 | 20.03.09 | 198900 | Work Completed
24 | 2008-10-08 | 01.09.08 | C/o back courtyard of B-115 and B-133 by pdg.CC and drainage in West Patel Nagar in C-94/KBZ. | 498000 | 348/16.12.08/EE(M)-I | M/s S. Gupta Const. Co. | 05.01.09 | 29.01.09 | 497492 | Work Completed
25 | 2008-10-08 | 01.09.08 | C/o road along B-143 to B-255 along Nallah by pdg. CC and drainage in West Patel Nagar in C-94/KBZ. | 499000 | 406/24.12.08/EE(M)-I | M/s Jolly Const Co. | 16.01.09 | 12.02.09 | 499000 | Work Completed
26 | 2008-10-08 | 01.09.08 | C/o side lane of 29/49 to 29/54 by pdg. CC and drainage in West Patel Nagar in C-94/KBZ. | 198000 | 407/24.12.08/EE(M)-I | M/s Shalu builders | 16.01.09 | 30.03.09 | 197800 | Work Completed
27 | 2008-10-08 | 01.09.08 | C/o side lane from 32/1 to 32/9 by pdg. CC and drainage in West Patel Nagar in C-94/KBZ. | 199000 | 351/16.12.08/EE(M)-I | M/s S.P. Entp. | 05.01.09 | 23.03.09 | 198383 | Work Completed
28 | 2008-10-08 | 01.09.08 | C/o lane and bylanes by pdg. CC and drainage along 28/89 to 28/95,28/105 to 28/98 in West Patel Nagar in C-94/KBZ. | 498000 | 357/16.12.08/EE(M)-I | M/s Fabcon Engineers | 22.12.08 | 11.02.09 | 497984 | Work Completed
29 | 2008-10-08 | 01.09.08 | C/o back courtyard of A-Block West Patel Nagar by pdg. CC and drainage in West Patel Nagar in C-94/KBZ. | 499000 | 360/16.12.08/EE(M)-I | M/s S.K. Aggarwal | 16.01.09 | 28.02.09 | 498520 | Work Completed
30 | 2008-10-08 | 01.09.08 | C/o back courtyard of B-39 and B-215 by pdg. CC and draiange in West Patel Nagar in C-94/KBZ. | 496000 | 356/16.12.08/EE(M)-I | M/s Sh. Shanker Gupta | 05.01.09 | 29.01.09 | 496000 | Work Completed
31 | 2008-06-20 | 28.05.08 | C/Olane and by lanes by pdg. RMC and SW drainage from 8A/3 to8A/60 in WEA in C-149/KBZ. | 498300 | 229/23.07.08/EE(M)-I | M/s Vijay Kumar | 30.07.08 | 22.01.09 | 498040 | Work Completed
32 | 2008-06-20 | 28.05.08 | C/O of lane and by lanes by pdg. RMC and drainage from 8A/36 to8A/61 in WEA in C-149/KBZ | 499100 | 224/23.07.08/EE(M)-I | M/s Unique Const. | 30.07.08 | 17.12.08 | 497931 | Work Completed
33 | 2008-06-20 | 28.05.08 | Pdg. C.C.pav. and SW drainage surrounding of park in 14A Block in WEA inC-149/KBZ | 195844 | 225/23.07.08/EE(M)-I | M/s Tajinder Const. Co. | 30.07.08 | 26.12.08 | 195736 | Work Completed
34 | 2008-06-20 | 28.05.08 | C/O of lane and by lanes by pdg.RMC and drainage from 14A/5 to park in WEA in C-149/KBZ | 497600 | 227/23.07.08/EE(M)-I | M/s Sunil Kumar Gulati | 01.08.08 | 21.10.08 | 494628 | Work Completed
35 | 2008-06-20 | 28.05.08 | C/O of lane and by lanes by pdg. RMC and SW drainage from 9A/2 to 9A/47 in WEA in C-149/KBZ. | 498500 | 223/23.07.08/EE(M)-I | M/s Y.S Engineer & Builders | 29.07.08 | 20.03.09 | 497323 | Work Completed
36 | 2008-06-20 | 28.05.08 | C/O of lane and by lanes by pdg. RMC and drainage from 14A/74 to14A/80 WEA in C-149 in KBZ. | 499200 | 228/23.07.08/EE(M)-I | M/s S.K.Verma | 29.07.08 | 28.10.08 | 492501 | Work Completed
37 | 2008-06-20 | 28.05.08 | C/O of lane and by lanes bypdg. RMC and SW drainage from 9A/31 to9A/48 in WEA in C-149/KBZ. | 497800 | 230/23.07.08/EE(M)-I | M/s A & N Bros. | 09.08.08 | 06.04.08 | 496407 | Work in Prog.
38 | 2008-06-20 | 28.05.08 | C/O lanes and bylanes by pdg RMC and SW drainage from 9A/8 to 9A/79 in WEA in C-149/KBZ | 498900 | 279/21.08.08/EE(M)-I | M/s Manchanda Const | 29.08.08 | 23.03.09 | 497020 | Work Completed
39 | 2008-06-20 | 28.05.08 | C/O lanes And bylanes by pdg RMC and SW drainage from 9A/24 to 9A/89 in WEA in C-149/KBZ | 497700 | 231/23.07.08/EE(M)-I | M/s Sanjay builders | 29.07.08 | 02.01.09 | 495792 | Work Completed
40 | 2008-05-28 | 26.05.08 | C/o lanes and by lanes by pdg cc and drainage near Sunil Singh and Jile Singh house in gali no. 14 and 12 (Lower Side) in Prem nanage -94/KBZ | 499365 | 112/30.06.08/EE(M)-I | M/s S. Gupta Const Co. | 21.07.08 | 29.08.08 | 499062 | Work Completed
41 | 2008-05-28 | 26.05.08 | C/o of lane and by lanes by pdg cc and drainage near Shri. PAndit ji house in gali no. 16B Prem nagar C-94/KBZ | 499821 | 122/30.06.08/EE(M)-I | M/s Chinmay Const Co. | 21.07.08 | 27.08.08 | 499350 | Work Completed
42 | 2008-05-01 | 26.05.08 | Dev of lane by pdg. cc near Temple in DDA flat Padav nagar w.no. 150/KBZ | 199500 | 14/13.05.08/EE(M)-I | M/s Nikhil builders | 22.05.08 | 20.08.08 | 199128 | Work Completed
43 | 2008-06-20 | 26.05.08 | C/O lanes and bylanes by pdg cc and drianage near Vermaji house in gali no.15 in Prem ngr.C-94/KBZ | 498304 | 106/30.06.08/EE(M)-I | M/s Naresh Kumar | 21.07.08 | 03.10.08 | 497264 | Work Completed
44 | 2008-06-20 | 26.05.08 | C/O lanes and bylanes by pdg cc and drainage near Sh. Narai Mitter house in gali no.17 Prem Ngr. C-94/KBZ | 499463 | 111/30.06.08/EE(M)-I | M/s J.S. Const. | 01.08.08 | 05.05.09 | 498993 | Work Completed
45 | 2008-06-20 | 26.05.08 | C/O lanes and bylanes by pdg cc and drainage near Sh. Guptaji house in gali no.19 Prem Ngr. C-94/KBZ | 498417 | 114/30.06.08/EE(M)-I | M/s Sanjay builders | 05.07.08 | 02.09.08 | 497551 | Work Completed
46 | 2008-06-20 | 26.05.08 | C/O lanes and bylanes by pdg cc and drainage near Smt. Hemlata house in gali no.17B Prem Ngr. C-94/KBZ | 499413 | 117/30.06.08/EE(M)-I | M/s Vijay Kumar | 25.07.08 | 30.01.09 | 499222 | Work Completed
47 | 2008-06-20 | 26.05.08 | C/O lanes and bylanes by pdg cc and drainage near Sh. Surender Giri house in gali no.21 Prem Ngr. C-94/KBZ | 496045 | 118/30.06.08/EE(M)-I | M/s Sunil Kumar Gulati | 08.07.08 | 18.10.08 | 496045 | Work Completed
48 | 2008-06-20 | 26.05.08 | C/O lanes and bylanes by pdg cc and drainage near Sh. Ram Lal Thakur house in gali no.20 Prem Ngr. C-94/KBZ | 497890 | 107/30.06.08/EE(M)-I | M/s Sarthak Const Co. | 24.07.08 | 06.08.08 | 497349 | Work Completed
49 | 2008-06-20 | 26.05.08 | C/O lanes and bylanes by pdg cc and drainage near Sh. Rajesh Kaushik house in gali no.19 Prem Ngr. C-94/KBZ | 499734 | 115/30.06.08/EE(M)-I | M/s Shiv Shanker Gupta | 21.07.08 | 28.08.08 | 499688 | Work Completed
50 | 2008-06-20 | 26.05.08 | C/O lanes and bylanes by pdg cc and drainage near Sh.Natthu Ram And Prema house in gali no.18 Prem Ngr. C-94/KBZ | 496132 | 121/30.06.08/EE(M)-I | M/s Fabcon Engineers | 21.07.08 | 29.08.08 | 496132 | Work Completed
51 | 2008-05-01 | 01.04.08 | Dev of lane by pdg cc near Mother Dairy Booth in Trasit Camp in PAndav NAgar w.no. 150/KBZ | 199300 | 15/13.05.08/EE(M)-I | M/s Y.S Engineer & Builders | 22.05.08 | 26.05.09 | 198806 | Work Completed
|  |  |  | 21630240 |  |  |  |  | 21396219

## Sheet2
Status Report of MLA, Sh. P.C. Yogi (AC-67), 2008-09
S.No. | Date of Booking | Date of Consent | Name of Work | Amount booked | Work order no. with date i/c division | Name of agency | D.O.S | D.O.C | Expenditure | Remarks
1 | 2008-06-20 | 01.05.08 | Dev. of lane by pdg. CC and drain near Shiv Mandir in village in C-152/KBZ | 199268 | 253/12.08.08/EE(M)-I | M/s Pankaj Udyog | 12.08.08 | 10.09.08 | 199268 | Work Completed
2 | 2008-06-20 | 19.05.08 | C/O walkway in Tulsi Garden park G-block Naraina vihar in C-152/KBZ | 210007 | 232/23.07.08/EE(M)-I | M/s Maa Bhoomika Entp. | 01.08.08 | 30.01.09 | 208488 | Work Completed
3 | 2008-07-09 | 23.06.08 | Dev. of back lane and road berms from E-82 to E-46 in Naraina Vihar in C-152/KBZ. | 373795 | 297/21.08.08/EE(M)-I | M/S Chimmy Const. Co. | 31.08.08 | 08.11.08 | 373371 | Work Completed
4 | 2008-09-22 | 23.08.08 | Pdg RMC and drainage on Square behind R-888 in R-Block Rajender Ngr.in C-149/KBZ | 298000 | 365/16.12.08/EE(M)-I | M/S Nikhil Builders | 22.12.08 | 23.03.09 | 298000 | Work Completed
5 | 2008-09-22 | 23.08.08 | Imp to lane and bylane of 12-Block from 12/5 to 112/36 in Old Rajender Ngr.in C-149/KBZ | 226000 | 368/16.12.08/EE(M)-I | M/s Herry Const. Co. | 20.12.08 | 19.01.09 | 226000 | Work Completed
6 | 2008-09-22 | 23.08.08 | Imp to lane and bylane by RMC and Drain along M.C.Pry.School New Rajender Ngr.to C-103 in New Rajender Ngr.in C-149/KBZ | 499000 | 364/16.12.08/EE(M)-I | M/s Rakesh Kumar Gupta | 20.12.08 | 02.02.09 | 498964 | Work Completed
7 | 2008-09-22 | 23.08.08 | Imp to back lane and square F-272 in F- Block in New Rajender Ngr.in C-149/KBZ | 499800 | 336/13.10.08/EE(M)-I | M/S K-3 Infrastructure | 18.10.08 | 21.01.09 | 499278 | Work Completed
8 | 2008-09-22 | 23.08.08 | P/F Grills on Square and Footpath near Water Tank in Old Rajender Ngr.in C-149/KBZ | 335000 | 445/02.01.09/EE(M)-I | M/S Sanjay Builders | 09.01.09 | 06.05.09 | 334577 | Work Completed
9 | 2008-09-22 | 23.08.08 | Imp to back lane and side lanes from J-361 to DDA Mkt.in FA-Block in New Rajender Ngr.in C-149/KBZ | 498000 | 363/16.12.08/EE(M)-I | M/S Manoj Kumar Bhatia | 20.12.08 | 27.01.09 | 497284 | Work Completed
10 | 2008-09-22 | 23.08.08 | Pdg Storm Water drain to berms from R-710 to R-738 in R-Block in C-149/KBZ | 497600 | 444/02.01.09/EE(M)-I | M/S Manchada Const. | 07.01.09 | 14.02.09 | 497127 | Work Completed
11 | 2008-09-22 | 23.08.08 | Imp to lanes between J-396 to J-397 in J-Block New Rajender Ngr. in C-149/KBZ | 195000 | 425/14.12.08/EE(M)-I | M/S Vijay Kumar | 01.01.09 | 09.04.09 | 194868 | Work Completed
12 | 2008-09-22 | 23.08.08 | Dev of Walkway of Hare Krishna Mandir Park in J-Block New Rajender Ngr. in C-149/KBZ | 240300 | 385/18.12.08/EE(M)-I | M/S Unique Const.Co. | 25.12.08 | 20.02.09 | 240300 | Work Completed
13 | 2008-09-22 | 23.08.08 | Dev of Park by grit wash and grill near DMS Booth in D/S in New Rajender Ngr. in C-149/KBZ | 219000 | 446/02.01.09/EE(M)-I | M/S Manchada Const. | 05.01.09 | 16.02.09 | 218648 | Work Completed
14 | 2008-09-25 | 03.08.08 | Pdg dense carpet surfacing atinterval roads in EF,EA,RA Block in Inderpuri C-151/KBZ (from EF-1R to P.S. Inderpuri,A-1/146 to EA-34,RA-44 to RB-6,EA-101 to WZ-256 | 766900
15 | 2008-09-25 | 28.07.08 | Pdg dense carpet surfacing at interval roads in B,A-1 and EA-1/1 Block in Inderpuri C-151/KBZ (from A-1/148 to EA-1/30, EA-1/30 to EA-1/34,EA-1/67 to B-65,A-20 to EA-61 | 939100
16 | 2008-09-25 | 11.08.08 | Pdg dense carpet surfacing at interval roads in A,EA, Block in Inderpuri C-151/KBZ (from A-63 to EA-100,RA-32 to EA-48 | 717850
17 | 2008-09-25 | 04.08.08 | Pdg dense carpet surfacing at interval roads in RA and B Block in Inderpuri C-151/KBZ (from B-80 to R-46,EA-1/65 to B-65 | 760500
18 | 2008-04-24 | 22.04.08 | Pdg drainage and RMC of lane from EA-101 to EA-107 in Inderpuri C-151/KBZ | 387796 | 71/18.06.08/EE(M)-I | M/s Pankaj Const. | 02.07.08 | 12.09.08 | 387796 | Work Completed
19 | 2008-04-24 | 22.04.08 | Pdg drainage and RMC of lane from EA-108 to EA-114 in Inderpuri C-151/KBZ | 388541 | 53/05.06.08/EE(M)-I | M/s Pankaj Const. | 08.07.08 | 10.09.08 | 378452 | Work Completed
20 | 2008-04-24 | 22.04.08 | Pdg drainage and RMC of lane from EF-1R to EF-9R in Inderpuri C-151/KBZ | 240155 | 72/18.06.08/EE(M)-I | M/s Pankaj Const. | 04.07.08 | 20.09.08 | 239371 | Work Completed
21 | 2008-04-24 | 22.04.08 | Pdg drainage and RMC of lane from EG-31 to EG-49 and EF-1 to EF-10 in Inderpuri C-151/KBZ | 309324 | 49/05.06.08/EE(M)-I | M/s Pankaj Const. | 07.07.08 | 12.09.08 | 304571 | Work Completed
22 | 2008-09-25 | 01.05.08 | Pdg RMC from h.no. RB-1 to RB-8 in Inderpuri C-151/KBZ | 485500 | 319/10.10.08/EE(M)-I | M/S Shah Builders | 23.10.08 | 14.01.09 | 484941 | Work Completed
23 | 2008-09-25 | 01.05.08 | Dev of footpath and side berms by pdg cc and drainage from EB-4 to EA-1/78 in Inderpuri in C-151/KBZ | 456200 | 322/10.10.08/EE(M)-I | M/S Sehgal Bros. | 24.10.08 | 19.01.09 | 450997 | Work Completed
24 | 2008-06-20 | 19.05.08 | Dev of open space and bylanes infront of I-290 in Naraina Vihas in C-152/KBZ | 406806 | 164/14.07.08/EE(M)-I | M/s Herry Const. Co. | 24.07.08 | 08.10.08 | 406806 | Work Completed
25 | 2008-06-20 | 19.05.08 | Dev of lane by pdg cc from I-84 to I-91 in Naraina Vihar C-152/KBZ | 412943 | 163/14.07.08/EE(M)-I | M/s Tyagi Assos. | 24.07.08 | 23.10.08 | 412943 | Work Completed
26 | 2008-06-20 | 19.05.08 | Dev of lane and bylanes from WZ-358 to WZ-344 in Naraina Vihar C-152/KBZ | 406806 | 165/14.07.08/EE(M)-I | M/s Maa Bhoomika Entp. | 23.07.08 | 19.01.09 | 406099 | Work Completed
27 | 2008-06-20 | 19.05.08 | Dev of lane by pdg cc from WZ-873 near Apna Bazar to WZ-884C in Naraina Vill. C-152/KBZ | 406806 | 264/12.08.08/EE(M)-I | M/s Hariash Kumar | 21.08.08 | 20.01.09 | 404787 | Work Completed
28 | 2008-06-20 | 19.05.08 | Dev of lane and by lanes adj to h.no.WZ-583 in Naraina Vill. in C-152/KBZ | 199649 | 162/14.07.08/EE(M)-I | M/s S.P. Entp. | 18.07.08 | 19.09.08 | 199649 | Work Completed
29 | 2008-06-20 | 19.05.08 | Dev of open space in DDA Flats H-Block Naraina Vihar near Railway Line in C-152/KBZ | 199649 | 202/16.07.08/EE(M)-I | M/s Pankaj Udyog | 17.07.08 | 01.09.08 | 199331 | Work Completed
30 | 2008-06-20 | 19.05.08 | Dev of lane by pdg cc from D-45 to Tagore Public School in Naraina vihar C-152/KBZ | 460648 | 294/21.07.08/EE(M)-I | M/s Fabcon Engineers | 31.08.08 | 08.11.08 | 460345 | Work Completed
31 | 2008-06-20 | 19.05.08 | Dev of park opp. B-108 Naraina Vihar C-152/KBZ | 199906 | 203/16.06.08/EE(M)-I | M/s Tanwar Const Co. | 28.07.08 | 19.01.09 | 199097 | Work Completed
32 | 2008-06-20 | 19.05.08 | Dev of road berms from h.no.B-110 to B-130 in Naraina Vihar C-152/KBZ | 199624 | 268/12.08.08/EE(M)-I | M/s R.K. builders | 22.08.08 | 21.11.08 | 199624 | Work Completed
33 | 2008-06-20 | 19.05.08 | Dev of road berms from h.no.B-27 to B-43 in Naraina Vihar C-152/KBZ | 197170 | 167/14.07.08/EE(M)-I | M/s Naresh Entp. | 23.07.08 | 05.11.08 | 196853 | Work Completed
34 | 2008-06-20 | 19.05.08 | Dev of lane and by lanes from h.no.WZ-429A to chintu Park in Naraina vill. C-152/KBZ | 199649
35 | 2008-06-20 | 19.05.08 | Dev of Footpath and road berms from Gurudwara to B-19 in Naraina vihar c-152/KBZ | 499602 | 299/21.08.08/EE(M)-I | M/s Shiv Shanker Gupta | 01.09.08 | 29.11.08 | 499128 | Work Completed
36 | 2008-06-20 | 19.05.08 | Dev of lane by pdg cc from WZ-415B to WZ-403 in Naraina Vihar C-152/KBZ | 406806 | 199/16.07.08/EE(M)-I | M/s Tyagi Assos. | 25.07.08 | 22.12.08 | 406806 | Work Completed
37 | 2008-06-20 | 19.05.08 | Dev of lane by psdg cc from WZ-429A to WZ-430E in NAraina Vihar c-152/KBZ | 400669 | 265/12.08.08/EE(M)-I | M/s Rakesh Kumar Gupta | 18.08.08 | 21.11.08 | 400315 | Work Completed
38 | 2008-06-20 | 19.05.08 | Dev of road berms along the B/Wall of park opp. factory no.B-246 to B-248 in Naraina Indl. Area Ph-1 in C-152/KBZ | 199624 | 200/16.07.08/EE(M)-I | M/s Pappu seth | 26.07.08 | 18.12.08 | 199618 | Work Completed
39 | 2008-06-20 | 19.05.08 | Dev of opev space and road berms by pdg cc at Dhobi Ghat in C-Block Naraina Vihar C-152/KBZ | 199649 | 166/14.07.08/EE(M)-I | M/s R.K. builders | 22.10.08 | 05.11.08 | 199601 | Work Completed
40 | 2008-06-20 | 19.05.08 | Dev to open space near Community Center C-Block Naraina Vihar in C-152/KBZ | 434095 | 267/12.08.08/EE(M)-I | M/s S.Gupta Const Co. | 21.08.08 | 30.01.09 | 434059 | Work Completed
41 | 2008-06-20 | 19.05.08 | Dev to Walkway in Sita Mata Park in R-Block New Rajender Ngr. C-149/KBZ | 473300 | 222/23.07.08/EE(M)-I | M/s Vikas Const Co. | 29.07.08 | 16.12.08 | 472589 | Work Completed
42 | 2008-06-20 | 19.05.08 | Dev of gali from Bazar Marg 4A-1 to Amrit Sarpal Marg by RMC and drianage in Old rajender Ngr. C-149/KBZ | 465600 | 226/23.07.08/EE(M)-I | M/s R.P. Aggarwal | 27.07.08 | 15.10.08 | 465192 | Work Completed
43 | 2008-05-27 | 01.05.08 | Dev of lane by pdg cc and drain near WZ-4 in village Dasgherah C-150/KBZ | 199670 | 151/14.07.08/EE(M)-I | M/s Jolly Const. | 23.07.08 | 22.10.08 | 199670 | Work Completed
44 | 2008-05-27 | 01.05.08 | Dev of lane by pdg cc and druian near WZ-139 in village Dasghera h C-150/KBZ | 199240 | 144/14.07.08/EE(M)-I | M/s Kapoor Bros. | 24.07.08 | 20.10.08 | 199240 | Work Completed
45 | 2008-05-27 | 01.05.08 | Dev of lane by pdg cc and drain near WZ-39 in Village Dasgherha C-150/KBZ | 199730 | 183/16.07.08/EE(M)-I | M/s Amit builders | 28.07.08 | 06.10.08 | 199137 | Work Completed
46 | 2008-06-20 | 01.05.08 | Dev of lane by pdg cc and drian near Dispensary in Vill. Dasghara in C-150/KBZ | 199800 | 147/14.07.08/EE(M)-I | M/s S.K. Entp. | 21.07.08 | 09.09.08 | 199800 | Work Completed
47 | 2008-06-20 | 01.05.08 | Dev of lane by pdg cc and drian near WZ-108 in Vill. Todapur in C-150/KBZ | 498900 | 180/16.07.08/EE(M)-I | M/S Bunty Builders | 25.07.08 | 15.09.08 | 498900 | Work Completed
48 | 2008-06-20 | 01.05.08 | Dev of lane by pdg cc and drian near WZ-121 in Vill. Todapur in C-150/KBZ | 199500 | 150/14.07.08/EE(M)-I | M/S Raghav Consts. | 11.08.08 | 18.10.08 | 199168 | Work Completed
49 | 2008-06-20 | 01.05.08 | Dev of lane by pdg cc and drian near WZ-110 in Vill. Dasghara in C-150/KBZ | 199600 | 145/14.07.08/EE(M)-I | M/S Sunil Kumar Gulati | 23.07.08 | 22.10.08 | 199117 | Work Completed
50 | 2008-06-20 | 01.05.08 | Dev of lane by pdg cc and drian near Police Beat Box in Vill. Dasghara in C-150/KBZ | 495900 | 149/14.07.08/EE(M)-I | M/S MK Verma | 21.07.08 | 22.10.08 | 495542 | Work Completed
51 | 2008-06-20 | 01.05.08 | Dev of lane by pdg cc and drian near WZ-78 in Vill. Todapur in C-150/KBZ | 199700 | 184/16.07.08/EE(M)-I | M/S Tajinder Const.Co. | 25.07.08 | 2.10.08 | 199700 | Work Completed
52 | 2008-06-20 | 05.05.08 | Dev of footpath and lane by cc and drainage from h.no.A-84 to Hanuman mandir in Inderpuri C-151/KBZ | 198900 | 260/12.08.08/EE(M)-I | M/S Guru Kirpa Const. Co. | 01.09.08 | 19.11.08 | 197678 | Work Completed
53 | 2008-06-20 | 05.05.08 | Dev of side bermas from h.no. R-19 to C-104 in Inderpuri C-151/KBZ | 246700 | 189/16.07.08/EE(M)-I | M/S Ved Pal Bhatia | 17.07.08 | 24.11.08 | 245957 | Work Completed
54 | 2008-06-20 | 05.05.08 | Pdg cc and drainagr from h.no.EA-100 to EA-49 in Inderpuri C-151/KBZ | 409600 | 160/14.07.08/EE(M)-I | M/S SK Verma | 21.07.08 | 22.10.08 | 404054 | Work Completed
55 | 2008-06-20 | 05.05.08 | Dev of back lane and bylanes by pdg cc and drainage from h.no.RB-1 to RB-6 in Inderpuri C-151/KBZ | 285480 | 198/16.07.08/EE(M)-I | M/S Unique Const.Co. | 24.07.08 | 20.11.08 | 284964 | Work Completed
56 | 2008-06-20 | 05.05.08 | Dev of footpath and side berms by pdg cc and chequerred tiles from R-5 to C-114 in Inderpuri C-151/KBZ | 311300 | 158/14.07.08/EE(M)-I | M/S Nikhil Builders | 23.07.08 | 20.11.08 | 310899 | Work Completed
|  |  |  | 19955657 |  |  |  |  | 16528969

## Sheet4
Status Report of MLA, Sh. Rajesh Lilothia (AC-70), 2008-09
S.No. | Date of Booking | Date of consent | Name of Work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount Verified | Present Position
1 | 2008-05-27 | 14.05.08 | Pdg drainage and cc from h.no.1762 to 1766 and adj near Main New Rohtak Road in Than Singh Ngr. C-95/KBZ | 193877 | 72/25.06.08/EE(M)-II | M/s Rakesh Kr. Gupta | 04.07.08 | 29.10.08 | 190031 | Work Completed
2 | 2008-05-27 | 14.05.08 | Pdg cc and drainage system from h.no.725/3 to 723 and adj in gali no.3,Panjabi Basti in Thansingh Ngr C-95/KBZ | 199000 | 98/25.06.08/EE(M)-II | M/s Narender Singh Dhanker | 04.07.08 | 15.10.08 | 198584 | Work Completed
3 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from h.no.713/4 to 713/9,713/10 to 707/13,713/13 to 715/3 and adj in gali no.5 in Panjabi Basti Yhansingh Ngr.C-95/KBZ | 199921 | 66/25.06.08/EE(M)-II | M/s SP Const. | 04.07.08 | 16.02.09 | 199830 | Work Completed
4 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from h.no.721/5 to 721/2 near h.no.720 and adj in gali no.5 Panjabi BAsti Thansingh Ngr C-95/KBZ | 198000 | 67/25.06.08/EE(M)-II | M/s Deepak Const.Co. | 04.07.08 | 15.04.09 | 198000 | Work Completed
5 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from D-124 to 2606 and adj in Baljit ngr C-93/KBZ | 186500 | 93/25.06.08/EE(M)-II | M/s Markanda Const. | 25.06.08 | 15.12.08 | 186319 | Work Completed
6 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from BNB-1083 to T-634/A-7,WT-634/15F and adj gali in B aljit Ngr C-93/KBZ | 198660 | 88/25.06.08/EE(M)-II | M/s Tania Const. | 02.07.08 | 01.12.08 | 198395 | Work Completed
7 | 2008-05-27 | 14.05.08 | C/O B/Wall and gate in Sanjay Park in Baljit Ngr In C-93/KBZ | 188580 | 74/25.06.08/EE(M)-II | M/s SK Ent. | 04.07.08 | 03.10.08 | 188270 | Work Completed
8 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from h.no.D-101 to D-217 and adj in Baljit Ngr C-93/KBZ | 192000 | 69/25.06.08/EE(M)-II | M/s SP Ent. | 04.07.08 | 22.01.09 | 191960 | Work Completed
9 | 2008-05-27 | 14.05.08 | Pdg drainage and cc from T-667,T-556,BNB 2152 and adj lane in Baljit Ngr C-93/KBZ | 196600 | 99/25.06.08/EE(M)-II | M/S Balaji Const.Co. | 04.07.08 | 15.09.08 | 196350 | Work Completed
10 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from h.no.BNB-2694 to BNB-2610 and adj near road no.22 in Baljit Ngr C-93/KBZ | 186000 | 68/25.06.08/EE(M)-II | M/s Harish Kr. | 04.07.08 | 02.10.08 | 186000 | Work Completed
11 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from h.no.2550,T-650/L4E,T-2606 and T-2591/A-i and adj in Baljit Ngr C-93/KBZ | 196700 | 91/25.06.08/EE(M)-II | M/s Pappu Seth | 04.07.08 | 26.09.08 | 196620 | Work Completed
12 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from h.no.T-2591/A-1,T-2575/C,T-2564 andT-2574 and adj lane in Baljit Ngr C-93/KBZ | 197550 | 90/25.06.08/EE(M)-II | M/s Harpreet Arora | 04.07.08 | 25.09.08 | 197550 | Work Completed
13 | 2008-08-29 | 18.08.09 | P/L drainage system and cc floring in gali no.5 Panjabi Basti Gulshan Chowk in C-94/KBZ | 401500 | 337/13.10.08/EE(M)-II | M/s Bajaj Const.Co. | 20.10.08 | 02.04.09 | 396919 | Work Completed
14 | 2008-08-29 | 18.08.09 | P/L drainage system and cc floring in gali no.3 Panjabi Basti Gulshan Chowk in C-94/KBZ | 410000 | 333/13.10.08/EE(M)-II | M/s RP Aggarwal | 23.10.08 | 30.12.08 | 406044 | Work Completed
15 | 2008-08-29 | 18.08.09 | P/L drainage system and cc floring in gali no.4 Panjabi Basti near Gulshan Chowk in Baljeet Ngr.in C-94/KBZ | 363300 | 332/13.10.08/EE(M)-II | M/s Vikas & Co. | 22.10.08 | 08.01.09 | 362807 | Work Completed
16 | 2008-08-29 | 18.08.09 | P/L cc and drainage in Gulshan Chowk and near stairs in Panjabi Basti in Baljeet Ngr.in C-94/KBZ | 357900 | 329/13.10.08/EE(M)-II | M/s Markanda Const. | 15.10.08 | 22.12.08 | 356857 | Work Completed
17 | 2008-08-29 | 20.08.08 | P/L drainage system and cc floring from h.no.P-279 along Neelkanth Mandir Panjabi Basti in Baljeet Ngr.in C-94/KBZ | 462600 | 331/13.10.08/EE(M)-II | M/s Pankaj Contractor | 15.10.08 | 05.12.08 | 462244 | Work Completed
18 | 2008-08-29 | 20.08.08 | P/L drainage system and cc floring from h.no. PB-439 to PB-575 and adj lane and along B-93 to B-68/A in gali no.5 Panjabi Basti in Baljeet Ngr.in C-94/KBZ | 455200 | 315/08.10.08/EE(M)-II | M/s SP Entp. | 10.10.08 | 15.12.08 | 455053 | Work Completed
19 | 2008-08-29 | 20.08.08 | P/L drainage system and cc floring from h.no.A-72 to T-22 along A-61 in Panjabi Basti in Baljeet Ngr.in C-94/KBZ | 293900 | 336/13.10.08/EE(M)-II | M/s Surbhi Const | 22.10.08 | 21.01.09 | 293078 | Work Completed
20 | 2008-08-29 | 20.08.08 | P/L drainage system and cc floring from h.no.B-89 to near Gurudwara in gali no.7 Panjabi Basti in Baljeet Ngr.in C-94/KBZ | 405100 | 334/13.10.08/EE(M)-II | M/s Shah Builders | 15.10.08 | 22.12.08 | 405083 | Work Completed
21 | 2008-08-29 | 20.08.08 | P/L drainage system and cc floring from B-105 to behind Shetla Mata Mandir in Panjabi Basti in Baljeet Ngr.in C-94/KBZ | 476000 | 335/13.10.08/EE(M)-II | M/s Rakesh Kr. Gupta | 24.10.08 | 30.12.08 | 473995 | Work Completed
22 | 2008-08-29 | 20.08.08 | P/L drainage system and cc floring along Ambedkar Park Panjabi Basti in Baljeet Ngr.in C-94/KBZ | 424500 | 338/13.10.08/EE(M)-II | M/s Pappu Seth | 25.10.08 | 10.12.08 | 424495 | Work Completed
23 | 2008-08-29 | 20.08.08 | P/L drainage system and cc floring from h.no.A-46 to A-100 and adj in gali no.10 Panjabi Basti in Baljeet Ngr.in C-94/KBZ | 383700 | 330/13.10.08/EE(M)-II | M/s Tanya Const | 17.10.08 | 05.01.09 | 383021 | Work Completed
24 | 2008-10-08 | 06.10.08 | P/L drainage system and cc flooring in gali no.10 Nehru nagar in C-94/KBZ | 423900 | 373/13.10.08/EE(M)-II | M/s Vikas & Co. | 25.10.08 | 11.12.08 | 423370 | Work Completed
25 | 2008-10-08 | 06.10.08 | Pdg brick work etc. in park and P/L drainage system around park in C-94/KBZ | 497250 | 372/13.10.08/EE(M)-II | M/s Rakesh Kr. Gupta | 15.10.08 | 30.12.08 | 496139 | Work Completed
26 | 2008-10-08 | 06.10.08 | Pdg drainage system near gali Chacha Chakki wali Nehru nagar and Punjabi basti Baljeet nagar in C-94/KBZ | 498648 | 374/13.10.08/EE(M)-II | M/s RP Aggarwal | 23.11.08 | 20.03.09 | 498648 | Work Completed
27 | 2008-10-08 | 06.10.08 | P/L drainage system & cc flooring in gali no.8 Nehru nagar in w.no94/KBZ | 489700 | 371/13.10.08/EE(M)-II | M/s Bajaj Const.Co. | 22.10.08 | 20.01.09 | 488767 | Work Completed
28 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from h.no. 407 to 407/1 and near h.no. 407/1 and adg. near Hanuman MAndir gali no.1 Than singh nagar C-95/KBZ | 198000 | 80/25.06.08/EE(M)-II | M/s Amit Gupta | 04.07.08 | 30.09.08 | 198000 | Work Completed
29 | 2008-05-27 | 14.05.08 | Pdg cc and drainege from h.no. 407/E-2 to 375 to 407/J-5 in Than Singh nagar C-95/KBZ | 198000 | 82/25.06.08/EE(M)-II | M/s Surbhi Const | 21.07.08 | 03.10.08 | 198000 | Work Completed
30 | 2008-06-20 | 25.05.08 | C/O lane by pdg. CC pav. and drainage system from h.no.715/5;713/12;722;721 and 721/5 and in Adj. lane in Than Singh Nagar C- 95/KBZ | 499400 | 200/20.08.08/EE(M)-II | M/s Markanda Const. | 27.08.08 | 25.11.08 | 498136 | Work Completed
31 | 2008-06-20 | 25.05.08 | /C/O of lane by pdg. CC pav. and drainage system from h.no.J-5 to T-35 to h.no.553 and adj. lane in Punjabi Basti Than Singh C-95/KBZ | 460900 | 233/01.09.08/EE(M)-II | M/s Nikhil Builders | 10.09.08 | 27.03.09 | 460645 | Work Completed
32 | 2008-06-20 | 25.05.08 | /C/O lane by pdg.CC pav. and drainage system from h.no.720 to716/3 and713/13 and715/1A and adj. lane in Than Singh Nagar C-95/KBZ | 439700 | 311/19.09.08/EE(M)-II | M/s guru Kirpa Const.CO. | 28.09.08 | 25.12.08 | 439666 | Work Completed
33 | 2008-06-20 | 25.05.08 | Pdg. drainage and CC from h.no.271/9 to296; h.no.296 to301 and adg. in Than Singh Nagar C-95/KBZ | 384000 | 231/01.09.08/EE(M)-II | M/s Malhotra Const.Co. | 01.09.08 | 08.12.08 | 383548 | Work Completed
34 | 2008-06-20 | 25.05.08 | C/O lane by pdg. CC pav. and drainage system from h.no.17/62 to Shri Bhagwan Mandir and lane in Than Singh Nagar in C-95/KBZ | 343100 | 236/01.09.08/EE(M)-II | M/s Surbhi Const | 09.09.08 | 02.03.09 | 342498 | Work Completed
35 | 2008-06-20 | 25.05.08 | C/O lane by pdg. CC nearh.no.194/1; near Kuenwala Mandir 165/7, 101/A,17/74 to 95/7 and adj lane in Than Singh Ngr. C-95/KBZ | 499950 | 214/25.08.08/EE(M)-II | M/s YS Builders | 29.08.08 | 03.11.08 | 498877 | Work Completed
36 | 2008-06-20 | 25.05.08 | C/O lane by pdg. CC and drainage system from h.no.17/69 and adj lane in Than Singh Ngr. C-95/KBZ | 389950 | 232/01.09.08/EE(M)-II | M/S Balaji Const.Co. | 10.09.08 | 21.1.08 | 389950 | Work Completed
37 | 2008-05-27 | 14.05.08 | Pdg cc and drainge from h.no. 406 to 322 to h.no. 322/A in gali no.1 to gali no.2 Than Singh nagar in C-95/KBZ | 192000 | 73/25.06.08/EE(M)-II | M/s Amit builders | 04.07.08 | 02.10.08 | 189102 | Work Completed
38 | 2008-05-27 | 14.05.08 | Pdg cc and draineg from h.no. 406A to 368 to h.no.m 319/1 in Than Singh NAgar C-95/KBZ | 199645 | 102/25.06.08/EE(M)-II | M/s Sunil Kumar gulati | 04.07.08 | 15.12.08 | 198192 | Work Completed
39 | 2008-06-20 | 25.05.08 | C/O lane by pdg cc and drainage from h.no.715/1 to 715/3A and 715/5, h.no.556 to 5/55 and adj lane in Than Singh Ngr. in c-95/KBZ | 447850 | 234/01.09.08/EE(M)-II | M/s Amit builders | 10.09.08 | 28.04.09 | 444542 | Work Completed
40 | 2008-06-20 | 25.05.08 | C/O lane by pdg. CC and drainage system from GH-6 to GH-9 and h.no.208/1A to 197/7E and adj lane in Than Singh Ngr. C-95/KBZ | 495400 | 235/01.09.08/EE(M)-II | M/s Narender Singh Dhanker | 10.09.08 | 09.12.08 | 493914 | Work Completed
41 | 2008-06-20 | 25.05.08 | C/O lane by pdg. CC and drainage system from h.no.723 to 725/3A,5/174 and 5/556 to h.no.443 and adj lane in Than Singh Ngr. C-95/KBZ | 499000 | 213/25.08.08/EE(M)-II | M/s Y.S. builders | 04.09.08 | 03.12.08 | 496151 | Work Completed
42 | 2008-05-27 | 14.05.08 | pdg cc and drainge from h.no. 389/1 to near h.no. 390/1 and adj in Than Singh nagar C-95/KBZ | 199000 | 76/25.06.08/EE(M)-II | M/s Unique Const. | 01.09.08 | 03.10.08 | 198382 | Work Completed
43 | 2008-06-20 | 25.05.08 | C/O lane by pdg. CC and drainage system from h.no.244/2,242,244/1,257 and 279/A and adj lane in Than Singh Ngr. C-95/KBZ | 497500 | 317/13.10.08/EE(M)-II | M/s Chimmy Const Co. | 23.10.08 | 20.01.09 | 496922 | Work Completed
44 | 2008-06-20 | 26.05.08 | Pdg cc and drainage P.no.KNC/13 to KNC/24 and adj in Vishvakarma Marg Anand Parbat w.no.74/KBZ | 482450 | 322/13.10.08/EE(M)-II | M/s Chimmy Const Co. | 13.10.08 | 14.01.09 | 481790 | Work Completed
45 | 2008-05-27 | 14.05.08 | Pdg drainge system from h.no. 186/8 to h.no. 196/8 and adj and gali no.8 in Than Singh Nagar C-95/KBZ | 177000 | 78/25.06.08/EE(M)-II | M/s Fabcon Engineers | 04.07.08 | 10.09.08 | 176839 | Work Completed
46 | 2008-05-27 | 14.05.08 | Pdg cc and flooring from h.no. 186/8 to h.no. 196/8 to adj in gali no.8 Than Singh nagar C-95/KBZ | 188902 | 83/25.06.08/EE(M)-II | M/s Vikas & Co. | 10.07.08 | 29.09.08 | 188636 | Work Completed
47 | 2008-06-20 | 26.05.08 | Pdg cc and drainage system from P.no. KNB/1 to KNB/13 and adj in Vishvakarma Marg Anand Parbat in C-74/KBZ | 498600 | 320/13.10.08/EE(M)-II | M/s S Gupta Const Co. | 14.10.08 | 12.01.09 | 498132 | Work Completed
48 | 2008-06-20 | 26.05.08 | Pdg cc and drainage system from RA/22 to RA/26 to S/1 to S/9 and adj in Vishvakarma Marg Anand Parbat in C-74/KBZ | 474000 | 117/14.07.08/EE(M)-II | M/s Y.S. builders | 23.07.08 | 15.09.08 | 473920 | Work Completed
49 | 2008-06-20 | 26.05.08 | Pdg cc flooring from PP-42 to PP-44,PP-51 to PP-55C, PP-52 to PP-45 and adj in gali no.10 Teliwalan side Anand Parbat in C-74/KBZ | 492800 | 148/18.07.08/EE(M)-II | M/s Tajinder Const.Co. | 27.07.08 | 02.01.09 | 491695 | Work Completed
50 | 2008-06-20 | 26.05.08 | Prov. cc and drainage from P.no. P/8A/3 to P/10 and adj in Vishvkarma Marg Anand Parbat C-74/KBZ | 498400 | 118/14.07.08/EE(M)-II | M/s Y.S. builders | 23.07.08 | 15.09.08 | 498274 | Work Completed
51 | 2008-06-20 | 26.05.08 | Prov. cc flooring from P.no. N-25 to P.no. N-26 and near N-26N and adj lane in middle portion of gali no.9 and gali no.10 indl.area Anand Parbat C-74/KBZ | 448000 | 147/18.07.08/EE(M)-II | M/s Shah Builders | 01.08.08 | 20.10.08 | 439255 | Work Completed
52 | 2008-06-20 | 26.05.08 | Prov. cc flooring from P.no. N-5 to P.no. N-10-22 to P.no. P-4 and adj in gali no.10 near Urinal Block indl.area Anand Parbat C-74/KBZ | 424800 | 154/18.07.08/EE(M)-II | M/s Rakesh Kr. Gupta | 27.07.08 | 15.09.08 | 422831 | Work Completed
53 | 2008-05-27 | 14.05.08 | Pdg cc and draionge from h.no. 196/7, CBR/1 to 17/94 and adj in gali no.7 opp. MC Pry School in Than Singh nagar C-95/KBZ | 190000 | 84/25.06.08/EE(M)-II | M/s Bhardwaj Const Co. | 04.07.08 | 29.12.08 | 189631 | Work Completed
54 | 2008-05-27 | 14.05.08 | Pdg cc and drainge frm h.no. 17/167 oto 95/5A and adj in gali no.6in Than Singh nagar C-95/KBZ | 199871 | 104/25.06.08/EE(M)-II | M/s A&N Bros. | 04.07.08 | 16.01.09 | 199042 | Work Completed
55 | 2008-05-27 | 14.05.08 | Pdg draainge system from h.no. 17/148 to h.no. 76/2 and adj in gali no.5 Than Singh nagar C-95/KBZ | 199000 | 96/25.06.08/EE(M)-II | M/s Naresh Kumar | 04.07.08 | 31.10.08 | 199000 | Work Completed
56 | 2008-05-27 | 14.05.08 | Pdg cc flooring from h.no. 17/148 to 76/2 and adj in gali no. 5 in Than Singh nagar C-95/KBZ | 199000 | 71/25.06.08/EE(M)-II | M/s Tajinder Const.Co. | 04.07.08 | 25.02.09 | 198489 | Work Completed
57 | 2008-06-20 | 26.05.08 | Pdg cc and drainage from KND/11 to KND/19 and adj lane in vishvakarma Marg Anand Parbat C-74/KBZ | 499900 | 297/15.09.08/EE(M)-II | M/s Naresh Kumar | 19.09.08 | 23.12.08 | 499900 | Work Completed
58 | 2008-06-20 | 26.05.08 | Pdg cc flooring from p.no.R-29 to p.no.29Q/9 and adj lane in gali no.4 indl.area Anand Parbat w.no.74/KBZ | 385400 | 150/18.07.08/EE(M)-II | M/s Surbhi Const | 01.08.08 | 20.11.08 | 385391 | Work Completed
59 | 2008-06-20 | 26.05.08 | C/O Toilet Block near M.C.Pry School in Baljit Ngr C-93/KBZ | 200200
60 | 2008-06-20 | 16.05.08 | Pdg drainage system from main road(road no.89) to road no.22 and adj in Baljit Ngr.C-93/KBZ | 460000 | 126/18.07.08/EE(M)-II | M/s Malhotra Const.Co. | 28.07.08 | 18.10.08 | 459729 | Work Completed
61 | 2008-06-20 | 16.05.08 | Pdg cc flooring from main road(road no.89) to road no.22 and adj in Baljit Ngr.C-93/KBZ | 472000 | 318/13.10.08/EE(M)-II | M/s Fabcon Engineers | 14.10.08 | 02.12.08 | 471396 | Work Completed
62 | 2008-06-20 | 16.05.08 | Pdg cc flooring opp. Ganga Mata Mandir and adj lane in Baljit Ngr. w.no.93/KBZ | 350000 | 133/18.07.08/EE(M)-II | M/s Markanda Const. | 27.07.08 | 24.10.08 | 349586 | Work Completed
63 | 2008-06-20 | 16.05.08 | Pdg drainage system near Dispensary to near Gurudwara Singh Sabha and adj lane in Baljit Ngr. C-93/KBZ | 465000 | 129/18.07.08/EE(M)-II | M/s Tanya Const | 27.07.08 | 12.02.08 | 464794 | Work Completed
64 | 2008-06-20 | 16.05.08 | Pdg cc flooring near Dispensary to near Gurudwara Singh Sabha and adj lane in Baljit Ngr.C-93/KBZ | 470000 | 308/19.09.08/EE(M)-II | M/s Kapoor Bros. | 27.09.08 | 12.02.09 | 469651 | Work Completed
65 | 2008-06-20 | 16.05.08 | Pdg drainage and cc flooring from Chachi Mandir to Shani Mandir and adj in Baljit Ngr. C-93/KBZ | 325000 | 127/18.07.08/EE(M)-II | M/s Malhotra Const.Co. | 28.07.08 | 24.10.08 | 324734 | Work Completed
66 | 2008-06-20 | 16.05.08 | Pdg drainage and cc from h.no.T-650/A-4 to T-640/A-4 and adj in Baljit Ngr. w.no.93/KBZ | 410000 | 139/18.07.08/EE(M)-II | M/s Ved pal Bhatia | 27.08.08 | 23.10.08 | 409812 | Work Completed
67 | 2008-05-27 | 14.05.08 | pdg cc and drainage 101/A to 165/17 and adj in cross gali no.5 to gali no.6 in Than Singh nagar C-95/KBZ | 195940 | 94/25.06.08/EE(M)-II | M/s Jasvinder Gulati | 04.07.08 | 15.01.09 | 195940 | Work Completed
68 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from h.no. 17/139 to 142/1 and adj in gali no.5 in Than singh nagar C-95/KBZ | 192923 | 70/25.06.08/EE(M)-II | M/s Naresh Kumar Bansal | 04.07.08 | 03.10.08 | 192923 | Work Completed
69 | 2008-06-20 | 16.05.08 | C/O gate at Ram Swaroop Vidhyarthi Park in Baljit Ngr. w.no.93/KBZ | 250000
70 | 2008-06-20 | 16.05.08 | C/O gate at h.no.T-1/A-1,road no. 89 in Baljit Ngr. w.no.93/KBZ | 250000
71 | 2008-05-27 | 14.05.08 | Pdg cc and drainge from h.no./ 17/199 to 147/2 and adj in cross galui no.3 and gali no.5 in Than Singh nagar C-95/KBZ | 191000 | 65/25.06.08/EE(M)-II | M/s RK Builders | 25.06.08 | 18.08.08 | 188288 | Work Completed
72 | 2008-05-27 | 14.05.08 | Pdg cc florring from h.no. 17/137 to 102 and adj in gali no. 4 in Than Singh Ngara C-95/KBZ | 190920 | 85/25.06.08/EE(M)-II | M/s Bhatia Const. Co. | 03.07.08 | 18.1.08 | 189733 | Work Completed
73 | 2008-06-20 | 16.05.08 | C/O gate at Amberkar Park in Baljit Ngr. w.no.93/KBZ | 250000 | 138/18.07.08/EE(M)-II | M/s Manchanda Const. | 25.07.08 | 19.02.09 | 250000 | Work Completed
74 | 2008-06-20 | 16.05.08 | Pdg cc flooring from h.no.T-637 behind Baba Ramdev Mandir and adj in Baljit Ngr.w.no.93/KBZ | 490000 | 306/19.09.08/EE(M)-II | M/s A&N Bros. | 29.09.08 | 23.02.09 | 489502 | Work Completed
75 | 2008-06-20 | 16.05.08 | Pdg drainage and cc from h.no.T-650/EA-1 to T-650/H/5A/IB and adj in Baljit Ngr.w.no.93/KBZ | 345000 | 134/18.07.08/EE(M)-II | M/s SP Entp. | 19.07.08 | 24.08.08 | 344745 | Work Completed
76 | 2008-06-20 | 16.05.08 | Pdg drainage and cc from h.no.T-650/H/5A/IB to T-650/2A and adj in Baljit Ngr.w.no.93/KBZ | 420000 | 143/18.07.08/EE(M)-II | M/s Kailash Chander | 28.07.08 | 24.02.09 | 419207 | Work Completed
77 | 2008-06-20 | 16.05.08 | Pdg drainage and cc from h.no.E-91 to T-76 and adj in Baljit Ngr.w.no.93/KBZ | 395000 | 142/18.07.08/EE(M)-II | M/s Bhatia Const. Co. | 28.07.08 | 25.10.08 | 394983 | Work Completed
78 | 2008-06-20 | 16.05.08 | C/O stair case and fixing of MS grills near h.no.T-30/29 in Baljit Ngr.w.no.93/KBZ | 145000
79 | 2008-06-23 | 28.05.08 | P/L cc and drainage system in Amba Bagh from h.no.2/49 to 5/49 and adj lane in Amba Bagh C-75/SPZ | 199617 | 145/18.07.08/EE(M)-II | M/s Mohd. Rashid | 09.07.08 | 22.08.08 | 199594 | Work Completed
80 | 2008-05-27 | 14.05.08 | Pdg drainge system near h.no.95/5a , 76/2 and adj near MC Pry School in Than Singh nagar in C-95/KBZ | 183939 | 87/25.06.08/EE(M)-II | M/s S.Gupta Const. Co. | 04.07.08 | 18.02.09 | 183375 | Work Completed
81 | 2008-05-27 | 14.05.08 | Pdg cc flooring nar h.no 95/5A, 76/2 and adj lanes near MC Pry School Than Singfh Nagar C-95/KBZ | 198773 | 101/25.06.08/EE(M)-II | M/s Sonu Builders | 04.07.08 | 20.04.09 | 198699 | Work Completed
82 | 2008-05-27 | 14.05.08 | Pdg cc and drainge from Atta Chakki to h.no. 17/62 and adj near main new Rohtak road in Than Singh nagar C-95/KBZ | 183000 | 79/25.06.08/EE(M)-II | M/s Sahil Const. | 04.07.08 | 18.10.08 | 182492 | Work Completed
83 | 2008-05-27 | 14.05.08 | Pdg cc and drainge from H.NO.17/66 TO 17/73 and adj near main new Rohtak road in Than Singh nagar C-95/KBZ | 199717 | 81/25.06.08/EE(M)-II | M/s SK Verma | 04.07.08 | 15.01.09 | 199717 | Work Completed
84 | 2008-05-27 | 14.05.08 | Pdg drainge system from toilet towards Ghati road (LHS)in C-95/KBZ | 195000 | 92/25.06.08/EE(M)-II | M/s ESS GEEConst. | 04.07.08 | 07.01.09 | 194078 | Work Completed
85 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from h.no. 53 to T-36 to App-89 and adj in gali no.6 Punjabi basti in Than singh nagar C-95/KBZ | 183892 | 75/25.06.08/EE(M)-II | M/s Bajaj Const.Co. | 26.06.08 | 23.09.08 | 183752 | Work Completed
86 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from h.no. 656C to 654/3 to 3/71 and adj in gali no.3 Punjabi basti in Than singh nagar C-95/KBZ | 199753 | 103/25.06.08/EE(M)-II | M/s JS Const. | 04.07.08 | 18.02.09 | 199647 | Work Completed
87 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from near h.no. 662/4, 657/3 to 34/3 and adj in gali no.2 Punjabi basti in Than singh nagar C-95/KBZ | 182000 | 95/25.06.08/EE(M)-II | M/s RP Aggarwal | 03.07.08 | 28.11.08 | 181563 | Work Completed
88 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from h.no. 685/1 to 8/228-229 and adj in Punjabi basti in Than Singh nagar C-95/KBZ | 199827 | 97/25.06.08/EE(M)-II | M/s Som Dutt Dwevidi | 04.07.08 | 18.03.09 | 199827 | Work Completed
89 | 2008-05-27 | 14.05.08 | Pdg cc and drainage from h.no. 717/5 to 17/22 and adj lanes in gali no.3 in Punjabi basti in Than Singh nagar C-95/KBZ | 199843 | 86/25.06.08/EE(M)-II | M/s Shah Builders | 04.07.08 | 20.10.08 | 198677 | Work Completed
|  |  |  | 28571448 |  |  |  |  | 27660223

## Sheet3
Status Report of MLA, Sh. S.P. Ratawal (AC-68), 2008-09
S.No. | Date of Booking | Date of Consent | Name of Work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount Verified | Present Position
1 | 2008-06-23 | 19.05.08 | Pdg cc pav. with drainage system in gali no.7 in C-92/KBZ | 498700 | 208/25.08.08/EE(M)-II | M/s S Gupta Const Co. | 25.08.08 | 22.09.08 | 498120 | Work Completed
2 | 2008-06-23 | 19.05.08 | Pdg cc pav. with drainage system in gali no.1 in C-92/KBZ | 495000 | 207/25.08.08/EE(M)-II | M/s A&N Bros. | 25.08.08 | 19.09.08 | 487252 | Work Completed
3 | 2008-07-23 | 21.07.08 | Pdg cc pav. in gali Kalu Pan Wali,H.S. Road from h.no.16/65-I,16/203-E to 16/189-E(Gali Achar Wali)16/313-E to 16/321-E in Bapa Ngr. in C-92/KBZ | 431600 | 355/13.10.08/EE(M)-II | M/s Amit Cost. | 24.10.08 | 22.01.09 | 431485 | Work Completed
4 | 2008-07-23 | 21.07.08 | Pdg Kota Stone plate in lane from Sanitary office to H.S. road in Gaffar Mkt. in C-91/KBZ | 234000
5 | 2008-07-23 | 21.07.08 | C/O Archer near Ladies Park in Ajmal Khan Park in C-91/KBZ | 367000 | 422/14.01.09/EE(M)-II | M/s Malhotra Const Co. | 15.01.09 | 20.04.09 | 366026 | Work Completed
6 | 2008-07-23 | 21.07.08 | Pdg drainage system in Jheggi lane near Dalao Maharana Pratap Mkt. in C-91/KBZ | 267700 | 357/13.10.08/EE(M)-II | M/s Manchanda Const. | 10.11.08 | 07.01.09 | 267114 | Work Completed
7 | 2008-07-23 | 21.07.08 | Pdg cc pav with drain in gali no.14 Beadonpura in C-91/KBZ | 350900 | 353/13.10.08/EE(M)-II | M/s Amit builders | 17.10.08 | 04.12.08 | 349857 | Work Completed
8 | 2008-07-23 | 21.07.08 | Pdg cc pav with drain in gali no.15 Beadonpura in C-91/KBZ | 354000 | 352/13.10.08/EE(M)-II | M/s Herry Const Co. | 15.10.08 | 10.12.08 | 350875 | Work Completed
9 | 2008-07-23 | 21.07.08 | Pdg cc pav in gali no.72 Regharpura in C-91/KBZ | 499800 | 350/13.10.08/EE(M)-II | M/s Harpreet Arora | 04.11.08 | 03.12.08 | 496592 | Work Completed
10 | 2008-07-23 | 21.07.08 | Pdg cc pav. and berms from xing. A.S.Road to tank Road on Vishnu Mandir Marg in C-91/KBZ | 498800 | 346/13.10.08/EE(M)-II | M/s Fabcon Engineers | 20.10.08 | 20.01.09 | 498363 | Work Completed
11 | 2008-07-23 | 21.07.08 | Pdg cc pav. in gali no.73 in Regharpura in C-91/KBZ | 499900 | 358/13.10.08/EE(M)-II | M/s Malhotra Const Co. | 22.10.08 | 30.12.08 | 499815 | Work Completed
12 | 2008-07-23 | 21.07.08 | Pdg cc pav. in gali no.75 in Regharpura in C-91/KBZ | 499000 | 345/13.10.08/EE(M)-II | M/s Akriti Decore | 23.10.08 | 06.01.09 | 498867 | Work Completed
13 | 2008-07-23 | 21.07.08 | Pdg cc pav. in gali no.76 in Regharpura in C-91/KBZ | 499000 | 343/13.10.08/EE(M)-II | M/s Deepali builders | 22.10.08 | 12.01.09 | 498727 | Work Completed
14 | 2008-07-23 | 21.07.08 | Pdg cc pav. in gali no.77 in Regharpura in C-91/KBZ | 499000 | 354/13.10.08/EE(M)-II | M/s Bunty builders | 15.10.08 | 12.12.08 | 499000 | Work Completed
15 | 2008-07-23 | 21.07.08 | Pdg cc pav. in gali no.78 in Regharpura in C-91/KBZ | 499700 | 349/13.10.08/EE(M)-II | M/s Kapoor Bros. | 13.10.08 | 17.11.08 | 496675 | Work Completed
16 | 2008-07-23 | 21.07.08 | Pdg cc pav. in gali no.53 in Regharpura in C-91/KBZ | 499900 | 342/13.10.08/EE(M)-II | M/s Vedpal Bhatia | 15.10.08 | 15.12.08 | 499506 | Work Completed
17 | 2008-07-23 | 21.07.08 | Pdg cc pav. with drainage in gali no.1,Rattan Ngr.in C-91/KBZ | 498800 | 359/13.10.08/EE(M)-II | M/s Raghav Const. | 21.10.08 | 30.03.09 | 498497 | Work Completed
18 | 2008-07-23 | 21.07.08 | Pdg cc pav.in gali no.3 and adj area in Christan Colony in C-91/KBZ | 499000 | 348/13.10.08/EE(M)-II | M/s Guru Kripa Const Co. | 15.10.08 | 11.12.08 | 499000 | Work Completed
19 | 2008-07-23 | 21.07.08 | Pdg cc pav.with drainage from h.no.794 to h.no.807 in joshi lane (between D.B. Gupta Road to Khajoor Road)in C-91/KBZ | 499710 | 347/13.10.08/EE(M)-II | M/s Manoj Kumar Bhatia | 15.10.08 | 30.12.08 | 499705 | Work Completed
20 | 2008-07-23 | 21.07.08 | Pdg cc pav.with drainage from h.no.807 to h.no.879 in joshi lane (between D.B. Gupta Road to Khajoor Road)in C-91/KBZ | 499710 | 340/13.10.08/EE(M)-II | M/s Bhatia Const Co. | 23.10.08 | 20.1.08 | 499341 | Work Completed
21 | 2008-07-23 | 21.07.08 | Pdg cc pav.and berms in lanes Pusa Road (between A.S.Road to Road no.29)in C-91/KBZ | 499700 | 341/13.10.08/EE(M)-II | M/s Som Dutt Dwevedi | 15.10.08 | 04.12.08 | 499156 | Work Completed
22 | 2008-07-23 | 21.07.08 | Pdg kota Stone Flooring from shop no.67A to shop no.88 in Ghaffar Mkt. in C-91/KBZ | 499900 | 361/13.10.08/EE(M)-II | M/s S. Gupta Const Co. | 24.10.08 | 10.01.09 | 499885 | Work Completed
23 | 2008-07-23 | 21.07.08 | Pdg kota Stone Flooring from shop no.23 to shop no.44 in Ghaffar Mkt. in C-91/KBZ | 499800 | 360/13.10.08/EE(M)-II | M/s S.K Verma | 20.10.08 | 21.01.09 | 499149 | Work Completed
24 | 2008-07-23 | 21.07.08 | Pdg cc pav. with drainage system from h.no.59 on Anand Parbat Road in C-91/KBZ | 500000 | 356/13.10.08/EE(M)-II | M/s Shiv Shanker Gupta | 24.10.08 | 05.01.09 | 498948 | Work Completed
25 | 2008-07-23 | 21.07.08 | Pdg cc pav. from h.no.5704/80 to G.M. Marg in gali no.80 and adj area in Regharpura in C-91/KBZ | 312700 | 209/25.08.08/EE(M)-II | M/s Yuvraj Const Co. | 25.08.08 | 22.09.08 | 312354 | Work Completed
26 | 2008-06-19 | 19.05.08 | Pdg cc pav. with drainage system in gali no.2 Krishna Ngr. in c-91/KBZ | 452600 | 276/05.09.08/E(M)-II | M/s Shiv Shanker Gupta | 06.09.08 | 15.02.08 | 451677 | Work Completed
27 | 2008-06-19 | 19.05.08 | Pdg cc pav. with drainage system in gali no.1 in Krishna Ngr. c-91/KBZ | 449700 | 275/05.09.08/E(M)-II | M/s Naresh Kumar | 08.09.08 | 28.11.08 | 449456 | Work Completed
28 | 2008-06-19 | 19.05.08 | Pdg cc pav. with drainage system in gali no.63 in Regharpura C-91/KBZ | 431300 | 175/28.07.08/EE(M)-II | M/s Tyagi Assos. | 06.08.08 | 06.11.08 | 431155 | Work Completed
29 | 2008-06-19 | 19.05.08 | Pdg cc pav. with drainage system in gali no.56 in Regharpura C-91/KBZ | 423210 | 181/28.07.08/EE(M)-II | M/s Rakesh Kumar Gupta | 01.08.08 | 12.09.08 | 423129 | Work Completed
30 | 2008-06-19 | 19.05.08 | Pdg cc pav. with drainage system in gali no.81 in Regharpura C-91/KBZ | 427650 | 180/28.07.08/EE(M)-II | M/s Som Dutt Dwevedi | 06.08.08 | 16.09.08 | 427366 | Work Completed
31 | 2008-06-19 | 19.05.08 | Pdg cc pav. with drainage system in gali no.43 in Regharpura C-91/KBZ | 432320 | 351/13.10.08/EE(M)-II | M/s Gupta Const Co. | 22.10.08 | 30.12.08 | 431605 | Work Completed
32 | 2008-06-19 | 19.05.08 | Pdg cc pav. with drainage system in gali no.48 in Regharpura C-91/KBZ | 434200 | 274/05.09.08/EE(M)-II | M/s Kapoor Bros. | 12.09.08 | 22.05.08 | 431226 | Work Completed
33 | 2008-06-19 | 19.05.08 | Pdg cc pav. with drainage system in gali no.50 in Regharpura C-91/KBZ | 425100 | 248/01.09.08/EE(M)-II | M/s R.P. Aggarwal | 05.09.08 | 31.10.08 | 424590 | Work Completed
34 | 2008-06-19 | 19.05.08 | Pdg cc pav. with drainage system in gali no.38 in Regharpura C-91/KBZ | 396200 | 179/28.07.08/EE(M)-II | M/s Yuvraj Const Co. | 05.08.08 | 23.01.09 | 395258 | Work Completed
35 | 2008-06-19 | 19.05.08 | Pdg cc pav. with drainage system in gali no.34 in Regharpura C-91/KBZ | 392500 | 171/18.07.08/EE(M)-II | M/s Malhotra Const Co. | 19.07.08 | 29.08.08 | 391459 | Work Completed
36 | 2008-06-23 | 19.05.08 | Pdg cc pav. on berms from road no.4 to xing of New Pusa Road in Arya Samaj Road in C-91/KBZ | 399104 | 298/15.09.08/EE(M)-II | M/s Naresh Kumar | 23.09.08 | 13.02.09 | 399109 | Work Completed
37 | 2008-06-23 | 19.05.08 | Pdg cc pav. near Military road h.no.I-16/552 in Bapa Ngr.in C-92/KBZ | 399400 | 296/15.09.08/EE(M)-II | M/s Chinmay Const Co. | 23.09.08 | 10.02.09 | 399106 | Work Completed
38 | 2008-06-23 | 19.05.08 | Pdg cc pav. on berms from Military road to Guru Nanak road Xing in Pyre Lal Road in C-92/KBZ | 399870 | 206/25.08.08/EE(M)-II | M/s Guru Kripa Const Co. | 29.08.08 | 01.12.08 | 399499 | Work Completed
39 | 2008-06-23 | 19.05.08 | Pdg cc pav. in gali no.24 in Naiwala in C-91/KBZ | 342110 | 186/28.07.08/EE(M)-II | M/s Bunty builders | 30.07.08 | 05.09.08 | 341570 | Work Completed
40 | 2008-06-23 | 19.05.08 | Pdg cc pav. in gali no.28 in Naiwala in C-91/KBZ | 340300 | 177/28.07.08/EE(M)-II | M/s Honey Const | 06.08.08 | 08.05.09 | 339819 | Work Completed
41 | 2008-06-23 | 19.05.08 | Pdg cc pav. in gali no.21 in Naiwala in C-91/KBZ | 336640 | 193/11.08.08/EE(M)-II | M/s Guru Kripa Const Co. | 12.08.08 | 10.10.08 | 336355 | Work Completed
42 | 2008-06-23 | 19.05.08 | Pdg cc pav. in gali no.8 in Naiwala in C-91/KBZ | 333000 | 170/18.07.08/EE(M)-II | M/s Manchanda Const. | 25.07.08 | 05.03.09 | 332996 | Work Completed
43 | 2008-06-23 | 19.05.08 | Pdg cc pav. with drainage system in gali no.2 in Shiv Ngr. in C-91/KBZ | 333415 | 184/28.07.08/EE(M)-II | M/s Deepak Const Co. | 05.08.08 | 20.04.09 | 333221 | Work Completed
44 | 2008-06-23 | 19.05.08 | Pdg Kota Stone and B/Work between gali no. 35 Beadonpura and gali no.14 Ragharpura on Nalla in C-91/KBZ | 326600 | 185/28.07.08/EE(M)-II | M/s Welcome Assos | 15.08.08 | 22.09.08 | 325289 | Work Completed
45 | 2008-06-23 | 19.05.08 | Pdg cc pav. from h.no.E-16/945 to E-16/937E and h.no.H-16/143 to H-16/115 (gali Bansi Wali)in Bapa Ngr. C-92/KBZ | 302840 | 173/18.07.08/EE(M)-II | M/s Pankaj Contractor | 21.07.08 | 27.10.08 | 300182 | Work Completed
46 | 2008-06-23 | 19.05.08 | Pdg cc pav. in gali no.20 from h.no.E-16/1614 to E-16/1641 and h.no.E-16/1641 to E-16/1654 in Bapa Ngr. C-92/KBZ | 301920 | 174/18.07.08/EE(M)-II | M/s Manoj Kumar Bhatia | 25.07.08 | 22.10.08 | 301919 | Work Completed
47 | 2008-06-23 | 19.05.08 | Pdg RMC Pav. of road berms on rpad no.29 in C-91/KBZ | 297400 | 176/28.07.08/EE(M)-II | M/s Honey Const | 04.08.08 | 25.11.08 | 296743 | Work Completed
48 | 2008-06-23 | 19.05.08 | Pdg cc pav. in gali no 66 in Naiwala w.no.91/KBZ | 279130 | 187/28.07.08/EE(M)-II | M/s Vikas & Co. | 01.08.08 | 15.09.08 | 278972 | Work Completed
49 | 2008-06-23 | 19.05.08 | Pdg cc pav. in gali no.2 in Shivaji Street between A.S.road and H.S.road in C-91/KBZ | 274600 | 178/28.07.08/EE(M)-II | M/s Vedpal Bhatia | 28.07.08 | 16.09.08 | 274470 | Work Completed
50 | 2008-06-23 | 19.05.08 | Pdg cc pav. in gali no.34 in Naiwala in C-91/KBZ | 273700 | 189/28.07.08/EE(M)-II | M/s Balaji Const. | 06.08.08 | 31.10.08 | 273196 | Work Completed
51 | 2008-06-23 | 19.05.08 | Pdg cc pav. in gali no.5 in Naiwala In C-91/KBZ | 271850 | 182/28.07.08/EE(M)-II | M/s Manoj Kumar Bhatia | 28.07.08 | 25.04.09 | 271527 | Work Completed
52 | 2008-06-23 | 19.05.08 | Pdg cc pav. in gali no.22 in Naiwala In C-91/KBZ | 271900 | 168/18.07.08/EE(M)-II | M/s SK Entp. | 25.07.08 | 20.03.09 | 271499 | Work Completed
53 | 2008-06-23 | 19.05.08 | Pdg cc pav. with drainage system in gali no.64 in Naiwala In C-91/KBZ | 267600
54 | 2008-06-23 | 19.05.08 | Pdg cc pav. in gali no.1 in Shivaji Street between A.S. road and H.S. road in C-91/KBZ | 265500 | 172/18.07.08/EE(M)-II | M/s Ma Bhoomika Entp. | 25.07.08 | 24.01.09 | 264864 | Work Completed
55 | 2008-06-23 | 19.05.08 | Pdg cc pav. in gali no.35 in Naiwala in C-91/KBZ | 264600 | 169/18.07.08/EE(M)-II | M/s R.P. Aggarwal | 01.08.08 | 20.09.08 | 264291 | Work Completed
|  |  |  | 21849579 |  |  |  |  | 21305857