## AC-3
S.no. | Date of Booking | Date of Consent | Name of work | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-06-26 | 28.03.09 | Dev of toilet block of swepers qrs.by replacing doors tiles and roof grading in w.no.153/CZ | 198973
2 | 2008-06-23 | 09.01.09 | Prov. of semi high mast lioght pole near h.no.832 Kotla Firozshah CZ | 218811 | 59/29.09.08/EE(E)-I | M/s Channa & Co. | 06.03.09 | 04.05.09 | 175157
3 | 2008-06-23 | 09.01.09 | Prov. of semi high mast lioght pole near banglo no.130 Sunder Ngr.CZ | 222335 | 50/17.09.08/EE(E)-I | M/s Channa & Co. | 27.01.09 | P | 167793
4 | 2008-06-23 | 09.01.09 | Prov. of semi high mast lioght pole near banglo no.99 Sunder Ngr.CZ | 220810 | 174/16.01.09/EE(E)-I | M/s Channa & Co. | 24.01.09 | P | 183539
5 | 2008-06-23 | 09.01.09 | P/F of HPSV street light fitting atSunder Ngr and Nizamuddin East.CZ | 240618 | 101/31.10.08/EE(E)-I | M/s Repair Shop | 07.11.08 | 06.01.09 | 238856
6 | 2008-06-23 | 09.01.09 | Prov. of semi high mast lioght pole near banglo no.19 Sunder Ngr.CZ | 218978 | 49/12.09.08/EE(E)-I | M/s Channa & Co. | 15.01.09 | P | 166956
7 | 2008-07-15 | 11.07.08 | P/l RMC with drainage on road berms from Banglow no.12 to 9 in Jaipur Estate in w.no.154 CZ | 199131 | 144/20.08.08/EE(M)-I | M/s Sudhir Const. | 20.08.08 | 25.09.08 | 197900
8 | 2008-07-15 | 11.07.08 | P/l RMC in lane from h.no. C-27 to B-29A with drainage in Nijammuddin West in w.no.154 CZ | 196859 | 135/20.08.08/EE(M)-I | M/s Shabin Entp. | 23.08.08 | 07.10.08 | 196571
9 | 2008-07-15 | 11.07.08 | P/l RMC with drainage on road berms from D-6 to D-1 and A-86 to 90 in Nizamuddin East in w.no.154 CZ | 199534 | 136/20.08.08/EE(M)-I | M/s Roop Narain Chaudhary | 22.08.08 | 23.10.08 | 199519
10 | 2008-07-22 | 11.07.08 | Dev of gali no.18 Bhargav lane and adj lane by pdg RMC in Darya Ganj in w.no. 153 CZ | 186733 | 142/20.08.08/EE(M)-I | M/s Suman Assos. | 22.08.08 | 09.09.08 | 186733
11 | 2008-07-22 | 11.07.08 | Dev of gali adj T-Series, building Darya Ganj by pdg by RMC in w.no.153 City Zone | 194055 | 137/20.08.08/EE(M)-I | M/s Roop Narain Chaudhary | 21.08.08 | 17.10.08 | 194055
12 | 2008-07-22 | 11.07.08 | Dev of Bharat Ram road & back lane side of Police station near Hindi park by pdg RMC in w.no.153 CZ | 182146 | 145/20.08.08/EE(M)-I | M/s Tarun Entp. | 26.08.08 | 24.09.08 | 182146
13 | 2008-07-29 | 25.07.08 | P/L RMC in lane from h.no.67 to C-29 in Jangpura-B in C-154/CZ | 197595 | 197/04.0908/(M)-I | M/s Bansal Entp. | 05.09.08 | 10.11.08 | 197152
14 | 2008-07-29 | 25.07.08 | P/L cc interlocking tile on road berms along park opp.103 to 126 and Kucha berm infront of h.no.144 to 120 in Sunder Ngr. in C-154/CZ | 198914 | 200/04.09.08/EE(M)-I | M/s Manoj Assos. | 04.09.08 | 10.10.08 | 198914
15 | 2008-07-29 | 25.07.08 | P/L cc interlocking tiles inthe lane along park side of Banglow no.30 and 37 in Sunder Ngr. C-154/CZ | 197754 | 194/04.09.08/EE(M)-I | M/s Ajay Const Co. | 04.09.08 | 18.09.08 | 196547
16 | 2008-07-30 | 25.07.08 | Dev of gali in Harijan Basti and near Mandir at Village Nangli Razapur by pdg RMC in C-153/CZ | 194270
17 | 2008-07-30 | 25.07.08 | Dev of gali in nafisa Masjid at Sarai Kale Khan by pdg RMC in C-153/CZ | 135055 | 199/04.09.08/EE(M)-I | M/s Kay Const Co. | 05.09.08 | 31.10.08 | 128513
18 | 2008-07-30 | 25.07.08 | Dev of gali no.T-86 at sarai Kale Khan by pdg RMC in C-153/CZ | 164243 | 192/04.09.08/EE(M)-I | M/s Ajay builders | 05.09.08 | 04.12.08 | 161156
19 | 2008-07-30 | 25.07.08 | Dev of gali Chand Biwi Camp at sarai Kale Khan by pdg RMC in C-153/CZ | 191688 | 198/04.09.08/EE(M)-I | M/s Laxmi Assos. | 05.09.08 | 31.10.08 | 191688
20 | 2008-08-01 | 11.07.08 | Dev of gali near DJB Office in 1 Darya Ganj by pdg RMC in C-153/CZ | 491540 | 226/24.09.08/EE(M)-I | M/s Bansal Entp. | 29.09.08 | 28.11.08 | 491062
21 | 2008-08-06 | 25.07.08 | P/L RMC interlocking tiles on road berms around park and Banglow from 52 to 71 in Sunder ngr. C-154/CZ | 418937 | 227/24.09.08/EE(M)-I | M/s Suman Assos. | 25.09.08 | 21.10.08 | 418937
22 | 2008-08-06 | 05.08.08 | Dev of footpath and side berms from shop no.4574/15 to 4551/16 at Padam Singh Marg by pdg RMC in Darya Gamj in C-153/CZ | 358906 | 357/02.01.09/EE(M)-I | M/s Priyadar Sri Const Co. | 12.03.09 | 10.06.09 | 350267
23 | 2008-08-06 | 05.08.08 | C/O Steps near Mandir at Vikram Ngr. in C-153/CZ | 275635 | 376/02.01.09/EE(M)-I | M/s Narender Kumar Const Co. | 16.01.09 | 09.03.09 | 275635
24 | 2008-08-14 | 14.06.08 | C/O Community Hall/Recreation Center at Sarai Kale Khan in CZ | 5000000 | 05/23.09.08/EE(M)-I | M/s Ashok Kumar Jain | 03.10.08 | P | 1488770
25 | 2008-09-29 | 28.08.08 | Dev of both side berm infront of Khalsa School at Khar Khana road road in w.no. 153 CZ | 184683 | 371/02.01.09/EE(M)-I | M/s Dinesh Kumar | 09.01.09 | 23.03.09 | 184050
26 | 2008-09-29 | 28.08.08 | Dev of fotthpath Dargah Shawri to shop no. 5045/9 at Khar Khana Darya Ganj in w.no. 153 CZ | 179292 | 356/02.01.09/EE(M)-I | M/s Manoj Assos. | 12.01.09 | 05.03.09 | 179292
27 | 2008-09-29 | 28.08.08 | Dev of footpath from foot over bridge to shop no. 5044/9 at Khar Khana road Darya Ganj in w.no. 153 CZ | 173052
28 | 2008-08-29 | 28.08.08 | Dev of road surface by bituman mastic in side road of DC Office Darya Ganj in C-153/CZ | 482000 | 464/26.02.09/EE(M)-I | M/s Ashok Kumar Gupta | 27.02.09 | 24.04.09 | 475076
29 | 2008-09-17 | 05.09.08 | prov. of lighting arrangement in badminton Court at Nizamuddin Basti near Community Hall Center under C-153/CZ | 90813 | 140/12.12.08/EE(E)-I | M/s AE Engg. & builders | 20.12.08 | 06.01.09 | 82190
30 | 2008-09-17 | 05.09.08 | Prov. of street lighting arrangement with GI pole 8 mtr. at Nizamuddin East at Nizamuddin Basti under CZ | 196787
31 | 2008-09-17 | 05.09.08 | Prov. of semi high mast pole near Mother Dairy at Radha Krishan Mandir at Jungpura-B under CZ | 154072 | 187/03.02.09/EE(E)-I | M/s Kamal Elect. | 15.02.09 | 06.03.09 | 106728
32 | 2008-09-29 | 24.09.08 | Dev of road from h.no. 4759/23 to 4764/23 by pdg RMC adj. Ansari road at Darya Ganj in w.no.153/CZ | 240171 | 484/27.02.09/EE(M)-I | M/s Puneet Const Co. | 27.04.09 | 22.06.09 | 236422
| 2008-09-29 | 24.09.08 | Dev of road from h.no. 4768/23 to 4765/23 by pdg RMC adj Bharat Ram road at Darya Ganj in w.no. 153/CZ | 163491 | 416/04.02.09/EE(M)-I | M/s Kay Const Co. | 16.02.09 | 23.04.09 | 416491
34 | 2008-09-29 | 25.09.08 | Dev of road from h.no. 32 to 40 by pdg RMC at Brij Mohan marg in darya Ganj in w.no. 153/CZ | 307293 | 486/27.02.09/EE(M)-I | M/s Bansal Entp. | 27.02.09 | 06.04.09 | 307293
35 | 2008-09-29 | 20.09.08 | Dev of road infront of h.no. 26A by pdg RMc adj Medical Association road at Darya Ganj in w.no. 153 CZ | 294241 | 473/27.02.09/EE(M)-I | M/s Monu Entp. | 27.02.09 | 06.04.09 | 293293
36 | 2008-11-29 | 24.09.08 | Dev of road surface by pdg mix concrete infront of h.no. 71 near Police Station at Darya Ganj in w.no. 153 City Zone | 198358 | 415/27.02.09/EE(M)-I | M/s Narender Kumar Const Co. | 05.02.09 | 31.03.09 | 198358
37 | 2008-06-19 | 26.05.08 | Dev of lane between h.no.T-61 and T-62 in Nangli Razapur by pdg RMC in w,vo.153/CZ | 199708 | 97/06.08.08/EE(M)-I | M/s Bansal Entp. | 07.08.08 | 08.09.08 | 199595
38 | 2008-06-19 | 26.05.08 | Dev of lane between h.no.B-47,B-36, B-37,A-41, and A-44,A-42 in Vikram Ngr.w.no.153/CZ | 199780 | 94/06.08.08/EE(M)-I | M/s Pooja Const. | 02.09.08 | 06.04.09 | 199780
39 | 2008-06-19 | 26.05.08 | Dev of open space and gali near h.no.E-49 Vikram Ngr.in w.no.153/CZ | 199075
40 | 2008-06-19 | 26.05.08 | Dev of gali near Gurudwara in Vikram Ngr. in w.no.153/CZ | 199606 | 99/06.08.08/EE(M)-I | M/s Saman Assos. | 07.08.08 | 01.10.08 | 199606
41 | 2008-06-19 | 26.05.08 | Dev of Footpath of Mahrishi Naval Marg from JLN Marg to Sweepers Qtr. by pdg RMC w.no.153/CZ | 197548 | 96/06.08.08/EE(M)-I | M/s Pooja Const. | 18.08.08 | 14.16.08 | 197548
42 | 2008-06-19 | 16.05.08 | Prov. of semi-high mast pole near Mahila Park Nizamuddin West under CZ w.no.154 | 276192
43 | 2008-06-19 | 16.05.08 | Prov. of semi-high mast pole near RB house Nizamuddin Basti CZ w.no.154 | 235714 | 59/29.09.08/EE(M)-I | M/s Channa & Co. | 06.03.09 | 04.05.09 | 170928
44 | 2008-06-19 | 16.05.08 | Prov. of semi -high mast pole near Bavli Gate Nizamuddin Basti under CZ w.no.154 | 275617
45 | 2008-06-19 | 16.05.08 | Prov.of semi-high mast pole at opp. Musafir Khan Nizamuddin Basti CZ w.no.154 | 272983 | 58/29.09.08/EE(E)-I | M/s Channa & Co. | 12.01.09 | P | 168427

## AC-58
S.no. | Date of Booking | Date of Consent | Name of work | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-09-23 | 11.09.08 | Dev of Storm Water drainage system from shop no.101 to shop no.K-229, shop no.K-94 to shop no.344 and shop no.232 to shop no.K-89 in C-79/CZ | 376400 | 2008-09-23
2 | 2008-09-23 | 11.09.08 | Dev of storm water drainager system from Subhash Marg to Urdu Bazar in C-79/CZ | 691700 | 2008-09-23

## AC-59
S.no. | Date of Booking | Date of Consent | Name of work | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-05-28 | 22.05.08 | Dev iof gali Mahal Sarai and side lane by pdg RMC in w.no.86/City Zone | 195072 | 48/04.07.08/EE(M)-II | M/s Gupta Builders | 25.08.08 | 29.12.08 | 195072
2 | 2008-05-28 | 22.05.08 | Dev of gali Khazoor wali and side lane in w.no.86/City Zone | 198154 | 54/04.07.08/EE(M)-II | M/s Aman Const Co. | 01.08.08 | 30.08.08 | 198086
3 | 2008-05-28 | 22.05.08 | Pdg RMC from h.no.4956 to 5120 main Kucha Rehman road and side lanes in w.no.86/City Zone | 485000 | 71/16.07.08/EE(M)-II | M/s Roop Narain Chaudhary | 25.07.08 | 16.10.08 | 478991
4 | 2008-05-28 | 22.05.08 | P/L mastic asphalt from shop no 1400 to 1306 in Farash Khana in w.no.85/S.P.Zone | 496500 | 715/13.10.08/EE(M)-II | M/s Ashok Kumar Gupta | 05.12.08 | P | 421722
5 | 2008-05-28 | 22.05.08 | P/L mastic from shop no 1471 to 1399 in Farash Khana in w.no.85/S.P.Zone | 498800 | 716/13.10.08/EE(M)-II | M/s Ashok Kumar Gupta | 05.12.08 | P | 402111
6 | 2008-05-28 | 22.05.08 | P/L cc in gali Neer Madari from h.no.2353 to 2338 and its link in Rodgran in w.no.85/S.P.Zone | 438634 | 173/10.07.08/EE(M)-II | M/s Jag Mohan Kapoor | 12.07.08 | 12.09.08 | 437607
7 | 2008-05-28 | 22.05.08 | P/L mastic asphalt from G.B. Road to 1470 in Farash Khana in w.no.85/S.P.Zone | 497700 | 718/13.10.08/EE(M)-II | M/s Ashok Kumar Gupta | 01.12.08 | P | 396311
8 | 2008-05-28 | 22.05.08 | P/L mastic asphalt from shop no 1307 to Lal Kuan Road in Farash Khana in w.no.85/S.P.Zone | 496600 | 717/13.10.08/EE(M)-II | M/s Ashok Kumar Gupta | 04.12.08 | P | 406975
9 | 2008-07-07 | 20.06.08 | C/O lane from h.no.1460 to 1454 near Rabia Girls School in gali Qasimjan Ballimaran C-86/CZ | 155515 | 178/01.08.08/EE(M)-II | M/s Aman Const Co. | 02.08.08 | 18.08.08 | 155465
10 | 2008-07-14 | 05.07.08 | Dev of katra no.1592 and 2165 in gali Chule Wali in C-85/SPZ | 199367 | 397/21.08.08/EE(M)-II | M/s Guru Kripa Const Co. | 01.16.08 | 28.11.08 | 198433
11 | 2008-07-14 | 05.07.08 | Dev of katra no.1573 Haziwala near Sarai Khalil in C-85/SPZ | 198913 | 360/11.08.08/EE(M)-II | M/s Kapoor Const. | 09.09.08 | 17.11.08 | 198521
12 | 2008-07-14 | 05.07.08 | Dev of katra no.1559 Pathamwala near Sarai Khalil in C-85/SPZ | 199249 | 393/21.08.08/EE(M)-II | M/s RP builders | 22.08.08 | 22.10.08 | 198703
13 | 2008-07-14 | 05.07.08 | Dev of Lav. Block at 24 Qtrs. Nawab Road in C-85/SPZ | 199000 | 398/21.08.08/EE(M)-II | M/s Royal Entp. | 01.09.08 | 30.10.08 | 198823
14 | 2008-09-04 | 26.08.08 | P/L of MS Signal Boards in the area of C-86/CZ | 97518 | 244/02.12.08/EE(M)-II | M/s Sh. Krishna Vashistha | 05.12.08 | 05.12.08 | 97518
15 | 2008-09-04 | 26.08.08 | Dev of lane/side lanes of Chatta Sira at Ahata kaley Sahab h.no.2013 to 2115 in C-86/CZ | 99225 | 247/02.12.08/EE(M)-II | M/s Ajay Const Co. | 02.12.08 | 12.12.08 | 99225
16 | 2008-09-18 | 26.08.08 | Const. of B/wall from behind katra bhootparet to Masque in sarai Khalil in w.no. 85/SPZ | 277352 | 691/03.10.08/EE(M)-II | M/s Divine Const Co. | 03.10.08 | 28.11.08 | 276794
17 | 2008-09-18 | 26.08.08 | P/L of RMC on road from Moter Dairy to main road Sarai Khalil in w.no.85/SPZ | 481383 | 855/17.12.08/EE(M)-II | M/s JP Const. | 26.12.08 | 27.01.09 | 480677
18 | 2008-09-29 | 03.09.08 | Dev of gali meer Jumla from Lal kua road to h.no. 1709 and other side lane in w.no. 86/City Zone | 498601 | 410/16.07.09/EE(M)-II | M/s Ajay Const Co. | 28.02.09 | 24.04.09 | 498601
19 | 2008-05-28 | 22.05.08 | Dev of gali Batarion from Kharibaoli to naya Bazar by pdg RMC in w.no. 86/City Zone | 198808
20 | 2008-05-28 | 22.05.08 | Dev of gali Kalyan and side lanes by pdg RMC in w.no.86/City Zone | 195808 | 53/04.07.08/EE(M)-II | M/s Himalya Const Co. | 12.09.08 | 05.09.09 | 195808
21 | 2008-05-28 | 22.05.08 | Dev of gali Khirkiwali by pdg RMC w.no.86/City Zone | 199629 | 52/04.07.08/EE(M)-II | M/s Mumtaz Ahmed Khan | 25.08.08 | 12.12.08 | 199629
22 | 2008-05-28 | 22.05.08 | Dev of gali from Lal Masjid to Panjabi Fatak Dalao by pdg RMC in w.no.86/City Zone | 198872 | 51/04.07.08/EE(M)-II | M/s Shokin Entp. | 14.08.08 | 09.09.08 | 198872
23 | 2008-05-28 | 22.05.08 | Dev of gali Ahata Kale Saheb main from Xing with gali Kasim Jan in w.no.86/City Zone | 197669 | 50/04.07.08/EE(M)-II | M/s Ajay Const Co. | 24.07.08 | 28.08.08 | 197669
24 | 2008-05-28 | 22.05.08 | Dev of gali Choekidar wali and chowk by pdg RMC in w.no.86/City Zone | 197024

## AC-60
S.no. | Date of Booking | Date of Consent | Name of work | Work order no. with date | Name of the agency | DOS | DOC | Amount verified | Remarks
1 | 2008-04-17 | 17.04.08 | C/o urinal block for Khoya Mandi at Mori Gate in w.no.80/City Zone | 198400
2 | 2008-04-25 | 25.04.08 | Dev of entry way of Naya Bazar at (Pilli Kothi)in w.no.80/City Zone | 536400
3 | 2008-04-25 | 25.04.08 | Dev of entry at G.T.Road entry of Kucha Mahatter Khan in w.no.80/City Zone | 195900 | 83/01.08.08/EE(M)-I | M/s Monu Entp. | 01.09.08 | 08.11.08 | 195367
4 | 2008-04-25 | 25.04.08 | Dev of entry at gali Gurudwara wali Nickalsan Road Mori Gate in w.no.80/City Zone | 198200 | 85/01.08.08/EE(M)-I | M/s Monu Entp. | 08.08.08 | 13.11.08 | 198200
5 | 2008-04-25 | 25.04.08 | Dev of entry of at Tanga Stand Road Kucha Mattar Khan in w.no.80/City Zone | 193100 | 84/01.08.08/EE(M)-I | M/s Monu Entp. | 01.09.08 | 08.11.08 | 192845
6 | 2008-04-25 | 25.04.08 | Dev by pdg stone flooring in katra Mahal Sarai in w.no.80/City Zone | 314800
7 | 2008-04-25 | 25.04.08 | Pdg RMC pav in gali Hanuman Prashad in w.no.80/City Zone | 246900 | 208/17.09.08/EE(M)-I | M/s Adbhena Engg. & Contct. | 17.10.08 | 25.12.08 | 220361
8 | 2008-06-20 | 28.05.08 | Dev of gali Telian and adj lane by pdg rmc in w.no.80/CZ | 497531 | 178/04.09.08/EE(M)-I | M/s Pooja Const. | 10.09.08 | 01.12.08 | 495492
9 | 2008-06-20 | 28.05.08 | Dev of Chatta Madan Gopal by pdg rmc in w.no.80/CZ | 499404 | 176/04.09.08/EE(M)-I | M/s Aman Const Co. | 10.09.08 | 01.12.08 | 498887
10 | 2008-06-23 | 17.05.08 | Dev of pvt.katra no.9145 to 9152 and 9176 to 9183 in Nawab Ganj C-78/CLZ by pdg kota Stone | 203300 | 127/13.10.08/EE(Pr.)/CLZ | M/s Shree Builders | 20.10.08 | P | 195202
11 | 2008-06-23 | 17.05.08 | Dev of pvt.katra no.10169 to 10175 and 10200 to Chowk in Nawab Ganj C-78/CLZ by pdg cc | 227650 | 128/13.10.08/EE(Pr.)/CLZ | M/s Shree Builders | 22.10.08 | P | 219861
12 | 2008-06-23 | 17.05.08 | Dev to katra Tejab in Nawab Ganj C-78/CLZ by pdg SW drain | 559850 | 130/13.10.08/EE(Pr.)/CLZ | M/s Shree Builders | 16.10.08 | P | 558774
13 | 2008-06-23 | 17.05.08 | Dev of Library road by dense carpetting from Azad Mkt. Chowk to Sanatan dhram mandir C-78/CLZ | 1562300
14 | 2008-05-12 | 08.04.08 | Dev of court yard and internal lane by pdg cc from 1G to 48G in Sarai Phoas in w.no.78/Civil Line Zone | 1761400
15 | 2008-06-23 | 30.05.08 | Dev of passage to Hanuman Temple by UV poly carbonet in C-77/CLZ | 2383800
16 | 2008-06-23 | 17.05.08 | Imp/Stg.of Kripa Narain marg,Maharaja Lal lane Rajnath Marg C-77/CLZ | 1784000
17 | 2008-06-23 | 19.05.08 | Dev of approach road to 6 Atour Rehman Lane in w.no.78/CLZ | 470100 | 116/21.08.08/EE(M)-II/CLZ | M/s Shree Builders | 01.09.08 | 10.11.08 | 469902
18 | 2008-06-23 | 19.05.08 | Dev of Atour Rehman Lane by pdg missing strome water drain in w.no.78/CLZ | 370000
19 | 2008-06-23 | 20.05.08 | Prov.rain water harwesting system in battrey lane w.no.78/CLZ | 499400
20 | 2008-06-23 | 20.05.08 | Dev of lane in Yamuna Bazar w.no.77/CLZ | 538000
21 | 2008-06-23 | 20.05.08 | Dev to common land near S.I office Arun Ngr. Majnu ka Tilla w.no.78/CLZ | 195000
22 | 2008-05-15 | 20.05.08 | Dev of pvt Katra no 9182,9183,9184A,9184B by pdg common flooring and drainage system at Nawab Ganj in w.no.78/Civil Line Zone | 205000
23 | 2008-05-15 | 12.05.08 | Dev of Approch Road to Dhobi Lane in Khyber Pass by M/P in w.no.77/Civil Line Zone | 313900 | 46/02.07.08/EE(M)-II | M/s RCC | 19.08.08 | 24.09.08 | 312999
24 | 2008-05-21 | 17.05.08 | Dev of approch and passage to MCW Center Kayber Pass in w.no.78/Civil Line Zone | 341800 | 63/17.07.08/EE(M)-II | M/s Barohi Const. | 21.07.08 | 24.11.08 | 242642
25 | 2008-05-21 | 17.05.08 | C/o urinal block infront of DDA Mkt. Aruna Ngr Majnu Ka Tila in w.no.78/Civil Line Zone | 262450 | 111/20.08.08/EE(M)-II | M/s Om Prakash Soni | 25.08.08 | P | 229006
26 | 2008-05-21 | 17.05.08 | Dev of lane behind Church near Army Press Khyber Pass in w.no.78/Civil Line Zone | 239200 | 62/16.07.08/EE(M)-II | M/s Barohi Const. | 21.07.08 | 24.11.08 | 174839
27 | 2008-07-08 | 24.05.08 | Dev of Chamnwara Road by RMC in C-80/CZ | 199850 | 120/12.08.08/EE(M)-I | M/s Kay Const Co. | 10.08.08 | 30.09.08 | 198937
28 | 2008-07-08 | 24.05.08 | Dev of gali Hiranand and adj lane by pdg RMC in C-80/CZ | 199338 | 127/12.08.08/EE(M)-I | M/s Monu Entp. | 16.08.08 | 15.09.08 | 199083
29 | 2008-07-08 | 24.05.08 | Dev of gali Neem wali Chhaghara,Satghara and adj lane by pdg RMC in C-80/CZ | 199153 | 190/04.09.08/EE(M)-I | M/s Yogendra Sachdeva | 01.10.08 | 12.11.08 | 198962
30 | 2008-07-08 | 24.05.08 | Dev of Bhojpura and adj lane by pdg RMC in C-80/CZ | 199151 | 128/12.08.08/EE(M)-I | M/s Bansal Entp. | 25.08.08 | 30.09.08 | 198901
31 | 2008-07-08 | 24.05.08 | Dev of main gali of katra Ishwar Dhawan by pdg RMC in C-80/CZ | 198796
32 | 2008-07-08 | 24.05.08 | Dev of gali Jute wali,gali Lade wali,gali Khanchi,gali Phool ki Bakkal and adj lane by pdg RMC in C-80/CZ | 197952 | 129/12.08.08/EE(M)-I | M/s Suman Assos. | 16.08.08 | 15.09.08 | 197952
33 | 2008-07-08 | 24.05.08 | Dev of main gali of katra Modgran and adj lanes by pdg RMC in C-80/CZ | 198395
34 | 2008-07-08 | 24.05.08 | Dev of katra Tejab and gali Batlan by pdg RMC and stone floaring in C-80/CZ | 198609
35 | 2008-07-08 | 09.4.08 | Dev of toilet and common places of Katra Ashrfi in w.no.80/CZ | 199470 | 184/04.09.08/EE(M)-I | M/s Vats Const Co. | 15.09.08 | 02.03.09 | 199167
36 | 2008-07-08 | 09.4.08 | Dev of Khoya Mandi Mori gate by raising the height of B/wall and pdg RMC on footpath in w.no.80/CZ | 450000 | 179/04.09.08/EE(M)-I | M/s Shri Krishna Vashitha | 08.09.08 | 10.11.08 | 450000
37 | 2008-07-08 | 26.06.08 | Dev of saroundnig of Walled city musiom at Lahori gate in CZ | 481500 | 86/01.08.08/EE(M)-I | M/s Monu Entp. | 09.10.08 | 08.10.08 | 478517
38 | 2008-07-08 | 26.06.08 | Dev of wall city musiom at Lahori gate CZ | 198900 | 78/30.07.08/EE(M)-I | M/s Monu Entp. | 07.10.08 | 01.10.08 | 151520
39 | 2008-07-08 | 24.05.08 | Dev of Chirakhana gali from Mali wara to Masjid by pdg RMC in w.no.80/CZ | 498641 | 169/04.09.08/EE(M)-I | M/s Ajay Bros. | 13.09.08 | 29.04.09 | 489942
40 | 2008-07-08 | 24.05.08 | Dev of Vaidwara and adj lane by pdg RMC in w.no.80/CZ | 488881
41 | 2008-07-08 | 24.05.08 | Dev of lane along Church at Church Mission road and lane by pdg RMC in w.no.80/CZ | 498765 | 186/04.09.08/EE(M)-I | M/s S.K. & Co. | 08.09.08 | 12.11.08 | 498765
42 | 2008-07-10 | 08.07.08 | Dev of intersaction near Nigam Bodh creamation ground and Ring road in w.no. 77/CLZ | 96179 | 91/05.08.08/EE(M)-II | M/s Khanna Const. | 05.08.08 | 25.08.08 | 96179
43 | 2008-07-10 | 08.07.08 | Dev of intersaction near Gaddi Suthre Shah and road to Old Yamuna Bridge in w.no. 77/CLZ | 97344 | 92/05.08.08/EE(M)-II | M/s Khanna Const. | 05.08.08 | 22.08.08 | 97045
44 | 2008-07-30 | 29.07.08 | Pdg Duct system from 4A under hill road to 10 nos under hill lane in w.no.78/CLZ | 194000
45 | 2008-07-30 | 18.07.08 | Dev to pvt katra at 9F by imp. common lav block and passage in w.no.78/CLZ at Rajpur road | 128500 | 178/09.09.08/EE(M)-II | M/s Khanna Const. | 11.09.08 | 10.10.08 | 128129
46 | 2008-07-30 | 18.07.08 | Dev to pvt katra at 9H Rajpur road by imp. drainage and cc lane in w.no.78/CLZ | 187600 | 161/05.09.08/EE(M)-II | M/s Khanna Const. | 08.09.08 | 21.10.08 | 186632
47 | 2008-07-30 | 18.07.08 | Dev of approach of Telephone exchange near Mori gate in w.no.77/CLZ | 98900 | 186/18.09.08/EE(M)-II | M/s RCC | 25.09.08 | 04.11.08 | 91808
48 | 2008-07-30 | 29..07.08 | Dev of intersaction of Pull Mithai in w.no.77/CLZ | 99300 | 187/18.09.08/EE(M)-II | M/s RCC | 24.09.08 | 06.11.08 | 99184
49 | 2008-07-30 | 29..07.08 | Dev of intersaction of Khebarpass in w.no.78/CLZ | 98500 | 184/18.09.08/EE(M)-II | M/s Khanna Const. | 18.09.08 | 18.10.08 | 98440
50 | 2008-07-30 | 29..07.08 | Dev of intersaction of Queen Mary School and Sarai Phoos road in w.no.78/CLZ | 97800 | 151/04.09.08/EE(M)-II | M/s Khanna Const. | 09.09.08 | 04.10.08 | 97255
51 | 2008-07-30 | 29..07.08 | Dev of open space and passgae at Nicolsan road near 1/783 w.no.77/CLZ | 281200
52 | 2008-08-07 | 03.08.08 | Dev Aturrehman lane by pdg missing stone water drainage in w.no.78/CLZ | 370000 | 213/06.10.08/EE(M)-II | M/s Khanna Const. | 08.10.08 | 01.12.08 | 369419
53 | 2008-08-14 | 04.08.08 | Pdg drainage system in pv. katra Car Ghar Sarai Phoos in w.no.78/CLZ | 198750
54 | 2008-08-18 | 12.05.08 | Dev of pvt. katra no.17 Boulward road in C-78/CLZ | 463800 | 129/13.10.08/EE(Pr.)/CLZ | M/s Shree Builders | 21.10.08 | 30.01.09 | 461725
55 | 2008-08-18 | 14.08.08 | Dev of main drainage system at pvt. katra no.3 Atturrehman lane in w.no.78/CLZ | 238000 | 243/13.10.08/EE(M)-II | M/s RCC | 24.10.08 | 20.01.09 | 230354
56 | 2008-08-18 | 14.08.08 | Dev of main passage of ovt. katra no.4 Atturehman lane in w.no.78/CLZ | 176100 | 258/13.10.08/EE(M)-II | M/s RCC | 20.10.08 | 22.11.08 | 162698
57 | 2008-08-25 | 25.08.08 | Dev of entrance near Dada Darbar Yamuna Bazar C-77/CLZ | 369800
58 | 2008-08-25 | 25.08.08 | Dev of entrance near Sutre Shah Yamuna Bazar C-77/CLZ | 338900
59 | 2008-08-28 | 28.08.08 | Dev of passage at pvt.katra no.32 Sham Nath MArg C-28/CLZ | 196900
60 | 2008-09-04 | 27.08.08 | Dev of foot path katra Jaipuria building by pdg Red Sand Stone in common panel in w.no.80/City Zone | 198500 | 389/13.01.09/EE(M)-I | M/s Monu Entp. | 11.02.09 | 20.03.09 | 198500
61 | 2008-09-04 | 27.08.08 | Dev of gali parathe wali adj. lane by pdg RMC in w.no.80/City Zone | 190000
62 | 2008-09-04 | 27.08.08 | Dev of flooring drainage system and laboratry block of katra no. 1982 Katra lachhu sing chah Indira in w.no.80/CZ | 190100 | 386/13.01.09/EE(M)-I | M/s Pawan builders | 14.01.09 | 28.02.09 | 190100
63 | 2008-09-03 | 03.09.08 | Dev of gali Chah Rahat from h.no. 1135 to 1144 in Dariba kalan by p/l RMC in w.no.79/CZ | 199331 | 230/01.12.08/EE(M)-II | M/s Yogendra Sachdeva | 10.12.08 | 30.01.09 | 196726
64 | 2008-09-03 | 03.09.08 | Dev of gali kucha seth from h.no. 1530 to 1578 in Dariba kalan by pdg lanes by RMC in w.no.79/CZ | 199533
65 | 2008-09-03 | 03.09.08 | Dev of gali Krishna in Dariba Kalan from gali Guliyan in 1774 in w.no. 79/CZ | 146917 | 234/01.12.08/EE(M)-II | M/s Gupta builders | 02.12.08 | 29.12.08 | 146917
66 | 2008-05-15 | 12.05.08 | Dev of Khalil wali gali by pdg RMC and drainage system in Nawabganj C-78/CZ | 469183 | 124/28.08.08/EE(M)-II | M/s Bansal Const. | 07.01.09 | 09.04.09 | 469006
67 | 2008-06-17 | 30.05.08 | Dev of approach road in pvt katra no.19 Rajniwas Marg by mettaling and premixing in C-78/CZ | 498932
68 | 2008-06-23 | 19.05.08 | Dev of pvt katra Mohsin,Kashmiri Gate by improving common latrine and court yard in C-77/CLZ | 418398
69 | 2008-06-23 | 20.05.08 | Dev of gali Mahal Sarai and side lane Kashmiri Gate in C-77/CLZ | 526088
70 | 2008-06-23 | 30.05.08 | C/O passage on both side of Bharat Sewak Samaj Khebar Pass and dev of common lav. block in C-77/CLZ | 2500037 | 242/13.10.08/EE(M)-II/CLZ | M/s Shree Builders | 23.10.08 | 18.02.09 | 2499038
71 | 2008-09-24 | 17.09.08 | Dev/Imp of Court Yard at Tikona Park Kashmiri Gate in C-77/CLZ | 97100 | 267/13.10.08/EE(M)-II | M/s RCC | 16.10.08 | 18.11.08 | 96923
72 | 2008-06-17 | 17.05.08 | Dev of Racquit road by dense carpetting from Rajpur road to Sham Nath Marg w.no.78/CLZ | 364000
73 | 2008-06-17 | 13.05.08 | Dev of lavtory Block Bhargav lane in w.no.78/CLZ | 404000
74 | 2008-06-17 | 13.05.08 | Dwv of Footpath infront of Fauzi Jat Dhramshala Jamuna Bazar w.no.77/CLZ | 379900 | 93/05.08.08/EE(M)-II | M/s Khanna Const. | 11.08.08 | 19.09.08 | 340474
75 | 2008-06-17 | 13.05.08 | Dev of open Coutryard in pvt. Katra Cristian colony Sarai Phoos w.no.78/CLZ | 513700 | 59/14.07.08/EE(M)-II | M/s Vinod Kumar | 02.08.09 | 28.01.09 | 369079
76 | 2008-06-17 | 17.05.08 | Dev of Common Coutryard and Lav. Block in Pvt. Katra no.652 to 656 in gali Nalbandan Kashmeri Gate w.no.77/CLZ | 206800 | 188/18.09.08/EE(M)-II | M/s RCC | 22.10.08 | 27.02.09 | 168716
77 | 2008-06-17 | 17.05.08 | Dev of common courtyard and drainage system in pvt.katra no 1950 Jamna Bazar in w.no.77/CLZ | 199000
78 | 2008-06-17 | 17.05.08 | Dev of common courtyard and Lav. Block in pvt. no.1949 Jamna Bazar w.no.77/CLZ | 199700
79 | 2008-06-17 | 17.05.08 | Pdg RMC and drainage system from P-24 to N-68/537 in Aruna Ngr. w.no.78/CLZ | 318000 | 64/17.07.08/EE(M)-II | M/s Aditi Const. | 24.07.08 | P | 274428
80 | 2008-06-17 | 17.05.08 | Dev of common courtyard and Lav.Block in pvt. Katra no 657 to 670 in galim Nalbadan Kashmeri Gate w.no.77/CLZ | 195000 | 190/18.09.08/EE(M)-II | M/s RCC | 22.10.08 | 12.03.09 | 165987
81 | 2008-06-17 | 17.05.08 | Imp to road from K-Block Dalao to Outer Ringroad in Aruna Ngr. w.no.78/CLZ | 463950
82 | 2008-06-17 | 17.05.08 | C/o Urinal block at Rajendra Mkt. Petrol Pump w.no.78/CLZ | 261000
83 | 2008-06-17 | 17.05.08 | C/O Urinal block near Majnu KA Tilla in w.no.78/CLZ | 255000 | 220/06.10.08/EE(M)-II | M/s RCC | 08.12.08 | 27.02.09 | 224341
84 | 2008-06-17 | 30.05.08 | Dev of common courtyard and lav. Block in pvt.katra no 680 to 684 in gali Nalbadan Kashmeri Gate w.no.77/CLZ | 199000 | 189/18.09.08/EE(M)-II | M/s RCC | 22.10.08 | 09.03.09 | 168181
85 | 2008-06-17 | 30.05.08 | P/F direction Board in CLZ from LG hs to Zonal Office in C-78/CLZ | 95017
86 | 2008-06-19 | 30.05.08 | Dev of Dhobi Wada Kinari bazar by pdg RMC w.no.80/CZ | 199852 | 183/04.09.08/EE(M)-II | M/s Roop Narain Chaudhary | 12.11.08 | P | 199246
87 | 2008-06-19 | 28.05.08 | Dev of katra Kacha Tabela and adj lane by pdg drainage and flooring in w.no.80/CZ | 199645 | 124/12.08.08/EE(M)-II | M/s Dinesh Kumar | 10.08.08 | 28.11.08 | 199179
88 | 2008-06-19 | 28.05.08 | Dev Kucha Mohatter Khan and Mori Gate by pdg drainage line in w.no.80/CZ | 199536
89 | 2008-06-19 | 28.05.08 | Dev of gali Kunjs and adj lane by pdg RMC in w.no.80/CZ | 199506 | 175/04.08.08/EE(M)-II | M/s Himalaya Const Co. | 05.09.08 | 01.10.08 | 198251
90 | 2008-06-19 | 28.05.08 | Dev of pvt katra no.2183,2158 to 2160 gali Hanuman Prashad and pvt. katra 1921 gali Mata Wali by pdg drainage and flooring in w.no.80/CZ | 199447 | 172/04.09.08/EE(M)II | M/s Ajay Const Co. | 12.11.08 | 12.01.08 | 199447
91 | 2008-06-20 | 28.05.08 | Dev of Kucha Natwa by pdg RMC in w.no.80/CZ | 499851 | 185/04.09.08/EE(M)-II | M/s Mumtaz Ahmed Khan | 12.09.08 | 12.11.08 | 499786