## Sheet1
Status Report of MLA, Sh. Mangat Ram Singhal(AC-56), 2008-09
S.No. | Date of Booking | Date of consent | Name of Work | Amount booked | Wrk order no. with date | Name of the agency | DOS | DOC | Amount Verified | Present Position
1 | 2008-07-11 | 28.06.08 | P/O lighting arrangement in MPL.Park at A-Block near h.no.1800 Jahangirpuri in C-16/CLZ | 169792 | 148/03.10.08/EE(E)-II | M/s Kamal Electricals | 10.10.08 | 16.11.08 | 165770 | Work Completed
2 | 2008-07-29 | 03.07.08 | C/o B/wall of park near h.no.E-51X and E-68X inSlum Tenaments inC-15/CLZ | 352623 | 322/28.07.09/EE(M)-III | M/s Prakash Khanna | 19.09.08 | P | 346182 | In Prog.
3 | 2008-07-29 | 10.07.08 | Dev. of side berms by pdg.RMC (LHS)from POLICE Post (Prayas)to Mahindra Park in Slum Tenaments in C-15/CLZ. | 481863 | 325/10.09.08/EE(M)-III | M/s Tarun Const co. | 22.09.08 | 16.02.09 | 478905 | Work Completed
4 | 2008-07-29 | 10.07.08 | C/O drain and culvert along both sides of Post office road from Police post (Prayas)to Mahinder park in Slum Tenaments in C-15/CLZ | 491531 | 301/10.09.08/EE(M)-III | M/s Tarun Const co. | 10.10.08 | 16.02.09 | 491531 | Work Completed
5 | 2008-07-29 | 03.07.08 | C/O B/wall of park near D-62X in Slum Tenaments in C-15/CLZ | 477786 | 321/10.09.08/EE(M)-III | M/s Jai Kumar | 10.10.08 | 16.02.09 | 476205 | Work Completed
6 | 2008-07-29 | 10.07.08 | C/O of Footpath and MS grill inmain park of Slum Tenaments in block B in C-15/CLZ | 499486 | 305/10.09.08/EE(M)-III | M/s Subash Const Co. | 10.10.08 | 18.02.09 | 498567 | Work Completed
7 | 2008-07-29 | 10.07.08 | Dev of side berms by pdg RMC(RHS)from Police Post(Prayas) to Mahindra Park in Saleem Teramrts in C-15/CLZ | 477968 | 310/10.09.08/EE(M)-III | M/s Tarun Const co. | 22.09.08 | 16.02.09 | 477712 | Work Completed
8 | 2008-07-29 | 03.07.08 | C/O B/Wall of park near h.no. D-37X to D-57X in Slum Tenaments in C-15/CLZ | 359834 | 277/08.09.08/EE(M)-III | M/s vinod kumar | 17.09.08 | 16.02.09 | 359834 | Work Completed
9 | 2008-08-06 | 29.07.08 | Dev of Parking space infront of h.no. 231(near Dal Mill) in Village Sarai Pipal Thala in C-15/CLZ | 393193 | 297/10.09.08/EE(M)-III | M/s Suresh Pal Rana | 10.10.08 | 16.02.09 | 391570 | Work Completed
10 | 2008-08-06 | 19.07.08 | C/O B/Wall of park near Flat no. F-23X in Slum Tenament in C-15/CLZ | 499447 | 304/10.09.08/EE(M)-III | M/s Tarun Const co. | 19.09.08 | 29.04.09 | 499334 | Work Completed
11 | 2008-08-06 | 28.07.08 | Dev of lane by pdg RMC and drainage system from h.no. 1 to 20 and h.no. 41 to 45 in Village Sarai Pipal Thala in C-15/CLZ | 439495 | 323/10.09.08/EE(M)-III | M/s Prakash Khanna | 10.10.08 | 16.02.09 | 434645 | Work Completed
12 | 2008-08-12 | 26.06.08 | Dev of footpath at Ramlila Ground in H-Block Jahangirpuri in C-16/CLZ | 473296 | 295/10.09.08/EE(M)-III | M/s Tarun Const co. | 19.09.08 | 17.02.09 | 472489 | Work Completed
13 | 2008-08-12 | 26.06.08 | Dev of B/Wall of Ramlila Ground at H-Block Jahangirpuri in C-16/CLZ | 375200
14 | 2008-09-01 | 30.08.08 | Dev of lane by pdg RMC and drainage system from h.no.2 to h.no.39 in Village Sarai Pipal Thala in C-15/CLZ | 495440
15 | 2008-09-01 | 27.08.08 | Dev of lane by pdg RMC and drainage system from NDPL Transfarmer to Dalao in Village Bharola in C-15/CLZ | 497998 | 359/23.09.08/EE(M)-III | M/s Shiv Shakti Sales Entp. | 10.10.08 | 27.02.09 | 497002 | Work Completed
16 | 2008-09-01 | 27.08.08 | Dev of Chowk and lane by pdg RMC and drainage system from h.no.140 to 137 in Village Bharola in C-15/CLZ | 497505 | 409/23.10.08/EE(M)-III | M/s Jai Kumar | 29.10.08 | 23.03.09 | 494505 | Work Completed
17 | 2008-09-01 | 27.08.08 | Dev of lane by pdg RMC and drainage system from h.no.12 to Sweet Shop near Tyagi Mkt. in Village Bharola in C-15/CLZ | 495362 | 408/23.10.08/EE(M)-III | M/s Jai Kumar | 24.10.08 | 30.03.09 | 494091 | Work Completed
18 | 2008-09-01 | 27.08.08 | Dev of lane by pdg RMC and DDA Flats from B-47 to B-37,B-25 to B-36 and B-1 to B-12 in Village Bharola in C-15/CLZ | 494092 | 355/22.09.08/EE(M)-III | M/s vinod kumar | 01.10.08 | P | 488765 | In Prog.
19 | 2008-09-01 | 23.08.08 | Dev of lane by pdg RMC and drainage system from h.no.69 to 86 in Village Bharola in C-15/CLZ | 498488 | 354/22.09.08/EE(M)-III | M/s vinod kumar | 01.10.08 | 09.02.09 | 498488 | Work Completed
20 | 2008-09-01 | 23.08.08 | Dev of lane by pdg RMC and drainage system from M.C.Pry.School to Bari Chaupal in Village Bharola in C-15/CLZ | 484545 | 414/23.10.08/EE(M)-III | M/s Tarun Const co. | 27.10.08 | 23.03.09 | 484545 | Work Completed
21 | 2008-09-04 | 23.08.08 | Dev of lane by pdg RMC and drainage system from h.no.83 to 95 in Village Bhorala in C-15/CLZ | 463410
22 | 2008-09-04 | 30.08.08 | Dev of Punjabi gali by pdg RMC and drainage system from h.no.236 to 247 in Village Sarai Pipal Thala in C-15/CLZ | 495209 | 419/24.10.08/EE(M)-III | M/s Shiv Shakti Sales Entp. | 03.11.08 | 20.02.09 | 493632 | Work Completed
23 | 2008-09-04 | 30.08.08 | Dev of lane by pdg RMC and drainage system from GTK road to h.no.199/1 and from h.no.220 to Shiv Mandir 247 in Village Sarai Pipal Thala in C-15/CLZ | 497263 | 424/24.10.08/EE(M)-III | M/s Suresh Pal Rana | 02.11.08 | P | 494770 | In Prog.
24 | 2008-09-04 | 30.08.08 | Dev of lane by pdg RMC and drainage system from h.no.2 to h.no.319 in Village Sarai Pipal Thala in C-15/CLZ | 499094 | 407.23.10.08/EE(M)-III | M/s vinod kumar | 01.11.08 | 18.02.09 | 499094 | Work Completed
|  |  |  | 10909920 |  |  |  |  | 9537636

## Sheet2
Status Report of MLA, Sh. Kunwar Karan Singh(AC-62), 2008-09
S.No. | Date of Booking | Date of consent | Name of Work | Amount booked | Work order no. with date | Name of the agency | DOS | DOC | Amount Verified | Present Position
1 | 2008-06-23 | 09.06.08 | Dev of service lane along G.T.road from A-1 to A-22 Gunjrawala Town Part-1 in C-71/CLZ | 1870200 | 251/03.09.08/EE(M)-III | M/s Bansal Const. | 06.09.08 | P | 1838990 | In Pro.
2 | 2008-06-23 | 13.06.08 | P/F MS steel benches in parks under jurisdiction of w.no.70/CLZ | 393800 | 436/27.10.08/EE(M)-III | M/s Vipin Traders | 19.12.08 | 04.03.09 | 391200 | Work Completed
3 | 2008-06-23 | 22.04.08 | Dev of cc pav near h.no.E-1 to E-1/103,E-2/1 to E-4/20,E-4/10 to E-4/20 to E-4/21A in E-block Model Town, in C-72/CLZ | 247800 | 210/07.08.08/EE(M)-III | M/s Triveni Const & Govt. Supp. | 14.08.08 | 04.09.08 | 247737 | Work Completed
4 | 2008-07-09 | 04.10.07 | Dev of road from H-2/4 to D-12/14 Model Town-II by pdg RMC in C-72/CLZ | 2485000
5 | 2008-07-09 | 30.06.08 | P/F M.S. Street name boards in Rana Pratap Bagh Gupta Colony Kalyan Vihar Priya darshi Vihar etdc in C-70/CLZ | 320000
6 | 2008-07-15 | 01.05.08 | Dev of lane by pdg RMC near h.no.T-72, T-158, near Suresh hs, h.no.T-83, T123 and adj lanes in Rajpura Gurmandi in C-70/CLZ | 499300
7 | 2008-07-15 | 03.06.08 | Dev of B/Wall of park opp. h.no.88 and another park opp h.no.43 to 54 in Priya Darshni Vihar in C-70/CLZ | 468300 | 228/20.08.08/EE(M)-III | M/s Sharique Entp. | 26.08.08 | P | 466274 | In Pro.
8 | 2008-07-15 | 01.05.08 | Dev of lane by pdg RMC near h.no.T-136 to T-46 near Bhagmal Hs.Pali Hs. T-110, T-58 and adj lanes in Rajpura Gurmandi in C-70/CLZ | 499500
9 | 2008-07-15 | 14.07.08 | Dev of B/Waqll of E-block park of cc Colony in C-70/CLZ | 458100 | 175/30.07.08/EE(M)-III | M/s Balgar singh & Bros. | 09.08.08 | P | 323271 | In Pro.
10 | 2008-07-15 | 14.07.08 | Dev of B /Wall of C-Block park in CC Colony in C-70/CLZ | 484200 | 173/30.07.08/EE(M)-III | M/s Balgar singh & Bros. | 07.08.08 | P | 324473 | In Pro.
11 | 2008-07-15 | 14.07.08 | Dev of Lajpat RAi park of OLd Gupta Colony in c-70/CLZ | 214300 | 174/30.07.08/EE(M)-III | M/s Balgar singh & Bros. | 08.08.08 | P | 212670 | In Pro.
12 | 2008-07-28 | 03.07.08 | Stg of road by pdg dence carpet from h.no. A-12 to A-27 in CC Colony in C-70/CLZ | 925900
13 | 2008-07-28 | 14.07.08 | Pdg drainage system from h.no.109 to 132 in Gur Mandi in C-70/CLZ | 199971
14 | 2008-07-30 | 04.07.08 | Dev of common facilities in B-Block Sangam Park C-71/CLZ (SH:- Dev of common stairs in B-Block from h.no. B-1 to B-32 in Sangam Park in C-71/CLZ | 616000
15 | 2008-07-31 | 21.07.08 | Dev of B/Wall and Walkway of chacha Park in Gurmandi in C-70/CLZ | 99900 | 399/15.10.08/EE(M)-III | M/s Sharique Entp. | 21.10.08 | 23.12.08 | 98900 | Work Completed
16 | 2008-08-01 | 04.07.08 | Stg of road by pdg dense carpet from h.no. B-61 to B-48 in CC Colony in C-70/CLZ | 520400
17 | 2008-08-21 | 01.08.08 | Dev. of lane by pdg RMC from gate of old Gupata cly to Kaltyan vihar main road along Gym. in Kalyan vihar w.no.70/CLZ | 791639 | 273/05.09.08/EE(M)-III | M/s SK Gupta & Co. | 17.09.08 | P | 489322 | In Pro.
18 | 2008-08-21 | 01.08.08 | Dev of B/wall of park near h.no. B-33, B-34 in cc cly in w.no.70/CLZ | 791883 | 264/05.09.08/EE(M)-III | M/s SK Gupta & Co. | 15.09.08 | P | 775003 | In Pro.
19 | 2008-08-21 | 01.08.08 | Dev of Gurunanak gali by RMC and drainage and interlocking tiles in old Gupta cly. in w.no.70/CLZ | 694163 | 272/05.09.08/EE(M)-III | M/s SK Gupta & Co. | 08.09.08 | P | 278076 | In Pro.
20 | 2008-04-29 | 28.04.08 | Dev of backlane of D-17 to D-60 by pdg M.S. Gratings in Azad Pur Mpl. colony in w.no.72/CLZ | 198712 | 123/25.06.08/EE(M)-III | M/s Goldy & Co. | 02.07.08 | P | 193126 | In Pro.
21 | 2008-09-18 | 02.08.08 | Dev of common facilities in B block Sangam park in c-71/CLZ Sh:- Dev of common stairs in B block from h.no. B-33 to B-64 in Sangam park in C-71/CLZ | 616000
22 | 2008-09-18 | 02.08.08 | Dev of common facilities in B block Sangam park in c-71/CLZ Sh:- Dev of common stairs in B block from h.no. B-65 to B-96 in Sangam park in C-71/CLZ | 616000
23 | 2008-09-18 | 02.08.08 | Dev of common facilities in B block Sangam park in c-71/CLZ Sh:- Dev of common stairs in B block from h.no. B-99 to B-128 in Sangam park in C-71/CLZ | 616000
24 | 2008-09-18 | 02.08.08 | Dev of common facilities in B block Sangam park in c-71/CLZ Sh:- Dev of common stairs in B block from h.no. B-129 to B-160 in Sangam park in C-71/CLZ | 616000
25 | 2008-09-18 | 02.08.08 | Dev of common facilities in B block Sangam park in c-71/CLZ Sh:- Dev of common stairs in B block from h.no. B-161 to B-192 in Sangam park in C-71/CLZ | 616000
26 | 2008-09-18 | 01.08.08 | Dev of B/wall of park near h.no. B-55 and lane along park in CC cly. w.no.70/CLZ | 708862
27 | 2008-10-01 | 08.09.08 | Dev of backlane by P/L interlocking tiles from h.no.255 to 248 in Kalyan Vihar in C-70/CLZ | 612743
28 | 2008-10-03 | 03.10.08 | Dev of lane by pdg RMC from B-3/6 to B-2/6 and B-2/11 to B-3/11 in Rana Pratap Bagh in C-70/CLZ | 463400 | 525/07.01.09/EE(M)-III | M/s Satbir Singh | 09.01.09 | P | 309956 | In Pro.
29 | 2008-10-03 | 03.10.08 | Dev of B/Wall of Park near Laxmi Narain Mandir in B-Block Rana Pratap Bagh in C-70/CLZ | 596800
30 | 2008-10-03 | 18.09.08 | Stg. of road by pdg bituman mastic wearing course from C-1/1 to C-1/6,C-1 to C-5,Main Road between Sardar Ngr. A-4/6 to Ramlila Ground,A-1 to D-29 and along Mkt. in Sardar Ngr. in C-70/CLZ | 2499700
|  |  |  | 20740573 |  |  |  |  | 5948998

## Sheet5
MLA Report of Sh. Shadi Ram (AC-63), 2008-09
S.no. | Date of Booking | Date of consent | Name of Work | Amount Booked | Work order no. with date | Name of the agency | DOS | DOC | Bill verified | Present Status
1 | 2008-06-19 | 31.05.08 | C/o lane by pdg cc pav and drainage system from h.no. 80 to 89 in Anand Nagar C-74/KBZ | 307150 | 242/10.09.08/EE(M)-II/KBZ | M/s Harpreet Arora | 10.09.08 | 08.12.08 | 304427 | Work Completed
2 | 2008-06-19 | 31.05.08 | C/o lane by pdg cc pav from h.no. 107 to 112 and adj lane in Anand Nagar C-74/KBZ | 367400 | 323/13.10.08/EE(M)-II/KBZ | M/s Chimmy Const Co. | 24.10.08 | 07.01.09 | 367270 | Work Completed
3 | 2008-06-19 | 16.05.08 | Pdg cc pavment with drainage in lane and adj lane from h.no. B-3/17 near Dispensary in Inderlok in C-74/KBZ | 199909 | 271/03.09.08/EE(M)-II/KBZ | M/s RP Const. Co. | 20.09.08 | 10.12.08 | 194122 | Work Completed
4 | 2008-06-19 | 16.05.08 | Pdg cc pav. with drainage in lane and adj lanes from h.no. B-5/33 to B-5/40, B block Inderlok C-74/KBZ | 199260 | 265/01.09.08/EE(M)-II/KBZ | M/s JD Const Co. | 10.09.08 | 24.10.08 | 199214 | Work Completed
5 | 2008-06-19 | 16.05.08 | Pdg cc pav. with drainage from h.no. A-18 in Inderlok C-74/KBZ | 199973 | 268/01.09.08/EE(M)-II/KBZ | M/s Sonu builders | 10.09.08 | 21.11.08 | 199973 | Work Completed
6 | 2008-06-19 | 16.05.08 | Dev of side berms by Pdg cc from entrance gate Inderlok to 33/44B -22 in Inderlok C-74/KBZ | 107650 | 266/01.09.08/EE(M)-II/KBZ | M/s Unique Const. | 10.09.08 | 19.01.09 | 107629 | Work Completed
7 | 2008-06-19 | 31.05.08 | C/o road by pdg cc pavment from h.no. 117 to 37 and h.no. 41 to 43A in Anand nagar C-74/KBZ | 499200 | 324/13.10.08/EE(M)-II/KBZ | M/s S. Gupta Const Co. | 14.10.08 | 05.12.08 | 498933 | Work Completed
8 | 2008-06-19 | 17.05.08 | Pdg cc and drainage from h.no. 19/274 to 19/260 to 19/246 and adj lanes in Sarai basti near TB centre C-74/KBZ | 367700 | 417/05.01.09/EE(M)-II/KBZ | M/s United Const co. | 07.01.09 | 25.02.09 | 298420 | Work Completed
9 | 2008-06-19 | 16.05.08 | Pdg cc and flooring from h.no. 19/240 to 19/230, 19/239 to 19/235 and adj lanes in Sarai basti C-74/KBZ | 303100 | 418/05.01.09/EE(M)-II/KBZ | M/s United Const co. | 07.01.09 | 02.03.09 | 245993 | Work Completed
10 | 2008-06-19 | 16.05.08 | Pdg cc flooring from h.no. 313/76C to h.no. 313/90A and adj. in Tulsi nagar C-74/KBZ | 385000 | 420/05.01.09/EE(M)-II/KBZ | M/s United Const co. | 14.01.09 | 31.03.09 | 314309 | Work Completed
11 | 2008-06-19 | 16.05.08 | Pdg cc and draiage from h.no. B-2A to C-1/19A and adj lanes near Dhobi ghat in DDa flats sarai basti C-74/KBz | 362700 | 480/30.01.09/EE(M)-II/KBZ | M/s United Const co. | 31.01.09 | 09.03.09 | 290857 | Work Completed
12 | 2008-06-19 | 31.05.08 | C/oback lane in B-8 block by pdg cc and drainage system in Inderlok C-74/KBz | 225500 | 240/01.09.08/EE(M)-II/KBZ | M/s Pappu Seth | 01.09.08 | 04.11.08 | 224037 | Work Completed
13 | 2008-06-19 | 16.05.08 | Pdg cc flooring from h.no. 19/200 to 19/185 and adj lanes in sarai basti near Usha MAta MAndir C-74/KBZ | 365000 | 419/05.01.09/EE(M)-II/KBZ | M/s United Const co. | 07.01.09 | 02.03.09 | 298779 | Work Completed
14 | 2008-06-19 | 16.05.08 | dev to road by pdg cc from road no.40 petrol pump to factory no. 308/16 in Shahzada bagh Indl. area C-74/KBZ | 487200 | 421/14.01.09/EE(M)-II/KBZ | M/s Malhotra const Co. | 15.01.09 | 16.02.09 | 398643 | Work Completed
15 | 2008-06-20 | 16.05.08 | Pdg cc and drainage from factory no.82 to plot no.65 and adj in Shahzada bagh extn. C-74/KBZ | 361000 | 411/01.01.09/EE(M)-II/KBZ | M/s United Const co. | 10.01.09 | 25.03.09 | 301159 | Work Completed
16 | 2008-07-09 | 16.05.08 | Imp to lane by pdg RMC pav. and drainage system from gali no.7 in M block Shastri nagar in C-73/SPZ | 489000 | 732/13.10.09/EE(M)-I/SPZ | M/s Vardaan builders | 13.10.08 | 02.12.08 | 489000 | Work Completed
17 | 2008-07-09 | 16.05.08 | Imp to lane by pdg cc pav. and drainage system L-11 to L-20 in Shastri nagar w.no. 73/SPZ | 445000 | 774/13.10.09/EE(M)-I/SPZ | M/s Sonu builders | 16.10.08 | 28.02.09 | 444485 | Work Completed
18 | 2008-07-09 | 16.05.08 | Imp to lane by pdg cc pav. and drainage system from B-1555 to MC Pry School Lalita block in Shastri nagar w.no. 73/SPZ | 440607 | 441/22.08.08/EE(M)-I/SPZ | M/s V.K Assos. | 05.09.08 | 18.10.08 | 440368 | Work Completed
19 | 2008-07-09 | 16.05.08 | Imp to lane by pdg cc pav. and drainage system from B-1527 to Nand Kishore gupta marg in Shastri nagar w.no. 73/SPZ | 440000 | 655/22.09.08/EE(M)-I/SPZ | M/s Akriti Const | 29.09.08 | 18.12.08 | 440000 | Work Completed
20 | 2008-07-09 | 16.05.08 | Imp to lane by pdg RMC pav. and drainage system from Gurudwara to B-1605 in Shastri nagar w.no. 73/SPZ | 489000 | 444/22.08.08/EE(M)-I/SPZ | M/s Bhatia Const Co. | 28.08.08 | 05.12.08 | 489000 | Work Completed
21 | 2008-07-09 | 16.05.08 | Imp to lane by pdg RMC pav. and drainage system from B-1680 to B-1693 in Shastri nagar w.no. 73/SPZ | 498621 | 440/22.08.08/EE(M)-I/SPZ | M/s Kunal Tehri | 03.09.08 | 22.11.08 | 498204 | Work Completed
22 | 2008-07-09 | 16.05.08 | Imp to lane by pdg RMC pav. and drainage system from B-1782 to Sr. Sec. School Lalita block back side in Shastri nagar w.no. 73/SPZ | 496627 | 442/22.08.08/EE(M)-I/SPZ | M/s Manoj Kumar Bhatia | 30.08.08 | 24.11.08 | 496339 | Work Completed
23 | 2008-07-09 | 16.05.08 | Imp to lane by pdg RMC pav. and drainage system from B-1715 to B-1730 in Shastri nagar w.no. 73/SPZ | 498000 | 852/17.12.08/EE(M)-I/SPZ | M/s D.K const Co. | 18.12.08 | 17.02.09 | 497319 | Work Completed
24 | 2008-07-09 | 16.05.08 | Imp to lane by pdg RMC pav. and drainage system from E-204 to road no.40 in Shastri nagar w.no. 73/SPZ | 489749 | 445/22.08.08/EE(M)-I/SPZ | M/s Shivansh Const. | 28.08.08 | 18.10.08 | 489609 | Work Completed
25 | 2008-07-09 | 16.05.08 | Imp to lane by pdg cc pav. and drainage system from L-1 to L-10 in Shastri nagar w.no. 73/SPZ | 480651 | 346/11.08.08/EE(M)-I/SPZ | M/s Durga builders | 16.08.08 | 05.12.08 | 480030 | Work Completed
26 | 2008-07-09 | 16.05.08 | Dev. of road by pdg RMC pav. and drainage system from L-269 to L-266 and along Shastri nagar w.no. 73/SPZ (along shastri booth park) | 459000 | 230/22.07.08/EE(M)-I/SPZ | M/s Som Dutt Dwevedi | 18.09.08 | 24.10.08 | 458895 | Work Completed
27 | 2008-07-09 | 16.05.08 | Imp to lane by pdg cc pav. and drainage system from L-2/276 to post office in Shastri nagar w.no. 73/SPZ | 403000 | 347/11.08.08/EE(M)-I/SPZ | M/s Rajesh Kumar | 28.08.08 | 17.11.08 | 402715 | Work Completed
28 | 2008-07-09 | 16.05.08 | Imp to lane by pdg RMC pav. and drainage system from E-53 to E-110 in Shastri nagar w.no. 73/SPZ | 499000 | 485/22.08.08/EE(M)-I/SPZ | M/s Chaudhary const. | 08.09.08 | 18.11.08 | 498862 | Work Completed
29 | 2008-07-09 | 16.05.08 | Imp to lane by pdg RMC pav. and drainage system from L-177 to L-168 (front lane) in Shastri nagar w.no. 73/SPZ | 498975 | 573/09.09.08/EE(M)-I/SPZ | M/s Essco Traders | 15.09.08 | 14.04.09 | 498013 | Work Completed
30 | 2008-07-09 | 16.05.08 | Dev to lane by pdg RMC pav. and drainage system from gali no.13 in M block in Shastri nagar w.no. 73/SPZ (RHS) | 383000 | 471/22.08.08/EE(M)-I/SPZ | M/s Jupiter Const. | 27.08.08 | 10.08.08 | 383000 | Work Completed
31 | 2008-07-09 | 16.05.08 | Imp to lane by pdg RMC pav. and drainage system from gali no.12 in M block Shastri nagar w.no. 73/SPZ (LHS) | 449000 | 737/13.10.08/EE(M)-I/SPZ | M/s Arora Const Co. | 22.10.08 | 04.12.08 | 448623 | Work Completed
32 | 2008-07-09 | 16.05.08 | Imp to lane by pdg RMC pav. and drainage system from gali no.12 in M block Shastri nagar w.no. 73/SPZ (RHS) | 485689 | 634/22.09.08/EE(M)-I/SPZ | M/s Kapoor Const. | 30.09.08 | 10.12.08 | 485345 | Work Completed
33 | 2008-07-09 | 16.05.08 | Imp to lane by pdg cc pav. and drainage system from L-2/22 to L-2/30 in Shastri nagar w.no. 73/SPZ (LHS) | 389537 | 86817.12.08/EE(M)-I/SPZ | M/s Kalra Const. | 22.12.08 | 20.01.09 | 388933 | Work Completed
34 | 2008-07-09 | 16.05.08 | Dev to lane by pdg cc pav. and drainage system from B-1731 to B-1757 (back lane)in Shastri nagar w.no. 73/SPZ (LHS) | 497004 | 799/11.12.08/EE(M)-I/SPZ | M/s J.P. const Co. | 16.12.08 | 22.01.09 | 496741 | Work Completed
35 | 2008-07-09 | 31.05.08 | Dev.of lane by pdg. RMC pav. and draiage system from h. no.A-80 toA-507/1A in Shastri Nagar in C-73/SPZ. | 478683 | 220/22.07.08/EE(M)-I/SPZ | M/s Mohd. Rashid | 30.07.08 | 21.10.08 | 478643 | Work Completed
36 | 2008-07-09 | 16.06.08 | Dev of road by pdg RMC pav. and drainage system from A-721 to A-708 in shastri Ngr.in C-73/SPZ | 497088 | 436/22.08.08/EE(M)-I/SPZ | M/s S.K. entp. | 26.08.08 | 03.10.08 | 496979 | Work Completed
37 | 2008-07-09 | 16.06.08 | Dev of lane by pdg RMC pav. and drainage system from h.no.A-684 to A-695 in Shastri Ngr. C-73/SPZ | 498803 | 703/13.10.08/EE(M)-I/SPZ | M/s Deepali builders | 20.10.08 | 14.12.08 | 498676 | Work Completed
38 | 2008-07-09 | 16.06.08 | Dev of lane by pdg RMC and drainage system from h.no.A-681 to Shiv Mandir in Shastri Ngr. C-73/SPZ | 498133 | 224/22.07.08/EE(M)-I/SPZ | M/s Pawan Const. | 16.08.08 | 08.10.08 | 498004 | Work Completed
39 | 2008-07-09 | 16.06.08 | Dev of lane by pdg cc pav. and drainage system from A-683 to A-707 in Shastri Ngr. C-73/SPZ | 419379 | 1182/24.02.09/EE(M)-I/SPZ | M/s Sonu builders | 27.02.09 | 02.05.09 | 418670 | Work Completed
40 | 2008-07-09 | 16.06.08 | Dev to lane by pdg cc and drainage syustem from h.no.L-177 to L-168(backlane)in Shastri Ngr. C-73/SPZ | 423825 | 455/22.08.08/EE(M)-I/SPZ | M/s Jolly const co. | 20.9.08 | 30.11.08 | 423503 | Work Completed
41 | 2008-07-09 | 31.05.08 | Dev by pdg RMC pav. and drainage system from E-2/103 to E-2/84 in Shastri Ngr. C-73/SPZ | 498678 | 473/22.08.08/EE(M)-I/SPZ | M/s Jain Const. | 28.08.08 | 22.10.08 | 498555 | Work Completed
42 | 2008-07-09 | 31.05.08 | Dev by pdg RMC pav. and drainage system from E-2/206 to E-2/189 in Shastri Ngr. C-73/SPZ | 498983 | 474/22.08.08/EE(M)-I/SPZ | M/s Deepak Kumar | 02.09.08 | 22.10.08 | 498430 | Work Completed
43 | 2008-07-09 | 31.05.08 | Dev by pdg RMC pav. and drainage system from E-2/28 to E-2/18 in Shastri Ngr. in C-73/SPZ | 498014 | 660/22.09.08/EE(M)-I/SPZ | M/s Sethi Entp. | 30.09.08 | 22.12.08 | 497840 | Work Completed
44 | 2008-07-09 | 31.05.08 | Dev by pdg cc pav. and drainage system from B-1701 to B-1730 on Shastri Ngr. in C-73/SPZ | 486906 | 536/09.09.08/EE(M)-I/SPZ | M/s Prakash Traders | 06.10.08 | 12.12.08 | 486860 | Work Completed
45 | 2008-07-09 | 31.05.08 | Dev by pdg ARMC pav. and drainage system from A-400/9 to A-437 in Shastri Ngr.C-73/SPZ | 497745 | 366/11.08.08/EE(M)-I/SPZ | M/s Bhatia Const Co. | 28.08.08 | 17.11.08 | 497686 | Work Completed
46 | 2008-07-09 | 31.05.08 | Dev by pdg RMC pav.and drainage system from A-545 to A-609 in Shastri ngr.in C-73/SPZ | 495431 | 345/11.08.08/EE(M)-I/SPZ | M/s Shri Madhav builders | 18.08.08 | 04.12.08 | 495253 | Work Completed
47 | 2008-07-09 | 31.05.08 | Dev by pdg RMC pav. and drainage system from A-730 to Main road in Shastri Ngr. C-73/SPZ | 498048 | 439/22.08.08/EE(M)-I/SPZ | M/s Sanjeev builders | 26.08.08 | 03.10.08 | 497536 | Work Completed
48 | 2008-07-09 | 31.05.08 | Dev of lane by pdg RMC and drainage system from B-1903 to B-1912 in Shastri Ngr. c-73/SPZ | 497951
49 | 2008-07-09 | 31.05.08 | Dev by pdg RMC and drainage system from B-1416 to B-1467 in Shastri Ngr. C-73/SPZ | 496571 | 801/11.12.08/EE(M)-I/SPZ | M/s R.P. Entp. | 15.12.08 | 19.01.09 | 495964 | Work Completed
50 | 2008-07-09 | 31.05.08 | Dev by pdg RMC pav. and drainage system from B-1084 to B-1073 in Shastri Ngr. C-73/SPZ | 495403 | 437/22.08.08/EE(M)-I/SPZ | M/s Arora Const Co. | 15.09.08 | 29.11.08 | 495143 | Work Completed
51 | 2008-04-21 | 01.04.08 | Dev of drainage system and p/l cc pav in pvt katra no.15/4 in Sakti Ngr in w.no.69/SPZ | 196067 | 94/30.06.08/EE(M)-III | M/s Royal Entp. | 01.07.08 | 02.08.08 | 195969 | Work Completed
52 | 2008-08-29 | 31.05.08 | C/O road by pdg RMC from Inderlok Gurudwara to h.no.65 in Anand Ngr.C-74/KBZ | 677300
|  |  |  | 22222210 |  |  |  |  | 20542957

## Sheet4
Status Report of MLA fund for the year 2008-09. MLA: Sh. Surender Pal Singh (Bittoo) (AC-61)
S.no. | Date of Booking | Date of consent | Name of Work | Booking Amount | Work order no. with date | Name of the agency | DOS | DOC | Amount Verified | Present Status
1 | 2008-06-23 | 30.05.08 | Stg. of road from Hanuman MAndir to C-23 in Vijay Nagar S/S in C-12/CLZ | 1002500
2 | 2008-06-23 | 30.05.08 | Pdg mastic wearing coat from h.no. H-8B to Gurudwara in Vijay nagar S/S in C-12/CLZ | 499200
3 | 2008-06-23 | 30.05.08 | Dev to park infront of h.no. 526 in West PArmanand cly. C-12/CLZ | 518100 | 106/12.08.08/EE(M)-II | M/s Balkar Singh & Bros. | 13.09.08 | 20.11.08 | 498128 | Work Completed
4 | 2008-06-23 | 20.05.08 | Dev of back lane by pdg cc from h.no. 672 to 685 in Mukherji nagar C-11/CLZ | 172000 | 156/05.09.08/EE(M)-II | M/s Abhay Const.Co. | 14.09.08 | 29.10.08 | 172000 | Work Completed
5 | 2008-06-23 | 20.05.08 | Dev of back lane by pdg cc from 950 to 969 in Mukherji nagar C-11/CLZ | 248100 | 176/09.09.08/EE(M)-II | M/s Abhay Const.Co. | 18.09.08 | 22.10.08 | 248100 | Work Completed
6 | 2008-06-23 | 14.06.08 | Dev. of Internal drain infront of gate no.2 in Mall Apptt. in C-/CLZ | 377300 | 159/05.09.08/EE(M)-II | M/s Balkar Singh & Bros. | 14.09.08 | P | 368549 | In Prog.
7 | 2008-06-30 | 27.06.08 | P/O semi high mast pole near gali no.5 in Wazirabad inC-10/CLZ | 188932
8 | 2008-06-30 | 27.06.08 | P/O semi high mast pole at Mpl.park near Allahabad Bank,Luckhnow road Timar pur in C-10/CL. | 184441 | 103/28.08.08/EE(E)-II | M/s Cheena & Co. | 01.09.08 | 12.09.08 | 176408 | Work Completed
9 | 2008-06-30 | 27.06.08 | P/O semi high mast pole near gali no.17 in Wazirabad in C-10/CLZ | 186779
10 | 2008-06-30 | 27.06.08 | P/O semi high mast pole in Mpl. park (Tikona Park)near T-point Mukharji Ngr. in C-11/CLZ | 188416 | 116/12.09.08/EE(E)-II | M/s Bhima Electricals | 17.09.08 | 15.10.08 | 182519 | Work Completed
11 | 2008-06-30 | 27.06.08 | P/O semi high mast pole near Hari Mandir in Mukharji Ngr. in C-11/CLZ | 186312 | 105/04.09.08/EE(E)-II | M/s Cheena & Co. | 06.09.08 | 13.09.08 | 175808 | Work Completed
12 | 2008-06-30 | 27.06.08 | P/O semi high mast pole near Dhakka Jod infront of MCD Colony,Dhakka in C-11/CLZ | 188883 | 104/04.09.08/EE(E)-II | M/s Super Electricals | 10.09.08 | 30.04.09 | 183317 | Work Completed
13 | 2008-07-03 | 01.06.08 | Dev to lane by pdg cc and drainage system of Gautam Gali (main road) Malka Ganj to h.no.507 and Chakki wali gali (main road h.no.821/822 to Dr. Rehman Clinic in C-9/CLZ | 592800 | 123/27.08.08/EE(M)-II | M/s Sanjeev Builders | 05.09.08 | 29.12.08 | 590939 | Work Completed
14 | 2008-07-03 | 14.06.08 | Dev. of road and back lane from h.no.E-3 toE-11 in Vijay nagar S/S inC-12/CLZ | 679800
15 | 2008-07-03 | 14.06.08 | Dev. of chowk and galies in block no.3 in double storey Vijay Nagar in C-12/CLZ | 473700 | 143/29.08.08/EE(M)-II | M/s Lamba Bros. | 02.09.08 | 15.11.08 | 459589 | Work Completed
16 | 2008-07-03 | 14.06.08 | Dev. of back lane by pdg. RMC from h.no.2060 to 2075 in Otramline inC-12/CLZ | 277000 | 141/29.08.08/EE(M)-II | M/s Lamba Bros. | 04.09.08 | 17.11.08 | 277000 | Work Completed
17 | 2008-07-03 | 14.06.08 | Dev. of chowk and galies in block no.6 and infront of h.no.68 in block no.8,D/S in Vijay Nagar in C-12/CLZ | 461200 | 142/29.08.08/EE(M)-II | M/s Lamba Bros. | 15.09.08 | 04.12.08 | 450463 | Work Completed
18 | 2008-07-03 | 14.06.08 | Dev. of lane by pdg.mastic wearing course from Gauri Shanker Mandir to h. no.578 in West Parmanand Colony in C-12/CLZ | 495500 | 105/12.08.08/EE(M)-II | M/s Balkar Singh & Bros. | 21.08.08 | 13.09.08 | 495144 | Work Completed
19 | 2008-07-16 | 16.07.08 | Dev of beck lane by pdg RMC from h.no.249 to 262 in Indira Vihar Colony in C-11/CLZ | 174500 | 228/08.10.08/EE(M)-II | M/s Abhay Const.Co. | 08.10.08 | 08.12.08 | 146860 | Work Completed
20 | 2008-07-18 | 18.07.08 | Dev of branch lane gali no.1 from Ram Ghat in Vijay wali gali in Vill. Wazirabad in C-10/CLZ | 423385 | 85/04.08.08/EE(M)-II | M/s Lamba Bros. | 13.08.08 | 11.12.08 | 421395 | Work Completed
21 | 2008-07-23 | 15.07.08 | Dev of B/Wall of Mall Apprt. infront of h.no. 110 and 109 to 69 and 70 upto Pump House in Mall Apprt. in C-10/CLZ | 642900 | 342/19.12.08/EE(M)-II | M/s Shiva Const.Co. | 28.12.08 | 15.04.09 | 588097 | Work Completed
22 | 2008-07-24 | 22.07.08 | Dev of road by pdg RMC from h.no. G-25A to G-27B in Vijay Ngr. S/S in C-12/CLZ | 268800 | 211/06.10.08/EE(M)-II | M/s Lamba Bros. | 15.10.08 | 14.01.09 | 244028 | Work Completed
23 | 2008-07-24 | 22.07.08 | Dev of road from E-1B to E-2B and E-20 to E-24A in Vijay Ngr.S/S in C-21/CLZ | 498000 | 202/23.09.08/EE(M)-II | M/s Abhay Const.Co. | 10.10.08 | 26.12.08 | 446626 | Work Completed
24 | 2008-07-24 | 22.07.08 | P/L RMC in backlane from h.no. 1993 to 1980 in Autram Line in C-12/CLZ | 348200 | 201/23.09.08/EE(M)-II | M/s Abhay Const.Co. | 15.10.08 | 31.12.08 | 332168 | Work Completed
25 | 2008-07-28 | 10.06.08 | P/L RMC from h.no. 2012 to 2032 (Ram Mandir Road)in Autram Line in C-12/CLZ | 669200
26 | 2008-07-28 | 22.07.08 | Stg of road by pdg dense carpet in A-Block and B-Block in Vijay Ngr. S/S in C-12/CLZ | 628800
27 | 2008-08-06 | 19.07.08 | Dev of lane by pdg RMC from h.no. B-18 to B-35B in Vijay nagar Single SDtorey w.no.12 CLZ | 872000
28 | 2008-08-07 | 06.08.08 | Dev of lane by pdg mastic wearing course from h.no. 240 to 262 in Mukherji nagar w.no.11 CLZ | 498000 | 122/27.08.08/EE(M)-II | M/s Bansal Const.Co. | 05.09.08 | 04.12.08 | 479997 | Work Completed
29 | 2008-08-07 | 07.08.08 | Dev/Const. of B/wall of green belt opp. h.no. 1232 in Mukherji nagar w.no.11 CLZ | 421000 | 245/13.10.08/EE(M)-II | M/s Shiva Const.Co. | 13.10.08 | P | 391000 | In Prog.
30 | 2008-08-07 | 07.08.08 | Dev/Const. of B/wall of green belt between Jal board land to Dalao in Mukherji nagar w.no.11 CLZ | 421000 | 244/13.10.08/EE(M)-II | M/s Shiva Const.Co. | 13.10.08 | P | 402896 | In Prog.
31 | 2008-08-11 | 08.08.08 | Dev of back lane by pdg RMC from h.no. 758 to 771 in Mukherji nagar w.no.11 CLZ | 185600 | 239/10.10.08/EE(M)-II | M/s Abhay Const.Co. | 10.10.08 | 24.11.08 | 185600 | Work Completed
32 | 2008-08-14 | 02.08.08 | Dev of open drain from Hanuman Mandir to B-35 in Viajy nagar SS w.no.12 CLZ | 427900
33 | 2008-05-21 | 14.05.08 | dev to lane by pdg mastic wearing course from h.no.1064 to 1083 in Mukherji Ngr w.no.11/CLZ | 490800
34 | 2008-05-21 | 14.05.08 | Dev of lane by mastic wearing course from h.no.180 to 382 and one intersection in Mukherji Ngr.in w.no.11/CLZ | 496000
35 | 2008-05-21 | 14.05.08 | Dev to lane by pdg mastic wearing course from h.no.1121 to 1137 in Mukherji ngr.in w.no.11/CLZ | 497900
36 | 2008-05-21 | 14.05.08 | Dev of lane by pdg cc from h.no.253 to 268,225 to 238,301 to 316 and 457 to 468 in Parmand Colony in w.no.11/CLZ | 437000 | 78/30.07.08/EE(M)-II | M/s Malhotra Contractors | 07.08.08 | 24.03.09 | 425256 | Work Completed
37 | 2008-05-21 | 14.05.08 | Dev of lane by pdg cc from h.no.121 to 138,105 to 120,365 to 380 and 333 to 348 in Parmand Colony in w.no.11/CLZ | 487000 | 83/04.08.08/EE(M)-II | M/s Lamba Bros. | 13.08.08 | 08.11.08 | 378474 | Work Completed
38 | 2008-05-21 | 08.05.08 | P/O Tubewell in park near h.no.749,Dr.Mukherji Ngr.in w.no.12/CLZ | 158181 | 266/14.07.08/EE(E)-II | M/s Master Electric Store | 23.07.08 | 16.12.08 | 157804 | Work Completed
39 | 2008-05-21 | 08.05.08 | P/O tubewell in park near h.no.1874 outram line in w.no.12/CLZ | 158596 | 265/14.07.08/EE(E)-II | M/s Mani Electricals | 28.07.08 | 21.08.08 | 158135 | Work Completed
40 | 2008-05-21 | 08.05.08 | P/O Tubewell in park near h.no.376 Parmanand cvolony in w.no.12/CLZ | 157926 | 264/14.07.08/EE(E)-II | M/s Pee K ay Electricals | 30.07.08 | 21.08.08 | 147078 | Work Completed
41 | 2008-05-30 | 30.05.08 | Dev to branch lane by pdg brick flooring in gali no.3 Partap Wali gali in Village Wazirabad in w.no.10/CLZ | 274100 | 74/28.07.08/EE(M)-II | M/s Mudit Const. | 06.08.08 | P | 239680 | In Prog.
42 | 2008-05-30 | 30.05.08 | Dev to branch lane by pdg brick flooring in gali no.6 Parveen Beauty Parlour Wali gali in village Wazirabad in w.no.10/CLZ | 261000 | 70/28.07.08/EE(M)-II | M/s Mudit Const. | 06.08.08 | 04.12.08 | 232956 | Work Completed
43 | 2008-05-30 | 30.05.08 | Dev to gali no.8 Kharaksingh to Jai chand and infront of Ashok house(C-232)in village Wazirabad in w.no.10/CLZ | 338800 | 75/28.07.08/EE(M)-II | M/s Kalra Const.Co. | 07.08.08 | 23.10.08 | 299044 | Work Completed
44 | 2008-09-04 | 14.08.08 | P/O semi high mast pole at C-Block Vijay Ngr.T-Point Single Storey in C-12/CLZ | 197652
45 | 2008-09-04 | 14.08.08 | P/O semi high mast pole at A-Block Park/Ground Vijay Ngr.Single Storey in C-12/CLZ | 195314
46 | 2008-09-04 | 14.08.08 | P/O semi high mast lioght at park in D-Block Vijay Ngr.Single Storey in C-12/CLZ | 196249 | 228/31.12.08/EE(E)-II | M/s Bhima Electricals | 05.01.09 | 19.01.09 | 161125 | Work Completed
47 | 2008-07-16 | 16.07.08 | raising of B/wall along university land from h.no.69 to 211 in Indira Vihar w.no.11/CLZ | 755323 | 236/10.10.08/EE(M)-II | M/s Balkar Singh & Bros. | 31.10.08 | P | 563773 | In Prog.
48 | 2008-05-30 | 30.05.08 | Dev to branch lane by pdg brick flooring in gali no.6 flood nala to Ashok house in village Wazirabad in w.no.10/CLZ | 381900 | 72/28.07.08/EE(M)-II | M/s Mudit Const. | 06.08.08 | 01.12.08 | 341489 | Work Completed
49 | 2008-05-30 | 30.05.08 | Dev to branch lane of gali no.6 by pdg brick flooring from h.no.F-273 to F-323 in village Wazirabad in w.no.10/CLZ | 263500 | 71/28.07.08/EE(M)-II | M/s Mudit Const. | 06.08.08 | 03.12.08 | 235102 | Work Completed
50 | 2008-05-30 | 30.05.08 | Dev to branch lane of gali no.12 from Chap Rana wali gali and Vakil Wali gali in village Wazirabad in w.no.10/CLZ | 275900 | 88/04.08.08/EE(M)-II | M/s Lamba Bros. | 13.08.08 | 11.12.08 | 232687 | Work Completed
51 | 2008-05-30 | 30.05.08 | Dev to gali no.6 Sangam Vihar Pushta F-378 to F-226 in village Wazirabad in w.no.10/CLZ | 499000 | 73/28.07.08/EE(M)-II | M/s Mudit Const. | 06.08.08 | 04.12.08 | 449923 | Work Completed
52 | 2008-05-30 | 30.05.08 | Dev to drainage system on probyn road infrone of gate no.4 Mall Apartments in w.no.10/CLZ | 496000 | 138/29.08.08/EE(M)-II | M/s Narendra Const. Co. | 07.09.08 | 05.01.09 | 379483 | Work Completed
53 | 2008-06-02 | 30.05.08 | Imp to footpath on Roshanara road(RHS)from Baglow no.10 to Malka Ganj chowk in w.no.9/CLZ | 374000 | 107/13.08.08/EE(M)-II | M/s Sanjeev Builders | 25.08.08 | 14.11.08 | 247411 | Work Completed
54 | 2008-06-02 | 30.05.08 | Imp to footpath on Roshanara road(RHS)from Petrol Pump to Benglow no.5 in Malka Ganj in w.no.9/CLZ | 373700 | 108/13.08.08/EE(M)-II | M/s Sanjeev Builders | 25.08.08 | 14.11.08 | 246396 | Work Completed
55 | 2008-06-06 | 29.05.08 | P/O Semi-High Mast Pole on main road near Patrachar,Lucknow road in w.no.10/CLZ | 263000 | 135/26.09.08/EE(E)-II | M/s Kawatra Electricals | 01.10.08 | P | 170679 | In Prog.
56 | 2008-06-06 | 29.05.08 | P/O semi-high mast pole on main road Sanjay Basti,Timarpur in w.no.10/CLZ | 264000
57 | 2008-06-06 | 29.05.08 | P/O semi-high mast pole on main road near gali no 8 in Sangam Vihar in w.no.10/CLZ | 268000
58 | 2008-06-06 | 29.05.08 | P/O semi-high mast pole on main road Indra Basti,Timarpur in w.no.10/CLZ | 264000
59 | 2008-06-06 | 29.05.08 | P/O semi-high mast pole on main road Harijan Basti near Shiv Mandir in Wazirabad in w.no.10/CLZ | 267000 | 133/26.09.08/EE(E)-II | M/s Kawatra Electric Works | 03.10.08 | P | 164310 | Work in Prog.
60 | 2008-06-06 | 29.05.08 | P/O semi-high mast pole in Indra Vikas Colony in w.no.11/CLZ | 271000
61 | 2008-06-06 | 29.05.08 | P/O semi-high mast pole on main road near gali no.5 Sangam BVihar in w.no.10/CLZ | 268000 | 134/26.09.08/EE(E)-II | M/s Kawatra Electric Works | 10.10.08 | P | 167654 | Work in Prog.
62 | 2008-06-06 | 29.05.08 | P/O semi-high mast pole on main road in Munshi Ram Colony in w.no.11/CLZ | 267000 | 131/26.09.08/EE(E)-II | M/s Kawatra Electric Works | 01.10.08 | P | 163828 | Work in Prog.
63 | 2008-07-03 | 14.06.08 | Dev of road by pdg mastic wearing course from h.no.2681 to 2673 and 2690 to 2682 in Outram Line in C-12/CLZ | 548240
64 | 2008-07-03 | 20.05.08 | Dev of road by pdg mastic wearing course from h.no.72 to CSE Office in Parmanand Colony in C-11/CLZ | 861000 | 315/16.12.08/EE(M)-II | M/s Ashok Kr.Gupta | 16.12.08 | 31.12.08 | 861000 | Work Completed
65 | 2008-06-20 | 30.05.08 | Dev. of drain by covering of open drains by pdg. precast RCC slabs in Hakikat Nagar inC-12/CLZ | 316432 | 86/04.08.08/EE(M)-II | M/s Lamba Bros. | 12.11.08 | P | 201995 | In Prog.
66 | 2008-06-20 | 30.05.08 | Dev. of back lane by pdg. RMC h.no.469 to478; 509 to519 559 to568;639to648;579to588 in West pamanand Colony C-12/CLZ | 512300 | 100/06.08.08/EE(M)-II | M/s Lamba Bros. | 08.09.08/ | 12.1.08 | 494503 | Work Completed
|  |  |  | 25536061 |  |  |  |  | 15036416

## Sheet3
Status Report of MLA fund for the year 2008-09. MLA: Sh. J.S. Chauhan (AC-55)
S.no. | Date of Booking | Date of Consent | Name of Work | Booking Amount | Work order no. with date | Name of the agency | DOS | DOC | Amount Verified | Present Status
1 | 2008-06-23 | 02.06.08 | C/o gali no.44 from Premwali house to Shyam LAl house in Hanuman Kunj, Sant nagar in village Burari C-8/CLZ | 376000 | 88/13.08.08/EE(M)-I | M/sSatbir Singh | 22.08.08 | 10.10.08 | 360749 | Work Completed
2 | 2008-06-23 | 02.06.08 | C/o cross gali no. 1 from Ghan Shyam house to Shiv mandir Sant nagar in village Burari in C-8/CLZ | 382600 | 120/21.08.08/EE(M)-I | M/s Satish Const.Co. | 30.08.08 | 18.11.08 | 377420 | Work Completed
3 | 2008-06-23 | 01.05.08 | Dev of lane by pdg brick flooring and drainage system from h.no. B-1169 to 1195 (Sangram singh house) gali no.3 and along Balbir Singh house in Baba cly. Burari C-7/CLz | 433900 | 119/21.08.08/EE(M)-I | M/s Satish Const.Co. | 23.08.08 | 10.11.08 | 358086 | Work Completed
4 | 2008-07-02 | 10.06.08 | P/O semi high mast light pole near Cremation Ground at Burari Village in C-7/CLZ | 200102 | 115/12.09.08/EE(E)-II | M/s Bharat Trading CO. | 20.09.08 | 20.10.08 | 187170 | Work Completed
5 | 2008-07-02 | 10.06.08 | P/O semi high mast light pole near Flood Office at Phirni Road at Jagatpur Village in C-8/CLZ | 214322 | 117/12.09.08/EE(E)-II | M/s Aman Electrical | 20.09.08 | 20.10.08 | 204934 | Work Completed
6 | 2008-07-28 | 08.07.08 | C/O gali no. 9 from RD-110 to Jasvuinder House upto RD-220 in Village Jagatpur in C-8/CLZ | 497400 | 158/05.09.08/EE(M)-I | M/s Shree Prakash | 14.09.08 | 13.12.08 | 450561 | Work Completed
7 | 2008-07-28 | 08.07.08 | C/O lane from Anand House RD-02 to RD-95 in Village Jagatpur in C-8/CLZ | 479200 | 151/25.08.08/EE(M)-I | M/s Sourat Const. Co. | 04.09.08 | 28.05.09 | 470688 | Work Completed
8 | 2008-07-28 | 14.07.08 | C/O lane from Vijaypal House to RD-95 in Village Jagatpur in C-8/CLZ | 489200 | 171/23.09.08/EE(M)-I | M/s Sourat Const. Co. | 02.10.08 | 22.11.08 | 488889 | Work Completed
9 | 2008-07-28 | 14.07.08 | C/O gali no.9 from Teji House to RD-110 in Village Jagatpur in C-8/CLZ | 402500 | 320/12.12.08/EE(M)-II | M/s Hazarika Builders | 21.12.08 | 20.02.09 | 402500 | Work Completed
10 | 2008-07-29 | 12.05.08 | C/O galio no.18 from Sube Singh house to Shyam house and Parmali house to Lokesh house in Manav Kunj Part-II in Village Mukundpur in C-6/CLZ | 593600 | 180/23.09.08/EE(M)-I | M/s Prem & Co. | 21.10.08 | 20.05.09 | 540983 | Work Completed
11 | 2008-07-29 | 12.05.08 | C/O link of galio no.16 to 20 along B/Wall from Surender house to Shyam house in Manav Kunj Part-II in Village Mukundpur in C-6/CLZ | 380400 | 181/23.09.08/EE(M)-I | M/s Prem & Co. | 02.10.08 | 29.12.08 | 347290 | Work Completed
12 | 2008-07-29 | 12.05.08 | C/O gali no.19 from Vinod housr to Subhash house to B/Wall in Manav Kunj Part-II in Village Mukundpur in C-6/CLZ | 339400 | 178/23.09.08/EE(M)-I | M/s VK Cauhan | 02.10.08 | 26.12.08 | 308157 | Work Completed
13 | 2008-06-19 | 21.05.08 | C/O lane no.5 and gali linked ti lane no.5 from Subhash house to Ashok house from Mangle house Raje house from Zile Singh house to Jore Singh house and Bharam Prakash in Village Jagatpur C-8/CLZ | 603098 | 174/23.09.08/EE(M)-I | M/s Balkar Singh &Bros. | 02.10.08 | P | 341450 | In Prog.
14 | 2008-06-23 | 01.05.08 | C/O gali no.15 from Kundpal hs to Sriniwas and from TP Sharma hs to Jagdish hs in Village Sant Ngr. Burari in C-8/CLZ | 632127 | 152/25.08.08/EE(M)-I | M/s Sourat Const. Co. | 03.09.08 | 02.01.09 | 629257 | Work Completed
15 | 2008-08-27 | 14.08.08 | C/o gali no.1 from Jile Singh hs. to Kalu Ram hs. and from Gautam hs to Kishan Lal hs. in part-II Surender cly. in village Jhrodha w.no.8/CLZ | 490729 | 195/26.09.08/EE(M)-I | M/s Gaurav Mehta | 05.10.08 | 20.11.08 | 477167 | Work Completed
16 | 2008-08-27 | 14.08.08 | C/o main road from Sudhir hs. to Hari hs. in Bengali cly. Sant nagar w.no.8/CLZ | 434800 | 220/17.10.08/EE(M)-I | M/s Satbir Singh | 26.10.08 | 12.05.09 | 432008 | Work Completed
17 | 2008-08-27 | 14.08.08 | C/o main road from Small Wonders Public School RD0 to RD-40 in village Jharoda in w.no.8/CLZ | 316382 | 185/25.09.08/EE(M)-I | M/s rajesh Const.Co. | 04.10.08 | 26.05.09 | 316104 | Work Completed
18 | 2008-08-27 | 22.08.08 | C/o main road from RD-40 to Phirni road RD-110 in village Jharoda in w.no.8/CLZ | 452214 | 192/26.09.08/EE(M)-I | M/s Shiv Shakti sales Ent. | 05.10.08 | 27.1.08 | 452057 | Work Completed
19 | 2008-08-27 | 22.08.08 | C/o gali no.1 from Amar hs. to Suresh hs., divakar hs to Satpal hs. , Chander hs to Narender hs. and from Ashok hs to Rajkumar hs. in part-II in surender cly. village Jhroda w.o.8/CLZ | 496635 | 213/26.09.08/EE(M)-) | M/s Suresh Pal Rana | 05.10.08 | 03.03.09 | 495124 | Work Completed
20 | 2008-08-27 | 22.08.08 | C/o main road from Hari hs to Ved Prakash hs in Bengali cly. Sant Nagar in w.no.8/CLZ | 404200 | 219/17.10.08/EE(M)-I | M/s Satbir Singh | 26.10.08 | 12.05.09 | 402312 | Work Completed
21 | 2008-09-05 | 29.06.08 | C/o main road from Police Booth to Abodh Valley (Vatika) in village Mukandpur in C-6/CLZ. | 948400 | 301/10.12.08/EE(M)-I | M/s Sept.Const. | 19.12.08 | 20.03.09 | 938865 | Work Completed
22 | 2008-09-05 | 01.07.08 | C/O main road from Yogender Chadha hs. to Shiv Mandir on main road in village Mukandpur in C-6/CLZ. | 853400 | 302/10.12.08/EE(M)-I | M/s Sept.Const. | 19.12.08 | P | 680674 | In Prog.
23 | 2008-09-05 | 01.07.08 | C/O lane from Daya Chand hs. to Balaji Properties and Builders in Shamshan road in village Mukandpur in C-6/CLZ | 997700 | 378/12.01.09/EE(M)-I | M/s JB Ent. | 14.01.09 | 05.05.09 | 977581 | Work Completed
24 | 2008-09-05 | 03.07.08 | C/O main road from M.C.Primary School to Flood Nala in village Mukandpur in C-6/CLZ. | 964400
25 | 2008-09-05 | 03.07.08 | C/O main road from Abode Valley Resturant to Yogender Chadha hs. on main road in village Mukandpur in C-6/CLZ. | 948400 | 303/10.12.08/EE(M)-I | M/s Sept.Const. | 19.12.08 | 28.01.09 | 948178 | Work Completed
26 | 2008-06-19 | 01.05.08 | C/O gali no.31 from Raj Singh house to Ram Chander house in Sant Ngr. in Village Burari w.no.8/CLZ | 120600 | 86/13.08.08/EE(M)-I | M/s VK Cauhan | 22.08.08 | 16.12.08 | 105022 | Work Completed
27 | 2008-06-19 | 01.05.08 | C/O drain in gali no.5 from Gaurv fruit Corner to Som Dutt house in Sant Ngr. village Burari w.no.8/CLZ | 414000 | 159/05.09.08/EE(M)-I | M/s Shree Prakash | 14.09.08 | 20.1.08 | 299912 | Work Completed
28 | 2008-06-19 | 01.05.08 | C/O gali no.22 from S.C. Patel house to Suman House in Sant Ngr. Village Burari w.no.8/CLZ | 450300 | 142/24.09.08/EE(M)-I | M/s VK Cauhan | 04.09.08 | 10.04.09 | 357962 | Work Completed
29 | 2008-06-19 | 01.05.08 | C/o lane from Jagman house to Jai Singh house in Sant Ngr.Village Burari w.no.8/CLZ | 89600 | 79/01.08.08/EE(M)-I | M/s Sourat Const. Co. | 02.08.08 | 09.10.08 | 87723 | Work Completed
30 | 2008-06-19 | 21.05.08 | C/O gali linked to lane no.8 from Abdul Majid to Abdul hs in vill. Jagatpur w.no.8/CLZ | 67200 | 80/04.08.08/EE(M)-I | M/s Satbir Singh | 09.08.08 | 30.09.08 | 59507 | Work Completed
31 | 2008-06-19 | 21.05.08 | C/O gali no.6 from Gyanchand hs to Kalyan Singh hs in vill.jagatpur w.no.8/CLZ | 57700 | 87/13.08.08/EE(M)-I | M/s Satbir Singh | 22.08.08 | 03.10.08 | 45568 | Work Completed
32 | 2008-06-19 | 21.05.08 | C/O lane from h.no.2434 to h.no.2438, M.K.Gupta hs and along Suresh hs in Sant Ngr Vill.Burari w.no.8/CLZ | 444900 | 112/21.08.08/EE(M)-I | M/s Shiv Shakti Const.Co.I | 30.08.08 | 28.05.09 | 305148 | Work Completed
33 | 2008-07-23 | 01.05.08 | C/O Part-I main road from Aggarweal Sweets to vasudev hs in Vill. Mukundpur in C-6/CLZ (2442000/-) |  | Work Cancelled
34 | 2008-06-23 | 01.05.08 | C/O main road from Part-II main road (Shiv Mandir)to Ved Prakash hs in Vill. Mukundpur in C-6/CLZ | 2369800 | 176/23.09.08/EE(M)-I | M/a Oberai Const.Co. | 02.10.08 | P | 1785912 | In Prog.
|  |  |  | 17345209 |  |  |  |  | 14634958