## Sh. Jile Singh
STATUS REPORT OF MLA FUND FOR THE YEAR 2004-05 ( UP TO 15.2.06)
Municipal Corporation of Delhi
CIVIL LINE ZONE
Name Of MLA |  |  |  | Sh.Jile Singh | AC-55 |  | year 2004-05 |  | Allocation | 150.00 Lacs
Name of Constituency |  |  |  | Bhalswa
Ward Nos and Names |  |  |  | C.103 , Bhalswa , Jahangir Puri C-104 , Burari
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per | D.O.C. As per | First Running | Second Running | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  | 13 | 16
1 | Civil | 26.7.04 | 23.4.04 | C/o drain on main road from RD 230 to RD-430 in Sant Nagr. In c-104/CLZ | 523332 | EE-XII | 104 | 317/5.11.04/EE-xii | M/s Narendera Const co. | 6.11.04 | 3.1.05 | 523151 |  | 523151 | Comp.
2 | Civil | 26.7.04 | 30.6.04 | Imp to lane from towards Suresh Kr. Hs to near Hari Singh Hs in Village Mukand pur C-104/C.L.Z | 212237 | EE-XII | 104 | 153/dt 5.8.04 EE-XII | M/s Mayank Assocates | 11.8.04 | 25.9.04 | 211786 |  | 211786 | Comp.
3 | Civil | 26.7.04 | 30.6.04 | Imp to walkway in park between EE-2300 EE 2100 wali Gali in EE Block Jahangir Puri Coloney C-104 /CLZ | 185026 | EE-XII | 104 | 152 dt 5.8.04 EE-XII | M/s Mayank Assocates | 11.8.04 | 25.9.04 | 184776 |  | 184776 | Comp.
4 | Civil | 26.7.04 | 30.6.04 | Imp to Walk way in park between EE-2600 to EE2800 /wali Gali in EE-Block Jahangir puri Coloney C-104 /CLZ | 185026 | EE-XII | 104 | 154 /dt 5.8.04 EE-XIII | M/s Mayank Assocates | 11.8.04 | 25.9.04 | 184953 |  | 184953 | Comp.
5 | Civil | 27.7.04 | 27.7.04 | C/o drainage systme from Negi General Store to Sat pal Singh Hs in Sant Ngr. C-104 CLZ | 190570 | EE-XII | 104 | 169 /dt12.8.04 EE-XII | M/s Ram Doot Builder | 21.8.04 | 16.10.04 | 190201 |  | 190201 | Comp.
6 | Civil | 3.8.04 | 15.7.04 | Imp to lane from H.NO A-249 to A257 in Block A in Bhalswa Dairy Coloney C-103 CLZ | 353798 | EE-XII | 103 | 162 /dt 12.8.04 EE-XII | M/s Deepak Aggarwal | 12.8.04 | 26.10.04 | 352659 |  | 352659 | Comp.
7 | Civil | 3.8.04 | 15.7.04 | Imp to lane from H.NO A679 to A704 , Block A in Bhalswa Dariy Coloney C-103 CLZ | 369080 | EE-XII | 103 | 163 /dt 12.8.04 EE-XII | M/s Jai Maruti Const. | 13.8.04 | 26.10.04 | 367638 |  | 367638 | Comp.
8 | Civil | 4.10.04 | 15.7.04 | Imp to lane from H.No A-409 to A-416 in block A in Bhalswa Dairy in C-103/CLZ | 369704 | EE-XII | 103 | 281/15.10.04/XII | M/s Jai Maruti Const. | 15.10.04 | 31.12.04 | 369547 |  | 369547 | Comp.
9 | Civil | 4.10.04 | 22.6.04 | Imp to Park along C-104 , C-105 in Bhalswa Dairy Coloney in C-103/CLZ | 571780 | EE-XII | 103 | 267/15.10.04/XII | M/s Lalit const Co. | 16.10.04 | 15.2.05 | 571667 |  | 571667 | Comp.
10 | Civil | 4.10.04 | 22.6.04 | Imp to park along A-569 in Block A in Bhalswa Dary Coloney in c-103 /CLZ | 591234 | EE-XII | 103 | 268/15.10.04/XII | M/s Lalit const Co. | 15.10.04 | 14.2.05 | 584623 |  | 584623 | Comp.
11 | Civil | 5.10.04 | 18.8.04 | Imp to lane by Siromani to Vijender in Amrit vihar in Village Mathu pura C-104/CLZ | 203549 | EE-XII | 104 | 397/13.12.04/EE/XII | M/s Narendera Const co. | 25.12.04 | 21.3.05 |  |  | 203528 | Comp.
12 | Civil | 5.10.04 | 14.9.04 | Imp to lane from 25 foota road to Sudesh , Ram Kishore to Hari Narayan and Ajay to Bhatia in A-2 block Sant Ngr. Burari C-140/CLZ | 431500 | EE-XII | 104 | 275/15.10.04/XII | M/s SS Enterprises | 16.10.04 | 15.1.05 | 431047 |  | 431047 | Comp.
13 | Civil | 5.10.04 | 14.9.04 | Imp to lane & C/o drain from Jagbir to Mohit Hs Gali No-2 (LHS) in village Jagal pur in c-104/CLZ | 450294 | EE-XII | 104 | 282/15.10.04/XII | M/s SM Const | 18.10.04 | 24.12.04 | 450107 |  | 450107 | Comp.
14 | Civil | 11.10.04 | 27.7.04 | Imp to lane & drain in Gali No - 15 Sant Ngr. Burari Village C-104/CLZ | 375893 | EE-XII | 104 | 276/15.10.04/XII | M/s Shyam Lal Gupta | 24.10.04 | 11.1.05 | 375806 |  | 375806 | Comp.
15 | Civil | 27.1.05 | 11.7.04 | Imp to Lane from Rana's house to Jeewan vidya Public School in Kaushil Enclave village Burai in c-1047/CLZ | 501105 | EE-XII | 104 | 279/18.2.05 EE-XII | M/s S.S Enterp | 21.2.05 | 17.6.05 |  |  | 500992 | Comp.
16 | Civil | 27.1.05 | 9.9.04 | Imp to lane from H.NO C-7 to Dr Sajjan Clinik in Hardev Nagr in Jharoda Village C-104/CLZ | 531567 | EE-XII | 104 | 574/18.2.05 /EE-XII | M/s Narendera Const co. | 18.2.05 | 31.3.05 |  |  | 529535 | Comp
17 | Civil | 9.3.05 | 12.2.05 | I/s of main road from Subhash House to Reegal School in village Jagat pur C-104 CLZ | 294624 | EE-XII | 104 | 602/21.3.05 EE-XII | M/s Sona Consltant & Contrator | 24.3.05 | 7.6.05 |  |  | 293993 | Comp
18 | Civil | 9.3.05 | 12.2.05 | I/s of main road from Burari Rd to Manav Bhavan School to Ibrahim Pur Village in Nathu Pura C-104 CLZ | 839678 | EE-XII | 104 | 34/15.4.05 E-XII | M/s Sona Consltant & Contrator | 18.4.05 | 17.5.05 |  |  | 798498 | Comp
19 | Civil | 30.3.05 | 16.9.04 | Imp to different xing in Viillage Ibrahim pur C-104 CLZ | 218260 | EE-XII | 104 | 671/31.3.05 EE-XII | M/s S.S Enterp | 10.4.05 | 8.6.05 |  |  | 218222 | Comp
20 | Civil | 27.02.04 | 27.02.04 | C/o drain infront of h.no.I-1 to I-600 (along park) in block I in Jahngir puri colony C-103/CLZ | 590790 | EE-XII | 103 | 996/27.02.04/EE-XII | M/s R.K. Tushar Const Co. | 27.02.07 | 19.05.04 |  |  | 590790 | Comp
21 | Civil | 27.02.04 | 27.02.04 | C/o drain infront of h.no.I-681 to I-1250 in block I in Jahngir puri colony C-103/CLZ | 591629 | EE-XII | 103 | 995/27.02.04/EE-XII | M/s R.K. Tushar Const Co. | 28.03.04 | 18.05.04 |  |  | 588439 | Comp
22 | Civil | 27.02.04 | 27.02.04 | Imp to road/ draiage in I block from Mandir to end off Ram Garh road in Jhangir puri colony C-103/CLZ | 584122 | EE-XII | 103 | 993/27.02.04/EE-XII | M/s R.K. Tushar Const Co. | 27.02.04 | 19.05.04 |  |  | 583759 | Comp
23 | Civil | 27.02.04 | 27.02.04 | Imp to road/ draiage in K block from h.no. K-1001 to K-2000 in Jhangir puri colony C-103/CLZ | 584907 | EE-XII | 103 | 994/27.02.04/EE-XII | M/s R.K. Tushar Const Co. | 28.02.04 | 19.05.04 |  |  | 583809 | Comp
24 | Civil | 27.02.04 | 17.02.04 | Covering of drain in fron tof h.no. J-1000 to J-982 & J-982 to J-951 in J block Jhangir puri colony w.no.103/CLZ | 401978 | EE-XII | 103 | 1008/27.02.04/EE-XII | M/s S.K. Gupta & Co. | 27.02.04 | 05.05.04 |  |  | 401842 | Comp
25 | Civil | 27.02.04 | 17.02.04 | Imp to road from MC Pry chool Bhalswa to Desu Sub station in Bhalswa village w.no. 103/CLZ | 391719 | EE-XII | 103 | 1016/27.02.04/EE-XII | M/s Mohan Lal & Co. | 27.02.04 | 30.03.04 |  |  | 391708 | Comp
26 | Civil | 27.02.04 | 24.02.04 | Dev of rural villages Sh: C/o drain from 25' foota road to appex School (L.H.S) in Sant Nagar Burari w.no. 104/CLZ | 459482 | EE-XII | 104 | 1005/27.02.04/EE-XII | M/s Narendra Const Co. | 28.02.04 | 07.06.04 |  |  | 458676 | Comp
27 | Civil | 27.02.04 | 24.02.04 | Imp to lane from Mool chand huse to Darshan saree Emporium in village Jharoda C-104/CLZ | 579144 | EE-XII | 104 | 1007/27.02.04/EE-XII | M/s Narendra Const Co. | 28.02.04 | 07.06.04 |  |  | 578706 | Comp
28 | Civil | 27.02.04 | 25.02.04 | C/o drain from Sat Prakash house to Shiv Kumar house to Dilip hjouse to Ram Kumar house to & Raj Kumar house to Kunj Bihari house in village Burari C-104/CLz | 196832 | EE-XII | 104 | 1015/27.02.04/EE-XII | M/s A.K. Builders | 06.03.04 | 21.05.04 |  |  | 196486 | Comp.
29 | Civil | 27.02.04 | 25.02.04 | C/o drain from Chander pal singh house to Ranjeet singh house in village Burari C-104/CLz | 121418 | EE-XII | 104 | 1013/27.02.04/EE-XII | M/s A.K. Builders | 06.03.04 | 25.04.04 |  |  | 121041 | Comp.
30 | Civil | 27.02.04 | 25.02.04 | C/o drain from Ashok house to Sabudun house (LHS) gali no.65 in Sant ngar Burari C-104/CLZ | 189606 | EE-XII | 104 | 1014/27.02.04/EE-XII | M/s A.K. Builders | 06.03.04 | 24.05.04 |  |  | 189501 | Comp.
|  |  |  | Total | 12089884 | [8 empty] | 12027486
Remarks:-11 works (from s.no. 20 to 30) amounting to Rs 46.91 lacs were booked in 2003 -04 against the allocation made by UD Deptt. in Feb. 2004
for the financial year 2004 - 2005 and all these 11 works have been completed

## Sh. Mangat Ram (2)
STATUS REPORT OF MLA FUND FOR THE YEAR 2004-05
Municipal Corporation of Delhi
CIVIL LINE ZONE
|  | Name Of MLA |  | Sh. Manget Ram Singhal | AC-56
|  | Name of Constituency |  | Adresh Nagar
|  | Ward Nos and Names |  | C-105 , Adresh Ngar C-106 , Sarani Pipal Thala
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | first Running | Second Running | Up to date Expenditure | Remarks
1 | 2 | 3 | 4 | 5 | 6 |  |  | 13 | 16
1 | Civil | 26.7.04 | 28.6.04 | Imp to lane NO 14 from H.No A69 to A-64 in Sanjay Ngar, Mahendra Park in c-106 /CLZ | 165059 |  |  | 101978 | In progress
2 | Civil | 26.7.04 | 28.6.04 | Imp to lane no 13 from H.No 43 to 39 (park ) in Sanjay Ngr. Mahendra park c-106/CLZ ( by pdg RMC ) | 193600 |  |  | 89165 | In progress
3 | Civil | 29.7.04 | 27.5.04 | Imp to B/wall of park infront of H.No A-1 in Village Bharola in C-105/CLZ | 259500 |  |  | 209312 | Comp.
4 | Civil | 29.7.04 | 4.6.04 | Dev of U/R coloney Sh Connnecting the drain of Arya Samaj Road from 80' road to D.JB out fall drain in c-105 /CLZ | 473200 |  |  | 362694 | Comp.
5 | Civil | 29.7.04 | 4.6.04 | Dev of U/R coloney Sh Connnecting the drain of Rajan Babu from 80' road to D.JB out fall drain in C-105 /CLZ | 260700 |  |  | 194008 | Comp.
6 | Civil | 3.8.04 | 9.7.04 | Imp to drainage systm on Avtar Marg from Road no 5, IN Nirankari Coloney to Shaving Cream Factory in c-106/CLZ | 204600 | 148510 |  | 148510 | Comp.
7 | Civil | 3.8.04 | 2.7.04 | Imp to drainage system on road no- 5 from (RHS) H.No 5/159 to 5/115 Nirnkari Coloney. C-106/CLZ | 627000 | 627000 |  | 627000 | Comp.
8 | Civil | 3.8.04 | 9.7.04 | Imp to park near Transformen in Nirankari Coloney C-106/CLZ | 479300 | 455699 |  | 455699 | Comp.
9 | Civil | 3.8.04 | 9.7.04 | Imp to drainage (RHS) as Avtar Marg Opp Shaving Crem Factory in Nirankari Coloney C-106/CLZ | 288700 | 217182 |  | 217182 | Comp.
10 | Civil | 4.8.04 | 9.7.04 | Addl. Facilitees in J.J.R Sh. C/o Culvert No A-1 Mkt road in Jahangir puri C-106/CLZ | 378350
11 | Civil | 4.8.04 | 9.7.04 | Addl. Facilitees in J.J.R Sh. C/o Culvert on Drain near B-25 x Slum Tenaments Jahangir puri C-106/CLZ | 375522 | 375371 |  | 375371 | Comp
12 | Elect | 9.8.04 | 6.8.04 | P/of E.I and Fans at Newly Constracted Baradavi at H Block park Jahangir Puri W.No 106/CLZ | 119987 |  |  | 49768 | Comp
13 | Civil | 6.9.04 | 4.6.04 | Dev of U/R coloney Sh. Conneeting the Drain of P.L.K Marg from 80' road to D.J.B .out fall drain in c-105/clz | 709800 |  |  | 450067 | Comp.
14 | Civil | 6.9.04 | 28.6.04 | Conneting the drain (L.H.S) of Ashoka rd from M.e pry. School Majlis park to D.J.B out fall drain in C-105/CLZ | --
15 | Civil | 9.9.04 | 2.7.04 | C/o walkway in park near Lav block D& E block in Gandhi Vihar in C-106/CLZ | 339650 |  |  | 313709 | Comp.
16 | Civil | 4.10.04 | 28.6.04 | Connecting the drain (R.H.S) of Ashoka rd From M.C. pry school Majlis park to D.J.B out fall drain /C-105.CLZ RS/-(1713600)/-
17 | Civil | 5.10.04 | 1.9.04 | imp of B/wall and walkway in Main prk in block H(pvt-H-2) in Jahangir puri in C-106/CLZ(737100)/-
18 | Elect | 6.10.04 | 6.7.04 | P/o of Garden light at of subesh park adresh Ngr. Part-I W.No-105/CLZ
19 | Elect | 6.10.04 | 2.7.04 | P/o of Garden light at of subesh park , adresh Ngr, park-II. W.No 105/CLZ
20 | Civil | 6.10.04 | 16.9.04 | Imp to B/wall, Gate & C/O room Adresh Ngr. Foanctrnal park in C-105/CLZ | 445600 |  |  | 326430 | Comp.
21 | Civil | 4.11.04 | 1.9.04 | C/o remaing works of Baradavi in H-block in Jahangir Puri in C-106/CLZ(931200)/-
22 | Civil | 3.12.04 | 16.9.04 | Imp to Grills & gate by painting in Adresh Ngr. Park in C-105/CLZ | 11900 |  |  | 7865 | Comp.
23 | Civil | 27.1.05 | 30.11.04 | Imp to drainage from back of Gali no -5 and gali no-6 on Lal bagh rd in Niankari Coloney in c-106/CLZ | 245000 |  |  | 103333 | In Prog.
24 | Civil | 27.1.05 | 30.11.04 | Imp to lane and drainge H.NO 140 to 137m and H.No A-174 and H.NO 153 to Shaving Cream factory in Nirankari Coloney in c-106/CLZ | 444025 |  |  | 441725 | In Prog.
25 | Civil | 16.3.05 | 11.1.05 | Imp to lane no 6 from Factory no A81 to B14 in Sanjay nagar Mahindra Park C-106CLZ(by pdg CC and Drainge) | 186500 |  |  | 138971 | Comp.
26 | Civil | 16.3.05 | 30.11.04 | Imp toback lane of gali no 3 from h.no. 3/20 to 3/18 by laying CC in C -106 CLZ(Nirankari Cly) | 147200 |  |  | 95775 | Comp.
27 | Civil | 16.3.05 | 30.11.04 | Imp to gali no 1 from H.no. 13 to 18 and 19 in Sanjay Nagar in Mahindra Park by pdg CC C-106 CLZ | 208600 |  |  | 147158 | Comp.
|  |  |  | Total | 6563793 |  |  | 4855720

## Sh. Mangat Ram
STATUS REPORT OF MLA FUND FOR THE YEAR 2004-05
Municipal Corporation of Delhi
CIVIL LINE ZONE
|  | Name Of MLA |  | Sh. Manget Ram Singhal | AC-56 |  | year 2004-05 |  | Allocation | 100.00 Lacs
|  | Name of Constituency |  | Adresh Nagar
|  | Ward Nos and Names |  | C-105 , Adresh Ngar C-106 , Sarani Pipal Thala
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per | D.O.C. As per | first Running | Second Running | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  | 13 | 16
1 | Civil | 26.7.04 | 28.6.04 | Imp to lane NO 14 from H.No A69 to A-64 in Sanjay Ngar, Mahendra Park in c-106 /CLZ | 165059 | EE-XVI | 106 | 241/13.10.04 | M/s Lalit const com. | 22.11.04 | P |  |  | 101978 | In progress
2 | Civil | 26.7.04 | 28.6.04 | Imp to lane no 13 from H.No 43 to 39 (park ) in Sanjay Ngr. Mahendra park c-106/CLZ ( by pdg RMC ) | 193600 | EE-XVI | 106 | 229/05.10.04/EE-XVI | M/s Creative Const.Co. | 15.10.04 | P |  |  | 89165 | In progress
3 | Civil | 29.7.04 | 27.5.04 | Imp to B/wall of park infront of H.No A-1 in Village Bharola in C-105/CLZ | 259500 | EE-XVI | 105 | 288/3.11.04/EE-XVI | M/s Garg Const co | 25.11.04 | 10.3.05 |  |  | 209312 | Comp.
4 | Civil | 29.7.04 | 4.6.04 | Dev of U/R coloney Sh Connnecting the drain of Arya Samaj Road from 80' road to D.JB out fall drain in c-105 /CLZ | 473200 | EE-XVI | 105 | 575/29.03.05/EE-XVI | M/s Lalit const co. | 05.08.05 | 06.03.06 |  |  | 362694 | Comp.
5 | Civil | 29.7.04 | 4.6.04 | Dev of U/R coloney Sh Connnecting the drain of Rajan Babu from 80' road to D.JB out fall drain in C-105 /CLZ | 260700 | EE-XVI | 105 | 299/18.11.04/ EE-XVI | M/s Ravinder Const.Co. | 26.3.05 | 06.7.05 |  |  | 194008 | Comp.
6 | Civil | 3.8.04 | 9.7.04 | Imp to drainage systm on Avtar Marg from Road no 5, IN Nirankari Coloney to Shaving Cream Factory in c-106/CLZ | 204600 | EE-XVI | 106 | 242/13.10.04/XVI | M/s Subhash Const CO,. | 22.10.04 | 19.1.05 | 148510 |  | 148510 | Comp.
7 | Civil | 3.8.04 | 2.7.04 | Imp to drainage system on road no- 5 from (RHS) H.No 5/159 to 5/115 Nirnkari Coloney. C-106/CLZ | 627000 | EE-XVI | 106 | 323/6.12.04 /XVI | M/s Sanjeev Aggarwal | 18.12.04 | 15.1.05 | 627000 |  | 627000 | Comp.
8 | Civil | 3.8.04 | 9.7.04 | Imp to park near Transformen in Nirankari Coloney C-106/CLZ | 479300 | EE-XVI | 106 | 219/21.9.04 /XVI | M/s Sanjeev Aggarwal | 1.10.04 | 29.11.04 | 455699 |  | 455699 | Comp.
9 | Civil | 3.8.04 | 9.7.04 | Imp to drainage (RHS) as Avtar Marg Opp Shaving Crem Factory in Nirankari Coloney C-106/CLZ | 288700 | EE-XVI | 106 | 283/3.11.04 /XVI | M/s Prem Bros. | 4.11.04 | 20.11.04 | 217182 |  | 217182 | Comp.
10 | Civil | 4.8.04 | 9.7.04 | Addl. Facilitees in J.J.R Sh. C/o Culvert No A-1 Mkt road in Jahangir puri C-106/CLZ | 378350 | EE-XVI | 106
11 | Civil | 4.8.04 | 9.7.04 | Addl. Facilitees in J.J.R Sh. C/o Culvert on Drain near B-25 x Slum Tenaments Jahangir puri C-106/CLZ | 375522 | EE-XVI | 106 | 162/20.8.04 /XVI | M/s Sanjeev Aggarwal | 21.8.04 | 30.10.04 | 375371 |  | 375371 | Comp
12 | Elect | 9.8.04 | 6.8.04 | P/of E.I and Fans at Newly Constracted Baradavi at H Block park Jahangir Puri W.No 106/CLZ | 119987 | EEE-II | 106 | 136/4.11.04/EE(E)-II | M/s Bharat Electric & Electronics | 11.11.04 | 12.06.07 |  |  | 49768 | Comp
13 | Civil | 6.9.04 | 4.6.04 | Dev of U/R coloney Sh. Conneeting the Drain of P.L.K Marg from 80' road to D.J.B .out fall drain in c-105/clz | 709800 | EE-XVI | 105 | 60/20.12.04/EE-XVI | M/s Babu Ram Gupta | 27.12.04 | 27.10.05 |  |  | 450067 | Comp.
14 | Civil | 6.9.04 | 28.6.04 | Conneting the drain (L.H.S) of Ashoka rd from M.e pry. School Majlis park to D.J.B out fall drain in C-105/CLZ | -- |  |  | Work Cancelled as desired by Area MLA vide DO letter No MRS/AC-56/2006//18026 dt.04.03.06 and approved by E-in-C dt. 05.05.06
15 | Civil | 9.9.04 | 2.7.04 | C/o walkway in park near Lav block D& E block in Gandhi Vihar in C-106/CLZ | 339650 | EE-XVI | 106 | 293/05.11.04/ EE-XVI | M/s Rakesh Kumar | 14.11.05 | 13.2.05 |  |  | 313709 | Comp.
16 | Civil | 4.10.04 | 28.6.04 | Connecting the drain (R.H.S) of Ashoka rd From M.C. pry school Majlis park to D.J.B out fall drain /C-105.CLZ RS/-(1713600)/- |  | EE-XVI | 105 | Work Cancelled as desired by Area MLA vide DO letter No 2192/dt 3.6.05 and Recommeded by E-in -C dated 16.6.05
17 | Civil | 5.10.04 | 1.9.04 | imp of B/wall and walkway in Main prk in block H(pvt-H-2) in Jahangir puri in C-106/CLZ(737100)/- |  | EE-XVI | 106 | Work Cancelled as desired by Area MLA vide DO letter No MRS /AC-56 /05/2/274dt 28.6.05and Recommeded by E-in -C dated 8.8.05
18 | Elect | 6.10.04 | 6.7.04 | P/o of Garden light at of subesh park adresh Ngr. Part-I W.No-105/CLZ |  | EEE-II | 105 | Work Cancelled as desired by Area MLA vide DO letter No MRS /AC-56 /04/2/1920 dt 31.12.04and Recommeded by S.E.(E)-I dated 14.11.05 (Rs.197989.00)
19 | Elect | 6.10.04 | 2.7.04 | P/o of Garden light at of subesh park , adresh Ngr, park-II. W.No 105/CLZ |  | EEE-II | 105 | Work Cancelled as desired by Area MLA vide DO letter No MRS /AC-56 /04/2/1920 dt 31.12.04and Recommeded by S.E.(E)-I dated 14.11.05 (Rs.198240.00)
20 | Civil | 6.10.04 | 16.9.04 | Imp to B/wall, Gate & C/O room Adresh Ngr. Foanctrnal park in C-105/CLZ | 445600 | EE-XVI | 105 | 359/20.12.04/ EE-XVI | M/s Balkar Singh & Bros. | 28.4.05 | 01.7.05 |  |  | 326430 | Comp.
21 | Civil | 4.11.04 | 1.9.04 | C/o remaing works of Baradavi in H-block in Jahangir Puri in C-106/CLZ(931200)/- |  | EE-XVI | 106 | Work Cancelled as desired by Area MLA vide DO letter No MRS /AC-56 /05/2/274dt 28.6.05and Recommeded by E-in -C dated 8.8.05
22 | Civil | 3.12.04 | 16.9.04 | Imp to Grills & gate by painting in Adresh Ngr. Park in C-105/CLZ | 11900 | EE-XVI | 105 | 540/04.3.05/ EE-XVI | M/s Narender Const.Co. | 08.4.05 | 12.4.05 |  |  | 7865 | Comp.
23 | Civil | 27.1.05 | 30.11.04 | Imp to drainage from back of Gali no -5 and gali no-6 on Lal bagh rd in Niankari Coloney in c-106/CLZ | 245000 | EE-XVI | 106 | 60/20.04.05/EE-XVI | M/s Deepak Aggarwal | 27.03.06 | P |  |  | 103333 | In Prog.
24 | Civil | 27.1.05 | 30.11.04 | Imp to lane and drainge H.NO 140 to 137m and H.No A-174 and H.NO 153 to Shaving Cream factory in Nirankari Coloney in c-106/CLZ | 444025 | EE-XVI | 106 | 91/06.5.05/ EE-XVI | M/s Prem Bros. | 14.5.05 | P |  |  | 441725 | In Prog.
25 | Civil | 16.3.05 | 11.1.05 | Imp to lane no 6 from Factory no A81 to B14 in Sanjay nagar Mahindra Park C-106CLZ(by pdg CC and Drainge) | 186500 | EE-XVI | 106 | 112/06.6.05/ EE-XVI | M/s K.K. Engg. | 15.6.05 | 25.8.05 |  |  | 138971 | Comp.
26 | Civil | 16.3.05 | 30.11.04 | Imp toback lane of gali no 3 from h.no. 3/20 to 3/18 by laying CC in C -106 CLZ(Nirankari Cly) | 147200 | EE-XVI | 106 | 114/06.6.05/ EE-XVI | M/s Narender Const.Co. | 15.6.05 | 20.8.05 |  |  | 95775 | Comp.
27 | Civil | 16.3.05 | 30.11.04 | Imp to gali no 1 from H.no. 13 to 18 and 19 in Sanjay Nagar in Mahindra Park by pdg CC C-106 CLZ | 208600 | EE-XVI | 106 | 113/06.6.05/ EE-XVI | M/s Narender Const.Co. | 15.6.05 | 16.8.05 |  |  | 147158 | Comp.
|  |  |  | Total | 6563793 | [8 empty] | 4855720
Remarks:- No. of works booked=27, No of works cancelled=6

## S.P.s.(bitto)
STATUS REPORT OF THE MLA FUND FOR THE YEAR 2004-05
Municipal Corporation of Delhi
CIVIL LINE ZONE
|  | Name Of MLA |  | Sh.Surender Pal Singh | AC-61 |  | year 2004-05 |  | Allocation | 200.00 Lacs
|  | Name of Constituency |  | Timar Pur
|  | Ward Nos and Names |  | C-115 & C 116, G.T.B Nagar
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14
1 | Elect | 10.8.04 | 4.8.04 | P/o of street lighting at Vijay Ngr. & Hudson Line in AC-61 W.NO-116/CLZ | 199758 | EE(E)-11 | 116 | 138/18.11.04/EE(E)-II | M/s Bharat Electriclas and Electronics | 26.12.04 | 20.03.06 | 191194 |  |  | Comp.
2 | Elect | 10.8.04 | 4.8.04 | Imp of Semi hight Mast lighting arrangement in AC-61 under C.L.Z.(Timar pur,) Mukherji Ngr. And adjoing area W.No-115 & 116/CLZ | 199194 | EE(E)-11 | 115-116
3 | Civil | 24.8.04 | 23.7.04 | Imp to lane from H.no 103 to 115 in west Mukherji Ngr. In C-116/CLZ | 198966 | EE-XII | 116 | 234/23.9.04/ EE-XII | M/s Lamba Bros. | 20.10.04 | 29.11.04 | 198532 |  |  | Comp.
4 | Civil | 24.8.04 | 23.7.04 | Imp to lane from H.NO 640 to 648in Parmanand coloney in C-116/CLZ | 90817 | EE-XII | 116 | 244/23.9.04/ EE-XII | M/s Saurabh Const | 15.10.04 | 1.11.04 | 90706 |  |  | Comp.
5 | Civil | 24.8.04 | 2.8.04 | C/o walkway in Mahila prk in Malka Ganj in c-115/CLZ | 224796 | EE-XII | 115 | 195/03.9.04/ EE-XII | M/s Mayanak Associates | 14.9.04 | 25.10.04 | 224570 |  |  | Comp.
6 | Civil | 5.10.04 | 23.7.04 | Imp to footpath from Mall Rd to Dhalao on B.B.M rd in c-116/CLZ | 236780 | EE-XII | 116 | 299/15.10.04/ EE-XII | M/s Lamba Bros. | 28.10.04 | 29.11.04 | 236541 |  |  | Comp.
7 | Civil | 11.10.04 | 24.9.04 | Dev. Of R/ colonies Sh: Imp to lane from A-520 to A-495 by pdg C.C. in Nehru vihar C-115/CLZ | 194143 | EE-XII | 115 | 271/15.10.04/ EE-XII | M/s Elise Enterprises | 25.10.04 | 1.12.04 | 191877 |  |  | Comp.
8 | Civil | 11.10.04 | 24.9.04 | Imp to side lane form Bata shop Towards Laxmi Dary on Kingsway Camp rd in C-116/CLZ | 202903 | EE-XII | 116 | 30921.10.04/ EE-XII | M/s Jai Const Co. | 30.10.04 | 26.11.04 | 202903 |  |  | Comp.
9 | Civil | 11.10.04 | 24.9.04 | Imp to lane by pdg c.c. form H.NO 2558 to 2573 in Hudson lane in c-116/CLZ | 570092 | EE-XII | 116 | 278/15.10.04/EE-XII | M/s Ashima Associates | 1.12.04 | 22.2.05 | 546681 |  |  | Comp.
10 | Civil | 11.10.04 | 24.9.04 | Dev. Of appd coloney Sh: Imp to lane by pdg C.c. from H.NO 116 to 138 in West Mukherjee Ngr.in C-116/CLZ | 567862 | EE-XII | 116 | 280/15.10.04/EE-XII | M/s Ashima Associates | 2.12.04 | 22.2.05 | 567862 |  |  | Comp.
11 | Civil | 11.10.04 | 24.9.04 | Imp to lane by pdg C.C. from E block in H.NO E-11 to E-15 , E-47 to E-39 , E23 , E25 E-33 ,E35 in MalkaGanj in C-115/CLZ | 153433 | EE-XII | 115 | 279/15.10.04/EE-XII | M/s Ashima Associates | 13.04.05 | 15.06.05 | 153352 |  |  | Comp.
12 | Civil | 8.12.04 | 1.10.04 | Imp to lanes by pdg C.C. form Hs NO B-1/30 to B-1/54 . B -1/31-32 to B-1 /19 -20 by NO B-1/35 to B B-1/19-20 in Malka Ganj C-115/CLZ | 327470 | EE-XII | 115 | 663/31.03.05 EE-XII | M/s Kavinder Veer Singh | 16.08.05 | 29.09.05 | 326903 |  |  | Comp.
13 | Civil | 8.12.04 | 1.10.04 | P/f Retro Reflective street Sign Boards on Parmanad rd in c-116/CLZ | 202000 | EE-XII | 116
14 | Civil | 1.2.05 | 10.1.05 | Imp to lane by pdg C.C. pav from NDPL office to H.NO 1196 in Mukharjee Ngr. C-116/CLZ | 258000 | Br.-II | 116 | 34/30.3.05 EE (BR)-II | M/s Sanjeev Aggarwal | 4.4.05 | 17.6.05 | 239495 |  |  | Comp
15 | Civil | 1.2.05 | 10.1.05 | Imp to lane by pdg c.c. from H.NO 135to 153, 163 /A to 162 and Shiv Mandir Gali In Malik pur C-116/CLZ | 247000 | Br.-II | 116 | 30/30.3.05 EE (BR)-II | M/s Gupta Enterps | 4.4.05 | 24.01.06 | 238822 |  |  | Comp
16 | Civil | 1.2.05 | 10.1.05 | C/o Boundary wall of park infront of Kabir Mandir in Malka Ganj in c-115 CLZ | 490142 | Br.-II | 115 | 10/26.4.05 EE(BR)-II | M/s Jai Maruti Const | 2.5.05 | 28.6.05 | 490110 |  |  | Comp
17 | Civil | 1.2.05 | 10.1.05 | Imp to lane by pdg Dranage & C.c. form H.NO B-23 to B-18 in Vijay Ngr. C-116/CLZ | 239420 | Br.-II | 116 | 32/30.3.05 EE(BR)-II | M/s Gupta Enterps | 4.4.05 | 18.6.05 | 237042 |  |  | Comp
18 | Civil | 1.2.05 | 30.12.04 | C/o boundary wall from H.NO 513 to 450 and infront of Dispensary in Mukharjee Ngr. C-116/CLZ | 247400 | Br.-II | 116 | 33/30.3.05 EE(BR)-II | M/s Deepak Aggarwal | 1.4.05 | 16.5.05 | 247400 |  |  | Comp
19 | Civil | 7.2.04 | 15.12.04 | Imp to lane by pdg C.C from H.NO 1138 to 1147 in Mukharjee Ngr. In c-116/CLZ | 244356 | Br.-II | 116 | 8/21.4.05BR)-II | M/s Mendiratta Traders | 25.4.05 | 27.6.05 | 244074 |  |  | Comp
20 | Civil | 7.2.05 | 15.12.04 | Imp to lane by pdg c.c. and open drain fron H.NO 26/A to H.NO 340 in Malikpur C-116/CLZ | 226900 | Br.-II | 116 | 29/30.03.05/EE-Br-II | M/s Sanjaeev Aggarwal | 06.04.05 | 15.12.05 | 213788 |  |  | Comp
21 | Civil | 7.2.05 | 30.12.04 | Imp to lane by pdg C.C. & drain from H.NO 2428 to 2433 in Hudson lanes in c-116/CLZ | 242640 | Br.-II | 116 | 11/26.4.05/ EE-Br.-II | M/s Sanjeev Aggarwal | 09.6.05 | 04.7.05 | 242089 |  |  | Comp
22 | Civil | 7.2.05 | 14.1.05 | Imp to lane by providing c.C. from H.No 715 to 802 in Mukherjee Ngr. C-116/CLZ | 237595 | Br.-II | 116 | 24/14.6.05/ EE-Br.-II | M/s Jai Maruti Const | 27.7.05 | 14.10.05 | 237585 |  |  | Comp
23 | Civil | 7.2.05 | 14.1.05 | Imp to drainage system by providng precast R.C.C. slabs from H.NO 1472 to 1486 (L.H.S) in Outram line in c-116/CLZ | 182079 | Br.-II | 116 | 9/26.4.05/EE-Br-II | Ms Jai Maruti const | 1.6.05 | 29.6.05 | 182079 |  |  | Comp
24 | Civil | 7.2.05 | 14.1.05 | Imp to lane by providing C.C. from H.NO 1472 to 1486 in outram lines in c-116/CLZ | 236299 | Br.-II | 116 | 26/14.6.05/ EE-Br.-II | Ms Jai Maruti const | 15.6.05 | 22.8.05 | 236194 |  |  | Comp
25 | Civil | 7.2.05 | 14.1.05 | C/o s.w. drainage from Mahavir Vatika park to H.NO 715 in Mukherjee ngr C-116/CLZ | 258600 | Br.-II | 116 | 28/21.6.05/ EE-Br.-II | M/s Mendiratta Traders | 21.6.05 | 02.11.05 | 258600 |  |  | Comp
26 | Civil | 7.2.05 | 14.1.05 | Imp to lane by providing c.c. from H.NO 786 to 801 in Mukherjee Ngr. C-116 /CLZ | 238170 | Br.-II | 116 | 12/26.4.05/ EE-Br.-II | M/s Raj Brothers | 15.6.05 | 07.9.05 | 238013 |  |  | Comp
27 | Civil | 15.2.05 | 6.12.04 | C/o drain from H.NO 182 to H.NO 276 in Indira Vihar C-116/CLZ | 490813 | EE-XII | 116 | 111/03.6.05/ EE-XII | M/s Madan Lal Gupta | 14.8.05 | 01.10.05 | 490395 |  |  | Comp
28 | Civil | 15.2.05 | 6.12.04 | C/o drain form H.NO 69 to 168 and from 169 to 182 in Indira Vihar c-116/CLZ | 491742 | EE-XII | 116 | 143/08.7.05/ EE-XII | M/s Satish Const.Co. | 16.8.05 | 24.9.05 | 491363 |  |  | Comp
29 | Civil | 23.2.05 | 10.1.05 | Imp to gali NO-4 from house of Parmal Tyagi to Tirath Rams house by pdg C.C. & drain in Wazirabad vill. C-115/CLZ | 251600 | Br.-II | 115 | 29/27.6.05/ EE-Br-II | M/s Lamba Bros. | 04.7.05 | 24.8.05 | 251600 |  |  | Comp
30 | Civil | 23.2.05 | 10.1.05 | Imp to lane by providng C.C and drain from Sanjeev house To H.NO 13 in Gali nop -4, Wazirabad Village. C-115/CLZ | 201099 | Br.-II | 115 | 4/14.4.05/EE-Br-II | M/s Durga Const co | 20.4.05 | 17.6.05 | 198245 |  |  | Comp
31 | Civil | 23.2.05 | 10.1.05 | Imp to lane by providing C..C and drain from Kaptan Singh house to OM Niwas in Gali NO-6 Wazirabad village. C-115/CLZ | 203893 | Br.-II | 115 | 5/14.4.05/EE-Br-II | M/s Durga Const co | 19.4.05 | 17.6.05 | 203851 |  |  | Comp
32 | Civil | 23.2.05 | 10.1.05 | C/o S.W. drainage inforint of Sh Sanjeev house in Gali NO-4 in Wazirabad village in C-115/CLZ | 252300 | Br.-II | 115 | 25/14.6.05/ EE-Br-II | M/s Lamba Bros. | 20.6.05 | 18.8.05 | 248132 |  |  | Comp
33 | Civil | 21.3.05 | 6.12.04 | Imp tolane by pdg CC from H.n. 469 to 2518 inParmanand Colony West C-116 CLZ | 282319 | EE-XII | 116 | 245/05.08.05/EE-XII | M/s Bhanu Const.co. | 30.08.05 | 12.12.05 | 281957 |  |  | Comp
34 | Civil | 21.3.05 | 6.12.04 | Imp to lane by pd CC from H.no.381 to 396 and from H.no. 380 to 365 in Parmanand Cly C-116 CLZ | 598800 | EE-XII | 116 | 249/05.8.05/ EE-XII | M/s A.R.Const.Co. | 01.9.05 | 28.11.05 | 373602 |  |  | Comp
35 | Civil | 21.3.05 | 6.12.04 | Imp to lane by pd CC from h.no. 333 tio 348 in Parmanand Cly C-116 CLZ | 358684 | EE-XII | 116 | 244/05.08.05/EE-XII | M/s Bhanu Const.co. | 09.09.05 | 30.11.05 | 358161 |  |  | Comp
36 | Civil | 21.3.05 | 6.12.04 | Imp to lane by pdg CC from H.no. 364 to 397 inParmanand Cly C-116 CLZ | 388925 | EE-XII | 116 | 250/05.8.05/ EE-XII | M/s A.R.Const.Co. | 20.9.05 | 28.11.05 | 388853 |  |  | Comp
37 | Civil | 21.3.05 | 24.1.05 | Face liftfing of park infornt of H.no. 72 in Vwest Parmanand Cly C-116 CLZ(by pdg Gate and Grills) | 199000 | EE-XII | 116 | 713/17.03.06/EE-XII | M/s Globe Const.Co | 15.05.06 | 10.07.06 | 198890 |  |  | Comp.
38 | Civil | 24.3.05 | 21.3.05 | Const of Walk way in park infornt of Gurudwara at Nehru Vihar C-115 CLZ | 122900 | Br.-II | 115 | 2/14.4.05/EE-Br-II | M/s Lamba Bros. | 16.4.05 | 19.5.05 | 117806 |  |  | Comp
39 | Civil | 24.3.05 | 11.1.05 | Imp to lane by pdg Drainage and CC from H.no. 41 to 40 in Malik pur C-116 CLZ | 66900 | Br.-II | 116 | 51/06.10.05/EE-Br-II | M/s Jindal Enterprises | 21.10.05 | 12.12.05 | 60014 |  |  | Comp
40 | Civil | 28.3.05 | 27.3.05 | Imp to lane by pdg CC aloong H.no. 1/36 Vijay Nagar (Double Storey) C-116 CLZ | 199900 | EE-XII | 116 | 149/14.7.05/ EE-XII | M/s Ancon | 14.7.05 | 08.8.05 | 153997 |  |  | Comp.
41 | Civil | 25.02.04 | 20.02.04 | Imp to lane from h.no. 2410 to 2388 in Hudson lane in C-116/CLZ | 545600 | EE-XII | 116 | 985/27.02.04/EE-XII | M/s Lamba Bros. | 27.02.04 | 13.04.04 | 545451 |  |  | Comp
42 | Civil | 25.02.04 | 20.02.04 | Imp to lane by pdg cc pavment from h.no. D-33 to D-45 in Vijay nagar in C-116/CLZ | 322600 | EE-XII | 116 | 983/27.02.04/EE-XII | M/s Lamba Bros. | 27.02.04 | 31.03.04 | 321230 |  |  | Comp
43 | Civil | 25.02.04 | 20.02.04 | Imp to lane from h.no. 284 to 273 & 238 to 307 in Parmanand colony in C-116/CLZ | 476379 | EE-XII | 116 | 981/27.02.04/EE-XII | M/s Lamba Bros. | 27.02.04 | 11.05.04 | 475978 |  |  | Comp
44 | Civil | 25.02.04 | 19.02.04 | Imp to park near h.no. 2328 I Hudsn lane C-116/CLZ | 199700 | EE-XII | 116 | 979/27.02.04/EE-XII | M/s Sanddep Associates | 27.02.04 | 21.03.04 | 188799 |  |  | Comp
45 | Civil | 25.02.04 | 19.02.04 | Imp to back lane from h.no. 48/1 to D-1 in between Banglore road qtrs. W.no. C-116/CLZ | 96000 | EE-XII | 116 | 978/27.02.04/EE-XII | M/s Sanddep Associates | 27.02.04 | 21.03.04 | 95425 |  |  | Comp
46 | Civil | 25.02.04 | 19.02.04 | Imp to road from h.no. 4/33 to 7/46 in Vijay nagar (D/S) in C-116/CLZ | 238761 | EE-XII | 116 | 992/27.02.04/EE-XII | M/s Sanddep Associates | 27.02.04 | 21.03.04 | 238368 |  |  | Comp
47 | Civil | 25.02.04 | 19.02.04 | Imp to lane from h.no. 758 to 771 in Dr, Mukherji nagar C-116/CLZ | 195400 | EE-XII | 116 | 977/27.02.04/EE-XII | M/s Sanddep Associates | 27.02.04 | 21.03.04 | 193964 |  |  | Comp
48 | Elect | 25.02.04 | 16.02.04 | P/o of street lighting arrangemtent in west Mukherjim nagar W.NO-116/CLZ | 194602 | EE(E)-II | 116 | 28/16.07.04/EE(E)-II | M/s Kawatra Electricas works | 17.07.04 | 28.07.04 | 184984 |  |  | Comp
49 | Elect | 25.02.04 | 16.02.04 | P/o semi high mast light near Police Post opp. Vijay nagar w.no.116/CLZ | 135267 | EE(E)-II | 116 | 27/16.07.04/EE(E)-II | M/s Kawatra Electricas works | 17.07.04 | 28.07.04 | 130918 |  |  | Comp
50 | Elect | 25.02.04 | 16.02.04 | P/o semi high mast light at outram line opp. H.no. 2085 w.no.116/CLZ | 144001 | EE(E)-II | 116 | 26/16.07.04/EE(E)-II | M/s Kawatra Electricas works | 17.07.04 | 28.07.04 | 134878 |  |  | Comp
51 | Civil | 27.02.04 | 25.02.04 | Imp of lane by pdg cc from h.no. 2032 to 2075 in outram line w.no. 116/CLZ | 594000 | EE-XII | 116 | 988/27.02.04/EE-XII | M/s Gupta Engg. Co. | 27.02.04 | 08.04.04 | 593994 |  |  | Comp
52 | Civil | 27.02.04 | 25.02.04 | Imp to drainage system Tagore marg from h.no. 252 to 244 in Tagore park C-116/CLZ | 405400 | EE-XII | 116 | 989/27.02.04/EE-XII | M/s Gupta Engg. Co. | 20.03.04 | 10.06.04 | 405155 |  |  | Comp
53 | Civil | 27.02.04 | 25.02.04 | Imp to back lane from h.no. 296 to 277 in Indira vihar W.no. C-116/CLZ | 153221 | EE-XII | 116 | 986/27.02.04/EE-XII | M/s Baldev Raj Khurana | 10.04.04 | 04.05.04 | 153030 |  |  | Comp
54 | Civil | 27.02.04 | 25.02.04 | Imp to lane & draianage system from h.no. 24 to 46 in Indira Vihar C-116/CLZ | 530000 | EE-XII | 116 | 987/27.02.04/EE-XII | M/s Baldev Raj Khurana | 15.05.04 | 29.06.04 | 526093 |  |  | Comp
55 | Civil | 27.02.04 | 25.02.04 | Imp to back lane from h.no. 360 to 341 in Indira Vihar C-116/CLZ | 158342 | EE-XII | 116 | 991/27.02.04/EE-XII | M/s Baldev Raj Khurana | 15.03.04 | 12.07.04 | 157948 |  |  | Comp
56 | Civil | 27.02.04 | 25.02.04 | Imp to back lane from h.no. 197 to 210 in Indira Vihar C-116/CLZ | 156000 | EE-XII | 116 | 990/27.02.04/EE-XII | M/s Baldev Raj Khurana | 15.04.04 | 04.05.04 | 155997 |  |  | Comp
57 | Civil | 27.02.04 | 25.02.04 | Imp to gali shastri by pdg cc in Kabir Basti w.no. 115 /CLZ | 184652 | EE-XII | 115 | 982/27.02.04/EE-XII | M/s Lamba Bros. | 27.02.04 | 31.03.04 | 182911 |  |  | Comp
58 | Civil | 27.02.04 | 25.02.04 | Imp to gali from h.no. T-1200, 584 & 548 Gautam in Kabir Basti by pdg cc in w.no. 115 /CLZ | 235024 | EE-XII | 115 | 984/27.02.04/EE-XII | M/s Lamba Bros. | 28.02.04 | 12.04.04 | 232157 |  |  | Comp
[5 empty] | 15790639 | [6 empty] | 14970558
Remarks:-18 works amounting to Rs 49.65 lacs were booked in 2003 -04 against the allocation made by UD Deptt. in Feb. 2004
for the financial year 2004 - 2005 and out of these 18 works 18 works have been completed & one is in progress.

## Sh K.K Singh
STATUS REPORT OF MLA FUND FOR THE YEAR 2004-05 UP TO 15.2.06
MUNICIPAL CORPORATON OF DELHI
CIVIL LINE ZONE
|  | Name Of MLA |  | Sh. Karan Kanwar Singh | AC-62 |  | year 2004-05 |  | Allocation | 197.35 lacs
|  | Name of Constituency |  | Model Town
|  | Ward Nos and Names |  | C-117 Rana Partap Bagh C-118 ,Model Town
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agency | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Civil | 28.7.04 | 27.7.04 | Imp to lane forn factory no B-7 to B-1 in GTK Industrial area in c-117/CLZ | 599125 | XII | 117 | 182/18.08.04/XII | M/s Narendra Const CO. | 28.8.04 | 25.1.05 | 597416 |  |  | Comp.
2 | Civil | 28.7.04 | 27.7.04 | Imp to lane from factory No B-41 to B-91 in GTK Indl. Area C-117/CLZ | 599125 | XII | 117 | 184/18.08.04/XII | M/s Narendra Const CO. | 28.8.04 | 25.1.05 | 598265 |  |  | Comp.
3 | Civil | 28.7.04 | 27.7.04 | Imp to lane from factory no B-22 to B-27 in G.T.K. Indl. Area C-117/CLZ | 599125 | XII | 117 | 183/18.08.04/XII | M/s Narendra Const CO. | 28.8.04 | 25.1.05 | 598805 |  |  | Comp.
4 | Civil | 2.8.04 | 8.7.04 | Imp to main park in Lal Bagh c-117 /CLZ sh C/o B/wall (Partetion wall) for dividing the park in Two parts. | 181179 | XII | 117 | 172/12.08.04/XII | M/s Lamba Bros. | 13.8.04 | 12.10.04 | 179887 |  |  | Comp.
5 | Civil | 2.8.04 | 8.7.04 | Imp to lane from H.no A-63 to A-69 in A Block Gujrawala town -I C-117/CLZ | 345808 | XII | 117 | 170/12.08.04/XII | M/s Lamba Bros. | 16.8.04 | 4.10.04 | 345804 |  |  | Comp.
6 | Civil | 2.8.04 | 8.7.04 | Imp to lane from H.NO C-3/1 to C-4/17 in Rana Pratap Bagh C-117/CLZ | 154398 | XII | 117 | 173/12.08.04/XII | M/s Lamba Bros. | 13.8.04 | 13.10.04 | 154395 |  |  | Comp.
7 | Civil | 2.8.04 | 27.7.04 | C/o walkway in park in Naniwala in c-117/CLZ-II | 1014788 | XII | 117 | 414/21.12.04/EEXII | M/s Narendra Const CO. | 21.12.04 | 29.3.05 | 1014745 |  |  | Comp
8 | Elect | 3.8.04 | 28.7.04 | Provision of street light at Rana Pratap Bagh AC-62 under CLZ | 199089 | EE(E)-II | 117 | 106/17.9.04EE(E)-II | M/s Kavatra Electric works | 26.9.047 | 25.10.04 | 192909 |  |  | Comp
9 | Elect | 3.8.04 | 28.7.04 | Provision of street light at Derawal colony AC-62 under CLZ | 199089 | EE(E)-II | 117 | 107/17.09.04/EE(E)-II | M/s Kawatra Electric works | 02.02.05 | 24.03.05 | 191683 |  |  | Comp.
10 | Elect | 3.8.04 | 28.7.04 | Provision of streel light at Model town Ac-62 under CLZ W.no-117 | 199089 | EE(E)-II | 117 | 105/17.9.04EE(E)-II | M/s Kavatra Electric works | 25.9.04 | 25.10.04 | 193776 |  |  | Comp
11 | Civil | 3.8.04 | 22.7.04 | Imp to B/wall of park infront of H.NO A-89 to A-74 in Rajpura Gurmadi in C-117/CLZ | 444527 | XII | 117 | 164/12.08.04/XII | M/s Deepak Aggarwai | 13.8.04 | 8.10.04 | 444523 |  |  | Comp
12 | Civil | 3.8.04 | 22.7.04 | C/O S.W. drain fron H.NO C-6/2 to road about in Rana Partap Bagh C-117/CLZ | 176685 | XII | 117 | 194/3.9.04/XII | M/s Jai Maruti Const | 6.9.04 | 11.11.04 | 156859 |  |  | Comp
13 | Elect | 12.8.04 | 11.8.04 | P/O lighting arrangement at Entrance of Gupta Coloney & Kalyan vihar Bus Stand under CLZ zone w.no 117 (Rs195464/-) | …….. | EE(E)-II | 117 | Work Cancelled as desired by Area MLA vide letter no Nil dated 23.5.07 and approved by CE( Elect.) dated 28/5/07.
14 | Elect | 12.8.04 | 11.8.04 | Provison of lighting arrangement at Mehandru Enclave & Malwa taxi Stand under C.L.Z w.No-117(Rs. 197356/-) | …….. | EE(E)-II | 117 | Work Cancelled as desired by Area MLA vide letter no Nil dated 23.5.07 and approved by CE( Elect.) dated 28/5/07.
15 | Elect | 12.8.04 | 11.8.04 | Provision of lighting arrangement at Gujrawala town ,B-block tanki wala park & Gujrawala part-II under CLZ W.NO-117(Rs.199921/-) | …….. | EE(E)-II | 117 | Work Cancelled as desired by Area MLA vide letter no Nil dated 23.5.07 and approved by CE( Elect.) dated 28/5/07.
16 | Elect | 12.8.04 | 11.8.04 | Provision of lighting arrangement at C.C. Coloney Duplex Corner 99 No & DDA Jim corner Priya Darshani vihar under CLZ W.NO-117(Rs.195646/-) | …….. | EE(E)-II | 117 | Work Cancelled as desired by Area MLA vide letter no Nil dated 23.5.07 and approved by CE( Elect.) dated 28/5/07.
17 | Elect | 12.8.04 | 11.8.04 | Provision of lighting arrangement at Sangam park Community Hall & Sangam park A-block near DDA footpath under CLZ w.No-117(Rs.197356/-) | …….. | EE(E)-II | 117 | Work Cancelled as desired by Area MLA vide letter no Nil dated 23.5.07 and approved by CE( Elect.) dated 28/5/07.
18 | Civil | 20.8.04 | 30.7.04 | Imp to lane infront of H.NO 154 in Kalyan vihar and H.NO-110 in old Guptal Colony in C-118/CLZ | 302491 | XII | 118 | 199/3.9.04/XII | M/s Gupta Engineering Co./ | 3.9.04 | 10.11.04 | 302392 |  |  | Comp
19 | Civil | 20.8.04 | 30.7.04 | Imp to inter section of Police line rd & kingsway rd near Vijary ngr & Hudson line in c-118/CLZC | 385917 | XII | 117 | 197/3.9.04/XII | Ms/ Vipin Kumar Gupta | 3.9.04 | 17.11.04 | 384025 |  |  | Comp
20 | Civil | 2.9.04 | 10.7.04 | Imp to foot path for Dalao(near Gurudwara Nanak PIO) to main entrace towards C.C. coloney in G.T. RD in C-117/CLZ | 187067 | XII | 117 | 230/23.9.04/XII | Ms/ Shiv Const oc. | 24.9.04 | 1.12.04 | 187065 |  |  | Comp
21 | Civil | 5.1.05 | 3.8.04 | P/l brick pavement in Ram hila park in Model Town -II in C-118 /CLZ | 599800 | XII | 118 | 310/3.11.04/XII | M/s Yoginder Const | 15.10.04 | 5.1.05 | 363167 |  |  | Comp
22 | Civil | 5.10.04 | 4.10.04 | Imp to drinage System from H.no 25 to H.NO 33 in jain coloney in C-117/CLZ | 153000 | XII | 117 | 293/15.10.04/XII | M/s Lamba Bros. | 15.10.04 | 23.12.04 | 152475 |  |  | Comp
23 | Civil | 5.10.04 | 4.10.04 | Imp lane from H.no 1 to 7 & H.NO 8 to H.No 15 in Jain coloney in c-117/CLZ | 172200 | XII | 117 | 291/15.10.04/XII | M/s Lamba Bros. | 15.10.04 | 23.12.04 | 171066 |  |  | Comp
24 | Civil | 5.10.04 | 4.10.04 | Imp to lane from factory NO B-51 to B-54 & B-55 to B-57 in G.T.K. Indl .Area in c-117/CLZ | 304544 | XII | 117 | 306/21.10.04/XII | M/s Mohan Lal & Co. | 23.10.04 | 29.1.05 | 304519 |  |  | Comp
25 | Civil | 5.10.04 | 4.10.04 | Imp to park in Jain colony in w.NO-117/CLZ | 149465 | XII | 117 | 295/15.10.04/XII | Ms/ DV Const Co. | 16.10.4 | 23.12.04 | 149464 |  |  | Comp
26 | Civil | 5.10.04 | 4.10.04 | Imp to drinage from system fron H.no 34 to 43 in Jain Coloney in c-117/CLZ | 132255 | XII | 117 | 277/15.10.04/XII | M/s Rakesh Kumar | 16.10.04 | 23.12.04 | 132250 |  |  | Comp
27 | Civil | 14.10.04 | 10.7.04 | Imp to rd berms opp H.no A-57 to Mahvir Jain Model School & NDPL office to park in Gujrawala Town 'A' block in c-117/CLZ | 206340 | XII | 117 | 416/21.12.04/XII | M/s Shiva Const Co. | 23.12.04 | 24.1.05 | 206328 |  |  | Comp
28 | Civil | 29.10.04 | 25.6.04 | Imp to lane form H.no c-7/4 to opp of C-7/10 in Rana pratapBagh c-117/CLZ | 390000 | XII | 117 | 417/21.12.04/XII | M/s Sept Const. | 22.12.04 | 25.4.05 | 389400 |  |  | Comp
29 | Civil | 16.12.04 | 4.4.04 | Imp to lane from H.no 248 to 266 & 191 to 203 in B- Block Derawal Ngr. C-118/CLZ ( BY R.M.C) | 1773885 | XII | 118 | 251/08.8.05/ EE-XII | M/s Unique Enterprises | 08.8.05 | 27.1.06 | 1773610 |  |  | Comp
30 | Civil | 16.12.04 | 4.4.04 | Imp to lane from h.no A-117 to a330 in Derawal Ngr. In c-118/CLKZ(by RMC) | 1681600 | XII | 118 | 59/21.04.05/EE-XII | M/s Surya Kant Sharma | 21.04.05 | 02.03.06 | 1230471 |  |  | Comp.
31 | Civil | 16.12.04 | 4.4.04 | Imp to lane form H.no A-138 to A292 in Derawal Ngr. In C-118.CLZ (By RMC) | 1119384 | XII | 118 | 66/26.4.05/ EE-XII | M/s Rana Const.Co. | 26.4.05 | 13.10.05 | 1117760 |  |  | Comp.
32 | Civil | 16.12.04 | 4.4.04 | C/o Rd along Meera Bai park in old Gupta colony in C-118/CLZ | 345272 | XII | 118 | 539/4.2.05/XII | M/s Sorout Const co. | 4.2.05 | 29.3.05 | 344761 |  |  | Comp.
33 | Civil | 16.12.04 | 5.4.04 | Imp to lane form H.no B-37 to B-47 in C.C. coloney in c-118/CLZ | 199700 | XII | 118
34 | Civil | 16.12.04 | 4.4.05 | Imp to lane along H.NO 41 & 42 in Kewal park in c-118 /CLZ ( by pdg C.C.) | 99600 | XII | 118 | 596/18.3.05 | M/s Sourabh Const | 18.3.05 | 29.3.05 | 92142 |  |  | Comp.
35 | Civil | 16.12.04 | 4.4.05 | Raising of drain from H.NO A-298 to 138 in Derawal Ngr. In c-118/CLZ | 152942 | XII | 118 | 571/17.2.05/XII | M/s Narendra Const CO. | 17.2.05 | 29.3.05 | 152932 |  |  | Comp.
36 | Civil | 16.12.04 | 4.4.05 | Imp to park opp H.NO M-2-39 in M-Block Model town in c-118/CLZ | 61107 | XII | 118 | 570/17.2.05 | M/s Paras const Co | 17.2.05 | 31.3.05 | 61107 |  |  | Comp.
37 | Horti | 12.1.05 | 11.1.05 | Redevelopment of park VeerJain Coloney Rana Pratap Bagh Opp H.nO 88 in c-117 /CLZ | 93879 | ADH/ CLZ | 117 | 11/28.7.05/ ADH/CLZ | M/s Raj Kumar | 28.7.05 | 19.9.05 | 54570 |  |  | Comp.
38 | Horti | 12.1.05 | 11.1.05 | New tube well boring in Veer Jain coloney park Rana Pratap Bagh Opp H.NO 88 w.NO -117/CLZ | 97242 | ADH/ CLZ | 117
39 | Horti | 12.1.05 | 11.1.05 | I/s Moter Pump set veer Jain coloney park R.P.Bagh opp H.NO 88 w.No-117/CLZ | 45775 | DDH/CLZ | 117
40 | Horti | 12.1.05 | 11.1.05 | Redevelopment of park opp H.no 195 Kalyan vihar C-118/CLZ. | 91474 | DDH/CLZ | 118 | 71/25.11.05/DDH/CLZ | M/s V.K.Sales Corp. | 25.11.05 | 02.03.06 | 75717 |  |  | Comp.
41 | Horti | 12.1.05 | 11.1.05 | Re- development of park opp H.No-62 Kalyan vihar w.no-118/CLZ | 113882 | DDH/CLZ | 118 | 83/16.12.05/DDH/CLZ | M/s Mayur Enterprises | 16.12.05 | 02.03.06 | 113882 |  |  | Comp.
42 | Horti | 12.1.05 | 11.1.05 | Re- development of park op.H.NO 238 Kalyan vihar W.NO-118.CZ | 157768 | DDH/CLZ | 118 | 10/28.7.05/ ADH/CLZ | M/s V.K.Sales Corp. | 28.7.05 | 24.10.05 | 142522 |  |  | Comp.
43 | Horti | 12.1.05 | 11.1.05 | Boring for Const . Of New tube well in park opp H.NO 238 Kalyan viahr C-118/CLZ | 96320 | DDH/CLZ | 118
44 | Horti | 12.1.05 | 11.1.05 | I/s Moter Pump set 1-5 Hp in Park opp H.NO 238 Kalyan vihar C-118/CLZ. | 49663 | DDH/CLZ | 118
45 | Horti | 12.1.05 | 11.1.05 | Re- development of park behind Braham Kumari Ashram in Derawala Ngr. C-118/CLZ | 182285 | DDH/CLZ | 118 | 06/28.7.05/ ADH/CLZ | M/s Om Const.Co. | 28.7.05 | 23.9.05 | 156814 |  |  | Comp
46 | Civil | 20.1.05 | 4.1.05 | Raising of B/wall of park near H/.NO 273 Kalyan vihar C-118/CLZ | 102571 | XII | 118 | 648/31.3.05 EE-XII | M/s Pankaj Const Co | 31.3.05 | 8.6.05 | 102358 |  |  | Comp
47 | Civil | 20.1.05 | 4.1.05 | C/o walkway in park in infront of H.NO 162 Kalyan vihar c-118/CLZ | 199800 | XII | 118 | 645/31.3.05 EE-XII | M/s Pankaj Const Co | 31.3.05 | 8.6.05 | 136836 |  |  | Comp
48 | Civil | 23.3..05 | 29.1.05 | P/F gate in park infornt of H.no.D5/8 Model Town C-118 CLZ | 99300 | XII | 118 | 631/30.3.05/EE-XII | M/s Yoginder Const | 30.3.05 | 8.6.05 | 99178 |  |  | Comp
49 | Civil | 23.3..05 | 29.1.05 | Imp to B/wall of park infornt of H.no. D5/8 Model Town C-118 CLZ(by Marble Grit Wash) | 183000 | XII | 118 | 632/30.3.05/EE-XII | M/s Yoginder Const | 30.3.05 | 8.6.05 | 182470 |  |  | Comp
50 | Civil | 24.3.05 | 6.9.04 | Imp to lane from H.no. 248 to 266 in Kalyan Vihar in C-118 CLZ | 540724 | XII | 118 | 670/31.3.05/ EE-XII | M/s Narendra Const CO. | 09.4.05 | 23.7.05 | 538907 |  |  | Comp
51 | Civil | 24.3.05 | 29.1.05 | Imp to walkway of park infront of H.no. D5/8 Model Town C-118 CLZ ( by Red Sand Stone flooring) | 168998 | XII | 118 | 74/06.5.05/ EE-XII | M/s Ravinder Veer Singh | 06.5.05 | 13.7.05 | 168852 |  |  | Comp
52 | Civil | 31.3.05 | 4.1.05 | Imp to lane from B-158 to B 177 and B97 to B 114 in Darawalan Nagar C-118 CLZ (by pdg Betch Mix Concrete) | 1678251 | XII | 118 | 134/24.6.05/ EE-XII | M/s Unique Enterprises | 24.6.05 | 03.1.06 | 1678251 |  |  | Comp
|  |  |  | Total | 17029528 | [6 empty] | 15634358
Remarks:- No. of works booked=52, No. of works cancelled=5

## Sh.Shadi Ram
STATUS REPORT OF MLA FUND FOR THE YEAR 2004-05
Municipal Corporation of Delhi
CIVIL LINE ZONE
|  | Name Of MLA |  | Sh. Shadi Ram | AC-63 |  | year 2004-05 |  | Allocation | 180.00 Lacs
|  | Name of Constituency |  | KAMLA NAGAR
|  | Ward Nos and Names |  | C-119 Kamla Ngr. C-120 Shestri Ngr.
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Civil | 28.7.04 | 29.6.04 | Imp to rd by pdg RMC pav. & drainage systme between Tulsi Ngr and block B-5 in Inder Lok c-120 /CLZ | 793100 | EE-XVI | 120 | 246/15.10.04/EE_XVI | Ms/Surender kumar Jain | 23.11.04 | 28.12.04 | 731125 | Completed
2 | Civil | 28.7.04 | 4.7.04 | Imp to drainage systme in kamla Ngr. In c-119 (in back lane of area with 30'0'rd/CLZ | 184300 | EE-XVI | 119 | 145/9.8.04 | M/s Sanjeev Aggarwal | 16.8.04 | P | 184098 | In Progress
3 | Civil | 28.7.04 | 4.7.04 | Imp to drainage system in Shakti Ngr. In C-119 (backlane of the area with out 30'0' roads) CLZ. | 188100 | EE-XVI | 119 | 146/9.8.04 | M/s Sanjeev Aggarwal | 17.8.04 | 16.10.04 | 186856 | Completed
4 | Civil | 28.7.04 | 4.7.04 | Imp to road by pdg drainage & C.c. from H.NO Sk-46 to Sk-10 Sk60 to Sk-85 sk-14 to Sk 30 in sindharan Kalan C-119/CLZ | 397900 | EE-XVI | 119 | 147/9.8.04// EE-XVI | M/s HS Builders | 11.8.04 | 16.11.04 | 396220 | Completed
- | Civil | 28.7.04 | 4.7.04 | Imp to internal roads of ishwar Ngr by Dense carpeting in C-119 (H.NO 35UB to 2UA,77 UB to 32 UB,63 UA to 17 A/UA to 65 UB , 45 UA to 50 B/UA to 52 UB) | 49500 | EE-XVI | 119 | 396/07.1.05/ EE-XVI | M/s Vinod Kumar | 21.6.05 | P | 33781 | In Progress
5 | Civil | 11.8.04 | 30.6.04 | Imp to footpath from Gali no I to park in DDA flat Gulabi Bagh in c-119/CLZ | 306100 | EE-XVI | 119 | 163/20.8.04/ EE-XVI | M/s Shiva Const co | 26.8.04 | 24.12.04 | 303288 | Completed
6 | Civil | 11.8.04 | 30.6.04 | Imp to B/wall of park adjacent to MCD store in 16 Block shakti Ngr. C-119/CLZ | 92500 | EE-XVI | 119 | 164/20.8.04/EEXVI | M/s Shiva Const co | 23.8.04 | 27.9.04 | 87494 | Completed
7 | Civil | 16.8.04 | 4.7.04 | Imp to lane by pdg c.c. pave & drainage system form A-670 /4 jto A671 in "A" block Shestri Ngr. C-120/CLZ | 99298 | EE-XVI | 120 | 156/20.8.04 | M/s Sanjeev Builders | 18.9.04 | 13.12.04 | 97643 | Completed
8 | Civil | 16.8.04 | 4.7.04 | Imp to lane by pdg C.C. pave& drainage System from H.NO 122 to Main Road inder Lok in Anand Ngr. C-120/CLZ | 295891 | EE-XVI | 120 | 157/20.8.04/EEXVI | M/S Surender kr Jain | 31.8.04 | 5.11.04 | 294509 | Completed
9 | Civil | 16.8.04 | 4.7.04 | Imp to foot path from H.NO 116 to M.C pry School LHS in Anand Ngr. In c-120 CLZ by pdg R.C.C. Tiles & drainage system | 224754 | EE-XVI | 120 | 160/20.8.04/EEXVI | M/s Jindal Enterprises | 28.8.04 | 10.12.04 | 224129 | Completed
10 | Civil | 16.8.04 | 4.7.04 | Imp to lane by pdg c.c. pav. & drainage system from D-10 to D-5 back lane in lalita Block in Shestri Ngr. In c-120/CLZ | 349062 | EE-XVI | 120 | 159/20.8.04 | M/S Surender kr Jain | 27.10.04 | 27.12.04 | 348686 | Completed
11 | Civil | 17.8.04 | 4.7.04 | Imp to footpath from H.NO 21 to 30 in Anand Ngr. In C-120 /CLZ by pdg R.C.C tiles & drainage system | 350890 | EE-XVI | 120 | 158/20.8.04/EEXVI | M/S Surender kr Jain | 31.8.04 | 23.10.04 | 350327 | Completed
12 | Civil | 17.8.04 | 6.8.04 | Imp to lane by pdg.C. C. pav. &drainage system form WZ -12 to WZ-1 back side in Nimri Village C-120/CLZ | 261200 | EE-XVI | 120 | 454/2.02.05/EE-Xvi | M/s Shryastha Consts. | 11.02.05 | WIP | 168886 | In Progress
13 | Civil | 17.8.04 | 6.8.04 | Imp to lane by pdg c.c. pave & drainage system from WZ 56 to 59 and WZ-77 to 81 in Nimari Village C-120/CLZ | 234900 | EE-XVI | 120 | 322/6.12.04/EEXVI | M/s Sanjeev Aggarwal | 21.2.05 | 15.3.05 | 197072 | Complated
14 | Civil | 17.8.04 | 6.8.04 | Imp to lane by pdg c.c. pave & drainage system from WZ 149 to WZ-150 in Nimari Village in C-120/CLZ | 54300 | EE-XVI | 120 | 345/10.12.04/ EE-XVI | M/s Bansal Consts | 15.1.05 | 18.3.05 | 37339 | Complated
15 | Civil | 17.8.04 | 30.7.04 | Imp to lane by pdg R.M.C pav & drainage system form E-2/153 to E-2/110 in shastri Ngr. C-120/CLZ | 699800 | EE-XVI | 120 | 38/11.4.05/ EE-XVI | M/s S.Kumar & Bros. | 20.4.05 | 13.8.05 | 655488 | Complated
16 | Civil | 17.8.04 | 30.7.04 | Imp to lane by pdg R.M.C pav & drainage system form E-2/171 to E-2/151 in shastri Ngr. C-120/CLZ | 664400 | EE-XVI | 120 | 37/11.04.05/EE-XVI | M/s Kumar & Bros. | 08.07.05 | 19.08.05 | 620016 | Complated
17 | Civil | 24.8.04 | 30.7.04 | Imp to lane by pdg R.M.C. pav. And drainage System from E-2/74 to E-2/80 front side in shastri Ngr. C-120/CLZ | 735400 | EE-XVI | 120 | 522/22.2.05/EE-XVI | M/s Subash Const Co | 3.3.05 | 27.4.05 | 690036 | Comp
18 | Civil | 24.8.04 | 4.7.04 | Dev of U/R colonies in C-120/cLZ Sh: imp to lane by pdg C.c. pave and drainage system from F-8 to F-18 in Shastri Ngr. inC-120/CLZ | 308320 | EE-XVI | 120 | 172/8.9.04/EEXVI | M/s Sanjeev Builders | 9.11.04 | 26.12.04 | 308320 | Comp
19 | Civil | 24.8.04 | 4.7.04 | Dev. Of U/R coloney in c-120/cLZ Sh: imp to plane of pdy c.c. pave. & drainage System from D-38 to D30 back lane in Lalita block Shastri Ngr. C-120/CLZ | 300426 | EE-XVI | 120 | 173/8.9.04/ EE-XVI | M/s Bansal Consts | 24.11.04 | 24.12.04 | 300094 | Comp
20 | Civil | 24.8.04 | 6.8.04 | Imp to B/wall of fountain of Main park Sarai Bastri in c-120/CLZ | 52900 | EE-XVI | 120 | 576/29.03.05/EE-XVI | M/s Kewal Krishan & Co. | 14.03.06 | 23.03.06 | 42037 | Comp.
21 | Civil | 4.10.04 | 6.8.04 | Imp to lane by pdg R.M.C pav and drainage system on Main Rd from WZ 27 to WZ-9 in Nimari village. C-120/CLZ | 878900 | EE-XVI | 120 | 500/15.2.05/ EE-XVI | M/s S.Kumar & Bros. | 24.2.05 | 07.6.05 | 844597 | Comp
22 | Civil | 4.10.04 | 30.7.04 | Imp to lane by pdg R.M.C pav and drainage systemE-2 /28 to E-2/50 in Shastri Ngr. C-120/CLZ | 697900 | EE-XVI | 120 | 516/18.2.05/ EE-XVI | M/s S.Kumar & Bros. | 27.2.05 | 20.6.05 | 650778 | Comp
23 | Civil | 4.10.04 | 6.8.04 | Imp to park by pdg Grit wash plaster in A block near H.No A3 A in A block Slum Tanments flats in Sarai Basti C-120 W.Z | 92300 | EE-XVI | 120
24 | Civil | 4.10.04 | 6.8.04 | Imp to park by pdg gril wash plaster in 'B' block near H.No B_149 A in'B' block slum tenaments flats in Sarai Basti C-120/CLZ | 76500 | EE-XVI | 120
25 | Civil | 4.10.04 | 6.8.04 | Imp B/wall of park by pdg Marble wash plaster near police chowk Inderlok in C-120/CLZ | 557200 | EE-XVI | 120
26 | Civil | 4.10.04 | 6.8.04 | Imp to park by pdg gril wash plaster in 'A' block near H.No A-a in in A block Slum tenaments flats in Sarai Basti C-120/CLZ | 175200 | EE-XVI | 120
27 | Civil | 4.10.04 | 6.8.04 | Imp to lane by pdg R.M.C pav& drainage system from H.NO 527 to 510 ( front line Shahzada Bagh PH-I C-120/CLZ | 226700 | EE-XVI | 120 | 03/01.4.05/ EE-XVI | M/s Rakesh Bansal | 10.4.05 | 09.7.05 | 160158 | Comp
28 | Civil | 4.10.04 | 4.7.04 | Dev. Of U/R coloney in c-120/cLZ Sh: imp to side berms by pdg c.c. pave. & drainage System form A-149 to M&C-W centre in 'A' block shastri Ngr. In C-120/CLZ. | 336819 | EE-XVI | 120 | 247/15.10.04/ EE-XVI | M/s Suresh Kr Gupta | 20.10.04 | 18.12.04 | 336482 | Comp
29 | Civil | 4.10.04 | 6.8.04 | Imp to park by pdg gril wash Plaster in 'c' block near H.NO C-7 A in C-Block Slum Ternaments flast in Sarai Bastri in C-120/CLZ | 77800 | EE-XVI | 120
30 | Civil | 4.10.04 | 6.8.04 | Imp to park pdg gril wash plaster in 'c' block near H.NO C-4 A in 'C' block Slum ternaments flats in Sarai Basti in c-120/LZ | 90300 | EE-XVI | 120
- | Civil | 4.10.04 | 6.9.04 | Imp to road by pdg Mastie Asphalt Infront of A-block Gurudwara in Shastri Ngr. C-120 /CLZ Addl amount booked agist booking 2003.04 agasit Name of warok mentioned along total Rs 199800+73374=273174 | 73374 | EE-XVI | 120 | 248/15.10.04/ EE-XVI | M/s Rakesh Bansal | 24.10.04 | 21.1.05 | 72304 | Comp
31 | Civil | 1.12.04 | 21.8.04 | Imp to lane by pdg drainage and C.C in Chimniwala Katra in Shastri Ngr. C-119/CLZ | 302700 | EE-XVI | 119 | 518/18.2.05/ EE-XVI | M/s M.S.Consts. | 24.2.05 | 18.6.05 | 190986 | Comp
32 | Civil | 1.12.04 | 21.8.04 | Imp to lane by pdg drainage and C.c. in Dharam pura Lodge in Shakti Ngr. C-119/C-2 | 762600 | EE-XVI | 119 | 517/18.2.05/ EE-XVI | M/s M.S.Consts. | 24.2.05 | 17.6.05 | 534790 | Comp
33 | Civil | 1.12.04 | 21.8.04 | Imp to lane by pdg drainage and R.M.C from H.NO 55 45 to 5512 in Gali NO-5 New Chandra wal in c-119/CLZ | 736000 | EE-XVI | 119 | 471/10.2.05/ EE-XVI | M/s Shiva Const co | 14.2.05 | 3.6.05 | 691731 | Comp
34 | Civil | 1.12.04 | 21.8.04 | Imp to lane by pdg Drainage and R.M.c from H.NO 5775 to 5760 in New Chanderwal C-119/CLZ | 742200 | EE-XVI | 119 | 472/10.2.05/EEXVI | M/s Shiva Const co | 11.2.05 | 21.4.05 | 698306 | Comp
35 | Civil | 1.12.04 | 1.7.04 | Imp to lane by pdg Drainage and c.c. from H.NO 5790 to 5820 /7 in New Chanderwal in C-119/CLZ | 599400 | EE-XVI | 119 | 387/29.12.04/EEXVI | M/s Shiva Const co | 13.1.05 | 19.3.05 | 597685 | Comp
36 | Civil | 1.12.04 | 1.7.04 | Imp to lane by pdg drainage and R.M.C from H.No 5498 to 5804 and 5796 to 5803 Gali NO 6 New Chanderwal C-119/CLZ | 598800 | EE-XVI | 119 | 383/28.12.04/ EE-XVI | M/s Jindal Enterprises | 3.1.05 | 23.4.05 | 598800 | Comp
37 | Civil | 1.12.04 | 1.7.04 | Imp to Gali NO-2 bu pdg drainage & R.M.C of Prem Ngr. Shakti Ngr. In C-119/CLZ ( from H.NO 7266 to 7304 & its adj lanes) | 599100 | EE-XVI | 119 | 382/28.12.05/ EE-XVI | M/s Jindal Enterprises | 3.1.05 | WIP | 599100 | In prog
38 | Civil | 1.12.04 | 6.8.04 | Imp to lane adjoing M.c Pry SchoolSarai Basti & back lane of Main park Subhadra Coloney by pdg C.C. pav & drainage System in C-120/CLZ | 305600 | EE-XVI | 120 | 560/15.03.05/EE-XVI | M/s M.N. Associates | 7.04.06 | 12.05.06 | 169924 | Comp
39 | Civil | 1.12.04 | 6.8.04 | Imp to lanes by pdg C.C. pav and drainage system in 'A' block Slum tenaments flats in Sarai Basti in C-120/CLZ | 275400 | EE-XVI | 120
40 | Civil | 1.12.04 | 6.8.04 | Imp to lanes by pdg C.C. pav & drainage System in "B" block Slum Ternaments Flats in Sarai Basti c-120/CLZ | 254900 | EE-XVI | 120 | 72/28.4.05/ EE-XVI | M/s Inder Raj Sachdeva | 7.5.05 | 4.6.05 | 192835 | Comp
41 | Civil | 1.12.04 | 6.8.04 | Imp to lanes by pdg C.C. pav and drainage system in "C' block slum ternaments flats in Sarai basti c-120/CLZ | 263100 | EE-XVI | 120 | 81/3.5.05 EE-XVI | M/s Inder Raj Sachdeva | 12.5.05 | 26.6.05 | 199764 | Comp
42 | Civil | 1.12.04 | 6.8.04 | C/o footpath along main rd Sarai Basti from Rd NO-40 ToiE-55 in Sarai Basti in C-120/CLZ | 202600 | EE-XVI | 120 | 29/24.04.06/EE-XVI | M/s Deepak Aggarwal | 15.12.06 | 16.01.07 | 87062 | Comp
43 | Civil | 1.12.04 | 6.8.04 | Imp to main rds in Sarai Basti by pdg Dense capet surfacing form 'B" Road no 40 to M.C.Pry. School (iii) road between B& C block Slum Tenament flats (iii) chowk in the back of M.C Pry. School Sarai Basti C-120/CLZ | 795600 | EE-XVI | 120
44 | Civil | 1.12.04 | 30.7.04 | Imp to lane by pdg R.M.C pav and drainage system from E-2/17 to E-2/22 in Shastri Ngr. C-120/CLZ | 700000 | EE-XVI | 120 | 29/11.4.05/ EE-XVI | M/s Bansal Const. | 20.4.05 | 20.6.05 | 669254 | Comp
45 | Civil | 5.1.05 | 1.9.04 | Imp of drainage system on Nag Mandir Road in Shastri Ngr. & Diversion road in Shahzada Bagh in c-120/CLZ | 169900 | EE-XVI | 120 | 145/28.06.05/EE-XVI | M/s Vinod Kumar | 02.08.05 | 30.08.05 | 134165 | Comp
46 | Civil | 5.1.05 | 15.11.04 | imp to lane by pdg c.c. pave and drainage system form A-18 to A-41 in Shastri Ngr. In c-120/CLZ | 198400 | EE-XVI | 120 | 124/16.06.05/EE-XVI | M/s Rakesh Kumar Goel | 25.06.05 | 01.03.06 | 130411 | Comp.
47 | Civil | 5.1.05 | 15.11.04 | Imp to by pdg c.C. pav & drainage system from A-29to A-40 in Shastri Ngr. In c-120/CLZ | 198000 | EE-XVI | 120 | 125/16.06.05/EE-XVI | M/s Rakesh Kumar Goel | 25.06.05 | 01.03.06 | 129511 | Comp.
48 | Civil | 5.1.05 | 14.12.04 | Imp to lane by pdg C.c. pav& drainage system from F-34 to F-27 in F block in shastri Ngr. C-120/CLZ | 373700 | EE-XVI | 120 | 56/20.4.05/ EE-XVI | M/s Sanjeev Aggarwal | 29.4.05 | 30.6.05 | 253074 | Comp
|  |  |  | Total | 18004034 | [6 empty] | 14199161