## AC-22
STATUS REPORT OF THE MLA FOR THE YEAR 2004-05
Municipal Corporation of Delhi
Narela Zone
Name Of MLA |  |  |  | Sh. Surender Kumar | AC-22 |  | year 2004-05 |  | Allocation | 198.82 Lacs |  |  | Dated:-
Name of Constituency
Ward Nos and Names |  |  |  | C-37 Bawana C-38,Kanjhawla
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14
1 | Civil | 19.8.04 | 13.8.04 | Imp to Lane of pdg C.C. pav. From Jai Singh to Sube Gir Raj to Ram Chander House in village Darya Pur in C-37 Narela. | 243000 | Narela | 37 | 156/20.12.04 EE-Narela | M/s Brinder Singh Dabas | 4.1.05 | 20.5.05 | 218843 |  |  | Inprog.
2 | Civil | 19.8.04 | 13.8.04 | C/o O/S drain from Bakmike Mandir to out fall drain in village Qutabgarh in C-37 Narela. | 309000 | Narela | 37 | 328/22.3.05/ EE-Narela | M/s Ankit Associates | 29.3.05 | 23.7.05 | 284528 |  |  | Comp
3 | Civil | 19.8.04 | 13.8.04 | Imp to Lane by pdg C.C.pavement from Anand to Chopal in Village Qutab Garh in C-37 Narela. | 296301 | Narela | 37 | 188/04.1.05/ EE-Narela | M/s Satish Const.Co. | 11.1.05 | 30.4.05 | 296301 |  |  | Comp
4 | Civil | 19.8.04 | 13.8.04 | Imp to lane by pdg C.C. pavement from Darya Pur to Roshan & infornt of Chopal in vill. Qutab Garh in /c-37-II Narela. | 195800 | Narela | 37 | 151/20.12.04/ EE-Narela | M/s Amit const co | 29.12.04 | 20.4.05 | 176057 |  |  | Comp
5 | Civil | 19.8.04 | 13.8.04 | Imp ot lane by pdg C.C. pavement from Kehar Singh House to Hari singh & side lanes in village Katewara C-37-II Narela. | 236600 | Narela | 37 | 154/20.12.04 /EE-Narela | M/s Brinder Singh Dabas | 4.1.05 | 20.5.05 | 213788 |  |  | In Progress
6 | Civil | 19.8.04 | 13.8.04 | Imp to lane by pdg C.C. pavement form Rampat House to Shankar mor and side lanes in village pooth khurd in C-37 -I NArela | 588000 | Narela | 37 | 176/28.12.04/EE Narela | M/s Maya Builders | 5.1.05 | Wip | 538719 |  |  | In Progress
7 | Civil | 19.8.04 | 13.8.04 | Imp to lane of C.C. pavement from Main stand to Kalpna House in village Bawana C-37-I Narela. | 480174 | Narela | 37 | 174/28.12.04/EE-Narela | M/s Ramesh Kumar | 18.1.05 | 17.3.05 | 479764 |  |  | Comp
8 | Civil | 19.8.04 | 13.8.04 | Imp to lane by pdg C.C. pavement from Naveen to Daryao singh and Zile to Attar Singh House is village Nangal Thakran C-37-I Narela. | 224000 | Narela | 37 | 238/03.2.05/ EE-Narela | M/s Gaj Raj Singh | 10.2.05 | 20.5.05 | 203061 |  |  | Comp
9 | Civil | 19.8.04 | 13.8.04 | Imp to lane of pdy C.c. pavement from Ram kumar to Rania House and side lanes & Shyam wali gali in village Bajit pur C-37-I Narela. | 243000 | Narela | 37 | 286/24.2.05/ EE-Narela | M/s Brinder Singh Dabas | 16.3.05 | 15.6.05 | 223733 |  |  | Comp
10 | Civil | 19.8.04 | 13.8.04 | Imp to lane by pdg B/P from Sumer to Hawa Singh House in village salaha pur Majro in c-37 -I Narela. | 122500 | Narela | 37 | 157/20.12.04/EENarela | M/s Mathur Const Co | 10.2.05 | 28.3.05 | 111451 |  |  | Comp
11 | Civil | 19.8.04 | 13.8.04 | Imp of lane by pdg C.C. pav. From Mange Ram to Ram Kr. House and side lanes in village Darya pur C-37 Narela. | 325222 | Narela | 37 | 142/17.12.04/EE-N | Ms/ Vishal Const Co. | 20.12.04 | 15.4.05 | 325171 |  |  | Comp
12 | Civil | 19.8.04 | 13.8.04 | C/o O/S drain from Transformer of chopal in village Qutab Garh in C-37 Narela. | 351000 | Narela | 37 | 194/06.1.05 EE-NarelaE | M/s Rajesh Kumar | 12.1.05 | 12.5.05 | 318758 |  |  | Comp
13 | Civil | 19.8.04 | 13.8.04 | Imp to lane by C.C. pave. from Ram singh to Banbari and side lanes in Vill. Katewara in C-37-II Narela | 237000 | Narela | 37 | 155/20.12.04/EE Narela | M/s Brinder Singh Dabas | 4.1.05 | 17.5.05 | 213003 |  |  | In Prog.
14 | Civil | 19.8.04 | 13.8.04 | Imp of lane by pdg C.C. pave. from Azad to Inder House and side lanes in vill Mangesh pur C-37-I Narela. | 274000 | Narela | 37 | 120/10.12.04/EE-N | M/s Rakesh Kumar -II | 20.12.04 | P | 249352 |  |  | Inprog.
15 | Civil | 19.8.04 | 13.8.04 | Imp of lane by C.C. pav from Sumen to Phirni road in vill Sultan pur C-37-I Narela. | 185300 | Narela | 37 | 186/4.1.05 | M/s Vishal const Co | 28.1.05 | 21.3.05 | 172784 |  |  | Comp
16 | Civil | 19.8.04 | 13.8.04 | Imp of lane by B/P from Naresh to Parbhu Ram Hs in Nangal Thakran C-37-I Narela. | 136500 | Narela | 37 | 150/20.12.04 | M/s Amit const co | 4.1.05 | 28.3.05 | 128356 |  |  | Comp
17 | Civil | 19.8.04 | 13.8.04 | Imp to lane by pdg c.C. pave. from Pt Tara chand chawk to Lachhu rd. & Ajeet to karan singh Hs in vill Bajit pur C-37-I Narela. | 333200 | Narela | 37 | 152/20.12.04 EE Narela | M/s Sahil Builders | 27.12.04 | 18.5.05 | 303838 |  |  | In Prog.
18 | Civil | 19.8.04 | 13.8.04 | Imp of lane by pdg c.c. pave. from Balwan singh Hs to flood drain and Samsud in to Dharbir Hs in vill Salaha pur Majra C-37-I Narela. | 398756 | Narela | 37 | 145/17.12.04 | M/s Rajeev Sahrawat | 24.12.04 | 24.3.05 | 398464 |  |  | Comp.
19 | Civil | 31.8.04 | 15.7.04 | Imp to lane by C.C. Inder Gali of Ramphal Jai Parkesh & Chander Bhan in vill Bawana C-=37 N.Z. | 236072 | Project Rural | 37 | 72/10.12.04/EE-Pr.(R) | M/s Nikhil Builders | 17.12.04 | 24.1.05 | 235893 |  |  | Comp.
20 | Civil | 9.9.04 | 13.8.04 | Imp of Gali by c.c. from Hari Ram Pandit Hs to Nizam pur road in vill Jounti in C-38-I Narela. | 188400 | Narela | 38 | 161/20.12.04 | M/s OM Const co | 30.12.04 | 10.3.05 | 179451 |  |  | Comp.
21 | Civil | 9.9.04 | 13.8.04 | Imp of lane by B/P & O/s drain from Dr Dalal singh Hs & Mehavir Hs & its link Gali in Vill Nizam pur C-38-I Narela. | 149500 | Narela | 38 | 240/3.2.05 | M/s Rana Builders & Contcrater | 14.2.05 | 23.3.05 | 133916 |  |  | Comp.
22 | Civil | 9.9.04 | 13.8.04 | C/o O/s drain & M/P form Mandir & Toll Tax booth in vill Nizam pur C-38-I Narela | 157000 | Narela | 38 | 292/03.3.05/ EE-Narela | M/s Suresh Const.Co.-II | 14.3.05 | 08.7.05 | 151173 |  |  | Comp.
23 | Civil | 9.9.04 | 13.8.04 | M/P on Tikkri road from Toll Tax booth to Ajit Hs in vill. Nizam pur in c-38 -I Narela. | 197300 | Narela | 38 | 41/28.04.05 EE-Narela | M/S Satish Kumar | 30.04.05 | 05.09.05 | 197293 |  |  | Comp.
24 | Civil | 9.9.04 | 13.8.04 | C/o culvert at Tikkri Road near Toll Tax in Vill Nizam pur C-38-I Narela. | 133400 | Narela | 38 | 322/22.3.05/ EE-Narela | M/s Raj Roop Const. | 22.3.05 | 28.5.05 | 129717 |  |  | Comp
25 | Civil | 4.10.04 | 30.8.04 | Pdg M/p and O/S drain on Rd from Nasha Mukti Kentra to chopal and LInk Gali in Majri Vill. C-38-II/Narela | 470373 | Narela | 38 | 305/9.3.05 | M/s Naresh Kumar | 21.3.05 | 16.4.05 | 470186 |  |  | Comp
26 | Civil | 4.10.04 | 30.8.04 | Pdg c.c pave & remodelling O/s drain wazir General Store to sultan puri Rd in Kirari Vill C-38-II/Narela | 255800 | Narela | 38 | 183/4.1.05 | M/s Radhya Shyam | 10.1.05 | 27.3.05 | 245868 |  |  | Comp
27 | Civil | 4.10.04 | 30.8.04 | Pdg c.c. pave. Rd O/s drain from pandit syam singh to Devi singh near Phivni(Rd No-3) and park side chowk in village karala in c-38-II Narela. | 199800 | Narela | 38 | 141/17.12.04/EE-N | M/s Nand Kishore Gupta | 18.12.04 | 10.02.05 | 134255 |  |  | Comp.
28 | Civil | 4.10.04 | 30.8.04 | C/O O/s /drain from Sumit Building materral to Just Ahead of Kumar Decorators shop on Kirari Sultan Puri rd in Kirari vill.C-38-II/Karela | 600000 | Narela | 38 | 304/9.3.05 EENarela | M/s Naresh Kumar | 14.3.05 | 24.6.05 | 597000 |  |  | Comp
29 | Civil | 4.10.04 | 30.8.04 | Pdg c.c. and remodelhing O/s D from Tej Pal Hs to sumender singh Hs and LInk Gali in Karela Vill c-38-II/Narela | 182200 | Narela | 38 | 160/20.12.04/EE-N | M/s Nand Kishore Gupta | 21.12.04 | 10.1.05 | 121617 |  |  | Comp.
30 | Civil | 4.10.04 | 30.8.04 | Pdg c.c. pave and remodelhing O/s d/ from Narain Hs to Ram Kishan and Narender hs to Jagbir in Majri vill/C-38-II/Narela | 336100 | Narela | 38 | 228/27.1.05 EENarela | M/s Darawal Builders | 25.2.05 | 25.4.05 | 312076 |  |  | Comp
31 | Civil | 4.10.04 | 30.8.04 | C/o gali by M/P and O/s D/ from Bhari singh Hs to Phirni in Karala Vill c-38-II /Narela | 356861 | Narela | 38 | 294/03.3.05/ EE-Narela | M/s Laxmi Const.Co. | 28.3.05 | 26.9.05 | 353282 |  |  | In Prog
32 | Civil | 5.10.04 | 20.9.04 | P/f Gate type singh board at Kirari Rly Sation c-38/Narela | - | Project Rural | 38 | Work cancelled as desired by area MLA vide letter no.NIL dated 14.10.05 & recommanded by C.E-I dated 14.12.05 (Rs.199600.00)
33 | Civil | 5.10.04 | 20.9.04 | P/f gate type singh board on sultan puri rd Kirari in c-38/Narela | - | Project Rural | 38 | Work cancelled as desired by area MLA vide letter no.NIL dated 14.10.05 & recommanded by C.E-I dated 14.12.05 (Rs.199600.00)
34 | Civil | 5.10.04 | 20.9.04 | P/f Gate type singh board at Madan Pur Dabas Turining c-38/Narela | - | Project Rural | 38 | Work cancelled as desired by area MLA vide letter no.NIL dated 14.10.05 & recommanded by C.E-I dated 14.12.05 (Rs.199600.00)
35 | Civil | 5.10.04 | 20.9.04 | P/F Gate type singh board at Begum pur rd Karela,c-38/Narela | - | Project Rural | 38 | Work cancelled as desired by area MLA vide letter no.NIL dated 14.10.05 & recommanded by C.E-I dated 14.12.05 (Rs.443000.00)
36 | Civil | 27.10.05 | 30.11.04 | Imp of road from M..C school to irrigation canal in village Jounti M.C -38 I /Narela | 247042 | Narela | 38-I | 16/19.4.05/ EE-Narela | M/s Kamal Builders | 20.4.05 | 16.6.05 | 246971 |  |  | Completed
37 | Civil | 27.10.05 | 30.11.04 | Imp of Gali by pdg C.C. pav. and O/s drain from house of Jai Narain to Mehal in village Jounti c-38-I/ Narela | 135000 | Narela | 38-I | 1/08.4.05/ EE-Narela | M/s Shankar Const.Co. | 21.4.05 | 16.6.05 | 133343 |  |  | Completed
38 | Civil | 31.1.05 | 16.11.04 | C/o rd by MP from Rd No 3 to Phirni Rd along L&T Factory in villlage Mungesh Pur C-37-II Narela | 570000 | Narela | 37-II | 46/03.5.05/ EE-Narela | M/s Khatri Const.Co. | 06.5.05 | 05.8.05 | 496676 |  |  | Completed
39 | Civil | 31.1.05 | 16.11.04 | Imp to lane by CC Pav from Longs House to Phirni rd and Mahavir to Kishan House in village Harewali C-37-II Narela. | 199900 | Narela | 37-II | 3/08.4.05/ EE-Narela | M/s Raj Kumar | 18.4.05 | 05.8.05 | 155429 |  |  | Completed
40 | Civil | 31.1.05 | 22.11.04 | Imp t lane by pdg CC from main Narela Rd to Ramphal hous and Narela rd to Kalu Hs and adj lanes in village Bawana C-37-I | 88114 | Narela | 37-I | 49/03.5.05/ EE-Narela | M/s Ramesh Kumar | 10.5.05 | 05.9.05 | 87989 |  |  | Completed
41 | Civil | 4.2.05 | 16.11.04 | Const and Re-modelling of OS Drain from Nehar to chowk in Nithari Village C-38-II Narela | 214100 | Narela | 38-II | 23/27.4.05/ EE-Narela | M/s Barawal Builders | 03.5.05 | P | 152261 |  |  | In Progress
42 | Civil | 4.2.05 | 16.11.04 | Pdg M/.P and C/o open Suface drain from Narain Singh S/o Bharat Ram to Jagdish S/o Ganga Jha in village Karala C-38-II Narela | 482600 | Narela | 38-II | 83/26.5.05/ EE-Narela | M/s Surender Kumar Verma | 13.6.05 | 26.9.05 | 377500 |  |  | Completed
43 | Civil | 7.2.05 | 15.11.04 | Imp to lane by CC pav and C/o O./s Drain from Bhane to Kishan and Side lanes in village Dariya Pur C-37-II Narala | 244000 | Narela | 37-II | 71/13.5.05/ EE-Narela | M/s Raj Kumar | 02.6.05 | 19.7.05 | 188886 |  |  | Completed
44 | Civil | 7.2.05 | 22.11.04 | Imp to lane by Pdg RMC from Ghewara rd to Bhayan Chowk in village Bhawana C-37-I Nareala | 698000 | Narela | 37-I | 69/13.5.05/ EE-Narela | M/s Gupta Const.Co.-II | 20.5.05 | P | 574284 |  |  | In Progress
45 | Civil | 7.2.05 | 22.11.04 | Imp to lane by pdg CC Pav from Main Khanjhwala Rd to Ramphal (Mana) House and adj lanes villge Bawana C-.37-I Narela | 185104 | Narela | 37-I | 50/03.5.05/ EE-Narela | M/s Rakesh Kumar | 18.5.05 | 06.9.05 | 184791 |  |  | Completed
46 | Civil | 7.2.05 | 22.11.04 | Imp of lane by pdg CC Pav from Phirni Rd to Kartar hs in vllage Sultanpur C-37-I Nareala` | 42300 | Narela | 37-I | 359/30.3.05/ EE-Narela | M/s Barawal Builders | 30.5.05 | 07.7.05 | 33850 |  |  | Completed
47 | Civil | 7.2.05 | 16.11.04 | Imp of lane by B/P and C/o O/S Drain from Parveen Gupta to MC Pry School and side lanes in Ishwar Colony Bawna C-37-I Narela | 337155 | Narela | 37-I | 68/13.5.05/ EE-Narela | M/s Gupta Const.Co.-II | 20.5.05 | 06.9.05 | 335333 |  |  | Completed
48 | Civil | 7.2.05 | 16.11.04 | Imp of lane by pd CC Pav from Kishan Hs to Puran hs (Tele Wali Gali) in Village Salah pur Majra Dabas C-.37-I Narela | 140000 | Narela | 37-I | 33/27.4.05/ EE-Narela | M/s Mahboob Const.Co. | 18.5.05 | 30.6.05 | 105034 |  |  | Completed
49 | Civil | 7.2.05 | 16.11.04 | Imp of lane by BP and C/o O/S drain from Man Singh Hs to Flood Drain in village Chandpur Kalan in C-37-I Narela | 348723 | Narela | 37-I | 18/19.04.05/EE-Narela | M/s Alamba Const.CO | 26.04.05 | P | 313684 |  |  | In Prog.
50 | Civil | 16.3.05 | 15.2.05 | Imp to lane by CC Pav in Dayananad Pradhan Wali Gali in village Daryapur C-37-II Narela. | 117600 | Narela | 37-II | 156/26.07.05/EE-Narela | M/s Ravinder Kumar | 16.08.05 | 21.09.05 | 113878 |  |  | Comp.
51 | Civil | 16.3.05 | 15.11.04 | C/o Drain opposite Mandir to FC Drain in village Nithari C-38 Narela(Phrini Rd) Narela. | 260000 | Project Rural | 38 | 68/12.12.05/EE(Project)R | M/s Raj Engineers & Builders | 21.12.05 | P | 157962 |  |  | In Prog.
52 | Civil | 16.3.05 | 8.12.04 | I/C of Drian along main rd in village Jaunti C-38 Narela (Khanjhwala road on Phirni Rd) Narela. | 258000 | Project Rural | 38 | 70/12.12.05/EE(Project)R | M/s Raj Engineers & Builders | 20.12.05 | P | 196260 |  |  | In Prog.
53 | Civil | 21.3.05 | 13.8.04 | C/O O/s drain from Mehender Prajapat hs to Rd no 3 in village Tatesar C-38-I Narela | 271600 | Narela | 38-II | 139/19.07.05/EE-Narela | M/s Ravinder Kumar | 28.07.05 | 28.10.05 | 203303 |  |  | Completed
54 | Civil | 21.3.05 | 13.8.04 | Imp of gali by pdg BP and O/S Drain from Braham Chand hs to Ram Kumar Hs in village Nizampur C-38 -I Narela | 396500 | Narela | 38-II | 142/19.7.05/ EE-Narela | M/s Rajinder Singh Dahiya | 29.7.05 | 07.10.05 | 281771 |  |  | Completed
55 | Civil | 21.3.05 | 15.11.04 | Imp of rd by MP and O/s Drain from Ram Kumar Hs to Rishi Pal Hs and From Rajinder Hs to Umesh Singh hs in Village Khanjwala C-38-I Narela | 652800 | Narela | 38-II | 141/19.07.05 EE-Narela | M/s Garg Const.Co.II | 20.07.05 | 22.11.05 | 507275 |  |  | Completed
56 | Civil | 21.3.05 | 16.11.04 | Imp of lane by BP and O/s Drain from Community Hall to MC Pry school in Village Tatesar C-38-I Narela | 380000 | Narela | 38-II | 143/19.7.05/ EE-Narela | M/s Rajinder Singh Dahiya | 29.7.05 | 26.9.05 | 253255 |  |  | Completed
57 | Civil | 24.3.05 | 17.02.05 | Imp of lane by pdg. CC Pav from Jagdish Chander to Park and Culvert to Ganga Toli Rd and Drain park to Culvert in Village Pooth Khurd C-37-I Nareala | 298462 | Narela | 37-I | 144/19.7.05/ EE-Narela | M/s Surender Kumar Verma | 28.7.05 | 11.10.05 | 297873 |  |  | Completed
58 | Civil | 28.3.05 | 15.11.04 | Raising of rd by MP near school and Vijayaran Properties in village Nithari C-38 Narela | 260000 | Project Rural | 38 | 22/24.05.05/EE(pr.)R | M/s Naresh Kumar Garg | 02.06.05 | 20.08.05 | 195538 |  |  | Completed
59 | Civil | 31.3.05 | 17.2.05 | C/o B/wall ofpark in village Poothkhurd C-37-I Narela | 214350 | Narela | 37-I | 140/19.07.05/EE-Narela | M/s Ravinder Kumar | 11.09.05 | 20.10.05 | 214261 |  |  | Completed
60 | Civil | 31.3.05 | 17.2.05 | Imp of lane by pdg CC Pav from Mangat Ram Julaha to Dhanak Chopal in village Nangal Thakran C-37=-I Narela | 177712 | Narela | 37-I | 150/21.7.05/ EE-Narela | M/s Vikash Builders | 28.7.05 | 04.10.05 | 177549 |  |  | Completed
|  |  |  | Total | 15861221 | [6 empty] | 14102654
Remarks:- No of works booked=60, No of works cancelled=4
Note on I25: R.P.S:

## AC-54
STATUS REPORT OF THE MLA FOR THE YEAR 2004-05
Municipal Corporation of Delhi
Narela Zone
|  | Name Of MLA |  | Sh. C.S. Kandera | AC-54 |  | year 2004-05 |  | Allocation | 200.00 Lacs |  |  | Dated:-
|  | Name of Constituency |  | Narela
|  | Ward Nos and Names |  | C-101 , Narela C-102 Alipur
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14
1 | Civil | 29.7.04 | 23.7.04 | Imp of lane by pdg R.M.C and drain from Gyan singh S/o Meer singh Hs to Vijay pal Rana Hs vill Khara Kalan C-102/Narela | 759000 | Narela | 102 | 184/04.1.05/ EE-Narela | M/s Anil Gupta | 14.1.05 | P | 640292 |  |  | In Prog.
2 | Civil | 29.7.04 | 23.7.04 | C/o on RHS from main stand to Balbir Singh Hs near Johar in vill. Naya Bans C 102 /Narela. | 343000 | Narela | 102 | 229/27.01.05/EE-Narela | M/s Rajbeer & Sons Ent. | 27.01.05 | P | 343000 |  |  | In Prog.
3 | Civil | 29.7.04 | 23.7.04 | Imp of lane by pdg R.M.C and drain from Mohit General stone to Nihasl isht Hs vill Khera Kalan C-102/Narela | 181000 | Narela | 102 | 104/3.12.04 EE-Narla | M/s Anil Gupta | 10.12.04 | 9.3.05 | 145470 |  |  | In Prog.
4 | Civil | 29.7.04 | 23.7.04 | Imp of labe by pdg R.M.C and drain from Mohit General store to Nishat singh Hs at vill. Khera Kalan c-102/Narela | 795000 | Narela | 102 | 208/.12.1.05 EE-Narla | M/s Anil Gupta | 13.1.05 | P | 755481 |  |  | In Prog.
5 | Civil | 29.7.04 | 23.7.04 | Imp of road by P/M/P and drain from Balbir singh Hs to Jagdar singh Hs and Mahipal Hs to Krishna hs in vill Naya bans in C-102 /narela | 557716 | Narela | 102 | 112/31.12.04/EE-N | M/s Raj Associates | 5.12.04 | P | 557716 |  |  | In Prog.
6 | Civil | 29.7.04 | 23.7.04 | Imp of lane by pdg C.C. and drain in vill Holambi kalan c-102 from Chopal to old post office/ Narela. | 272000 | Narela | 102 | 200/10.1.05/ EE-Narela | M/s Rajbeer & Sons Ent. | 17.1.05 | 15.4.05 | 247391 |  |  | Comp.
7 | Civil | 29.7.04 | 23.7.04 | Imp of lane by interlocking tiles along Jai Maan Public school in vill. Khera Khurd c-102/ Narela | 212993 | Narela | 102 | 191/4.1.05/EE-N | M/s Satish Const CO. | 12.1.05 | 12.2.05 | 211307 |  |  | Comp.
8 | Civil | 29.7.04 | 24.7.04 | Pdg C. C. in the lanes from Braham Praksh Hs to Prahlad Hs vill Khera Kalan C-102-I /Narela | 275652 | Narela | 102 | 44/23.8.04 EE Narela | M/s Pratap Singh Rathi | 2.3.05 | P | 251061 |  |  | In prog.
9 | Civil | 29.7.04 | 24.7.04 | Pdg C.C. in the lanes from Hem Raj House to Hukam Chand Sharma Hs in village Khera Kalan in C-102 in /Narela | 260726 | Narela | 102 | 308/09.3.05/ EE-Narela | M/s J.S. Const.Co. | 10.3.05 | 02.7.05 | 260628 |  |  | Comp.
10 | Civil | 29.7.04 | 16.7.04 | Pdg c.c. in the lanes from Ratan Phalwan was to Anoop singh Hs and Sukhram to Beg Ram Hs in Vill Khera Khurd C-102-I/ Nerela. | 204458 | Narela | 102 | 42/23.8.04/EE-N | M/s AK Const CO-II | 28.8.04 | 29.11.04 | 203307 |  |  | Comp.
11 | Civil | 30.7.04 | 24.7.04 | C/o culvert on Main road infornt of Sani Sweets Corner is vill Holambi Kalan in C-102-I /Narela | 298300 | Narela | 102 | 250/11.2.05 EE Narela | M/s Chauhan Const co | 17.2.05 | P | 267551 |  |  | In Prog.
12 | Civil | 30.7.04 | 24.7.04 | P/f Retro reflactiave sign boards at Entry point on G.T road at cloud garden, Bakhtawar pur turn, Kherqa kalan, Holmbi Kurdh and Singu Border C-102/ Narela | 194700 | Narela | 102
| Civil | 20.8.04 | 12.8.04 | RE:- C/o R.C.C. Culvert on crossings/drain in Bagri colony and main road Gold smith Colony c-101, Narela | 10234 | Pr-Rural | 101 | 42/7.10.04/EE-Pr® | M/s Goela Assoc, | 16.11.04 | 22.11.04 | 9918 |  |  | Comp.
13 | Civil | 5.10.04 | 26.9.04 | Pdg c.c. pavement on O/S drain from surash Kr. Hs to Chand Singh Hs in village Alipur (Nehru Enclave) in C-102-I/ Narela | 130717 | Narela | 102 | 159/29/07/05 EE Narela | M/s Rajeev Sharawat | 29/07/05 | P |  |  | In Prog. | Prog.
14 | Civil | 5.10.04 | 26.9.04 | Pdg B/P and O/s drain from Sarin Hs to Jadgish Hs in village Budh Pur C-102-I Narela | 194100 | Narela | 102 | 140/17.12.04 EE.Narela | M/s Nand kishore Gupta | 25.12.04 | W.I.P | 134572 |  |  | Prog.
15 | Civil | 5.10.04 | 26.9.04 | Pdg B?P and drain forn suresh s/O Kartar singh To Salim Mia Hs in Ali pur c-102-I Narela | 128211 | Narela | 102 | 225/24.1.05 EE Narela | M/s Kamal Traders | 1.2.05 | 29.3.05 | 128211 |  |  | Comp.
16 | Civil | 20.10.04 | 1.8.04 | Pdg c.c. pav and remodeling O/S drain from Raj Singh to Shar singh Hs and Balber singh jto Dayal Hs in village Tigipur C-102 -II/ Narela | 216956 | Narela | 102 | 249/11.2.05 EE Narela | M/s A.K. const co -II | 11.2.05 | 30.4.05 | 216956 |  |  | Comp.
17 | Civil | 20.10.04 | 1.8.04 | Pdg C.C. pave B/P and drain from Mehender Singh to Ganga Ram Hs and Charan Singh Towards Harnam Hs in Jhangola in C-102-II/ N | 264508 | Narela | 102 | 344/28.3.05 EE Narela | M/s Kuldeep Const co | 28.3.05 | 10.5.05 | 263937 |  |  | Comp.
18 | Civil | 20.10.04 | 1.8.04 | Pdg C.C. pave and drain form main road Towards Masjid and Adjoing lane in vill. Palla in C-102 -II/N | 389900 | Narela | 102 | 206/12.1.05/ EE-Narela | M/s Amit Const.Co. | 12.1.05 | P | 242009 |  |  | In Prog.
19 | Civil | 20.10.04 | 1.8.04 | Pdg C.C pav and drain from chatter Singh Hs to M.C. pry school in vill. Sungar pur C-102-II/N | 206628 | Narela | 102 | 256/11.2.05 EE Narela | M/s A.K. const co -II | 11.2.05 | 30.4.05 | 206326 |  |  | Comp.
20 | Civil | 20.10.04 | 1.8.04 | Pdg M/p and drain from Atter Singh Hs to Joginder Hs in village Jhangola in c-102-II/Narela | 399200 | Narela | 102 | 134/01.07.05/EE-Narela | M/s Chauhan Const. | 01.07.05 | P | 189397 |  |  | In Prog.
21 | Civil | 20.10.04 | 1.8.04 | Pdg B/p and drain from Chopal to Rajpal House in village Tajpur in C-102-II/ Narela. | 396200 | Narela | 102 | 209/18.01.05 EE Narela | M/s Mathur Const.Co. | 18.01.05 | W.I.P | 151128 |  |  | In Prog.
22 | Civil | 1.11.04 | 22.10.04 | C/o retarining wall of approach road to Cremation Ground from Phirni road in village Bankner.C 101/N | 533223 | Pr-Rural | 101 | 142/14.3.05/ EE-Pr.® | M/s Jagdamba Trading Co. | 23.3.05 | 23.7.05 | 532050 |  |  | Comp.
23 | Civil | 1.11.04 | 22.10.04 | Imp of approch road to Cremation Ground from Pherni road to Cremation Ground in village Bankner. (By M/P and Brice pav.)/ Narela. | 521848 | Pr-Rural | 101 | 141/14.3.05/ EE-Pr.® | M/s Jagdamba Trading Co. | 23.3.05 | 02.12.05 | 515557 |  |  | Comp.
24 | Civil | 2.11.04 | 26.9.04 | Imp of lane by M/P and drain from Shanti Bhawan to Sh Bhim Singh Plot in Village Khera Khurd in C-102-II/Narela. | 335605 | Narela | 102 | 333/28.03.05 EE Narela | M/s Naresh Kumar | 04.04.05 | W.I.P | 335478 |  |  | In Prog.
25 | Civil | 2.11.04 | 26.9.04 | Pdg B/P and O/s drain form Naresh Kumar House to Khad factory and link gali in village Alipur in C-102-I/Narela | 448300 | Narela | 102-I
26 | Civil | 2.11.04 | 26.9.04 | Pdg B/P and drain form Naresh Kumar to Jagdish & Jaginder wali gali in village Ali pur C-102-I/Narela | 338600 | Narela | 102-I
|  | 9.11.04 | 26.9.04 | REVISED BOOKING-against B.S No 140 of 2003-04, pdg B/P and drain in the lane from Chander Bhan house to Raj Singh Hs and Rajinder House and Dulat house in Landless Coloney Budh pur C-102-II/Narela | 18458 | Narela | 102-I | 97/3.12.04 EE Narela | M/s Laxmi Const Co-II | 12.12.04 | P | 18042 |  |  | In Prog
27 | Civil | 19.11.04 | 18.11.04 | Imp of lane by pdy C.c. pave and O/s draih from Bal kishn hs to Rajpal Hs and its adjoin lanes in Pana Paposian c-101-I/Narela | 162100 | Narela | 101-I | 290/3.3.05 EE- Narela | M/s Shiv Raj Garg | 5.3.05 | 29.3.05 | 157406 |  |  | Comp.
28 | Civil | 19.11.04 | 18.11.04 | Imp of lane pdg C.C. pav. And O/s drain from Ramphal Hs to Mushi Ram House Via Sunil Dutt& Sanjeev Hs in Village Tikri Khurd c-101-II/Narela | 115200 | Narela | 101-I | 277/18.2.05/EE-Narela | M/s Ran Bir Singh | 19.2.05 | 24.3.05 | 114200 |  |  | Comp.
29 | Civil | 19.11.04 | 18.11.04 | Imp of lane by pdg M/p from Jain Bhagwan factory to Phirni Road in village Sanoth in C-101-II/Narela | 196281 | Narela | 101-I | 360/30.3.05/ EE-Narela | M/s Barawal Builders | 07.4.05 | 01.8.05 | 194185 |  |  | In Prog
30 | Civil | 6.12.04 | 5.10.04 | C/o drain on main road Swatanter Nrg. from Narela Bawana road to Narela Lampur road to Narela road. SH: Soil inverstigation for C/o R.C.C. drain om main road Swatanter Nrg. In Narela Zone | 40500 | Pr-Rural | 101 | 89/28.12.04/EE(Pr Rural) | M/s Allied Eng. | 28.12.04 | 10.1.05 | 40500 |  |  | Comp.
31 | Civil | 6.12.04 | 12.10.04 | C/o drain on main road swatenter Ngr. from Narela Bawana road to Narela Lampur road in Narela zone SH. Consultancy for design & drawing of drain Narela | 88200 | Pr-Rural | 101 | Advance to IIT Delhi Vide Cm. Orders Dt 5.11.04 | M/s IIT Delhi | Advance to M/s IIT Delhi Vide Cm. Orders Dt 5.11.04 |  | 88160 |  |  | Comp.
32 | Civil | 10.12.04 | 20.7.04 | C/o drain on main road Swatanter Nrg from Narela Bawana road to Narela Lampur road in C-101 PH-I (from RD1175 to 1500) | 6154940 | Pr-Rural | 101 | 33/13.06.05/EE-Pr-Rural | M/s Aggarwal Builders | 22.06.05 | P | 6142849 |  |  | In Prog
33 | Civil | 20.12.04 | 18.10.04 | Imp of Phirni road by providing C.C. pav. From Rishi House to Culvert in village Bakner C-101 -I , Narela | 258100 | Pr-Rural | 101-I
34 | Civil | 20.12.04 | 18.10.04 | Imp of Phirni road by private c.c. pavement from Ran singh House to Roshan house in Village Bankner C-101 Narela | 190240 | Pr-Rural | 101 | 61/07.12.05/EE-Pr.(Rural) | M/s A.K. const co | 16.12.05 | 18.02.06 | 189802 |  |  | Comp.
35 | Civil | 20.12.04 | 18.10.04 | Imp of Phirni road by pdg C.C. pavement from Kanwar Lal Hs to Ram Narain house in village Bankner C-101, Narela | 189593 | Pr-Rural | 101 | 60/07.12.05/EE-Pr.(Rural) | M/s A.K. const co | 16.12.05 | 18.02.06 | 189341 |  |  | Comp.
36 | Civil | 20.12.04 | 18.10.04 | Imp of Phivni road by pdg c.c. pavement From Prakash Hoise to Ram Kumar House in vollage Bankner C-101, Narela | 193249 | Pr-Rural | 101 | 80/16.12.05/EE-Pr.(Rural) | M/s Parvesh Const.Co. | 20.12.05 | 08.03.06 | 193095 |  |  | Comp.
37 | Civil | 20.12.04 | 18.10.04 | C/o open Surface drain from Lampur road to Maiwala Mander RHs in village Bankner C-101, Narela | 156993 | Pr-Rural | 101 | 79/16.12.05/EE-Pr.(Rural) | M/s Parvesh Const.Co. | 20.12.05 | 08.03.06 | 156991 |  |  | Comp.
38 | Civil | 20.12.04 | 18.10.04 | C/o open surface drain from Vetenary Hospital to Mai wala Mandir in village Bakner in C-101, Narela | 160798 | Pr-Rural | 101 | 78/16.12.05/EE-Pr.(Rural) | M/s Parvesh Const.Co. | 20.12.05 | 08.03.06 | 160797 |  |  | Comp.
39 | Civil | 20.12.04 | 18.10.04 | Imp of road by pdg C.C. pav. from Umrao house to Maiwala Mandir in village Bakner C-101, Narela | 181292 | Pr-Rural | 101 | 19/16.5.05 | M/s Naresh Kumar Garg | 16.5.05 | 17.6.05 | 181251 |  |  | Comp
40 | Civil | 20.12.04 | 18.10.04 | Imp of road by C.C. pavement from Lampur road to Satish House in village Bakner C-101-I Narela | 175538 | Pr-Rural | 101 | 34/14.6.05/ EE-Pr.® | M/s Naresh Kumar Garg | 14.6.05 | 10.7.05 | 175533 |  |  | Comp
41 | Civil | 20.12.04 | 18.10.04 | Imp of lane by pdy C.C. pav.and O/s drain in gali no 15 A from suresh Hs to Sirihi Hs and Side lane of gali no 15 C along Salber Kaushik Hs in Swatanter Ngr C-101, Narela | 258000 | Pr-Rural | 101 | 67/12.12.05/EE(Pr.) R | M/s Suresh Kumar | 19.12.05 | 17.03.06 | 192721 |  |  | Comp.
| Civil | 7.1.05 | 20.11.04 | REVISED BOOKING- against booking S.No 2, C/O drain on R.H.S from Main stand to Balbir Singh House near Johar in village Naya Bans in c-102-I Narela | 33599 | Narela | 102 | 229/27.01.05/EE-Narela | M/s Rajbeer & Sons Ent. | 27.01.05 | P | 31192 |  |  | In Prog.
42 | Civil | 7.1.05 | 20.11.04 | C/o of lane form Sushil Dal Mill to Narayan house in village Holambi Kalan in C-102-I Narela | 416940 | Narela | 102-I | 47/03.5.05/ EE-Narela | M/s Khatri Const.Co. | 10.5.05 | 10.8.05 | 416688 |  |  | Comp.
43 | Civil | 11.1.05 | 20.11.04 | C/o lane by pdg c.C. pav along Sh. Prem Singh house on Narela Ali pur Road in Ali pur C-102-I/N | 99800 | Narela | 102-I | 352/30.3.05/ EE-Narela | M/s Ankit Associates | 07.4.05 | 07.5.05 | 79632 |  |  | Comp.
44 | Civil | 11.1.05 | 12.10.04 | C/o drain from N.D.P.L office to Culvert on Swaroop Nagar Chowk , Narela | 240000 | Pr-Rural | 101 | 52/19.10.05/Pr-Rural | M/s Subhash Gupta | 19.10.05 | 26.12.05 | 176840 |  |  | Comp.
|  |  |  | Total | 18198596 | [6 empty] | 15707968