## Smt.Anjali Rai
STATUS REPORT OF THE MLA FOR THE YEAR 2004-05 UPTO 16.11.07
Municipal Corporation of Delhi
S.P.ZONE
|  | Name Of MLA |  | Smt Anjali | AC-57 |  | year 2004-05 |  | Allocation | 100.00 Lacs
|  | Name of Constituency |  | Paharganj
|  | Ward Nos and Names |  | C-108 , PaharGauj C-107, Bazar Sita Ram
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Div. | W.no | Work order no with date | Name of Agencys | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14
1 | Civil | 3.8.04 | 6.4.04 | Imp to foot path infront of sheela line Cinema at D.B. Gupta road at C-108 S.P.Zone. | 267600 | EE-III | 108 | 395/11.3.05 | M/s Sanjeev Builders | 12.3.05 | 20.4.05 | 226175 |  |  | Completed
2 | Civil | 3.8.04 | 8.4.04 | Imp to road suirface at Gali sangeet Rasha and other bitumen lanes in C-108 s.P.Z(BY pdg M/P) | 250000 | EE-III | 108 | 398/11.3.05 | M/s Jain Const | 18.3.05 | 12.4.05 | 249667 |  |  | Completed
3 | Civil | 3.8.04 | 6.4.04 | Imp to road from P.N. Bank to to St. Anthority school at D.B. Gupta rd at C-108/s.P.Z(by proding c.c.) | 248000 | EE-III | 108 | 397/11.3.05 | M/s Sanjeev Builders | 12.3.05 | 3.5.05 | 247533 |  |  | Completed
4 | Civil | 20.9.04 | 4.6.04 | Imp to B/wall turkman Gate flat at Ajmeri Gate in c-108 /S.P.Z | 279800 | EE-III | 108 | 461/30.3.05/ EEE-III | M/s Amit Kumar | 28.3.05 | 28.5.05 | 270982 |  |  | Completed
5 | Civil | 20.9.04 | 4.6.04 | Imp to lanes from H.No 114 to 103 and 304 to 1308 by pdy C.C in Baghichi Tan sukh Rai in c-108/S.P.Z | 241400 | EE-III | 108 | 151/8.11.04/ EE-III | M/s Amit Kumar | 18.10.04 | 30.11.04 | 232321 |  |  | Completed
6 | Civil | 20.9.04 | 4.6.04 | Imp to lanes by pdy C.C. from H.No 594 to 589, Gali Bal Mukanal and from Has 847 to 855,891 to 880 in Gali Beriwali C-108/s.P.Z | 246100 | EE-III | 108 | 152/8.11.04/ EE-III | M/s Amit Kumar | 15.10.04 | 17.11.04 | 235847 |  |  | Completed
7 | Civil | 20.9.04 | 4.6.04 | Imp to Lane by pdy c.c. from Hni 3214 To 3220 to 3198 and adjring laves at Gali Phatak telian in c-108 /S.P.Z | 241200 | EE-III | 108 | 270/29.12.04 EE-III | M/s Amit Kumar | 29.12.04 | 22.2.05 | 228538 |  |  | Completed
8 | Civil | 20.9.04 | 4.6.04 | Imp to lane by pdg C.c. from Shop no 2205 to 2122 in Chuna Mandi in C-108 to S.P.Z | 246100 | EE-III | 108 | 146/29.10.04 EE-III | M/s Manoj Const. | 16.10.04 | 16.11.04 | 232374 |  |  | Completed
9 | Civil | 20.9.04 | 4.6.04 | Imp to lane by pdg c.c. from H.no 9104 to 9089 in Multani Dhanda in c-108 s.P.Z | 243300 | EE-III | 108 | 147/29.10.04 EE-III | M/s Manoj Const. | 16.10.04 | 18.11.04 | 230379 |  |  | Completed
10 | Civil | 20.9.04 | 4.6.04 | Imp to lane by pdg C.c. from H.No 9033 to 9050 in Multani Dhanda in c-108 /S.P.Z | 242300 | EE-III | 108 | 150/8.11.04 EE-III | M/s Manoj Const. | 8.11.04 | 10.12.04 | 228989 |  |  | Completed
11 | Civil | 20.9.04 | 4.6.04 | Imp to lane by pdg C.c. from shop no 2795 To 2758 to chuna Mandi in c-108/s.p.Z | 241900 | EE-III | 108 | 144/29.10.04 EE-III | M/s Manoj Const. | 15.10.04 | 13.11.04 | 228635 |  |  | Completed
12 | Civil | 12.10.04 | 1.6.04 | Imp to lanes by pdg C.C. infront of pahtak Telian in Turk man Gate flats in C-108 S.P.Z | 239500 | EE-III | 108 | 267/29.12.04 EE-III | M/s Jagmohan Kapoor | 31.12.04 | 22.2.05 | 226784 |  |  | Completed
13 | Civil | 12.10.04 | 1.6.04 | Imp to lanes by pdg c.c. from H no 2869 to 2873 and Adj lanes in Bul Buli Khana in c-108/ s.P.Z | 243500 | EE-III | 108 | 269/29.12.04 EE-III | M/s Jagmohan Kapoor | 31.12.04 | 1.3.05 | 231572 |  |  | Completed
14 | Civil | 12.10.04 | 1.6.04 | Imp to lanes by pdg C.c. in Tarkman Gate flats at Ajmeri Gate in c-108/S.P.Z | 246400 | EE-III | 108 | 268/29.12.04 EE-III | M/s Jagmohan Kapoor | 30.12.04 | 15.2.05 | 232376 |  |  | Completed
15 | Civil | 14.10.04 | 8.10.04 | Providing tabe well at kunde wala Latrine Block in c-108/S.P.Z | 213551 | EE-III | 108 | 164/18.11.04 EE-III | M/s Sudhir Kumar | 15.11.04 | 25.11.04 | 213388 |  |  | Completed
16 | Civil | 10.12.04 | 1.6.04 | Imp to Gali no -2 by pdg C.C. in Multani Dhanda in C-108/S.P.Zone | 246600 | EE-III | 108 | 402/14.3.05 EE-III | M/s Malhotra Const Co | 15.4.05 | 25.5.05 | 235579 |  |  | Completed
17 | Civil | 13.1.05 | 1.6.04 | Imp to lanes by C.C. from H.NO 404 to 470 to 555 at Gali Chandi wali Mamtola in c-108/s.P.Zone | 233108 | EE-III | 108 | 342/7.2.05EE-III | M/s Ajit Singh Rana | 8.2.05 | 28.3.05 | 232728 |  |  | Completed
18 | Civil | 13.1.05 | 1.6.04 | P/l C.C. pave. From H.NO 4505 to 4512 at Lambi Gali and 4388 to 4412 to Shah Ganj in C-108/S.P.Zone | 229310 | EE-III | 108 | 343/7.2.05EE-III | M/s Ajit Singh Rana | 8.2.05 | 30.3.05 | 228745 |  |  | Completed
19 | Civil | 28.2.05 | 8.7.05 | Imp to lane by pdg CC from H.no. 8928 to 8942 in Multani Dhanda C-108 SPZ | 246100 | EE-III | 108 | 450/23.3.05/ EE-III | M/s Kushal Bharat | 06.4.05 | 05.7.05 | 178308 |  |  | Completed
20 | Civil | 28.2.05 | 8.7.05 | Imp to lane by pdg CC from Shop.no. 2123 to 2194 in Chuna Mandi C-108 SPZ | 246900 | EE-III | 108 | 456/30.3.05/ EE-III | M/s Kushal Bharat | 06.4.05 | 05.7.05 | 234817 |  |  | Completed
21 | Civil | 28.02.05 | 8.7.04 | Imp to lane by pdg CC from H.no. 8833 to 8973 in Multani Dhanda C-108 SPZ | 244300 | EE-III | 108 | 449/29.3.05/ EE-III | M/s Kushal Bharat | 17.4.05 | 18.7.05 | 182383 |  |  | Completed
22 | Civil | 2.3.05 | 17.12.04 | Imp to PVt Katra No 3977 Kaseru Walan Pehar Ganj and 462 Mantola Pahar Ganj C-108.SPZ(By pdg C C and Drainage etc_ | 261800 | EE-III | 108 | 239/08.08.05/EE-III | M/s S.K. Const Co | 15.12.05 | 24.05.06 | 170283 |  |  | Comp.
23 | Civil | 2.3.05 | 16.12.04 | Imp to PVt Katra No 2879 Bulbuli Khana Pahar Bhojla C-107.SPZ (By pdg C C and Drainage etc_ | 259700 | EE-III | 107 | 245/08.08.05/EE-III | M/s Kapoor Const. | 26.09.05 | 14.12.05 | 173531 |  |  | Comp.
24 | Civil | 2.3.05 | 16.12.04 | Imp to Pvt Katra NO 4998 Laddu Ghati and 15 main bazar Pahar Ganj C-108 spZ ( by pdg CC and Drainage etc) | 258800 | EE-III | 108 | 240/08.08.05/EE-III | M/s S.K Const.Co | 16.12.05 | 24.05.06 | 169908 |  |  | Comp.
25 | Civil | 2.3.05 | 16.12.04 | Imp to PVt Katra NO 4534 dal Mandi Pahar Ganj C-108 SPZ (By pdg CC and drainage etc) | 262300 | EE-III | 108 | 241/08.08.05/EE-III | M/s S.K Const.Co | 16.12.05 | 20.05.06 | 172289 |  |  | Comp.
26 | Civil | 2.3.05 | 16.12.04 | Imp to Pvt Katra NO 1366 sangat Rasha and general Market C-108 SPZ (By pdg CC and Drainage etc) | 254200 | EE-III | 108 | 242/08.08.05/EE-III | M/s Naveen Const. | 12.08.05 | 26.06.06 | 170768 |  |  | Comp.
27 | Civil | 2.3.05 | 16.12.04 | Imp to PVt Katra No 3824 Gali Hafiz Bannewali and 3815 Churi Walan C-107 SPZ (by pdg CC and drianage etc) | 254600 | EE-III | 107 | 243/08.08.05/EE-III | M/s Kapoor Const. | 31.08.05 | 15.12.05 | 169915 |  |  | Comp.
28 | Civil | 2.3.05 | 16.12.04 | Imp to PVt Katra No 2720 Gali NO 7 Chana Mandi Pahar Ganj C-108 SPZ (by pdg CC and drianage etc) | 250400 | EE-III | 108 | 244/08.08.05/EE-III | M/s S.K Const.Co | 18.12.05 | 20.05.06 | 162873 |  |  | Comp.
29 | Civil | 2.3.05 | 16.12.04 | Imp to PVt Katra No 5527 shora Kothir and Katra NO 4837 Laddu Ghati C-108 SPZ (by pdg CC and drianage etc) | 262900 | EE-III | 108 | 247/08.08.05/EE-III | M/s Manoj Const. | 26.09.05 | 14.12.05 | 175149 |  |  | Comp.
30 | Civil | 2.3.05 | 16.12.04 | Imp to PVT Katra No 2457 Nalwa Street and 3929 kaseru walan c-108 SPZ (by pdg CC and drianage etc) | 257100 | EE-III | 108 | 249/08.08.05/EE-III | M/s S.K Const.Co | 20.12.05 | 20.05.06 | 169085 |  |  | Comp.
31 | Civil | 2.3.05 | 16.12.04 | Imp to PVt Katra No 214 Ghee mandi 1936 Gali NO 10 Chuna Mandi and 93 Krishna Gali C-1087SPZ (by pdg CC and drianage etc) | 257200 | EE-III | 108 | 248/08.08.05/EE-III | M/s S.K Const.Co | 20.12.05 | 24.05.06 | 169008 |  |  | Comp.
32 | Civil | 2.3.05 | 16.12.04 | Imp to PVt Katra No 3840 Tel Mandi and 3620 Dariba Pan pahar Ganj C-108 SPZ (by pdg CC and drianage etc) | 257100 | EE-III | 108 | 238/08.08.05/EE-III | M/s S.K Const.Co | 15.12.05 | 24.05.06 | 167258 |  |  | Comp.
33 | Civil | 2.3.05 | 16.12.04 | Imp to PVt Katra No 5090 Phatak Bans Kucha Pandit 107 SPZ (by pdg CC and drianage etc) | 252300 | EE-III | 108 | 246/08.08.05/EE-III | M/s Naveen Const. | 16.08.05 | 20.06.06 | 168769 |  |  | Completed
34 | Civil | 2.3.05 | 18.8.04 | Imp to road surface by M/P at DB Gupta rd in C-1085 SPZ (by pdg CC and drianage etc) | 246700 | EE-III | 108 | 32/.5.5.05/ EE-III | M/s S.K. Const Co | 7.5.05 | 31.5.05 | 246253 |  |  | Completed
|  |  |  | Total | 8472069 | [6 empty] | 7093209
Note on J49: ACER:

## Sh. Rajesh jain
STATUS REPORT OF THE MLA FUND FOR THE YEAR 2004-05 UP TO 16.11.07
Municipal Corporation of Delhi
S.P.ZONE
Name Of MLA |  |  |  | Sh Rajesh Jain | AC-64 |  | year 2004-05 |  | Allocation | 177.42 Lacs
Name of Constituency |  |  |  | Sadar Bazazr
Ward Nos and Names |  |  |  | C-121 Subzi Mandi C-122, Sadar Bazazr
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per | D.O.C. As per | First Running | Second running | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  | 13 | 14
1 | Elect. | 26.7.04 | 23.6.04 | Imp to street light at various lanes of Partap Nagr , Andha Mugal , Roshnara Road w-no-121 S.P.Z | 199840 | EE(E)-I | 121 | 63/13.9.04/EEE-I | M/s Shivam Electricals | 22.9.04 | 21.10.04 | 193563 |  | 193563 | Completed
2 | Elect. | 26.7.04 | 23.6.04 | Imp of street light of various lane in Arya Pura , sohan Ganj , Ganta Ghar and Sabzi Mandi area w.NO-121 /S.P.Z | 199840 | EE(E)-I | 121 | 64/13.9.04/EEE-I | M/s Shivam Electricals | 22.9.04 | 21.10.04 | 193607 |  | 193607 | Completed
3 | Elect. | 26.7.04 | 23.6.04 | Imp of street light of various lane at sadar Bazar & Deputy Garj area s.P.ZW/no-122 | 199840 | EE(E)-I | 122 | 78/30.9.04/EEE-I | M/s ACE Engineers Bureau | 10.10.04 | 5.11.04 | 193675 |  | 193675 | Completed
4 | Elect. | 26.7.04 | 23.6.04 | Impt of street light of VCArious lane of B.G.Rd shivaji road & Pahari Dheraj area S.P.Z w.No-122 | 199840 | EE(E)-I | 122 | 79/30.9.04/EEE-I | M/s ACE Engineers Bureau | 8.11.04 | 10.11.04 | 193538 |  | 193538 | Completed
5 | Civil | 5.8.04 | 2.8.04 | P/L c.c. in Gali Rewari in c-121 a S.P.z | 202234 | EE-III | 121 | 606/22.01.07/EE-III | M/s R.P Enterprises | 24.01.07 | 24.03.07 |  |  | 202098 | Completed
6 | Civil | 5.8.04 | 2.8.04 | P/L c.c. in Gali Boriwali & Gali Chajjiu Lohar Wali in c-121 A/S.P.Z | 209266 | EE-III | 121 | 436/30.11.06/EE-III | M/s D.K Builders-I | 30.11.06 | 25.01.07 |  |  | 208775 | Completed
7 | Civil | 5.8.04 | 2.8.04 | P/L c.C. gali Ram , Rohanara Road in c-121 B /S.P.Z | 233731 | EE-III | 121 | 381/24.2.05/`EE-III | M?s Choudhary Associates | 25.2.05 | 23.3.05 | 233276 |  | 233276 | Completed
8 | Civil | 5.8.04 | 2.8.04 | Imp to Pvtt katra No 4628 in Indra Market in c-121/ S.P.Z | 230816 | EE-III | 121 | 380/24.2.05/`EE-III | M?s Choudhary Associates | 28.2.05 | 23.3.05 | 230054 |  | 230054 | Completed
9 | Civil | 17.8.04 | 12.8.04 | Imp to road surface by pdg M/P of Roshnara Bagh opp. Rohsan area bash Gate in c-121 a/S.P.Z | 261900 | EE-III | 121
10 | Civil | 17.8.04 | 12.8.04 | Imp to rd surface by pdgy M/P of Gulabi Bagh around centre park in c-121 B/S.P.z | 262100 | EE-III | 121 | 1103/31.03.08/EE-III | M/s R.P.Ent. | 26.04.08 | 09.06.08 |  |  | 261872 | Completed
11 | Civil | 24.8.04 | 11.5.04 | Imp to rd surface by pdgy M/P at Ram Bagh Rod Azad Market in c-122B S.PZ | 244400 | EE-III | 122 | 161/09.11.04/EE-III | M/s Hardit Singh Kochar | 20.11.04 | P |  |  | 171905 | In Prog.
12 | Civil | 24.8.04 | 7.5.04 | P/l R.M.C. pavement from Kandhanu Sweet to Gali Lotan Jat chowk in Pahari Dhiraj Rd in W.No-122 A/S.P.Z | 200409 | EE-III | 122 | 322/20.1.05/EE-III | M/s Sanjeev Builders | 22.1.05 | 4.3.05 | 200306 |  | 200306 | Completed
13 | Civil | 24.8.04 | 7.5.04 | P/L R.M.C from Ram Bagh Rd to Lita Gyan School at Baghe preetii in W.No-1228/S.PZ | 184204 | EE-III | 122 | 235/17.12.04/ EEE-II | M/s Wadhwa Const.Co. | 18.1.05 | 22.8.05 |  |  | 183830 | Completed
14 | Civil | 24.8.04 | 6.4.04 | P/l R.M.C pavement from Kishan Ganj Chowk to Takya Rajan Masjid at Shivaji Rd Azad Mkt in W.No-122 B/S.PZ | 495131 | EE-III | 122 | 128/29.9.04/EE-III | M/S Rakesh Bansal | 30.9.04 | 5.1.05 | 494872 |  | 494872 | Completed
15 | Civil | 24.8.04 | 6.4.04 | P/l R.M.C pavement from B.G rd to Kishan Ganj Chowk in w/No 122 B, S.P.Z | 596276 | EE-III | 122 | 127/29.9.04/EE-III | M/S Rakesh Bansal | 30.9.04 | 5.1.05 | 596147 |  | 596147 | Completed
16 | Civil | 26.8.04 | 20.8.04 | P/L Kota Marble flooring infront of Masjid gat sang trashan P.D rd from 3064 to 3067 4621 ti 4623 3007 to 2980 at B.G. rd in w.No-122 A/ S.P.Z | 177333 | EE-III | 122 | 60/24.5.05/ EE-III | M/s United Const. | 03.10.05 | 29.12.05 |  |  | 176903 | Completed
17 | Civil | 26.8.04 | 20.8.04 | P/l R.M.C pavement from Shivji rd Gali No-3 at /faiz Ganj in W.No-122 B,S.P.Z | 193435 | EE-III | 122 | 394/11.3.05/ EE-III | M/s R.K.Const. | 24.5.05 | 22.8.05 |  |  | 193282 | Completed
18 | Civil | 26.8.04 | 20.8.04 | P/L R.M.C PAV. FORM . ROAD TO Gali NO 3 at Faiz Ganj W.No-122 S.P.Z | 189587 | EE-III | 122 | 393/11.3.05/ EE-III | M/s R.K.Const. | 14.5.05 | 08.7.05 |  |  | 189439 | Completed
19 | Civil | 26.8.04 | 20.8.04 | P/l Marble & Kota Flooring infront of Mandir & Masjid at Bagchee Peerji in W.No-122 B /S.P.Z | 176155 | EE-III | 122 | 68/24.5.05/ EE-III | M/s D.K. Const co | 02.6.05 | 22.8.05 |  |  | 176046 | Completed
20 | Civil | 26.8.04 | 20.8.04 | Imp to road from Deputy Ganj to Gali Bawji /at B.G. Rd. in W.No-122 A/S.P.Z | 243800 | EE-III | 122
21 | Civil | 26.8.04 | 20.8.04 | Imp to road from Mandir Towards TCI Transport at Baghee peerji W.No-122 B S.P.Z | 182595 | EE-III | 122 | 7/25.04.05/EE-III | M/s United Const. | 15.06.06 | 29.12.06 |  |  | 176919 | Completed
22 | Civil | 10.9.04 | 30.6.04 | Imp to pvt Katra NO 2200 and 2238 im Mukem pura in C-121 /S.P.Z | 229894 | EE-III | 121 | 158/8.11.04/EE-III | M/s Jai Bhawani Builders | 18.11.04 | 10.02.05 | 229844 |  | 229844 | Completed
23 | Civil | 10.9.04 | 6.9.04 | Imp to C.C. flooring from H.No 4132 to 4152 in Gali jain Mandir wali & adj. Lane in C-121 A /S.P.Z | 179082 | EE-III | 121 | 583/17.01.07/EE-III | M/s R.P Singh | 05.02.07 | 07.04.07 | 229844 |  | 178167 | Completed
24 | Civil | 10.9.04 | 6.9.04 | Imp to c.C. flooring in Gali Chajju Lohar G T.Road and Adj lanes in C-121 A S.P.Z | 171511 | EE-III | 121 | 03/25.04.05/EE-III | M/s Goldy Const.Co | 18.05.05 | 09.09.05 |  |  | 36956 | Completed
25 | Civil | 4.10.04 | 5.7.04 | Imp to C.C. flooring from Qtrs no 33 to Qtr and its & adjoing lanes in Vasudev Ngr. In c-121 B S.P.Z | 239200 | EE-III | 121 | 216/DT.6.12.04 EE-III | M/s parkash Trad ers | 15.12.04 | 12.1.05 | 214270 |  | 214270 | Completed
26 | Civil | 4.10.04 | 5.7.04 | Imp to pvt katra NO 3225 to 3228 in Arya Pura in C-121 A S.P.Z | 231222 | EE-III | 121 | 141/DT.21.10.04 EE-III | M/s parkash Trad ers | 26.10.04 | 10.1.05 | 230372 |  | 230372 | Completed
27 | Civil | 4.10.04 | 5.7.04 | Imp to C.C. flooring from H.NO A-1 to A-8 in A Block in Pratap Ngr. In C-121 B S.P.Z | 223025 | EE-III | 121 | 140/DT.21.10.04 EE-III | M/s parkash Trad ers | 21.10.04 | 20.11.04 | 222688 |  | 222688 | Completed
28 | Civil | 4.10.04 | 5.7.04 | Imp to c.C. flooring from H.No B-I to B-16 in B -Block Pratap Ngr C-121 B | 225666 | EE-III | 121 | 142/DT.21.10.04 EE-III | M/s parkash Trad ers | 1.11.04 | 22.11.04 | 225053 |  | 225053 | Completed
29 | Civil | 5.10.04 | 8.6.04 | P/l C.C. pav & drainage system from G.T.Rd. to Roshanara Road 3692 and in Gali Thane wali in c-122 B S.P.Z | 232720 | EE-III | 122 | 228/DT.14.12.04 EE-III | M?s Gulati const co,. | 3.1.05 | 10.03.05 | 232307 |  | 232307 | Completed
30 | Civil | 5.10.04 | 3.7.04 | Imp to C.C. flooring H.No-1238 to 1773 in Sohan Ganj in C-121 A S.P.Z | 237008 | EE-III | 121 | 297/0DT.13.1.05 EE-III | M/s Jagmohan kapoor | 13.1.05 | 2.3.05 | 236561 |  | 236561 | Completed
31 | Civil | 5.10.04 | 5.7.04 | P/l c.c. in Gali pather wali & gali Beri Wali at G.T. Rd in C-121 A/S.P.Z | 229567 | EE-III | 121 | 239/0DT.17.12.04EE-III | M/s Malhotra Const co. | 17.12.04 | 18.1.05 | 228994 |  | 228994 | Completed
32 | Civil | 5.10.04 | 1.7.04 | P/l Marble stone flooring infront of Mandir Ram Dawara in Balmiki wara in C-121 A/S.P.Z | 222088 | EE-III | 121 | 488/02.02.06/EE-III | M/s M.C.Aren | 02.02.06 | 11.03.06 |  |  | 222088 | Completed
33 | Civil | 5.10.04 | 1.7.04 | P/l C.c. in gali at Kala Rest. (Malka Ganj ) from H.No T-1697 to 1700 in c-121 A S.P.Zone | 247300 | EE-III | 121 | 251/27.12.04/EE-III | M/s M.C Aren | 7.1.05 | 4.5.05 |  |  | 237673 | Completed
34 | Civil | 5.10.04 | 14.9.04 | Imp to C.C. pace in Arya Pura from H.No 113 to 124 in C-121/A s.P.Z. | 246095 | EE-III | 121 | 215/6.12.04 | M/s Kailash chand | 27.11.04 | 12.1.05 | 245748 |  | 245748 | Completed
35 | Civil | 5.10.04 | 6.9.04 | Imp to pvt. Katra No 1469 ,935 and 1475 in Panjabi Mohalla in c-121 S.P.Z | 173131 | EE-III | 121 | 04/25.04.05/EE-III | M/s Goldy Const.Co | 20.05.05 | 03.09.05 |  |  | 70797 | Completed
36 | Civil | 5.10.04 | 6.9.04 | Imp to c.c. flooring FromH.No N-32 / 1 to N-32 /46 and its adjoing lanes in sita Saran Coloney in c-121/S.P.Z | 176542 | EE-III | 121 | 69/24.05.05/EE-III | M/s D.K. Const co | 28.5.05 | 12.7.05 |  |  | 175932 | Completed
37 | Civil | 5.10.04 | 6.9.04 | Imp to c.c. flooring form H.No 1518 to 1530-31 in Lajja "Ram Building , Punjabi Mohalla and From H.No-1535 to 1546 in Deena Nath Building C-121 /S.P.Z | 176548 | EE-III | 121 | 58/24.5.05 /EE-III | M/s Kalra Const | 11.6.05 | 22.7.05 |  |  | 175468 | Completed
38 | Civil | 6.10.04 | 14.9.04 | P/L Polish Kota Stone infront of Mandir Masjid and Gurudawara in C-121/ S.P.Z name of Mandir - at Gali no 1 Partap Nagr Name of Gurudwara -Partap Nagr | 253244 | EE-III | 121 | 214/6.12.04 | M/s Kailash chand | 27.11.04 | 8.1.05 | 252769 |  | 252769 | Completed
39 | Civil | 27.1.05 | 4.6.04 | P/l Pavement from 5090 to 4905 in Rai Market in W.No-122 A /S.P.Z | 233663 | EE-III | 122 A | 429/22.3.05 EE-III | M/s Sidharth Const | 28.3.05 | 3.6.05 |  |  | 233560 | Completed
40 | Civil | 1.2.05 | 15.9.04 | P/L RMC From Foote road to Fountain Telewara Qutab road in w.no. 122 A SPZ (Imp to CC Pav by P/L RMC from Sindhi Mkt to Partap Mkt at BG Rd in w.n 122A spz | 387862 | EE-III | 122 A | 426/22.3.05/ EE-III | M/s D.K. Builders-I | 28.10.05 | 20.12.05 |  |  | 387814 | Completed
41 | Civil | 1.2.05 | 15.9.04 | P/L RMC From Foote road to Fountain Telewara Qutab road in w.no. 122 A SPZ (Imp to CC Pav by P/L RMC from Foote Rd to Gupta Mkt at BG Rd in w.n 122A spz | 491545 | EE-III | 122 A | 427/22.03.05/EE-III | M/s D.K.Builders-I | 31.03.05 | 20.12.05 |  |  | 491379 | Completed
42 | Civil | 1.2.05 | 15.9.04 | P/L RMC From Foote road to Fountain Telewara Qutab road in w.no. 122 A SPZ (Imp to CC Pav by P/L RMC from Gupta MKt to sindhi MKt in w.n 122A spz | 356505 | EE-III | 122 A | 428/22.3.05/ EE-III | M/s D.K. Builders-I | 02.11.05 | 20.12.05 |  |  | 356500 | Completed
43 | Civil | 16.2.05 | 20.7.04 | P/L CC in gali shafi bldg at Roshanara Road C-121A sPZ | 172263 | EE-III | 121A | 457/303.05 EE-III | M/s R.P Enterp | 7.5.05 | 10.6.05 |  |  | 171777 | Completed
44 | Civil | 16.2.05 | 20.7.04 | Imp to Pvt Katra No 2124 in Mukim Pura in C-121 SPZ (By CC and Drainage | 231194 | EE-III | 121 | 432/22.3.05 | M/s Choudhary Assoc. | 28.3.05 | 27.5.05 |  |  | 230687 | Completed
45 | Civil | 16.2.05 | 6.11.04 | Imp to Pvt Katra No 2224 , 2150 and 2146 in Shora Kothi in C-121 SPZ (by CC And drianage | 233255 | EE-III | 121A | 431/22.3.05 EE-III | M/s Choudhary Assoc. | 28.3.05 | 28.5.05 |  |  | 230835 | Completed
46 | Civil | 2.3.05 | 2.1.05 | Imp to lane by CC Pav from Mata Mandir Gate RA Rd to Ladhan Rajput Chopal in Arya Pura c-121A SPZ | 180377 | EE-III | 121A | 55/24.5.05/ EE-III | M/s Islamuddin | 25.5.05 | 14.8.05 |  |  | 180000 | Completed
47 | Civil | 2.3.05 | 4.1.05 | Imp to lane by CC Pav from 2466/1 Roshanara Rd to Community Centre in Punjabi Basti in C-121A SPZ | 179807 | EE-III | 121A | 59/24.5.05 EE-III | M/s Pawan Const | 4.6.05 | 11.7.05 |  |  | 179779 | Completed
48 | Civil | 2.3.05 | 17.1.05 | Imp to rd by pdg CC from Roshanara rd to Mata Mandir chowk C-121 SPZ | 181675 | EE-III | 121A | 272/16.08.05/EE-III | M/s Jagmohan kapoor | 18.08.05 | 30.09.05 |  |  | 181246 | Completed
49 | Civil | 2.3.05 | 12.8.04 | Imp to lane by CC Pav along O Block Park and adj lanes in Partap Nagar C-121B SPZ | 179233 | EE-III | 121B | 54/24.5.05 EE-III | M/s Kalra Const | 28.5.05 | 22.7.05 |  |  | 177837 | Completed
50 | Civil | 2.3.05 | 11.1.05 | Imp[ to Gali Ram mandir by CC Pav in Balmiki Bara C-121A SPZ | 181998 | EE-III | 121A | 468/31.3.05 EE-III | M/s Bajaj Const Co | 15.4.05 | 4.6.05 |  |  | 181722 | Completed
51 | Civil | 2.3.05 | 6.9.04 | Imp to Lav. Block of Sindhi Katra in Gali Kartar at Arya Pura C-121SPZ (By pdg CC and Drainage etc) | 131628 | EE-III | 121 | 96/02.06.05/EE-III | M/s Jagmohan kapoor | 11.06.05 | 04.09.05 |  |  | 131034 | Completed
52 | Civil | 2.3.05 | 7.8.04 | Imp to PVt katra N 2 & 3 in Gali Ganesh sohan ganj C-121A SPZ (By pdg CC and Drainage etc) | 229595 | EE-III | 121A | 71/27.5.05/ EE-III | M/s M.C.Aren | 27.5.05 | 30.7.05 |  |  | 229560 | Completed
53 | Civil | 2.3.05 | 6.8.04 | Imp to PVt katra N 4974 Arya puura C-121A SPZ (By pdg CC and Drainage etc) | 229988 | EE-III | 121A | 72/27.5.05/ EE-III | M/s M.C.Aren | 27.5.05 | 16.7.05 |  |  | 229532 | Completed
54 | Civil | 2.3.05 | 6.8.04 | Imp to PVt katra N 4151 at Arya puura C-121A SPZ (By pdg CC and Drainage etc) | 227525 | EE-III | 121A | 70/27.5.05/ EE-III | M/s M.C.Aren | 24.5.05 | 14.7.05 |  |  | 227486 | Completed
55 | Civil | 2.3.05 | 24.1.05 | Imp to Chopal Rajputana Main bazar Subzi Mandi C-121A sPZ SPZ (By pdg Marble stone flooring and Glaze tiles etc | 171688 | EE-III | 121A | 61/24.5.05/ EE-III | M/s Narender Singh Dhankar | 24.5.05 | 14.7.05 |  |  | 171198 | Completed
56 | Civil | 2.3.05 | 24.1.05 | Imp to Mata Mandir Chopal at Mata Mandir Chowk in C121A spz (by pdg K/S/F and glazed tiles ) | 170977 | EE-III | 121A | 220/18.07.05/EE-III | M/s V.P Gupta | 14.10.05 | 12.12.06 |  |  | 164354 | Completed
57 | Civil | 2.3.05 | 24.1.05 | Imp to Physical Centre oppositeSita saran Colony in C-121A SPZ SPZ (By pdg CC and Drainage etc) | 165719 | EE-III | 121A | 62/24.5.05/ EE-III | M/s Narender Singh Dhankar | 24.5.05 | 15.7.05 |  |  | 165412 | Completed
58 | Civil | 14.3.05 | 10.2.05 | Imp to PVt Katra no 557 and 144 in Mukim Pura a a Malka Ganj in C-121A SPZ (By pdg CC and Drainage etc) | 179265 | EE-III | 121A | 57/24.5.05/ EE-III | M/s Islamuddin | 24.5.05 | 16.7.05 |  |  | 178833 | Completed
59 | Civil | 16.3.05 | 15.3.05 | P/L CC Pav in glai NO 3 Noor Ganj in W.n. 122B SPZ | 183560 | EE-III | 122B | 182/28.6.05/ EE-III | M/s Jagmohan kapoor | 30.6.05 | 12.9.05 |  |  | 183457 | Completed
60 | Civil | 16.3.05 | 15.3.05 | P/L CC Pav from 6891 to 6900 in gali Maya Mam Sahib wali and 6875, gali Lal tain wali & 6930 to 6958 gali Chowk Wali in C-122 B SPZ | 181812 | EE-III | 122B | 109/06.6.05/ EE-III | M/s D.K.Const.Co. | 07.6.05 | 22.8.05 |  |  | 181695 | Completed
61 | Civil | 16.3.05 | 15.3.05 | P/L CC Pav and along to Entrance from BG Rd to Beri wala Chowk at Gali Jamadar in w.no. 122A sPZ | 177724 | EE-III | 122A | 110/06.6.05/ EE-III | M/s D.K.Const.Co. | 06.6.05 | 06.9.05 |  |  | 177482 | Completed
62 | Civil | 16.3.05 | 15.3.05 | P/L CC Pav in Gali no 1 Noor Ganj in W.no. 122B SPZ | 183438 | EE-III | 122B | 226/25.7.05/ EE-III | M/s National Const.Co. | 04.10.05 | 30.12.05 |  |  | 183337 | Completed
63 | Civil | 16.3.05 | 15.3.05 | P/L CC Pav and Imp to Stairs at Gali no 5 Faiz Ganj in wno. 122B SPZ | 182440 | EE-III | 122B | 225/25.7.05/ EE-III | M/s National Const.Co. | 04.10.05 | 30.12.05 |  |  | 182079 | Completed
64 | Civil | 16.3.05 | 15.3.05 | P/L CC Pav in gali Sheehse Wali at Kishan Ganj in W.no. 122B SPZ | 181741 | EE-III | 122B | 82/31.05.05/EE-III | M/s Islamuddin | 20.06.05 | 21.07.05 |  |  | 181509 | Completed
65 | Civil | 16.3.05 | 15.3.05 | P/L CC Pav in Katra (P) 4379 -4381 Lekh Ram in w.no. 122A SPZ | 182524 | EE-III | 122A | 83/31.5.05/ EE-III | M/s Islamuddin | 14.6.05 | 06.9.05 |  |  | 182091 | Completed
66 | Civil | 16.3.05 | 15.3.05 | P/l CC Pav in Gali Patna Wali 7184 to 720 & 7102 to 7125 to gali Madarsawali in Beri wala Bagh in C122B SPZ | 183119 | EE-III | 122B | 81/31.5.05/ EE-III | M/s Islamuddin | 15.6.05 | 22.8.05 |  |  | 182974 | Completed
67 | Civil | 16.3.05 | 1.3.05 | P/L CC Pav in gali no. 4 Faiz ganj in w.no. 122b SPZ | 164847 | EE-III | 122B | 97/02.6.05/ EE-III | M/s Jagmohan kapoor | 03.6.05 | 31.8.05 |  |  | 164749 | Completed
68 | Civil | 16.3.05 | 15.3.05 | Imp to Lav block in Katra (P) 4445, 4428 & Flooring main Entrance & CC Flooring in gali Nihal Singh & Imp to Lav block 90 Jatwara in C-122B SPZ | 180730 | EE-III | 122B | 117/06.6.05/ EE-III | M/s Islamuddin | 25.6.05 | 13.9.05 |  |  | 180491 | Completed
69 | Civil | 21.3.05 | 8.3.05 | P/L Premix Carpet in K Block Partap Nagar C-121B SPZ | 243100 | EE-III | 121B | 189/28.6.05/ EE-III | M/s Essco Traders | 15.7.5 | 24.8.05 |  |  | 242676 | Completed
|  |  |  | Total | 15337372 | [8 empty] | 14428879

## Sh. M.L. Sodhi
STATUS REPORT OF THE MLA FUND FOR THE YEAR 2004-05
Municipal Corporation of Delhi
S.P.ZONE
Name Of MLA |  |  |  | Sh. M.L. Sodhi | AC-69 |  | year 2004-05 |  | Allocation | 144.18 Lacs
Name of Constituency |  |  |  | Ram Nagar
Ward Nos and Names |  |  |  | C.131 Kadam Singh C-132, Manak Pura
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Divis-ion | W.no | Work order no with date | Name of Agencys | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Civil | 26.7.04 | 26.6.04 | Imp to C.C. flooring from Shop NO 6456 factory of road to 5733 Radhika Traders and adjoing lanes C-131 (B) S.P.Zone | 244500 | EE-III | 131 | 245/07.09.06/EE-III | M/s Sajid Khan | 20.10.06 | 15.12.06 | 199877 | Completed
2 | Civil | 26.7.04 | 26.6.04 | Imp to C.C. flooring from Shop NO 6426/1 factory road Ram Trading Co. factory road and adjoing lanes C-131 (B) S.P.Zone | 247000 | EE-III | 131 | 246/07.09.06/EE-III | M/s Sajid Khan | 26.10.06 | 15.12.06 | 201955 | Completed
3 | Civil | 26.7.04 | 26.6.04 | P/L C.C. main Gali in Model Basti from H.NO 8605/ 1 to 20 &21 to 23 C-132 A S.P.Zone,.(Rs.245800/-) | - | EE-III | 132 | wroks cancelled as desired by area MLA of letter dated 22.08.07 & approved by E-in-C dated 10.08.07
4 | Civil | 26.7.04 | 26.6.04 | P/L C.C. M. C. in Gali in Model Basti from H.NO 42 &43 & 44 to 50 C-132 A S.P.Zone.(Rs.236800/-) | - | EE-III | 132 | wroks cancelled as desired by area MLA of letter dated 22.08.07 & approved by E-in-C dated 10.08.07
5 | Elect | 26.7.04 | 26.6.04 | Modification of Semi Hight Mast pole Inst. At LIG & MiG flats Motia Khan wNo-132/S.P.Zone | 155526 | EEE-I | 132 | 81/5.10.04/EEE-I | Ms . Miglani Electricals | 14.10.04 | 2.11.04 | 149480 | Completed
6 | Civil | 27.7.04 | 21.4.04 | Imp to Chennel & S.W. drain Opp Mpl Workshop Jhandewallan in C-132 (B) S.P>Zone | 182300 | EE-III | 132 | 201/23.11.04/EE-III | M.s Hardit Singh Kochar | 30.11.04 | 16.2.05 | 163566 | Completed
7 | Civil | 27.7.04 | 28.4.04 | Imp to footpath of Service road at Ram Kumar marg At C-132 B SP.zone opp Mangla Hospital C-132.(Rs.278000/-) | - | EE-III | 132 | wroks cancelled as desired by area MLA of letter dated 22.08.07 & approved by E-in-C dated 10.08.07
8 | Civil | 27.7.04 | 15.7.04 | P/L Kota stone flooring infront of Mander Dharam Shalla at Nabi Karim & 52 Qurts. in C-131 B/S.P.zone | 247200 | EE-III | 131 | 171/18.11.04/EE-III | M/s Rajesh Const CO. | 18.11.04 | 31.12.04 | 209463 | Completed
9 | Civil | 27.7.04 | 15.7.04 | Imp to draing ststem and flooring in Pvt. Katra Mo109.119,122 in Chinnet Basti C-131 A S.P.zone.(Rs.247100/-) |  | EE-III | 131 | wroks cancelled as desired by area MLA of letter dated 22.08.07 & approved by E-in-C dated 10.08.07
10 | Civil | 27.7.04 | 15.7.04 | Imp to Pvt. Katra NO 9452 to 9462 in Bagh Raoji in C-132 A S.P.Z. | 247000 | EE-III | 132 | 172/18.11.04/EE-III | M/s Rajesh Const CO. | 20.12.04 | 5.2.05 | 229172 | Completed
11 | Civil | 27.7.04 | 15.7.04 | P/L C.C. in Laxman puri from H.NO L-117 to H.No L-120 and adjoing lanes in C-131 A/S.P.Zone.(Rs.242600/-) | - | EE-III | 131 | wroks cancelled as desired by area MLA of letter dated 22.08.07 & approved by E-in-C dated 10.08.07
12 | Civil | 27.7.04 | 16.7.04 | Imp to PVt karta no 9462 to 9447 in Bagh Raoji C-132 A.S.P.Zone.(Rs.247400/-) | - | EE-III | 132 | wroks cancelled as desired by area MLA of letter dated 22.08.07 & approved by E-in-C dated 10.08.07
13 | Civil | 27.7.04 | 16.7.04 | P/L C.C. Amar Puri from H.NO AB-138 To H.NO AB-145 (Gali Jhandewali) and Gali Bothewali and adjoing lanes in c-131 A(S.P.Zone.(Rs.246849/-) | - | EE-III | 131 | wroks cancelled as desired by area MLA of letter dated 22.08.07 & approved by E-in-C dated 10.08.07
14 | Civil | 27.7.04 | 1.7.04 | P/L C.C. in Amar Nagar in lane opp to H.No 7219 to H.NO 7226 and in adjoing lanes in c-131 A (S.P.Zone) | 247100 | EE-III | 131 | 178/23.11.04/EE-III | M/s Sajid Khan | 14.12.04 | 18.1.05 | 227410 | Completed
15 | Civil | 27.7.04 | 1.7.04 | P/L C.C. In Amar Puri , Siddartha Nagar from H.No AB-337 to H.No A-777 and in adjoing lanes in C-131 A/S.P.Zone | 223909 | EE-III | 131 | 175/23.11.04/EE-III | M/s Sajid Khan | 29.11.04 | 20.1.05 | 223858 | Completed
16 | Civil | 27.7.04 | 1.7.04 | P/L C.C. in Aram Nagar in the lane opp to H.NO 7206 to H.No 7215(Gali Bharat Siwak Samaj Wali ) and adjoing lanes in C-131 A/S.P.zone | 225087 | EE-III | 131 | 176/23.11.04/EE-III | M/s Sajid Khan | 29.11.04 | 12.1.05 | 224933 | Completed
17 | Civil | 27.7.04 | 1.7.04 | P/L C.C. in Amar Puri Siddartha Nagr . from H.No C-735 to H.No A-784 and adjoing lanes in C-131 a/S.P.Zone | 227724 | EE-III | 131 | 177/23.11.04/EE-III | M/s Sajid Khan | 27.12.04 | 22.1.05 | 227591 | Completed
18 | Civil | 29.7.04 | 24.6.04 | Imp of Service Road by c.c. pav at Ram Kumar marg C-132 B S.P.zone from Tagore Public School to Shop No 48 C-132 S.P.Z. | 172384 | EE-III | 132 | 568/27.03.06/EE-III | M/s Guru kirpa Entrp. | 18.04.06 | 27.05.06 | 172209 | Completed
19 | Civil | 29.7.04 | 4.6.04 | P/L c.C. in main Basti Arekasha Road From H.NO 7864 to 7889 and in adjoing lanes in w.No 131A/S.P.Zone | 247200 | EE-III | 131 | 64/24.05.05EE-III | M/s Manoj Const. | 25.05.05 | 22.7.05 | 236143 | Completed
20 | Civil | 29.7.04 | 16.7.04 | Imp to pvt. Karta Dhobi Wala in Bagh Raoji from 9432 to 9450 in C-132 A S.P.Z | 246500 | EE-III | 132 | 217/6.12.04EE-III | M/s Rajesh Const CO. | 14.12.04 | 28.2.05 | 225719 | Completed
21 | Civil | 29.7.04 | 20.7.04 | P/L C.C. in Tail Mill road Amar Puri from H.No AC- 1 to H.NO AC-15 15 and adjoing lanes in W.No-131 A/S.P.Zone | 245600 | EE-III | 131 | 170/18.11.04EE-III | M/s Rajesh Const CO. | 23.11.04 | 5.1.05 | 229636 | Completed
22 | Civil | 29.7.04 | 1.7.04 | Imp of different lane by c.c. pav. in Motia khan in c-132 B/S.P.ZoneFrom (D/S Qtrs) 70 B to 120 B | 174199 | EE-III | 132 | 370/24.02.05 EE-III | M/s Guru kirpa Entrp. | 20.04.05 | 3.06.05 | 173770 | Completed
23 | Civil | 29.7.04 | 15.7.04 | P/L Perforted tiles & Imp to drainge system from H.No ABC -58 to Parks in MIG,LIG flats Motia khan C-1321/ S.P.zone | 246750 | EE-III | 132 | 247/17.12.04EE-III | M/s Rajesh Const CO. | 16.12.04 | 25.1.05 | 214438 | Completed
24 | Civil | 2.8.04 | 30.7.04 | P/L perfortated Tiles & imp to draninge system from H.No 48A to 58 A in MIG and LIG in Motia Khan C-132/SPZ.(Rs.245700/-) | - | EE-III | 132 | wroks cancelled as desired by area MLA of letter dated 22.08.07 & approved by E-in-C dated 10.08.07
25 | Civil | 2.8.04 | 21.7.04 | P/L C.C. in Amar puri from H.No AB 420 to H.No AB 414 and adjing lanes in W.No -131 A/S. P.Zone | 246000 | EE-III | 131 | 169/18.11.04 | M/s Rajesh Const CO. | 18.11.04 | 5.2.05 | 230043 | Completed
26 | Civil | 2.8.04 | 6.6.04 | Imp to drainage system and P/L c.c. in Pvt Katra NO 5657/17 & T-144 gali Hanuman Mandir in c-131 B S.P.Z. | 245900 | EE-III | 131 | 63/24.5.05/ EE-III | M/s Ganesh Builders | 25.5.05 | 27.7.05 | 178578 | Completed
27 | Civil | 2.8.04 | 6.6.04 | Imp to drainage ststem & P/L C.C. in pvt. Katra NO 6499 & 64 73 in Gali Dhune wali in C-131 S.P.Z.(Rs.247100/-) | - | EE-III | 131 | wroks cancelled as desired by area MLA of letter dated 22.08.07 & approved by E-in-C dated 10.08.07
28 | Civil | 4.10.04 | 12.6.04 | P/L C.C. in Prem Nagar. from H.NO A-572 to H.No A-584 and adjoing lanes in W-131 A S.P.Zone | 173137 | EE-III | 131 | 341/19.10.05/EE-III | M/S Gulati Const CO. | 24.10.05 | 09.01.06 | 167001 | Completed
29 | Civil | 4.10.04 | 1.7.04 | Imp to C.C. flooring from 5983 factory road to 5991 Sikligaran and adj. Lanes in C-131 B/S.P.Z. | 245900 | EE-III | 131 | 287/7.1.05/EE-III | M/s Sajid Khan | 27.1.05 | 26.2.05 | 226371 | Completed
30 | Civil | 4.10.04 | 1.7.04 | Imp to C.C. flooring from 5993 Bag Mkt. To 6114 Gali RaviDass and adj. Lanes in C-131 B S.P.Z. | 247100 | EE-III | 131 | 273/4.1.05/EE-III | M/s Sajid Khan | 20.1.05 | 26.2.05 | 227543 | Completed
31 | Civil | 4.10.04 | 12.6.04 | P/L C.C. in Amar Puri from A-396 to H.No A-400 (Gali ka Sai wali) and in adjoing lanes in W No- 131 A S.P.Z | 246200 | EE-III | 131 | 344/24.10.05/EE-III | M/s Ravi Kumar Malhotra | 28.10.05 | 27.06.06 | 84412 | Completed
32 | Civil | 4.10.04 | 5.7.04 | Imp to foothpath at Gali No-2 Jhandawala Mandir in C-132 "B" S..Z | 196500 | EE-III | 132 | 131/14.6.05/ EE-III | M/s A.K. Const.Co.-II | 05.7.05 | 12.8.05 | 174737 | Completed
33 | Civil | 4.10.04 | 15.7.04 | Imp to footpath near Subash Suchalaya at Ram Kumar Marg in C-132 "B" S.P.Z.(Rs.199250/-) | - | EE-III | 132 | wroks cancelled as desired by area MLA of letter dated 22.08.07 & approved by E-in-C dated 10.08.07
34 | Civil | 4.10.04 | 7.6.04 | Imp to drainge system in Pvt. Katra no T-459 to T-462 (Charan Dhabe wala) in C-131 /B S.P.Z. | 245400 | EE-III | 132 | 378/24.2.05 | M/S Gulati Const CO. | 7.3.05 | 6.2.05 | 231548 | Completed
35 | Civil | 4.10.04 | 7.6.04 | Imp to lane by c.c. pave at LIG flats near A-189 in Motia Khan in c-132 B/ S.P.Z. | 246200 | EE-III | 132 | 122/14.6.05/ EE-III | M/s Guru kirpa Entrp. | 25.6.05 | 18.7.05 | 181729 | Completed
36 | Civil | 4.10.04 | 7.6.04 | Imp to C.C. pav at MIG flats near park from DESU back side in C-132 S.P.Z | 244900 | EE-III | 132 | 33/05.5.05/ EE-III | M/s K.K. Const.Co. | 14.5.05 | 15.7.05 | 180846 | Completed
37 | Civil | 4.10.04 | 7.6.04 | Imp to C.C pav in LIG flats near 228 A at Motia Khan in c-132 B KB Zone. | 244300 | EE-III | 132 | 233/01.8.05/ EE-III | M/s Kapoor Const. | 09.8.05 | 07.10.05 | 177384 | Completed
38 | Civil | 4.10.04 | 7.6.04 | Imp to Side lane by C.C. pav. From Building Matrial shop to Mandir in Motia Khan C-132 B S.P.Z | 244400 | EE-III | 132 | 73/27.5.05/ EE-III | M/s Jai Bhawani Builders | 27.5.05 | 30.8.05 | 236883 | Completed
39 | Civil | 4.10.04 | 7.6.04 | Imp to C.C. flooring from Qilla Kadam Sharif to Chhotrdi Hatte (Sweet Shop ) & adjoing lanes in C-131 B/ S.P.Zone | 244000 | EE-III | 131 | 56/24.5.05 EE-III | M/s Islamudin | 26.5.05 | 8.7.05 | 179177 | Completed
40 | Civil | 4.10.04 | 12.7.04 | Imp to pvt Katra No 9512, 9474, 9475 in Baghichi Raoji in c-131 A S.P.Z | 244700 | EE-III | 132 | 229/14.12.04/EE-III | M/S Gulati Const CO. | 24.12.04 | 18.2.05 | 220809 | Completed
41 | Civil | 6.10.04 | 30.7.04 | P/L Perf. Tiles & imp to drainage system from shop H.No-A30 to 20 IN MIG flats LIG Flats Motia Khan C-132 /S.P.Z. | 245900 | EE-III | 132 | 249/21.12.04/EE-III | M/s Rajesh Const CO. | 6.12.04 | 20.1.05 | 219597 | Completed
42 | Civil | 7.2.05 | 20.6.04 | Imp to A block Double Story qtrs motia khan Q no. 17 to 29 and 37 in C-132 B SPZ | 171710 | EE-III | 132B | 446/29.3.05/ EE-III | M/s K.K. Const.Co. | 20.4.05 | 20.5.05 | 171585 | Completed
43 | Civil | 7.2.05 | 20.6.04 | Imp to Gali NO 11 Motia Khan Pahar ganj C-132 B SPZ | 173580 | EE-III | 132B | 455/30.3.05/ EE-III | M/s K.K. Const.Co. | 28.4.05 | 03.6.05 | 173493 | Completed
44 | Civil | 31.3.05 | 1.7.04 | P/L CC in PVt Katra Amar Puri from H.no. AB-1, H.no. AB 214 and adj lane in C-131 SPZ | 243100 | EE-III | 131 | 30/5.5.05/EE-III | M/s Sajid Khan | 14.5.05 | 29.6.05 | 223757 | Completed
45 | Civil | 31.3.05 | 28.6.04 | Imp to Channel and rd by pdg CC Pav from Dr. Bhatia rd xing to transferrmar at Ram Kuamr Marg C -132B SPZ | 246500 | EE-III | 132B | 141/14.06.05/EE-III | M/s United Const.Co. | 16.06.05 | 16.01.06 | 179116 | Completed
46 | Civil | 31.3.05 | 6.9.04 | P/L CC in Katra no. 7388 and Katra NO 7404 and adj lanes in C-131A SP | 246027 | EE-III | 131A | 01/17.04.06/EE-III | M/s Rajesh Const CO. | 15.04.06 | 16.06.06 | 213796 | Completed
|  |  |  | Total | 8221433 | [6 empty] | 7187625
Ramarks:- No. of works booked=46, No. of works cancelled=10