## 17
MUNICIPAL CORPORATION OF DELHI
Name of MLA :- Sh. Anil Bhardwaj |  |  |  | A.C. No. 17 | Year :- 2004-05
Name of Constituency :- Tri Nagar
S.No | Depptt. | Date of Booking | Date of Consent | Name of Work | Amount | Div. | Ward no. | Work order No. with Date | Name of Agency | A.D.O.S. | A.D.O.C. | Expenditure | Phy Target | Phy. Ach. | Remarks
Total
1 | Elect. | 28.07.04 | 06.07.04 | Provision of Second high mest light in park between B-2 & B-3 Block Keshav Puram, W-No-28, Under RZ | 156820 | EE (E) VII | 28 | 82/25.8.04 | M/s Kamal Electricals | 2.9.04 | 8.9.04 | 148979 |  |  | Comp.
2 | Elect. | 28.07.04 | 06.07.04 | Imp. Of Semi High Mast Lights in C.No. 17, Tri Nagar, under Rohini Zone | 199420 | EE (E) VII | 27, 28 | 84/30.8.04 | M/s ankur Enterprises | 31.8.04 | 14.9.04 | 197530 |  |  | Comp.
3 | Civil | 4.8.04. | 13.5.04. | P/L CC in lane No,. 151 in Ganesh Pura in Tri Nagar, Ronini Zone | 156900 | R-I | 27 | 136/19.10.04 | M/s Tej Pal Singh | 27.10.04 | 11.1.05 | 132599 |  |  | Comp.
4 | Civil | 4.8.04. | 13.5.04. | Pdg/Laying Cement core in lane No 35 in Onkar Nagar in Tri Nagar, C-27, Rohini Zone. | 226500 | R-I | 27 | 169/8.11.04 | M/s Naresh Enterprises | 8.11.04 | 11.1.05 | 201621 |  |  | Comp.
5 | Civil | 4.8.04. | 13.5.04. | P/L CC in lane No. 62 in Lekhu Nagar in Tri Nagar, C-27 Rohini Zone | 100700 | R-I | 27 | 123/15.10.04 | M/s Naresh Enterprises | 18.10.04 | 5.1.05 | 91410 |  |  | Comp.
6 | Civil | 11.1.05 | 4.2.05 | Const of FP and Road berms between A-1 and A-2 Pocket Road of Keshav Puram | 338816 | R-I | 28 | 141/31.05.05 | M/s Vijay Builders | 09.06.05 | 12.09.05 | 337702 |  |  | Comp.
[5 empty] | 1179156 | [6 empty] | 1109841

## 18
MUNICIPAL CORPORATION OF DELHI
[7 empty] | Budget | Allocation | Vide Letter No |  | Dated
Name of MLA :- Sh. Dr. S.C. Vats |  |  |  | A.C. No. 18 | Year :- 2004-05 |  |  | i. 66.63 lacs ii. 33.37 lacs iii. 84.00 lacs iv. 3.27 lacs Total 187.27 | 140 233 330 CE-III/E-258 | Savings pre.yrs | 23.7.04 29.9.04 28.12.04 25.1.05
v. (-) 7.62 Booked for 04-05 in 03-04
Name of Constituency :- Shakurpur | [7 empty] | Net 179.65 lacs
S.No | Depptt. | Date of Booking | Date of Consent | Name of Work | Amount | Div. | Ward no. | Work order No. with Date | Name of Agency | A.D.O.S. | A.D.O.C. | Expenditure | Phy. Tar. | Phy. Ach. | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total |  |  | 17
1 | Civil | 26.7.04 | 24.6.04 | Const. of Walk way in park near H.N. C-139, in Pushpanjali Encl in C-30. | 222000 | Rohini I | 30 | 135/19.10.04 | M/s Pee Kay Const Co, | 19.10.04 | 7.12.04 | 188818 |  |  | Comp.
2 | Civil | 26.7.04 | 24.6.04 | Imp to back lane from H.nO. C1 to Corner of park in Pushpanjali in C-30. | 234800 | Rohini I | 30 | 141/25.10.04 | M/s Nishant Const CO. | 25.10.04 | 17.12.04 | 223568 |  |  | Comp.
3 | Civil | 26.7.04 | 24.6.04 | Imp to road side berms from C -69, to corner of park in Pushpanjali Enclave. | 243300 | Rohini I | 30 | 143/25.10.04 | M/s manoj Kumar Gupta | 25.10.04 | 16.11.04 | 211253 |  |  | Comp.
4 | Civil | 27.7.04 | 01.06.04 | P/F MS sheet board on Central Verge grills on Kabir Dass Marg Shakurpur JJ Colony, C29. | 47306 | Rohini I | 29 | 392/22.9.03 | M/s Shankar Builders | 1.10.03 | 18.10.03 | 46927 |  |  | Comp.
5 | Civil | 27.7.04. | 30.6.04 | Imp to lane by CC flooring from I-516, to I-491 & I-263 to I-288 and near Mandir in I Block Shakurpur in C-30. | 237138 | Rohini I | 29 | 165/8.11.04 | M/s Shankar Builders | 8.11.03 | 31.12.04 | 235580 |  |  | Comp.
6 | Civil | 27.7.04. | 24.6.04 | Imp to rod from Gali No. 4, in H.NO. 175, Shakti Vihar in C 30. | 215000 | Rohini I | 30 | 170/8.11.04 | M/s Ranjeet Mittal | 8.11.04 | 15.2.05 | 214856
7 | Civil | 27.7.04. | 24.6.04 | Const of Umbrella in park opp H.No. B -239, in Saraswati Vihar C-30 Rohini -I | 297899 | Rohini I | 30
8 | Civil | 27.7.04. | 19.4.04 | Covering of SW Drain & Imp to road side berms on Veer Hemu Marg from opp DDA Park to H .No., 58 in Sandesh Vihar in C-29-II | 385199 | Rohini I | 29 | 199/18.11.04 | M/s Rajeev Mittal | 18.11.04 | 10.01.05 | 384970 |  |  | Comp.
9 | Civil | 2.8.04 | 05.7.04 | Imp to park near I-315 Shakurpur J.J. Colony C-29. | 237655 | Rohini I | 29 | 197/18.11.04 | M/s Satyam Const CO. | 27.11.04 | 21.1.05 | 237645 |  |  | Comp.
10 | Civil | 2.8.04 | 22.6.04 | Imp to park & Channel form Guru Hari Kishan Marg to Kabir Dass Marg near L Block Shakurpur C-29. | 96000 | Rohini I | 29 | 140/25.10.04 | M/s Lakra Const CO. | 26.10.04 | 27.12.04 | 87845 |  |  | Comp.
11 | Civil | 2.8.04 | 25.6.04 | Imp/ Const of Boundary Wall of park near L:-86 Shakurpur JJ Colony. | 286633 | Rohini I | 29 | 213./25.11.04 | M/s Lakra Const CO. | 3.12.04 | 28.2.05 | 285540 |  |  | Comp.
12 | Civil | 2.8.04 | 5.4.07 | Imp to road and Channel near G block Community Centre Shakurpur C-29 near G-711, to G-303, C-29. | 172384 | Rohini I | 29 | 152/26.10.04 | M/s Satyam Const CO. | 29.10.04 | 29.12.04 | 172333 |  |  | Comp.
13 | Civil | 04.08.04 | 19.4.04 | Const of boundary wall of park opp H.No. 234, Near Mandir in Kohet Enclave in C-29.-II | 304000 | Rohini I | 29
14 | Civil | 04.08.04 | 19.4.04 | Providing and laying Cement Concerete from H.No. 295 to H.No. 207, in Kohat Enclave.C-29-II | 270313 | Rohini I | 29 | 155/29.10.04 | M/s Sonu Const.Co | 04.11.04 | 31.03.05 | 269714 |  |  | Comp.
15 | Civil | 04.08.04 | 19.4.04 | Covering of S.W. Drain from H.NO. 227 to 331 in Kohat Enclave,C-29 | 398407 | Rohini I | 29 | 183/17.11.04/EE-( R)-I | M/s J.D.Const.Co | 17.12.04 | 25.10.05 | 380928 |  |  | Comp.
16 | Civil | 04.08.04 | 19.4.04 | Imp to drainage & Road from H.No. 285, to 294 in Kohat Enclave.,C-29 | 651800 | Rohini I | 29 | 236/03.12.04 | M/s Sonu Const.Co | 12.12.04 | 31.03.05 | 464765 |  |  | Comp.
17 | Civil | 04.08.04 | 19.4.04 | Construction of passage in park opp H.No. 285, in Kohat Enclave.,C-29 | 95033 | Rohini I | 29 | 94/07.10.04 | M/s J.D.Const.Co | 08.10.04 | P | 77076 |  |  | Inprog.
18 | Civil | 12.8.04 | 05.07.04 | Dev of R/C Shakurpur C-29 SH:- Imp to drainage systgem on Maharishi Balmiki Marg near MC School H block Shakurpur ,C-29 | 205200 | Rohini I | 29 | 176/8.11.04 | M/s Ravinder Const | 9.11.04 | 12.1.05 | 204987 |  |  | Comp.
19 | Civil | 12.8.04 | 05.07.04 | Imp to open surface near G-179 in Shakurpur C-29. | 202800 | Rohini I | 29 | 187/17.11.04 | M/s Raj Const. | 17.11.04 | 20.12.04 | 202715 |  |  | Comp.
20 | Civil | 12.8.04 | 05.07.04 | Imp/Raising of Boundary Wall from J block Urinal to PP Towers on Kabir Dass Marg, Shakurpur.,C-29 | 168650 | Rohini I | 29 | 142/25.10.04 | M/s Raj Const. | 27.10.04 | 31.12.04 | 168583 |  |  | Comp.
21 | Civil | 25.8.04 | 05.7.04 | Covering of Drain from Gate of MC School H Block to Masjid and Up to Park in Shakurpur C-29. | 70190 | Rohini I | 29 | 255/14.12.04 | M/s Gujral Const. | 27.12.04 | P | 50887 |  |  | Inprog.
22 | Civil | 30.9.04 | 24.6.04 | Imp of lane by pdg along H.no. 960, 1205 to 1164, 1952 to 1961 in Rani Bagh in C-30 | 561000 | Rohini I | 30 | 292/3.1.05 | M/s Ranjeet Mittal | 12.1.05 | 7.6.05 | 545285 |  |  | Comp.
23 | Civil | 1.10.04 | 24.6.04 | Imp of lane by pdg CC 1198 to 1158 & 1134, 2154 to 2148 in Rani Bagh BG-214 to 767,772 to 781, 223 to 217 Rishi Nagar.in C-30 | 446000 | Rohini I | 30 | 335/18.01.05 | M/s Sharma & Co. | 27.01.05 | 07.06.05 | 432637 |  |  | Comp.
24 | Civil | 1.10.04 | 24.6.04 | Imp of lane by pdg CC 1844,1842,1847 to 1888 & 1716, 1246 to 1223, 1760 to 1762, 1625 to 1635 in Rani Bagh. | 378536 | Rohini I | 30 | 237/22.07.05 | M/s R.K Const. | 22.07.05 | 31.03.06 | 323788 |  |  | Comp.
25 | Civil | 1.10.04 | 24.6.04 | Imp to lane by pdg CC 2050A to 2051, 1971 to 3059, 1962 to 1967, 1138 to 1153, 1146 to 1149, 1130 to 1128,1138 to 1158 in Rani Bagh | 294741 | Rohini I | 30 | 180/23.06.05 | M/s R.K Const. | 02.07.05 | P | 82006 |  |  | Inprog.
26 | Civil | 1.10.04 | 24.6.04 | Imp to lanes by pdg CC 1805B to 1817, 1878 to 1867, 1907 to 1915 in Rani Bagh | 450000 | Rohini I | 30 | 334/18.01.05 | M/s Sharma & Co. | 27.01.05 | 18.06.05 | 436806 |  |  | Comp.
27 | Civil | 1.10.04 | 24.6.04 | Imp to lane by pdg CC from 1466 to 1479 1486 to 1500, 1601 to 1602 in Rani bagh | 270664 | Rohini I | 30 | 238/22.07.05 | M/s R.K Const. | 06.03.06 | 31.05.06 | 220043 |  |  | Comp.
28 | Civil | 1.10.04 | 24.6.04 | Imp to lan e by pgd CC from 1257 to 1255, 1562 to 1559, 1454 to 1399, 1807 to 1818 in Rani Bagh | 287685 | Rohini I | 30
29 | Civil | 6.12.04 | 24.6.04 | Imp to DS (LHS & RHS) and road fromH.no. 113 to 130 in Shakti Vihar | 984353 | Rohini I | 30 | 168/10.06.05 | M/s Gupta & Co. | 10.06.05 | 08.03.06 | 974353 |  |  | Comp.
30 | Civil | 6.12.04 | 24.6.04 | Imp to Drainage system LHS & RHS and road from H.no. 153 to 175 in Shakti Vihar and 110 to 118 in Anand Vihar. | 1045317 | Rohini I | 30 | 159/10.06.05 | M/s Rakesh Kumar Goel | 27.06.05 | 18.11.05 | 1045272 |  |  | Comp.
31 | Civil | 6.12.04 | 24.6.04 | Imp to Drainage System LHS & RHS and road from H.no. 140 to 151 in Anand Vihar/ | 967878 | Rohini I | 30 | 145/31.05.05 | M/s V.K Gupta | 09.06.05 | 17.11.05 | 967815 |  |  | Comp.
32 | Civil | 6.12.04 | 24.6.04 | Imp to Drainage System LHS & RHS and road from H.no. 152 to 165 in Anand Vihar. | 935497 | Rohini I | 30 | 109/30.05.05 | M/s Mukesh Kumar Bansal | 30.05.05 | 03.11.05 | 935369 |  |  | Comp.
33 | Civil | 6.12.04 | 5.10.04 | P/F Board near I Block, Jeewan Jyoti Apptt. GF & GH block Samrat Cinema near Harsh Vihar & adj Colonies in W.no. 29. | 197000 | Rohini I | 29
34 | Civil | 6.12.04 | 5.10.04 | P/F Board Near F Block Dalao, near PP Jewellers & in park in E block near Britania Chowk Shakar pur. | 187000 | Rohini I | 29
35 | Civil | 6.12.04 | 27.11.04 | Imp of park in C Block (Remaining Portion) Shakarpur JJ Cly | 88750 | Rohini I | 29
36 | Civil | 6.12.04 | 6.10.04 | Const of Culvert on Thiruvalluar Marg along Samrat cinema in E b lock Shakarpur, JJ Cly | 34200 | Rohini I | 29
37 | Elect. | 9.12.04 | 27.9.04 | Prov. Of Semi High Mast Light in Mpl Park Opp. B-59, Pushpanjali Enclave W.no. 30. | 171723 | EEE-VII | 30 | 312/31.3.05 | M/s Paras Const Co. | 8.4.05 | 28.4.05 | 127971
38 | Elect. | 9.12.04 | 27.9.04 | Prov of Semi High Mast light in Mpl park opp H.no. 1224, Rani Bagh, W.no. 30. | 172064 | EEE-VII | 30 | 281/29.3.05 | M/s Paras Const Co. | 6.4.05 | 26.4.05 | 127869
39 | Elect. | 9.12.04 | 27.9.04 | Prov. Of Semi High Mast Light in Pholla Ram Park, Rishi Nagar, opp Jagrati Apptt. W.no. 30. | 177757 | EEE-VII | 30 | 278/29.30.5 | M/s Paras Const Co. | 29.3.05 | 14.06.05 | 136539 |  |  | Inprog,
40 | Elect. | 9.12.04 | 27.9.04 | Prov. Of Semi High Mast Light in Mpl Park Opp H.no. F-13, Shakarpur, JJ Cly. | 172406 | EEE-VII | 29 | 279/29.3.05 | M/s Paras Const Co. | 29.3.05 | 14.06.05 | 127401 |  |  | Inprog,
41 | Elect. | 9.12.04 | 21.9.04 | Prov. Of Semi High Mast Light in Mpl Park behind H. no. 95 Kohet Enclave W.no. 29. | 169651 | EEE-VII | 29 | 285/29.3.05 | M/s Paras Const Co. | 29.3.05 | 25.4.05 | 127693 |  |  | Comp
42 | Elect. | 9.12.04 | 21.9.04 | Prov. Of Semi High Mast Light in Mpl Park opp H.no. 15, Rohit Kunj W.no. 29. | 170158 | EEE-VII | 29 | 314/31.03.05 | M/s Paras Const Co. | 5.4.05 | 25.4.05 | 129647 |  |  | Comp.
43 | Elect. | 9.12.04 | 21.9.04 | Prov. Of Semi High Mast Light in Jhor Wala Park, Part B opp Pitampura Village W.no. 29. | 169905 | EEE-VII | 29 | 276/29..3.05 | M/s Paras Const Co. | 29.3.05 | 6.4.05 | 132612 |  |  | Comp.
44 | Elect. | 9.12.04 | 21.9.04 | Prov. Of Semi High Mast Light in Mpl Park Opp E 283, Shakarpur, JJ Cly. | 170285 | EEE-VII | 29 | 280/29..3.05 | M/s Paras Const Co. | 29.3.05 | 25.4.05 | 127605 |  |  | Comp.
45 | Elect. | 9.12.04 | 17.9.04 | Prov. Of Semi High Mast Light in Mpl Park Opp H.No. E-1043 Part-A Saraswati Vihar W.no. 30. | 170918 | EEE-VII | 30 | 283/39.03.05 | M/s Paras Const Co. | 29.3.05 | 31.3.05 | 130999 |  |  | Comp.
46 | Elect. | 9.12.04 | 17.9.04 | Prov. Of Semi High Mast Light in Mpl Park Opp H.No. E-1043 Part-B Saraswati Vihar W.no. 30. | 171171 | EEE-VII | 30 | 282/29.3.05 | M/s Paras Const Co. | 29.3.05 | 31.3.05 | 130310 |  |  | Comp.
47 | Elect. | 9.12.04 | 17.9.04 | Prov. Of Semi High Mast Light in Mpl Park H.no. B-235 (Part-A) Saraswati Vihar W.no. 30. | 171552 | EEE-VII | 30 | 284/29.3.05 | M/s Paras Const Co. | 29.3.05 | 31.3.05 | 131802 |  |  | Comp.
48 | Elect. | 9.12.04 | 17.9.04 | Prov. Of Semi High Mast Light in Mpl Park H.no. B-235 (Part-B) Saraswati Vihar W.no. 30. | 171210 | EEE-VII | 30 | 277/29.3.05 | M/s Paras Const Co. | 29.3.05 | 31.3.05 | 133676 |  |  | Comp.
49 | Elect. | 9.12.04 | 25.9.04 | Prov. Of Lighting arranagement in Mpl Park, NHP Kapil Vihar Part-A W.no. 30. | 145811 | EEE-VII | 30 | 02/28.04.05 | M/s Shivam Electriclas | 05.05.05 | 20.05.05 | 124334 |  |  | Comp.
50 | Elect. | 9.12.04 | 25.9.04 | Prov. Of Lighting arranagement in Mpl Park, NHP Kapil Vihar Part-B W.no. 30. | 146666 | EEE-VII | 30 | 262/7.3.05 | M/s Ankur Enterprises | 15.3.05 | 31.3.05 | 137092 |  |  | Comp.
51 | Civil | 14.12.04 | 17.10.04 | Imp of Fountain in park in AG & H Block, Shakarpur, JJ Cly. | 74000 | Rohini I | 29
52 | Civil | 21.12.04 | 17.10.04 | Imp to Drain along Houses in K-Block, Shakarpur, JJ Cly | 261000 | Rohini I | 29
53 | Civil | 21.12.04 | 17.10.04 | Imp to Rd & Channel from I-1 to Mother Dairy on Kabir Dass marg, Shakarpur, JJ Cly. | 314600 | Rohini I | 29 | 162/10.06.05 | M/s Roshan Lal Builders IInd | 19.06.05 | 17.09.05 | 173261 |  |  | Comp.
54 | Civil | 21.12.04 | 18.10.04 | C/o Umberella in park near K-385, Shakarpur, JJ Cly. | 172500 | Rohini I | 29 | 16/7.4.05 | M/s Friends Consts and Bldg Materials Suppliers | 16.4.05 | 15.6.05 | 131543 |  |  | Comp.
55 | Civil | 5.1.05 | 6.12.04 | Imp to berms from Opp H.no.1 to 134(DDA Park Side in Lok Vihar, A Block in C-29. | 267053 | Rohini I | 29
56 | Elect. | 9.02.05 | 5.1.05 | Imp of Semi High Mast Light in Mpl Parks at Shakarpur, Rohini Zone | 199886 | EEE-VII | 29 | 26/27.06.05 | M/s Paras Const Co. | 01.07.05 | 29.07.05 | 154560 |  |  | Comp.
57 | Elect. | 9.02.05 | 27.1.05 | Imp of Semi High Mast Light in MPl parks at Saraswati Vihar, Rani Bagh, Engineers Encl. under Rohini Zone | 126099 | EEE-VII | 29 | 30/29.06.05 | M/s Bhanu Enterprises | 04.07.05 | 29.07.05 | 84060 |  |  | Comp.
58 | Civil | 27.02.04 | 23.02.04 | Construction of umbrella in Park opp. B-180 in Saraswati Vihar In C-30 | 299117 | Rohini I | 29 | 1072/31.03.04 | M/s R.K Const. | 09.4.04 | 27.05.05 | 274086 |  |  | Comp.
59 | Civil | 27.02.04 | 23.02.04 | Improvement toraod from H.NO 32 to gali NO.3 of Shakti Vihar & H.NO.174 to Sarv Siddh Shiv Mandir in Shakti Vihar C-30 | 218383 | Rohini I | 29 | 01/17.06.04 | M/s Rajeev Mittal | 26.06.04 | 20.08.04 | 215509 |  |  | Comp.
60 | Civil | 27.02.04 | 24.02.04 | Improvement of B/wall of park in front of H.No. 306 to 310 Tarun Enclave in C-30 | 244000 | Rohini I | 29 | 1086/31.03.04 | M/s Rajeev Mittal | 03.04.04 | 21.06.04 | 238890 |  |  | Comp.
[5 empty] | 16698243 | [6 empty] | 13169823

## 19
MUNICIPAL CORPORATION OF DELHI
Name of MLA :- Sh. Ravinder Nath Bansal |  |  |  | A.C. No. 19 | Year :- 2004-05
Name of Constituency :- Shalimar Bagh
S.No | Department | Date of Booking | Date of Consent | Name of Work | Amount | Div. | Ward no. | Work order No. with Date | Name of Agency | A.D.O.S. | A.D.O.C. | Expenditure | Phy. Tar. | Phy.Ach. | Remarks
1 | Elect. | 28.7.04 | 01.07.04 | Installation of Semi High Mast light opposite Shakti Mandir, Shalimar Bagh under Rohini Zone. | 143112 | EEE-VII | 31 | 80/25.8.04 | M/s Khanna Sales Corpo. | 2.9.04 | 20.9.04 | 138462 |  |  | Comp.
2 | Elect. | 28.7.04 | 01.07.04 | Installation of Semi High Mast Light in JD Block Market, Pitam Pura under Rohini Zone | 174475 | EEE-VII | 32 | 81/25.3.04 | M/s Khanna Sales Corpo. | 3.9.04 | 20.9.04 | 169167 |  |  | Comp.
3 | Civil | 30.7.04 | 30.7.04 | Raising/Stg. Of Boundary Wall from H.No. 1 to 18 in BU Block SFS (Flats) on Outer Ring Road in Putampura. | 242881 | R-I | 32 | 144/25.10.04 | M/s Manoj Kumar Gupta | 26.10.04 | 28.1.05 | 242842 |  |  | Comp.
4 | Civil | 2.8.04 | 15.7.04 | Provision of lighting arragnemetn in Mpl Park in AM block Park, Shalimar Bagh under Rohin Zone | 134069 | EEE-VII | 31 | 108/6.10.04 | M/s Khanna Sales Corpo. | 15.10.04 | 3.11.04 | 129308 |  |  | Comp.
| Civil | 4.8.04 | 4.8.04 | Raising/Stg. Of Boundary Wall from H.No. 33 to 67 in BU Block SFS (Flats) on Outer Ring Road in Putampura. (Booked at S.no. 03-04/at s.no. 121 Page 100 for Rs. 262000) | 16769 | R-I | 32 | 167/08.11.04 | M/s Manoj Kumar Gupta | 10.11.04 | 14.02.05 | 16744 |  |  | Comp.
5 | Civil | 5.8.04 | 30.7.04. | Const of 2 nos of Speed Breakers in Front of Shri Guru Govind Singh College of Commerce in Pitampura C-32. | 104415 | R-I | 32 | 233/20.07.05 | M/s Subhash Singh | 22.07.05 | 26.09.05 | 104336 |  |  | Comp.
6 | Civil | 5.8.04 | 6.7.04 | Improvement of Islands by pdg and Fixing MS Grills at RP Block Pitampura C-32. | 126333 | R-I | 32 | 161/10.06.05 | M/s Mittal Const.Co | 30.06.05 | 12.08.05 | 111665 |  |  | Comp.
7 | Civil | 5.8.04 | 2.7.04 | Imp of Drainge system and lane from H.No. 216 to 224, & 127 to 141A in CD Block, Pitampura., | 244200 | R-I | 32
8 | Civil | 5.8.04 | 2.7.04 | Improvement to Drainage system from LD-74 to LD-16 & LD-81 to LD-122 in LD Block Pitampura, C-32. | 244600 | R-I | 32 | 251/13.12.04 | M/s Friends Cosnt and bldg Mat supplier | 1.2.05 | 21.3.05 | 164114 |  |  | Comp.
9 | Civil | 5.8.04 | 2.7.04 | Imp. Of side berms from R.P.chowk to Mother Dairy Booth in RP Block, Pitam pura, C-32. | 173402 | R-I | 32 | 17/7.4.05 | M/s Friends Cosnt and bldg Mat supplier | 23.4.05 | 29.6.05 | 173377 |  |  | Comp.
10 | Civil | 9.9.04 | 12.5.04 | Const of Shelter in parks near H.no. HP 46 & G & JU Block Pitampura. | 166096 | R-I | 32 | 21/08.04.05 | M/s Naresh Enterprises | 12.04.05 | 15.07.05 | 165573 |  |  | Comp.
11 | Civil | 9.9.04 | 6.7.04 | Const of Two Nos Shelters in BD -FD park Pitampura | 230000 | R-I | 32 | 448/17.3.05 | M/s Manoj Kumar Gupta | 21.3.05 | 31.08.05 | 156976 |  |  | Comp.
12 | Hort. | 20.9.04 | 9.8.04 | Redevelopment of park in BU Block Pitampura Rohini Zone | 115819 | ADH ( R) | 32 | 11/10.1.05 | M/s Shree Om Traders | 10.1.05 | 28.3.05 | 106326 |  |  | Comp.
13 | Hort. | 29.9.04 | 11.9.04 | Prov. Of Semi High Mast Light in Mpl Park in NP Block Pitampura under Rohini Zone | 163004 | EEE-VII | 31 | 210/8.2.05 | M/s MJ Electricals & Electronic | 16.2.05 | 2.3.05 | 135187 |  |  | Comp.
14 | Elect. | 29.9.04 | 17.9.04 | Prov. Of Semi High Mast Light in Mpl BW Block park, Shalimar Bagh under Rohini Zone | 164140 | EEE-VII | 31 | 209/8.2.05 | M/s MJ Electricals & Electronic | 15.2.05 | 2.3.05 | 139533 |  |  | Comp.
15 | Elect. | 29.9.04 | 16.9.04 | Prov. Of Semi High Mast Lights in Mpl poark in AD/BD block near Community Hall, Pitampura under Rohini Zone | 165407 | EEE-VII | 32 | 211/8.2.05 | M/s MJ Electricals & Electronic | 16.2.05 | 2.3.05 | 143756 |  |  | Comp.
16 | Elect. | 29.9.04 | 16.9.04 | Prov of Semi High Mast Light in Mpl Park, AL Mkt Shalimar Bagh under Ronini Zone | 164078 | EEE-VII | 31 | 240/21.2.05 | M/s Sain & Sons | 1.3.05 | 21.3.05 | 128395 |  |  | Comp.
17 | Hort. | 4.10.04 | 10.8.04 | Dev. Of park in KD Block, Pitampura W>no. 32. | 98752 | ADH ( R) | 32 | 47/9.3.05 | M/s ARCHNA Enterprises | 9.3.05 | P | 78125 |  |  | Inprog.
18 | Hort. | 4.10.04 | 10.8.04 | Dev of park in LD & BD Block, Pitampura W.no. 32 near H.n. LD-19A and 41 and SD-65. | 95104 | ADH ( R) | 32
19 | Hort. | 4.10.04 | 10.8.04 | Installation of Tube Well in AC block park, Shalimar Bagh (Submersible Pump Set) | 79053 | ADH ( R) | 31 | 40/9.3.05 | M/s ARCHNA Enterprises | 9.3.05 | 24.3.05 | 59273 |  |  | Comp.
20 | Hort. | 4.10.04 | 10.8.04 | Dev of park in SD Block, Pitampura Rd W.no. 32 near H.no. SD-410 & 30-417, Pitampura. | 61789 | ADH ( R) | 32
21 | Hort. | 4.10.04 | 10.8.04 | Installation of Motor Pump in MD Block Pitampura, W.no. RC-22. | 74449 | ADH ( R) |  | 25/24.2.05 | M/s ARCHNA Enterprises | 24.2.05 | 24.3.05 | 70796 |  |  | Comp.
22 | Hort. | 4.10.04 | 10.8.04 | Installation of Tube Well in MD Block Pitampura, W.no. RC-22. | 84817 | ADH ( R) | 32 | 24/24.2.05 | M/s ARCHNA Enterprises | 24.2.05 | 24.03.05 | 82435 |  |  | Comp.
23 | Hort. | 4.10.04 | 10.8.04 | Boring of Tube Well in A C block park, Shalimar Bagh . | 84908 | ADH ( R) | 32 | 23/24.2.05 | M/s ARCHNA Enterprises | 24.2.05 | 24.3.05 | 60615 |  |  | Comp.
24 | Hort. | 4.10.04 | 10.8.04 | Dev of park in SD Block, Pitampura W.no. 32 near H.no. SD-117 and 196, Pitampura. | 97264 | ADH ( R) | 323
25 | Hort. | 4.10.04 | 10.8.04 | Dev. Of Park by pdg of Plants in KD & MD Block, Pitampura W.no. 32. | 79797
26 | Elect. | 14.10.04 | 6.10.04 | Prov. Of Semi High Mast Light in MPL park opp AC-175/B Delhi State Disp. In AC Block. | 169651 | EEE-VII | 32 | 216/8.2.05 | M/s Master Electric Store | 15.2.05 | 7.3.05 | 135426 |  |  | Comp.
27 | Civil | 1.11.04 | 12.9.04 | Const of Walkway in the park opp H.n o. 1A to 11A in NP Block in Pitampura | 214160 | R-I | 32 | 204/01.07.05 | M/s Rana Const.Co | 04.07.05 | 24.09.05 | 214151 |  |  | Comp.
28 | Civil | 1.11.04 | 14.9.04 | Imp to Drainage sytem from 19A to 15A to 20A in U&V block, Shalimar Bagh | 179600 | R-I | 32 | 376/22.2.05 | M/s Lord Krishna & Krishna Associates | 23.2.05 | 28.2.05 | 179463 |  |  | Comp.
29 | Civil | 1.11.04 | 14.9.04 | Imp of Drainage System opp H.no. HU-78 along Sarvodya Vidhalaya F-1 U block upto Ramlila Road xing in Pitampura. | 184155 | R-I | 32 | 13/07.04.05 | M/s Friends Cosnt and bldg Mat supplier | 21.04.05 | 18.08.05 | 172081 |  |  | Comp.
30 | Civil | 1.11.04 | 14.9.04 | Imp to road berm infront of NP block park near H.no. 160A in Pitampura | 128800 | R-I | 32 | 410/4.3.05 | M/s jasvinder gulati | 10.03.05 | 15.6.05 | 77084 |  |  | Comp.
31 | Civil | 1.11.04 | 14.9.04 | Const of Walkway in the park opposite H.n. 66A in NP Block park, Pitampura. | 218100 | R-I | 32 | 422/7.3.05 | M/s Chauhan Const CO. | 9.3.05 | 16.5.05 | 177502 |  |  | Comp.
32 | Civil | 3.11.04 | 28.8.04 | Imp and Stg of Road in i) RU Block from Ring Road to 448,448 to 434,415 to 43.0, park to 250, 145 to 154, 49 to 58 169 to 1 to 301 to 286 in Pitampura. | 1597757 | R-I | 32 | 449/24.11.05/ | M/s Competent Const.CO | 02.12.05 | 15.02.06 | 1596844 |  |  | Comp.
ii) VP block from 288 to 48A and 46A to 286A and in SD block from 153 to 114, 498 to 425 in Pitampura.
iii) QU block LIG from 127 to 134, 59 to 62 10A to NDPL office, 187 to 190, 143 to 152, 49 to 52 89 to park, 104 to 101, 231 to 234 in Pitampura.
iv) ED block from 72A to 67A , 78A to 13A, 66A to 61A. 34A to 7A, 42A to 37A, 60 to 55A in Pitampura
33 | Civil | 3.11.04 | 1.9.04 | Imp and Stg of Roads in i) JD Block from 32A to 11A, 2A to 67A, 10A to 3A,66A, 65A, 62A to 55A. 22A to 21A, 25A to 41A and near Parking in Pitampura. | 2956100 | R-I | 32 | 539/09.01.06/EE( R)-I | M/s Dhingra Const.Co | 12.05.06 | P | 3142986 |  |  | In Prog.
ii) LD Block from 130 to 201 road no 41 to MD block gate No. 2 and from Road no. 41 to DAV school in Pitampura,.
iii) NU block from 37A to 64A, 52A to 51A, MU71 to 89A, 88A to 77A, 104A to NDPL office, 89A to 1A and 25A to 36A in Pitam pura.
iv) GD block from 209 to 143, 205 to 188, 68 to 75, 50 to 14 in Pitampura,
v) PU Block from 12 to 24, 54 to 40, 85 to 71 and MIG From Main Gate to 305A 297A to 280A to 288A 312a to Gate No. 3 and CD Block from 13 to 25 and 97A to 110A in Pitampura.
vi) AD block from 136A to 113A, 119A to 18A , 30A to 29A, 62A to 61A, 101A to 110A, 106A to 103A, 130A to 7A, 82A to 79A, 94A to 91A, 55A to 56A in Pitampura in C-32.
34 | Elect. | 27.01.05 | 4.9.04 | Dev. Of park in AM block Shalimar Bagh w.no. 31. | 75810 | ADH ( R) | 31 | 51/15.3.05 | M/s R S Enterprises | 15.3.05 | P | 62877 |  |  | Inprog.
35 | Civil | 23.3.05 | 25.10.04 | \Imp of lane by pdg interlocking tiles from 270/A to 259/A in QU block LIG Pitam pura | 147596 | R-I | 32 | 297/04.08.05 | M/s Rakesh Kumar Goel | 25.08.05 | 27.09.05 | 147456 |  |  | Comp.
36 | Elect. | 31.3.05 | 24.12.04 | Prov of semi high mast light in the park situated in AP block Shalimar Bagh under RZ | 167498 | EEE-VII | 31 | 16/15.6.05 | M/s Kawatra Electric Works | 21.6.05 | 30.6.05 | 161657 |  |  | Comp.
37 | Elect. | 31.03.5 | 9.11.04 | Prov. Of Semi High Mast light in park opposite to Khilora Devi Dharamshala in RP block Pitampura | 168219 | EEE-VII | 32 | 18/15.6.05 | M/s Kawatra Electric Works | 22.6.05 | 1.7.05 | 163253 |  |  | Comp.
38 | Elect. | 31.03.05 | 6.12.04 | \Provb. Of semi high mast light in mpl park in the back side of Market of BH 87 and side of BH 87 Shalimar bagh under RZ | 167586 | EEE-VII | 31 | 17/15.6.05 | M/s Kawatra Electric Works | 21.6.05 | 30.6.05 | 164277 |  |  | Comp.
39 | Elect. | 31.03.05 | 9.11.04 | Prov. Of semi high mast light in main park in PP block Pitampura | 166644 | EEE-VII | 32 | 49/04.08.05 | M/s Pars Const.Co | 10.08.05 | 31.08.05 | 160194 |  |  | Comp.
40 | Elect. | 31.03.05 | 20.8.04 | Prov. Of Semi High Mast light in opposite Gyan Shakti Mandir in park at CB block Shalimar Bagh | 155088 | EEE-VII | 31 | 53/12.08.05 | M/s Kawatra Electric Works | 18.08.05 | 02.09.05 | 150383 |  |  | Comp.
[5 empty] | 10225497 | [6 empty] | 9282639

## 20
MUNICIPAL CORPORATION OF DELHI
Name of MLA :- Sh. Jai Bhagwan Aggarwal |  |  |  | A.C. No. 20 | Year :- 2004-05
Name of Constituency :- Badli
S.No | Department | Date of Booking | Date of Consent | Name of Work | Amount | Div. | Ward no. | Work order No. with Date | Name of Agency | A.D.O.S. | A.D.O.C. | Expenditure | Remarks
1 | Civil | 22.7.04 | 17.6.04 | Const of lane in Shivaji Colony Village Badli by pdg CC Pavement and OS Drain from House of Sh. Suraj Bhan to Bansi and Gian Chand to Bhulla and lane near Nathu Ram and Raj Kisore Houe in C-34. | 409996 | R-II | 34 | 255/29.11.04 | M/s Subhash Gupta | 29.11.04 | 1.2.05 | 409986 | Comp.
2 | Civil | 22.7.04 | 17.6.05 | Const of lane by pdg CC Pavement & OS Drain from Bhagmal House to Maichand House and Mohan Lal House to Laxman Singh House in Village Badli in C-34. | 191050 | R-II | 34 | 231/8.11.04 | M/s Dua Brothers | 8.11.04 | 30.12.04 | 187811 | Comp.
3 | Civil | 22.7.04 | 17.6.06 | Const of Lane by pdg CC Pavement & OS Drain from Shiv Pujan Shop to Nahar Singh House in Village Badli in C-34. | 182215 | R-II | 34 | 169/11.10.04 | M./s SS Builders | 20.10.04 | 19.1.05 | 182189 | Comp.
4 | Civil | 22.7.04 | 17.6.07 | Imp to Drainage system from Balmiki Mandir to Tikona Park in C-34 in Village Badli. | 250264 | R-II | 34 | 260/8.12.04 | M/s Subhash Gupta | 8.12.04 | 1.2.05 | 250256 | Comp.
5 | Civil | 22.7.04 | 17.6.08 | Imp to Chowk near Shivaji Colony Badli Village by CC and Const of Culvert in C-34. | 108050 | R-II | 34 | 276/14.12.04 | M/s Goel Const.Co | 14.12.04 | 15.02.05 | 105755 | Comp.
6 | Civil | 22.7.04 | 17.6.09 | Imp to lanes in village Badli by pdg CC Pavement and OS Drain from Budh Ram House to Ajit Yadav House, Parkash Rathore to Channa Hosue, Budh Ram House to Verma Tailor and Manoj Yadav Wali Lane in C-34-I. | 224100 | R-II | 34
7 | Civil | 22.7.04 | 5.7.04 | Imp of Ahatas by CC interlocking tiles near H.NO.275 to 285 and 197 to 205 in Pkt G-23 Sect-7 C-33 Rohini-II | 175900 | R-II | 33 | 199/29.10.04 | M/s Konark Const Co. | 16.12.04 | 7.1.05 | 175824 | Comp
8 | Civil | 22.7.04 | 5.7.04 | Imp of Ahatas in Pkt D-12 near H.No. 37, to 48 & 142 to 150 in Sec-7 C-33 Rohini -II | 126900 | R-II | 33 | 198/29.10.04 | M/s Konark Const Co. | 4.1.05 | 03.02.05 | 126883 | Comp.
9 | Civil | 2.8.04 | 5.7.04 | Imp of Ahatas in Pkt D-14 near H.No. 178, to 186 & 85 to 96 in Sec-7 C-33 Rohini -II | 149038 | R-II | 33 | 206/29.10.04 | M/s Patel Const. | 11.11.04 | 30.12.04 | 148983 | Comp.
10 | Civil | 2.8.04 | 5.7.04 | Imp of park in Pkt B-3 near H. NO 102 Sect-11 Rohini C-33. | 165900 | R-II | 33 | 205/29.10.04 | M/s Gulshan Const Co. | 8.11.04 | 18.1.05 | 165633 | Comp.
11 | Civil | 2.8.04 | 5.7.04 | Imp ot two Parks in Pkt H-1near H.No. 209 to 140 in Sec-II Rohini | 177700 | R-II | 33 | 200/29.10.04 | M/s Konark Const Co. | 10.11.04 | 7.1.05 | 177601 | Comp.
12 | Civil | 2.8.04 | 5.7.04 | Imp to two parks in Pkt D-2 near H.N O. 148 & 202 in Sec-2 Rohini | 175384 | R-II | 33 | 202/29.10.04 | M/s Gulshan Const Co. | 16.11.04 | 28.12.04 | 175245 | Comp.
13 | Civil | 2.8.04 | 5.7.04 | Imp of park near H.N. 515 & 484 in Pkt C-8 in Sect-8 Rohini | 173457 | R-II | 33 | 201/29.10.04 | M/s Gulshan Const Co. | 30.11.04 | 12.12.04 | 173369 | Comp.
14 | Civil | 2.8.04 | 5.7.04 | Imp of two parks in Pkt H-1 near H.N. 16 & 77 in Sect-11 Rohini. | 171700 | R-II | 33 | 203/29.10.04 | M/s Gulshan Const Co. | 6.11.04 | 22.3.05 | 170919 | Comp.
15 |  | 2.8.04 | 5.7.04 | Cancelled
16 | Civil | 2.8.04 | 5.7.04 | Const of SW Drai opposite H.No. 1 Pkt B-2 ini Sector-17 Rohini. | 179371 | R-II | 33 | 229/05.11.04 | M/s Prakash Khanna | 20.11.04 | 22.01.05 | 179330 | Comp.
17 | Civil | 2.8.04 | 5.7.04 | Imp the drainage system of F blcok by constructing the drain from F 18/1 to F 18/26 in sec-15 Rohini. | 547167 | R-II | 34 | 338/17.01.05 | M/s Subhash Chander Gupta and Co | 17.01.05 | 24.05.05 | 547167 | Comp.
18 | Civil | 2.8.04 | 5.7.04 | Imp of park in Pkt-I-4, near H.NO. 152, in Sector-16 Rohini in C-33. | 195695 | R-II | 33 | 242/19.11.04 | M/s Konark Const Co. | 15.1.05 | 8.02.05 | 195446 | Comp.
19 | Civil | 2.8.04 | 5.7.04 | Imp of park in Pkt-C-9 near H.NO. 24 in Sect-5 Rohini. | 200730 | R-II | 33 | 243/19.11.04 | M./s Chhabra Constr CO,. | 15.1.05 | 16.2.05 | 200012 | Comp.
20 | Civil | 4.10.04 | 5.7.04 | Imp of park in Pkt-F-I near H.no. 126 in Sec-11 Rohini C-33 | 177343 | R-II | 33 | 241/19.11.04 | M./s Chhabra Constr CO,. | 15.1.05 | 18.2.05 | 177297 | Comp.
21 | Civil | 4.10.04 | 5.7.04 | Imp to park in Pkt B-2 in Sec-II near H.no. 31, Rohini. | 176081 | R-II | 33 | 240/19.11.04 | M./s Chhabra Constr CO,. | 15.1.05 | 16.2.05 | 174998 | Comp.
22 | Civil | 4.10.04 | 5.7.04 | Imp to Two Parks near H.no. 307 & 593 in Pkt-C-8 Sect-8 Rohini. | 173289 | R-II | 33 | 235/9.11.04 | M/s Shiv Shakti Const -I | 20.11.04 | 5.2.05 | 172280 | Comp.
23 | Civil | 4.10.04 | 5.7.04 | Imp of Ahatas in Pkt D-16 near H.no. 457 to 464 to 8,203 to 210 & 244 to 455 in Sect-7 Rohini. | 136400 | R-II | 33 | 236/9.11.04 | M/s JB Enterprises | 20.11.04 | 2.2.05 | 135147 | Comp.
24 | Civil | 4.10.04 | 26.4.04 | Imp the side berms of road Prov,. Perforted tyupe interlocking tilesx from G-18/A to G1B/24 in G block Sect-15 Rohini. | 329258 | R-II | 34 | 339/17.1.05 | M/s Subhash Chander Gupta and Co | 17.1.05 | 20.5.05 | 329255
25 | Civil | 13.10.04 | 5.7.04 | Imp of park in Pkt F-3 near H.no. 61 in Sec-11, Rohini. | 170038 | R-II | 33 | 213/4.11.04 | M/s JMD Const CO. | 22.11.04 | 7..1.05 | 169642 | Comp.
26 | Civil | 14.10.04 | 12.10.04 | Imp of park by C/0 B/wall with MS Grill and grit wash near H.no. F8/48 in Sect-15. | 196600 | R-II | 34 | 343/17.01.05/EE-(R )-II | M/s Parkash Const.Co | 17.01.05 | P | 87997 | In Prog.
27 |  |  |  | Cancelled |  |  |  | Work cancelled as desired by area MLA vide his letter dated 27/11/06 and approved by SE(Rohini Zone) on dated 29/11/06
28 | Civil | 14.10.04 | 12.10.04 | Pdg MP in road from G1/28 to G-1/60 in G block Sector-15, Rohini. | 153725 | R-II | 34 | 365/31.01.05 | M/s DeePee Enterprises | 31.01.05 | 29.09.05 | 153680 | Comp.
29 | Civil | 14.10.04 | 12.10.04 | Pdg MP on road from H.no. C10/46 to Jain Hosp./ in Sect-15, Rohini. | 151457 | R-II | 34 | 366/31.01.05 | M/s Mayank Const.Co | 31.01.05 | 04.40.05 | 151455 | Comp.
30 | Civil | 14.10.04 | 12.10.04 | Pdg & Laying perforated type interlocking tile and Drainage system from H.no. C10/46 to Jain Hosp in Sect-15. | 329193 | R-II | 34 | 26/15.04.05 | M/s Manoj Kumar Const.Co | 15.04.05 | P | 137625 | In Prog.
31 | Civil | 14.10.04 | 12.10.04 | Imp of park by C/o B/wall with MS grilll and Grit Wash near H.no. D-8/9 and D9/19 in Sect-15 Rohini. | 196500 | R-II | 34 | 342/17.01.05/EE(R )-II | M/s Parkash Const.Co | 17.01.05 | P | 113535 | In Prog.
32 | Civil | 14.10.04 | 12.10.04 | Imp of park by C/o B/wall with MS grilll and Grit Wash near H.no. E-2/4 in Sect-15 Rohini. | 187300 | R-II | 34 | 381/11.02.05/EE(R )-II | M/s Parkash Const.Co | 11.02.05 | P | 113625 | In Prog.
33 | Civil | 14.10.04 | 12.10.04 | Imp of park by C/o B/wall with MS grilll and Grit Wash near H.no. E-13/1 in Sect-15 Rohini. | 187300 | R-II | 34 | 344/17.01.05/EE(R )-II | M/s Parkash Const.Co | 26.01.05 | P | 102951 | In Prog.
34 | Civil | 14.10.04 | 8.4.04 | P/f SFRC slabs on drain infront of Laxmi Kunj Apptt in Sect-13, Rohini. | 199600 | R-II | 33 | 299/29.12.04/EE(R )-II | M/s Gian Const.Co | 30.12.04 | P | 106073 | In Prog.
35 | Civil | 14.10.04 | 8.9.04 | Im of park near H.no. 296 in Block C in Prashant Vihar in Rohini. | 198300 | R-II | 33 | 307/05.01.05/EE(R )-II | M/s Gian Const.Co | 16.01.05 | P | 99699 | In Prog.
36 | Civil | 14.10.04 | 5.7.04 | Imp of park in Pkt F2 near H.no. 150& 25 in Sect-7, Rohini | 196600 | R-II | 33 | 306/02.01.05/EE(R )-II | M/s Gian Const.Co | 15.01.05 | P | 103902 | In Prog.
37 | Civil | 25.11.04 | 11.8.04 | Imp of Ahatas in Pkt A-3 near H.no. 160 in Sec-11, Rohini. | 178974 | R-II | 33 | 279/17.12.04 | M/s Pushpa Builders | 31.12.04 | 2.2.05 | 178260 | Comp.
38 | Civil | 7.1.05 | 9.10.04 | Imp of lanes by CC pav in Pkt C-8 in Sect-5 Rohini. | 200316 | R-II | 33 | 451/18.3.05 | M/s Kumar N & Co. | 1.4.05 | 9.6.05 | 198947 | Comp.
39 | Civil | 7.1.05 | 9.10.04 | Imp of park in Pkt-5 near H.no. 81 in Sect-5, Rohini. | 188201 | R-II | 33 | 433/14.3.05 | M/s Kumar N & Co. | 30.3.05 | 9.6.05 | 186299 | Comp.
40 | Civil | 7.1.05 | 27.12.04 | Imp of Drainage system with side berms from H.no. D-266 to D-281 in Prashant Vihar in Rohini | 116956 | R-II | 33 | 182/08.08.05 | M/s Tokas & Co. | 26.08.05 | 12.11.05 | 116158 | Comp.
41 | Civil | 7.1.05 | 27.12.04 | Imp of Ahatas in Pkt-B-6 near H.n. 195, 178 & 169 in Sect-5, Rohini. | 199000 | R-II | 33 | 42/26.4.05 | M/s Friends Const & Bldg Material suppliers | 24.5.05 | 27.6.05 | 110340 | Comp.
42 | Civil | 7.1.05 | 27.12.04 | Raising of lane by pdg CC pav in block A-1 near H.no. 146 in Sect-17, Rohini. | 198500 | R-II | 33
43 | Civil | 7.1.05 | 27.12.04 | P/F SFRC slabs on existing Drain in different Pkt of Block A & B in Sect-16, Rohini. | 116074 | R-II | 33 | 181/08.08.05 | M/s Tokas & Co. | 21.08.05 | 04.09.05 | 114979 | Comp.
44 | Civil | 7.1.05 | 27.12.04 | Imp of Walkway in park infront of H.no. E-25 in Prashant Vihar | 144574 | R-II | 33 | 68/12.05.05 | M/s Shiv Shanker Gupta | 24.05.05 | P | 143468 | In Prog.
45 | Civil | 7.1.05 | 5.7.04 | Imp of park near H.no. 55 Pkt A-1 near H.no. 46 Pk-B7 and H.no. 49 Pkt B-10 in Sect-18, Rohini | 387300 | R-II | 33 | 5/5.4.05 | M/s AD cosnt CO. | 27.5.05 | 04.07.05 | 386658 | In Prog.
46 | Civil | 15.3.05 | 8.9.04 | Imp of park in pkt B9 near H.no. 246,150 & 173 in Sec-5 Rohini Rs.195000/- |  | R-II | 33 |  | Work cancelled as desired by area MLA vide his letter dated 20.12.07 and approved by SE(Rohini Zone) on dated 20.12.07
47 | Civil | 15.3.05 | 8.9.04 | Regarding of drain in Pkt D-10 in sect-7 Rohini | 196500 | R-II | 33 | 139/05.07.05/EE( R)-II | M/s DeePee Enterprises | 18.07.05 | 26.10.05 | 137416 | Comp.
48 | Civil | 15.3.05 | 8.9.04 | Imp of park near H.no. 29 in Pkt A-6 near H.no. 40 in Pkt A-5 & near H.no. 80 I Pkt A-4 in Sec-16 Rohini | 295270 | R-II | 33
49 | Civil | 15.3.05 | 8.9.04 | Imp of lane by CC slabs in Pkt C-1 & C-4 in Sec-5 Rohini | 417065 | R-II | 33 | 100/20.06.05 | M/s Ajay Enterprises | 01.07.05 | 06.11.05 | 416238 | Comp.
50 | Civil | 15.3.05 | 27.12.04 | Imp of Ahatas by pdg parks Pkt B-6 near H.no. 1 to 12 & 37 & 48 in sect-5 Rohni Zone | 342300 | R-II | 33 | 107/22.06.05 | M/s Patel Const. | 08.07.05 | 20.09.05 | 184791 | Comp.
51 | Civil | 15.3.05 | 27.12.04 | Imp of Ahatas by pdg CC int & 165 in Sect-65 in Rohini Zone | 197800 | R-II | 33 | 154/15.07.05/EE(R )-II | M/s A.K Const.Co | 25.07.05 | P | 91443 | In Prog.
52 | Civil | 15.3.05 | 27.12.04 | Imp of Ahatas in by pdg CC inito Pav to 228,237,254 & 147 to 153 in Sect-5 Rohini zone | 215678 | R-II | 33 | 140/05.07.05 | M/s DeePee Enterprises | 20.07.05 | 30.10.05 | 214938 | Comp.
53 | Civil | 15.3.05 | 27.12.04 | Imp[ of Ahatas by pdg CC inter Pav Pkt A-1 near H.no. 415,430 & 278 insect 6 Rohini | 123124 | R-II | 33
54 | Civil | 15.3.05 | 27.12.04 | Imp of Ahastas by pdg Interlocking Pav in Pkt B4 near h.no. 148 to 158 & 235 to 245 in Sect 7 Rohni Zone (Rs. 133932.00) |  | R-II | 33 |  | Work cancelled as desired by area MLA vide his letter no. 08/35 dated 24/01/08 and approved by CE-I(Rohini Zone) on dated 25.01.08
55 | Civil | 15.3.05 | 27.12.04 | Imp of Ahastas by pdg CC interlocking tiles in Pkt B-6 near H.no. 223 to 230 & in pkt G-21 near H.no. 9 to 23 in Sec-7 Rohini.(Rs.116497.00) |  | R-II | 33 |  | Work cancelled as desired by area MLA vide his letter no. 08/35 dated 24/01/08 and approved by CE-I(Rohini Zone) on dated 25.01.08
56 | Civil | 15.3.05 | 27.12.04 | Imp of Ahastas by pdg CC interlocking tiles in Pkt D-11 near h.no. 37 to 54 & 54 to 60 in Sec-7 Rohini zone (Rs.234400.00) |  | R-II | 33 |  | Work cancelled as desired by area MLA vide his letter no. 08/35 dated 24/01/08 and approved by CE-I(Rohini Zone) on dated 25.01.08
57 | Civil | 15.3.05 | 27.12.04 | Const of B/wall of one side of park opp Pkt A-2 in Sec-8 Rohini | 235900 | R-II | 33 | 119/29.06.05 | M/s Ajay Enterprises | 12.07.05 | 03.10.05 | 174566 | Comp.
58 | Civil | 15.3.05 | 27.12.04 | Imp of Ahatas by pdg CC interlocking Pav A2 near H.no. 31 to 40, 82 to 71 & 179 to 187 in Sec-8 Rohini | 135243 | R-II | 33 | 156/15.07.05/EE(R )-II | M/s A.K Const.Co | 25.07.05 | 20.01.06 | 135215 | Comp.
59 | Civil | 15.3.05 | 27.12.04 | Imp of park opp H.no. A1/80, F9/58 & F-9/80 & berms near CSC Mkt in Sec 8 Rohini Zone | 308837 | R-II | 33 | 101/20.06.05 | M/s Mange Ram Gupta | 01.07.05 | 14.09.05 | 304276 | Comp.
60 | Civil | 15.3.05 | 27.12.04 | Const of Drain and raising of road by pdg RMC in pkt D-11 from h.no. 101 to 140 in Sec-8 Rohini zone | 644900 | R-II | 33 | 108/22.06.05 | M/s Patel Const. | 29.08.05 | P | 425290 | In Prog.
61 | Civil | 15.3.05 | 27.12.04 | Imp of Ahatas by pdg CC interlocking Pav Pkt -D14 near H,no. 187 to 145, 169 to 177, 115 to 123 & 85 to 96 in Sec-8 Rohini | 159879 | R-II | 33 | 113/24.06.05 | M/s Ajay Enterprises | 01.07.05 | 05.08.05 | 159319 | Comp.
62 | Civil | 15.3.05 | 27.12.04 | Const of lane by pdg CC inelocking pav in sec-14 in Rohini Zone | 214437 | R-II | 33 | 116/28.06.05/EE( R)-II | M/s Tokas & Co. | 08.07.05 | P | 109171 | In Prog.
63 | Civil | 15.3.05 | 27.12.04 | Imp of berms by pdg CC interlocking pav near H.no. D 125 D6 to to D56 and near park in prashant vihar (Rs.187400/-) | - | R-II | 33 |  | Work cancelled as desired by area MLA vide his letter dated 11.02.08 and approved by EE-M-IV/(Rohini Zone) on dated 14.02.08
64 | Civil | 15.3.05 | 27.12.04 | Imp of berms by pdg CC interlocking pav opp. Hr Sec. school B/wall & H.no. E-99 to F-100 & near Pak in Prashant Vihar (Rs.180000/-) | - | R-II | 33 |  | Work cancelled as desired by area MLA vide his letter dated 11.02.08 and approved by EE-M-IV/(Rohini Zone) on dated 14.02.08
65 | Civil | 15.3.05 | 27.12.04 | Imp of road by pdg Matellinh Primixing from H.no. J -64 to J-39 in Sec-16 Rohini | 212478 | R-II | 33 | 110/22.06.05 | M/s Patel Const. | 14.09.05 | 03.012.05 | 212421 | Comp.
66 | Civil | 15.3.05 | 27.12.04 | P/F SFRC slab on existing drain in different Pkt of block D sector 7 & Block B sect-6 Rohini (Rs.198600/-) | - | R-II | 33 |  | Work cancelled as desired by area MLA vide his letter dated 11.02.08 and approved by SE/(Rohini Zone) on dated 14.02.08
67 | Civil | 15.3.05 | 27.12.04 | Const of two umbrella in park near Navyug Apptt in Sec-9 C-33 Rohini zone | 356385 | R-II | 33 | 109/22.06.05 | M/s Patel Const. | 22.08.05 | 19.09.05 | 356337 | Comp.
68 | Civil | 16.3.05 | 2.8.04 | Imp of park by B/W & Grit wash in LIG Pkt op H.no. A1/178 & A1/184 in Sec-16 Rohini | 391500 | R-II | 33 | 233/29.08.05 | M/s Hindustan Const.Co | 29.08.05 | P | 242586 | In Prog.
69 | Civil | 16.3.05 | 5.7.04 | Imp of Ahats by interlocking tiles near H.no. 99 to 113, 114 to 120 in D-7 Sec-6 Rohini | 194100 | R-II | 33 | 155/15.07.05 | M/s A.K Const.Co | 22.08.05 | P | 72356 | In Prog.
70 | Civil | 16.3.05 | 5.7.04 | Imp of Ahatas by interlocking tiles near H.no. 130 to 144, 145 to 150 in D-7 Scc-6 Rohini zone 196300/- |  | R-II | 33 |  | Work cancelled as desired by area MLA vide his letter dated 20.12.07 and approved by SE(Rohini Zone) on dated 20.12.07
71 | Civil | 23.3.05 | 11.10.04 | Imp of berms by i/locking tiles CC near H.no. C87, C210 C209 C-162 & near Park Prashant Vihar | 187400 | R-II | 33
72 | Civil | 30.3.05 | 13.9.04 | Cosnt of additional room in existing Chopal of Naharpur village in W.no. 33. | 274360 | Br-IV | 33 | 15/12.8.04 | M/s Kumar N & Co. | 14.9.04 | 18.11.04 | 274360
73 | Civil | 30.3.05 | 13.9.04 | Imp of Compound of Nahar pur Chopal in W.no. C-33 Rohini Zone | 127890 | Br-IV | 33 | 118/26.9.03 | M/s Kumar N & Co. | 26.9.03 | 24.12.03 | 127315 | Comp.
74 | Civil | 30.3.05 | 13.9.04 | Imp to lane from B5/313 to B5/412 in Sect-11 Rohini zone | 136151 | Br-IV | 33 | 119/26.9.03 | M/s Kumar N & Co. | 6.10.03 | 2.1.04 | 127632 | Comp.
75 | Civil | 30.3.05 | 27.12.04 | Imp of Ahatas by interlocking Pavers tiles I Pkt D-6 near HG.no. 217 to 228 and 264 to 254 in Sect-6 Rohini zone | 176172 | R-II | 33 | 152/15.07.05 | M/s D.D.Builders | 06.08.05 | P | 143283 | In Prog.
76 | Civil | 31.3.05 | 5.7.04 | Imp of Ahatas by i/locking tiles in Pkt A-3 near h.no. 115 & 177 in Sec-7 Rohini zone | 113312 | R-II | 33 | 161/18.07.05 | M/s D.D.Builders | 22.07.05 | 22.08.05 | 113262 | Comp.
77 | Civil | 31.3.05 | 5.7.04 | Imp of Ahatas by i/locking tiles/pavers in Pkt-A3 near H.no. 133, 124 & 160 in sect-7 Rohini zone | 198500 | R-II | 33 | 342/16.11.05/EE(R )-II | M/s Patel Const. | 26.11.05 | P | 99014 | In Prog.
78 | Civil | 31.3.05 | 5.7.04 | Imp of Ahatas by i/locking tiles /pavers in Pkt B-9 near H.no. 303, 284 & 235 in sect-5 Rohini zone | 107940 | R-II | 33 | 151/13.07.05 | M/s Anil Goel | 14.07.05 | 05.083.05 | 107893 | Comp
[5 empty] | 14656617 | [6 empty] | 11565801
Remarks: No. of works booked=78, No. of works cancelled=10

## 21
MUNICIPAL CORPORATION OF DELHI
Name of MLA :- Sh. Kulawant Rana |  |  |  | A.C. No. 21 | Year :- 2004-05
Name of Constituency :- Shahbad Daulatpur
S.No | Department | Date of Booking | Date of Consent | Name of Work | Amount | Div. | Ward no. | Work order No. with Date | Name of Agency | A.D.O.S. | A.D.O.C. | Details of Demand of Varification |  |  |  | Phy. Tar. | Phy.Ach | Remarks
[12 empty] | I | II | III | Total
1 | Elect. | 27.7.04 | 29.4.04 | P/o 35 street light arrangment at village Shahdabd Daulatpur Ext under RZ | 199393 | EEE-VII | 36 | 55/25.8.04 | M/s Kwatra Electric Works | 26.8.04 | 30.8.04 | 192935 |  |  | 192935 |  |  | Comp.
2 | Elect. | 27.7.04 | 15.4.04 | P/o 35 street light arrangment at M Block Krishan Vihar Under RZ | 199393 | EEE-VII | 36 | 56/25.8.04 | M/s Kwatra Electric Works | 26.8.04 | 30.8.04 | 192245 |  |  | 192245 |  |  | Comp.
3 | Elect. | 27.7.04 | 15.4.04 | P/o 40 street light arrangment at Q,M & S Block Budh Vihar Under RZ | 199439 | EEE-VII | 35 | 57/25.8.04 | M/s Illuminator and Circuiter | 26.8.04 | 1.9.04 | 193292 |  |  | 193292 |  |  | Comp.
4 | Elect. | 27.7.04 | 22.4.04 | P/o 40 street light arrangment at A&B Block Budh Vihar Under RZ | 199439 | EEE-VII | 35 | 83/27.8.04 | M/as Bansal Electric Store | 27.8.04 | 2.9.04 | 190179 |  |  | 190179 |  |  | Comp.
5 | Elect. | 27.7.04 | 29.4.04 | P/o 35 street light arrangment at B Block Vijay Vihar Under RZ | 199563 | EEE-VII | 35 | 58/25.8.04 | M/s Punjab Electric Co. | 26.8.04 | 31.8.04 | 192594 |  |  | 192594 |  |  | Comp.
6 | Elect. | 27.7.04 | 02.4.04 | P/o 35 street light arrangment at A Block Rajiv Nagar, Begumpur Ext. under RZ | 199563 | EEE-VII | 36 | 59/25.8.04 | M/s Kamal Electricals | 25.8.04 | 30.8.04 | 193496 |  |  | 193496 |  |  | Comp.
7 | Elect. | 27.7.04 | 15.4.047 | P/o 35 street light arrangment at Mange Ram Park under RZ | 199563 | EEE-VII | 36 | 60/25.8.04 | M/s Kohinoor Electricals | 1.9.04 | 6.9.04 | 143150 | 49912 |  | 193062 |  |  | Comp.
8 | Elect. | 27.7.04 | 22.4.04 | P/o 40 street light arrangment at G-8, C Block Vijay Vihar Ph-I & Ph-II Under RZ | 199439 | EEE-VII | 35 | 61/25.8.04 | M/s Punjab Electric Co. | 26.8.04 | 31.8.04 | 190917 |  |  | 190917 |  |  | Comp.
9 | Elect. | 27.7.04 | 6.4.04 | P/o 35 street light arrangment at B Block Shahbad Dairy under RZB | 196401 | EEE-VII | 36 | 62/25.8.04 | M/s Sheela electric Work | 25.8.04 | 30.8.04 | 163600 | 26720 |  | 190320 |  |  | Comp.
10 | Elect. | 27.7.04 | 2.4.04 | P/o 35 street light arrangment at D & E Block Shahbad Dairy under RZB | 196401 | EEE-VII | 36 | 63/25.8.04 | M/s Sheela electric Work | 25.8.04 | 30.8.04 | 163600 | 26850 |  | 190450 |  |  | Comp.
11 | Elect. | 22.7.04 | 6.4.04 | P/o 30 Street Light Arragnement at Krishna Vihar, Jain Colony, Pal Colony under RZ | 197791 | EEE-VII | 36 | 64/25.8.04 | M/s Kwatra Electric Works | 26.8.04 | 30.8.04 | 190740 |  |  | 190740 |  |  | Comp.
12 | Elect. | 22.7.04 | 22.4.04 | P/o 30 Street Light Arragnement at at O Block Krishna Vihar under RZ | 197791 | EEE-VII | 36 | 65/25.8.04 | M/s Kwatra Electric Works | 26.8.04 | 30.8.04 | 190955 |  |  | 190955 |  |  | Comp.
13 | Elect. | 22.7.04 | 15.4.04 | P/o 35 Street Light Arragnement at Village Shahbad Daulatpur Eastern Wing RZ | 199393 | EEE-VII | 36 | 66/25.8.04 | M/s Kwatra Electric Works | 26.8.04 | 30.8.04 | 192805 |  |  | 192805 |  |  | Comp.
14 | Elect. | 22.7.04 | 20.4.04 | P/o 30 Street Light Arragnement at Village Shahbad Daulatpur Eastern Wing RZ | 196401 | EEE-VII | 36 | 67/25.8.04 | M/s Kwatra Electric Works | 26.8.04 | 30.8.04 | 189393 |  |  | 189393 |  |  | Comp.
15 | Elect. | 22.7.04 | 6.4.04 | P/o 40 Street Light Arragnement at Sector 20 Rohini Under RZ | 199439 | EEE-VII | 36 | 68/25.8.04 | M/s Kwatra Electric Works | 26.8.04 | 30.8.04 | 193117 |  |  | 193117 |  |  | Comp.
16 | Elect. | 22.7.04 | 15.4.04 | P/o 35 Street Light Arragnement at Kailash Vihar, Papur Colony, Krishna Colony, Shiv Vihar under RZ | 199563 | EEE-VII | 36 | 69/25.8.04 | M/s Kamal Electricals | 25.8.04 | 6.9.04 | 139650 | 53499 |  | 193149 |  |  | Comp.
17 | Elect. | 22.7.04 | 15.4.04 | P/o 35 Street Light Arragnement at C block Shahbad Dairy under RZ | 197163 | EEE-VII | 36 | 70/25.8.04 | M/s Sheela electric Work | 25.8.04 | 30.8.04 | 163600 | 27450 |  | 191085 |  |  | Comp.
18 | Elect. | 22.7.04 | 6.4.04 | P/o 40 Street Light Arragnement at E & H block Vijay Vihar Ph-I & Ph-II under RZ. | 199439 | EEE-VII | 35 | 71/25.8.04 | M/s Eminents Traders (India) | 27.8.04 | 2.9.04 | 192159 |  |  | 192159 |  |  | Comp.
19 | Elect. | 22.7.04 | 29.4.04 | P/o 35 Street Light Arragnement at B Block Rajiv Nagar, Begaurmpur West under RZ | 199563 | EEE-VII | 36 | 72/25.8.04 | M/s Kamal Electricals | 25.8.04 | 30.8.04 | 193278 |  |  | 193278 |  |  | Comp.
20 | Elect. | 22.7.04 | 6.4.04 | P/o 40 Street Light Arragnement at D & E Block Budh Vihar, Ph-I Under RZ | 199439 | EEE-VII | 35 | 73/25.8.04 | M/s Pragati Engineers | 27.8.04 | 2.9.04 | 191362 |  |  | 191362 |  |  | Comp.
21 | Elect. | 22.7.04 | 29.4.04 | P/o 40 Street Light Arragnement at O & S Block Budh Vihar, Ph-II Under RZ | 199439 | EEE-VII | 35 | 74/25.8.04 | M/s Perfact Electric Works | 30.8.04 | 6.9.04 | 190961 |  |  | 190961 |  |  | Comp.
22 | Elect. | 22.7.05 | 2.4.04 | P/o 40 Street Light Arragnement at M & N Block Budh Vihar, Ph-II Under RZ | 199439 | EEE-VII | 35 | 75/25.8.04 | M/s Eminents Traders (India) | 27.8.04 | 2.9.04 | 192905 |  |  | 192905 |  |  | Comp.
23 | Elect. | 22.7.06 | 2.4.04 | P/o 35 Street Light Arragnement at A block Vijay Vihar Ph-I under RZ | 199563 | EEE-VII | 35 | 76/25.8.04 | M/s Punjab Electric Co. | 26.8.04 | 31.8.04 | 192898 |  |  | 192898 |  |  | Comp.
24 | Elect. | 22.7.07 | 29.4.04 | P/o 35 Street Light Arragnement at A block Shahbad Dairy under RZ | 197163 | EEE-VII | 36 | 77/25.8.04 | M/s Sheela electric Work | 25.8.04 | 30.8.04 | 163600 | 27442 |  | 191042 |  |  | Comp.
25 | Elect. | 22.7.08 | 6.4.04 | P/o 30 Street Light Arragnement at C & D block Rajiv Nagar, Begumpur East under RZ | 193960 | EEE-VII | 36 | 78/25.8.04 | M/s Kamal Electricals | 25.8.04 | 30.8.04 | 188050 |  |  | 188050 |  |  | Comp.
26 | Elect. | 22.7.09 | 2.4.04 | P/o 35 Street Light Arragnement at Harsh Dev Park & Mange Ram Park Under RZ | 199393 | EEE-VII | 36 | 79/25.8.04 | M/s Kohinoor Electricals | 27.8.04 | 1.9.04 | 192975 |  |  | 192975 |  |  | Comp.
27 | Civil | 22.7.10 | 5.4.04 | Const of Drainf rom Sh. Satyawan House towards Satybir Singh Rama House on Phirni Road in Village Shahbad Daulatpur. | 246050 | R-II | 36 | 263/08.12.04 | M/s Oberoi builders | 10.02.05 | P | 203969 |  |  | 203969 |  |  | In prog.
28 | Civil | 18.10.04 | 30.9.04 | Const of Walkway in the park adj PWD road in village Mangolpur Kalan in C-35, Rohini | 495100 | R-II | 35 | 415/02.03.05 | M/s Dee Pee Enterprises | 03.01.06 | 10.06.06 | 248223 | 58470 |  | 306693 |  |  | Comp.
29 | Civil | 18.10.04 | 30.9.04 | Const of Walkway in the park oad no 3 Kanjhawla Road, Mangolpur Kalan village | 355500 | R-II | 35
30 | Civil | 18.10.04 | 30.9.04 | P/F MS Board at different Location in W.no. 35, Sect-3, Rohini.(Rs=106800/-) | - | R-II | 35 | Work cancelled as desired by area MLA vide letter no. 1513/KR/MLA/06 dated 30.12.06 and approved by SE-(RZ) on dated 20.12.06.
31 | Civil | 19.10.04 | 24.3.04 | Imp of Drainge system in Pkt F-24 in Sect-3, Rohini. | 528859 | R-II | 35 | 253/25.11.04 | M/s D.K.Const.Co | 06.02.06 | 28.03.06 | 518007 |  |  | 518007 |  |  | Comp.
32 | Civil | 1.11.04 | 17.9.04 | Prov. Of Water arrangement in MC Pry School, Rajeev Nagar in Rohini | 197000 | Br-IV | 36 | 34/20.1.05 | M/s Joginder singh | 1.2.05 | P | 106559 |  |  | 106559 |  |  | Inprog.
33 | Civil | 3.11.04 | 3.6.04 | Installation of road Sign Board near Sector 17 on Auchandi Road in C-36, Rohini.(Rs=472550/-) | - | R-II | 36 | Work cancelled as desired by area MLA vide letter no. 1513/KR/MLA/06 dated 30.12.06 and approved by CE-V on dated 09.01.07.
34 | Civil | 3.11.04 | 3.6.04 | Installation of Road Sign Board Village Barwala in Auchandi Road in C-36, Rohini. (Rs=472550/-) | - | R-II | 36 | Work cancelled as desired by area MLA vide letter no. 1513/KR/MLA/06 dated 30.12.06 and approved by CE-V on dated 09.01.07.
35 | Elect. | 3.01.05 | 17.12.04 | Provision of EI and Fans in Newly Built Community Hall in Mangolpur Kalan under Rohini. | 99438 | EEE-VII | 35 | 14/13.6.05 | M/s Seth Const./ | 20.6.05 | 29.7.05 | 86614 |  |  | 86614 |  |  | Comp.
36 | Elect. | 3.01.05 | 17.12.04 | Provision of EI and Fans in Newly Built Community Hall in Mangolpur Kalan under Rohini. | 99866 | EEE-VII | 35 | 15/13.6.05 | M/s Seth Const./ | 20.6.05 | 29.7.05 | 86802 |  |  | 86802 |  |  | Comp.
37 | Civil | 11.1.05 | 14.12.04 | Prov. Of Lane by pdg CC and Drainage System from Ram Singh House to Bharat House and adj lanes in village Shahbad Daulatpur. | 313200 | R-II | 36 | 183/08.08.05 | M/s Dua Const.Co | 08.08.05 | 17.11.05 | 225934 | 1437 |  | 227371 |  |  | Comp.
38 | Civil | 11.1.05 | 14.12.04 | Prov. Of Lane by pdg CC and Drainage System from Ved Parkash House to Phirni road and adj lanes in village Shahbad Daulatpur. | 407600 | R-II | 36 | 174/27.07.05 | M/s Dua Const.Co | 06.08.05 | 30.09.05 | 289096 | 2017 |  | 291113 |  |  | Comp.
39 | Civil | 11.1.05 | 14.12.04 | Const of lane by pdg CC and Drainage system from Hari Ram House to Master Reaj Singh House and adj lanes in village Shahbad Daulatpur | 397900 | R-II | 36 | 94/14.06.05 | M/s Bhagwati Const.Co | 23.06.05 | 23.09.05 | 274011 | 10226 |  | 284237 |  |  | Comp.
40 | Civil | 11.1.05 | 14.12.04 | Const of Lanes by pdg CC and Drainge System from Surender House to Chanraveer House and adj lanes in village Shahbad Daulatpur in C-36. | 345500 | R-II | 36 | 62/03.05.05 | M/s Dua Const.Co | 07.07.05 | 03.08.05 | 248888 |  |  | 248888 |  |  | Comp.
[5 empty] | 8649546 | [9 empty] | 7346617
Remarks: 40-3(NO.30,33 & 34 are Cancelled)=37

## 53
MUNICIPAL CORPORATION OF DELHI
Name of MLA :- Sh. Mange Ram Garg |  |  |  |  | Year :- 2004-05
A.C. No. 53
Name of Constituency :- Wazirpur
S.No | Department | Date of Booking | Date of Consent | Name of Work | Amount | Div. | Ward no. | Work order No. with Date | Name of Agency | A.D.O.S. | A.D.O.C. | Details of Demand of Varification |  |  |  | Phy.Tar. | Phy Ach. | Remarks
[12 empty] | I | II | III | Total
1 | Civil | 12.8.04 | 03.7.04 | Cosnt of SW Drain from Mother Dairy to C-2/6 in C -2 Block Phase-II Ashok Vihar C-100 RZ | 211400 | R-I | 100 | 168/8.11.04 | M/s SK Const CO. | 17.11.04 | P | 184917 |  |  | 184917 |  |  | Inprog.
2 | Civil | 12.8.04 | 03.7.04 | Cosnt of SW Drain from C-2/3 to C2/10 in C-2 Block Ph-II in Ashok Vihar. | 209000 | R-I | 100 | 189/17.11.04 | M/s SK Const CO. | 26.11.04 | P | 189455 |  |  | 189455 |  |  | Inprog.
3 | Civil | 12.8.04 | 03.7.04 | Imp of Open Surface of Ramlila Park in JJ Colony, Wazirpur C-99 RD-I | 200800 | R-I | 99 | 186/17.11.04 | M/s Ravinder Const,. | 17.11.04 | 16.1.05 | 200106 |  |  | 200106 |  |  | Comp.
4 | Civil | 12.8.04 | 03.7.04 | Imp to approach of Ramlila Stage in Rmlila Park JJ Colony, Wazirpur C-99 | 207200 | R-I | 99 | 203/22.11.04 | M/s Raj Const. | 22.11.04 | 16.1.05 | 206933 |  |  | 206933 |  |  | Comp.
5 | Civil | 12.8.04 | 03.7.04 | Imp to open surface along Community Centre L Block JJ Colony, Wazirpur in C-99 | 204600 | R-I | 99 | 194/18.11.04 | M/s Ravinder Const,. | 18.11.04 | 20.1.05 | 204552 |  |  | 204552 |  |  | Comp.
6 | Civil | 20.8.04 | 12.8.04 | Stg of B/wall of park near H.No. B-4/15 in B 4 block Ph-II Ashok Vihar. | 109000 | R-I | 100
7 | Civil | 30.8.04 | 3.8.04 | Imp to open surface Gurudwara to Dustbin in Nimri Colony in C-99. | 138523 | R-I | 99 | 180/10.11.04 | M/s Rakesh Kr Goel | 10.11.04 | 10.12.04 | 138439 |  |  | 138439 |  |  | Comp
8 | Civil | 30.8.04 | 3.8.04 | Imp to lane by pdg RMC form Qtr No. 86 to 162 in Nimri Colony Ph-II RZ. | 552000 | R-I | 99 | 171/8.11.04 | M/s Gaurav Const Co. | 8.11.04 | 30.12.04 | 421880 |  |  | 421880 |  |  | Comp
9 | Civil | 30.8.04 | 3.8.04 | Imp to lane by RMC From H.NO. 1 to 82 in Nirmri Colony, Ph-II C-99. | 400855 | R-I | 99 | 276/27.12.04 | M/s Gaurav Const Co. | 27.12.04 | 20.1.05 | 356316 | 41738 |  | 398054 |  |  | Inprog.
10 | Civil | 9.9.04 | 9.8.04 | Imp to drain and side berms along H.NO. 216, 217 and Park in B block in Ph-I Ashok Vihar | 230000 | R-I | 100 | 421/07.03.05 | M/s Dinesh Const.CO | 16.03.05 | 29.07.05 | 150888 |  |  | 150888 |  |  | Comp
11 | Civil | 9.9.04 | 12.8.04 | Imp to alne by pdg RMC form H.NO B 2/33 to Laxmi Narain Mandir in B-2 Block Ph-II Ashok Vihar | 215600 | R-I | 100 | 330/17.1.05 | M/s Manoj Kr Gupta | 17.1.05 | 06.04.05 | 149179 | 17107 |  | 166280 |  |  | inprog.
12 | Civil | 15.9.04 | 17.8.04 | Pdg and fixing M S boards in Various points in Ahok Vihar | 97700 | R-I | 100
13 | Elect. | 28.9.04 | 2.8.04 | P/o Pdg Arragnement in parks of J block MIG flats Ph-I Ahsok Vihar | 201686 | EEE-VII | 100 | 133/21.10.04 | M/s Singhal & Co. | 31.10.04 | 25.11.04 | 190385 |  |  | 190385 |  |  | Comp.
14 | Elect. | 28.9.04 | 2.8.04 | P/o Pdg arrangment in parks of KD Block E block and A block PH-I Ashok Vihar. | 185329 | EEE-VII | 100 | 132/21.10.04 | M/s Singhal & Co. | 30.10.04 | 25.11.04 | 177369 |  |  | 177369 |  |  | Comp.
15 | Elect. | 28.9.04 | 18.9.04 | Pdg Ltg arragment in MCD Park sof IB Block & H Block Ashok Vihar., | 180857 | EEE-VII | 100 | 221/14.02.05 | M/s Repair Shop | 16.2.05 | 1.4.05 | 84142 |  |  | 84142 |  |  | Comp.
16 | Elect. | 28.9.04 | 18.9.04 | P/o Ltg arrangement in MCD Parks of Pkt D Ashok Vihar Ph-III & in IA Block from Flat no., 45A to 67A, Ashok Vihar Ph-I. | 162190 | EEE-VII | 100 | 223/14.2.05 | M/s Prince Engineer works | 21.02.05 | 5.4.05 | 91869 |  |  | 91869 |  |  | Comp.
17 | Elect. | 28.9.04 | 18.9.04 | P/o Ltg arrangement in MCD Parks (6 poles) of IA block from flat NO. IA to 45A, Ashok Vihar. | 191574 | EEE-VII | 100 | 220/8.2.05 | M/s Repair Shop | 17.2.05 | 1.405 | 112392 |  |  | 112392 |  |  | Comp.
18 | Elect. | 28.9.04 | 18.9.04 | P/o Ltg arrangement in MCD Parks 10m poles of near Sanatan Dharam Mandir near Bangali Mandir Ashok Vihar, PH-II in Janta Flats in Ashok Vihar Ph-III and Nimri Cly infront of H.no. 125 Ph-I | 188255 | EEE-VII | 100 | 224/14.2.05 | M/s Prince Engineer works | 19.2.05 | 6.4.05 | 106929 |  |  | 106929 |  |  | Comp.
19 | Elect. | 28.9.04 | 18.9.04 | P/o Ltg arrangement in MCD Parks 10 poles at near H.no. 94 Ashok Vihar Ph-I Shakti Apptt Ashok Vihar Ph-III in W.no. 100 & near H.no. 45, H.n. 535 Neemri Cly in W.no. 99. | 189583 | EEE-VII | 100 | 225/14.2.05 | M/s Prince Engineer works | 18.2.054 | 6.4.05 | 106010 |  |  | 106010 |  |  | Comp.
20 | Civil | 8.10.04 | 22.9.04 | Imp of lane by pdg RMC From H.no. B1/60 to B1/68 in Ph-II, Ashok Vihar | 165400 | R-I | 100 | 331/17.1.05 | M/s Manoj Kr Gupta | 17.1.05 | 20.03.05 | 126154 | 261 |  | 126415 |  |  | Comp.
21 | Civil | 8.10.04 | 22.9.04 | Imp of B.wall of D pkt Flats PH-III in Ashok Vihar | 129500 | R-I | 100 | 264/07.03.06 | M/s H.P Const.Co | 07.03.06 | 31.03.06 | 105458 |  |  | 105458 |  |  | Comp.
22 | Civil | 8.10.04 | 22.9.04 | Const of Culvert near Agarsain Dharamshala in D block Ph-I Ashok Vihar | 65200 | R-I | 100 | 209/06.07.05 | M/s Sonu Const.Co | 11.07.05 | 02.09.05 | 58218 |  |  | 58218 |  |  | Comp.
23 | Civil | 14.10.04 | 1.10.04 | Imp ot lane by pdg & Laying RMC to From H.no. B4, /B/69 to B4/79, B4/53 to B4/68, B4/57 to B4/80 and B4/1 to B4/53 in B4 Block PH-II Ashok Vihar. | 357300 | R-I | 100 | 284/29.12.04 | M/s Gaurav Const Co. | 29.12.04 | 26.1.05 | 291846 | 3405 |  | 295251 |  |  | Comp.
24 | Hort. | 3.11.04 | 21.10.04 | Constof New Tube Well Bore at Site park in E block opp H.No. E-4 PH-I Ashok Vihar. | 83070 | ADH® | 100 | 29/14.2.05 | M/s Mayur Enterprises | 14.2.05 | 14.3.05 | 80303 |  |  | 80303 |  |  | Comp.
25 | Hort. | 3.11.04 | 21.10.04 | Installation of Motor Pump Set in Exist T/well bore hole at site park in E block Opp H.no. E-4 Ph-I, Ashok Vihar | 74449 | ADH® | 100 | 30/14.2.05 | M/s Mayur Enterprises | 14.2.05 | 14.3.05 | 69684 |  |  | 69684 |  |  | Comp.
26 | Civil | 8.11.04 | 21.10.04 | Covering of Drain from 73A to 14A and Imp to Berms from H.no. 68A to 73A and 9A to 14A in B4 Pkt PH-II Ashok Vihar | 49500 | R-I | 100 | 441/15.03.05 | M/s Hans Raj Const. | 24.03.05 | 22.04.05 | 28459 | 17012 |  | 45471 |  |  | Comp.
27 | Civil | 8.11.04 | 21.10.04 | Imp to SW Drain from Jivodya Hosp to Maharaja Agarsen Marg in A block Ph-I Ashok Vihar | 294400 | R-I | 100 | 131/30.05.05 | M/s Prince Engineer works | 09.09.05 | P | 165249 |  |  | 165249 |  |  | In Prog.
28 | Civil | 8.12.04 | 22.9.04 | Imp to park opp H.No. KC -49 and KC-1 in Ph-I, Ashok Vihar. | 340400 | R-I | 100 | 266/07.03.06/EE(Br.)III | M/s Gulshan Const.Co | 20.03.06 | 15.06.06 | 226437 |  |  | 226437 |  |  | Comp.
29 | Civil | 8.12.04 | 4.12.04 | Imp of lane by RMC from H.no. WP 586 to WP 83 and Chowk along H.no. WP92 and along Chopal in Wazirpur Village | 310700 | R-I | 100 | 106/24.5.05 | M/s Surander Const.Co | 2.6.05 | P | 209619 |  |  | 209619 |  |  | In Prog.
30 | Civil | 10.12.04 | 4.12.04 | Imp of B.wall of SFS Flats from gate no 5 to Last Corner near Nimri Cly in A-V PH-IV. | 356500 | R-I | 100 | 255/02.03.06/EE(Br.)-III | M/s Bindra builders | 12.04.06 | 08.06.06 | 264678 |  |  | 264678 |  |  | Comp.
31 | Civil | 23.12.04 | 19.12.04 | Imp of lane by RMC from H.no D-201 to D-184 in D block in AV Ph-I. | 258400 | R-I | 100 | 87/11.5.05 | M/s Dhruv Const. | 11.5.05 | 11.06.05 | 172381 |  |  | 172381 |  |  | Comp.
32 | Civil | 23.12.04 | 19.12.07 | Imp of laen by RMC from H.no C40 to C-48 in Av Ph-I | 141300 | R-I | 100 | 56/11.05.05 | M/s Dhruv Const. | 10.09.05 | 21.09.05 | 98616 |  |  | 98616 |  |  | Comp.
33 | Civil | 23.12.04 | 21.10.04 | P/F Over Head Retro Reflective Singh Board infront of Deep Cinema Mkt in AV. | 262300 | R-I | 100
34 | Civil | 23.12.04 | 21.10.04 | P/F Over Head Retro Reflective Singh Board infront of Shiv Mkt Wazir Pur Village | 263300 | R-I | 100
35 | Civil | 23.12.04 | 4.12.04 | P/F Over Head Retro Reflective Singh Board near Chhabra Sweets in AV Ph-I | 518300 | R-I | 100
36 | Civil | 28.12.04 | 4.12.04 | Imp of back lane by RMC from H.no. B3/31 to B3/14 in B block AV Ph-II. | 678400 | R-I | 100 | 130/30.05.05 | M/s Friends Const.& Bldg.Mat.Supp. | 08.06.05 | 26.08.05 | 510002 |  |  | 510002 |  |  | Comp.
37 | Elect. | 3.1.05 | 15.12.04 | P/oLtg arrangement with 10 mt pole in Parks of Nimri Cly in front of H.n. 430 in ward No 99 & with 6 mt polew at C-3 Block & Central Mkt Ashok Vihar | 175460 | EEE-VII | 99/100 | 1/13.4.05 | M/s Repair Shop | 20.4.05 | 27.5.05 | 117432 |  |  | 117432 |  |  | Comp.
38 | Civil | 7.1.05 | 4.12.04 | P.F Retro Reflective Board in BZ and B3 blocks in AV Ph-II | 199900 | R-I | 100
39 | Civil | 20.1.05 | 4.12.04 | Const of Walkway in park infront of H.no. 425 in Nimri Cly AV. | 199100 | R-I | 99 | 206/05.07.05 | M/s Dhruv Const. | 13.07.05 | P | 124483 |  |  | 124483 |  |  | IN Prog
40 | Civil | 20.1.05 | 4.12.04 | Imp of park infront of H.no. B-129 in AV-Ph-I | 198600 | R-I | 99 | 208/05.07.05 | M/s Surender Consts.Co. | 14.07.05 | 02.09.05 | 141137 |  |  | 141137 |  |  | Comp.
41 | Civil | 31.1.05 | 27.1.05 | Raising of Side Berms by RMC infront of H.no. A1 to A-10 in Satyawati Cly in C-99. | 141970 | R-I | 99 | 75/07.10..05 | M/s Dhruv Const. | 07.10.05 | P | 1400452 |  |  | 140452 |  |  | Comp.
42 | Civil | 31.1.05 | 27.1.05 | Imp to lane by RMC from Radha Cly park to NDPL Sub Site in Satyawati adj in C-99. | 197200 | R-I | 99 | 242/26.7.05 | M/s Rajeev Mittal | 27.7.05 | 17.8.05 | 184993 |  |  | 184993 |  |  | Comp.
43 | Civil | 31.1.05 | 27.1.05 | Raising of Side berms from C-4 to Corner of park in Satyawati Cly | 143262 | R-I | 99 | 04/04.08.05 | M/s Nishant Const.Co | 05.08.05 | 29.09.05 | 142579 |  |  | 142579 |  |  | Comp.
44 | Civil | 31.1.05 | 27.1.05 | Imp of Driange System from infront of A3/1 to Corner of Park in Satyawati Cly AV C-99. | 199200 | R-I | 99 | 256/29.07.05 | M/s Deepk Associates | 01.08.05 | 05.09.05 | 154026 |  |  | 154026 |  |  | Comp.
45 | Elect. | 4.02.05 | 27.1.05 | P/o Post Top Lentern in the park of C-2 Block, Ashok Vihar, Ph-II | 147633 | EEE-VII | 100 | 29/29.06.05 | M/s Bhanu Enterprises | 08.07.05 | 05.08.05 | 88365 |  |  | 88365 |  |  | Comp.
46 | Elect. | 4.02.05 | 25.1.05 | P/o Post Top Lentern in the park of C-3 Block, Ashok Vihar, Ph-II | 148359 | EEE-VII | 100 | 35/12.07.05 | M/s G.S.Electriclas | 12.07.05 | 10.08.05 | 92172 |  |  | 92172 |  |  | Comp.
47 | Elect. | 4.02.05 | 28.1.05 | P/o Post Top Lentern in the park of C-1 Block, Ashok Vihar, Ph-II | 98166 | EEE-VII | 100 | 37/12.07.05 | M/s G.S.Electriclas | 12.07.05 | 10.08.05 | 61507 |  |  | 61507 |  |  | Comp.
[5 empty] | 10273421 | [9 empty] | 6805528