## AC-66
STATUS REPORT OFMLA FUND FOR THE YEAR 2005-06
Municipal Corporation of Delhi
Karol Bagh
|  | Name Of MLA |  | Sh. Ramakant Goswami | AC-66 |  | year 2005-06 |  | Allocation |  | 100.00lacs
|  | Name of Constituency |  | Patel Nagar
|  | Ward Nos and Names |  | 125, East Patel Nagar 126, South Petal Nagar
S/No | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Div. | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Civil | 25.5.05 | 28.4.05 | Const of skating ring adjacement to Booster Pumping station of DJB Nagr in C-125. KBZ | 400600 | EE-I | 125 | 187/06..09.05/EE-I | M/s Rakesh Enterprises | 16.09.05 | 15.12.05 | 381036 | Comp.
2 | Civil | 25.5.05 | 11.5.05 | Imp to crossing near HNO 33/9 by pdg c.c. in W.P. Nagar in C-125 A/KBZ | 358400 | EE-I | 125 | 126/22.08.05/EE-I | M/s Kuldeep Singh | 31.08.05 | 31.03.06 | 247207 | Comp.
3 | Civil | 25.5.05 | 28.4.05 | Imp to back lane by pdg c.c. from HNO1/1 to 1/8 in West Patel Nagarin C-125 B/ KBZ | 443900 | EE-I | 125 | 111/08.08.05/EE-I | M/s Hem Lata Const.Co. | 09.08.05 | 20.10.05 | 303734 | Comp.
4 | Civil | 25.5.05 | 28.4.05 | Imp to back lane by pdg c.c. from HNO 3/17 to 3/32 in West Patel Nagr in C-125 A/KBZ | 443200 | EE-I | 125 | 112/EE-1/8.8.05 | M/s Kritiaka Consts | 9.8.05 | 6.10.05 | 299643 | Camp
5 | Civil | 2.6.05 | 28.4.05 | Imp to main entrance of Gaushala park near fountain in Prem Nagr in C-125/KBZ (Rs.264500/-) | - | EE-I | 125 |  | Work Cancelled as desired by area MLA vide letter dated 06.10.06 and approved by CE-IV dated 14.08.07
6 | Civil | 2.6.05 | 28.4.05 | C/o walkway opp Gaushala in Gaushala Park in Prem Nagar in C-125/KBZ | 383000 | EE-I | 125 | 283/7.11.05/EE-I | M/S pappu seth | 8.11.05 | 16.02.06 | 237619 | Comp.
7 | Civil | 2.6.05 | 11.5.05 | Imp to drainage system form HNO 33/9 to Community Centre 26 block in West Patel Nagr in C-125 AKBZ | 528100 | EE-I | 125 | 257/10.10.05/EEI | M/S S.P.Consts | 11.10.05 | 29.12.05 | 327577 | Comp.
8 | Civil | 3.8.05 | 13.6.05 | Imp to back lane by pdg c.c. pavement & S.w drainage from 14 a/ 32 jto 14 a/41 in WEA in c-126/K.B.Z | 249200 | EE-I | 125 | 273/25.10.05/EE-I | M/s Aggarwal Builders & Promotors | 11.11.05 | 12.01.06 | 167600 | Comp.
9 | Civil | 3.8.05 | 13.6.05 | Imp to back lane by pdg c.c flooring from 9 A/68 to 9 A/72 in WEA in C-126/KBZ | 135500 | EE-I | 125 | 285/07.11.05/EE-I | M/S S.K Aggarwal | 14.11.05 | 10.02.06 | 95031 | Comp.
10 | Civil | 23.02.06 | 28.01.06 | Imp to road by Pdg c.c Pavment from 2253/f to 2247 and near 2253/B 7 In Ranjeet nagar in C-126/kbz | 189563 | EE-I | 126 | 32/16.05.06/EE-I | M/s J.S Const. | 28.07.06 | 16.09.06 | 189424 | Comp.
11 | Civil | 23.02.06 | 28.01.06 | Imp to road by c.c pavement from 2252/A-7 to 2253/6 in Ranjeet Nagar in C-126/KBZ | 164388 | EE-I | 126 | 553/23.03.06/EE-I | M/s Jai Kumar | 02.05.06 | 20.07.06 | 161374 | Comp.
12 | Civil | 23.02.06 | 28.01.06 | Imp ro road by pdg. C.c pavement from 2253/C-3 to 2253/D-7 and from Gopla Dairy to 2253/A-1 in Ranjeet Nagar in C-126/KBZ | 192817 | EE-I | 126 | 558/29.03.06/EE-I | M/s Narendar Singh Dhankar | 07.04.06 | 10.06.06 | 192817 | Comp.
13 | Civil | 10.03.06 | 28.01.06 | Const of Hanuman Vyayamshela Park in E&F Block Ranjeet Nagar in C-126/KBZ | 699800 | EE-I | 126 | 130/26.09.06/EE-I | M/S S.K Aggarwal | 03.10.06 | 02.01.07 | 621666 | Comp.
14 | Civil | 10.03.06 | 28.01.06 | Const of Modern Umbrella canompy in sataym park near satyam cinema in Ranjeet Nagar in C-126/KBZ | 698400 | EE-I | 126 | 243/04.12.06/EE-I | M/s Rakesh Enterprises | 12.12.06 | 10.03.07 | 620454 | Comp.
|  |  |  | Total | 4886868 | [6 empty] | 3845182
Remarks:- No. of works booked=14, No. of works cancelled=1

## AC-67
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06
Municipal Corporation of Delhi
Karol Bagh
|  | Name Of MLA |  | Sh P.C. Yogi |  |  | year 2005-06 |  | Allocation | 173.48 Lacs |  |  | Dated:-
|  | Name of Constituency |  | Rajender Nagar | AC-67
|  | Ward Nos and Names |  | 127, Rajender Nagar 128 Naraina
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Div. | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Exp. | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14
1 | Civil | 20.5.05 | 17.5.05 | Imp & stg of Internal roads in C block Inderpur Naraina in KBZ , by pdg dense Carpet. | 885200 | Pr KBZ | 127 | 33/11.11.05 | M/s Radhey Shyam | 18.11.05 | 21.11.05 | 699235 |  |  | Comp.
2 | Civil | 1.6.05 | 31.5.05 | Imp to chowk by RMC from I- 181 to I-195 in I block Naraina Vihar in C-128/KBZ | 185900 | EE-I | 128 | 140/EE-I 22.8.05 | M/s Kuldeep Singh | 26.8.05 | 6.10.05 | 168384 |  |  | Complete
3 | Civil | 1.6.05 | 31.5.05 | Imp to Nalla from gate NO-1 to gate NO-2 in I block Naraina Vihar in C-128/KbZ | 80800 | EE-I | 128 | 153/24.08.05/EE-I | M/s Pankaj Contractors | 02.09.05 | 29.11.05 | 64099 |  |  | Comp.
4 | Civil | 1.6.05 | 31.5.05 | Imp to road berms by tiles and c.c from DESU transformer to Dalao in I block Narina Vihar in C-128/KBZ | 195800 | EE-I | 128 | 143/EE-1/22.8.05 | M/s Ganga Const Co | 23.8.05 | 15.9.05 | 103578 |  |  | Comp.
5 | Civil | 1.6.05 | 31.5.05 | Imp to chowk by RMC along A-6 and A-7 in A block Naraina Indl. Area PH-II in c-128/KBZ | 577000 | EE-I | 128 | 148/22.08.05/EE-I | M/s Kuldeep Singh | 23.08.05 | 03.11.05 | 435503 |  |  | Comp.
6 | Civil | 1.6.05 | 31.5.05 | Imp to gali by c.c. and drainage by open Surface drain from HNO E-164 to E-170 in E block Narina Vihar in C-128/KBZ | 295800 | EE-I | 128 | 152/24.08.05/EE-I | M/s Abhishek Enterprises | 20.08.05 | 30.11.05 | 215293 |  |  | Comp.
7 | Civil | 1.6.05 | 31.5.05 | Imp to walkway of park near HNO E-26 in E block Naraina Vihar in C-128/KBZ | 162400 | EE-I | 128 | 159/24.08.05/EE-I | M/s Hem Lata Const.Co | 12.09.05 | 05.12.05 | 119108 |  |  | Comp.
8 | Civil | 1.6.05 | 31.5.05 | Imp to gates of parks NO_5 in E block Naraina Vihar in c-128/KbZ | 188200 | EE-I | 128 | 142/22.08.05/EE-I | M/s Kuldeep Singh | 30.08.05 | 20.06.06 | 137841 |  |  | Comp.
9 | Civil | 1.6.05 | 31.5.05 | Imp to lane by RMC along A-5 and A-8 in A block Naraina Indl. Area PH-II C-128/KBZ | 411800 | EE-I | 128 | 146/22.08.05/EE-I | M/s Kuldeep Singh | 23.08.05 | 30.11.05 | 317486 |  |  | Complete
10 | Civil | 2.6.05 | 1.6.05 | Imp to lane by c.c. & drainage from 23/17 to 23/24 & by lanes of 23 block in old Rajinder Nagre C-127 A/KBZ | 141900 | EE-I | 128 | 182/EE-I/5.9.05 | M/s Inder Entp. | 10.9.05 | 5.11.05 | 91957 |  |  | Complete
11 | Civil | 2.6.05 | 1.6.05 | Imp to drainage system & side berm from shanker road to Narin Swami Marg along block NO :4,4A 4B &4D block in old Rajinder Nagr in C-127/KBZ | 256500 | EE-I | 128 | 176/05.09.06/EE-I | M/s Inder Entp. | 13.09.05 | 12.10.05 | 164665 |  |  | Complete
12 | Civil | 2.6.05 | 1.6.05 | Imp to lanes by pdg drainage & c.c. along park in F -432 to F-273 in New Rajinder Nagr In c-127 A/kBZ | 399200 | EE-I | 128 | 139/EE-I/22.8.05 | M/s Inder Entp. | 22.8.05 | 14.10.05 | 239326 |  |  | Camp.
13 | Civil | 2.6.05 | 1.6.05 | Imp to lanes by pdg drainage & c.c. along park in F -432 to F-273 in New Rajinder Nagr In c-127 A/KBZ | 372900 | EE-I | 128 | 141/22.08.05/EE-I | M/s Inder Entp. | 23.08.05 | 04.10.05 | 249302 |  |  | Comp.
14 | Civil | 2.6.05 | 1.6.05 | Imp to Square by pdg c.c near R-871 & R877 in New Rajinder Nagr C-127 A/KBZ | 228300 | EE-I | 128 | 133/EE-I/22.8.05 | M/s Manish Assoc. | 24.8.05 | 4.10.05 | 157220 |  |  | Comp
15 | Civil | 27.7.05 | 7.7.05 | Imp to lane by pdg drainage & C.C from HNO. 4A/1 to 4 A/16 & 4A/20 to 4 A/32 in old Rajinder Nagar in W.No 127 A KBZ | 261200 | EE-I | 128 | 173/EE-I/5.9.05 | M/s Inder Entp. | 5.9.05 | 7.11.05 | 173628 |  |  | Comp
16 | Civil | 27.7.05 | 7.7.05 | Imp to lane by pdg c.c from HNO R-880 to R-510 in R block, New Rajinder Nagr W.No 127 A/KBZ | 394700 | EE-I | 128 | 312/29.11.05 | M/s P.R .Const.Co | 23.01.06 | 26.02.06 | 263188 |  |  | Comp.
17 | Civil | 27.7.05 | 7.7.05 | Imp to lane & by lanes by pdg RMC from HNO D-169 to 173 & HNO D-140 to 150 in New Rajinder Nagar w.no 127 A/KBZ | 318700 | EE-I | 128 | 324/08.12.05/EE-I | M/s Amit Consts. | 19.12.05 | 12.07.05 | 275517 |  |  | Comp.
18 | Civil | 27.7.05 | 7.7.05 | Imp to footpath & pdg drainage system near Sindhi Pachayat & 10 block in old Rajinder Nagr in W.NO 127 A K>B>Z | 173400 | EE-I | 128 | 269/21.10.05/EE-I | M/s Inder Entp. | 24.10.05 | 23.03.06 | 104339 |  |  | Comp.
19 | Civil | 29.7.05 | 22.6.05 | Imp to lane by pdgc.c. & drainage in lane & by lanes of 4 D block from 4 D/29 to 4D/36 4D/21 to 4D/56 in old Rajinder Nagr in w.no 127 A/KBZ | 259100 | EE-I | 128 | 178/EE-I/5.9.05 | M/s Inder Entp. | 5.9.05 | 11.10.05 | 172905 |  |  | Camp
20 | Civil | 29.7.05 | 14.7.05 | pdg c.c path main entreance upto Pyres in Cremation ground Inderpuri in C-127 B/KBZ | 261200 | EE-I | 128 | 258/10.10.05 | M/s Tajinder Const.Co | 27.02.06 | 08.05.06 | 178824 |  |  | Comp.
21 | Civil | 29.7.05 | 14.7.05 | Imp to outer Boundary wall by raising & fencing at Cremation ground , Inderpuri C-127/B/KBZ | 185733 | EE-I | 128 | 295/21.11.05/EE-I | M/s Tajinder Const.Co | 28.11.05 | 31.12.05 | 183460 |  |  | Comp.
22 | Civil | 1.8.05 | 31.5.05 | Imp to drainage from D-92 to D-98 , D-85 to D-88, D-56 to D-62 in D block , Naraina Vihar ,in C-128/KBZ | 198900 | EE-I | 128 | 201/14.09.05/EE-I | M/s Sahil Consts. | 12.09.05 | 23.12.05 | 198900 |  |  | Comp.
23 | Civil | 1.8.05 | 31.5.05 | Imp to drainage b y open surface drain from E-231 to E-223 in E block Naraina Vihar in C-128/KBZ | 196700 | EE-I | 128 | 213/20.09.05 | M/s Bagga Builders | 30.09.05 | 29.12.05 | 196542 |  |  | Comp.
24 | Civil | 1.8.05 | 31.5.05 | Imp to drainage system by open Surface drain along park , Tulsi garden in G block Naraina Vihar in C-128/KBZ | 192700 | EE-I | 128 | 167/30.08.05/EE-I | M/s Harish Kumar | 12.09.05 | 23.11.05 | 192700 |  |  | Comp.
25 | Civil | 1.8.05 | 14.7.05 | Const of office block Ashthi Room and toilet block at Cremation ground, Inderpuri C-127 B/ KBZ (Rs.199600/-) |  | EE-I | 128 | Work Cancelled as desired by area MLA vide letter dated 06.10.08 and approved by SE-KBZ dated 13.03.08
26 | Civil | 1.8.05 | 14.7.05 | Imp to Surrounding of fuel Shed by Raising of B/wall and pdg M.S. gate in Shed at Cremation ground Inderpuri in C-127 B | 199800 | EE-I | 128 | 297/21.11.05 | M/s Tajinder Const.Co | 24.01.06 | 05.05.06 | 192945 |  |  | Comp.
27 | Civil | 8.8.05 | 31.5.05 | Imp of B/wall of park near C-96 in C block Narain Vihar in c-128/KBZ | 298900 | EE-I | 128 | 303/24.11.05/EE-I | M/s Kuldeep Singh | 24.11.05 | 15.12.05 | 298900 |  |  | Comp.
28 | Civil | 8.8.05 | 31.5.05 | Imp to B/wall of park from Pump House to C-91 in C block Naraina Vihar in c-128/KBZ | 376424 | EE-I | 128 | 445/09.01.06/EE-I | M/s P.R .Const.Co | 08.02.06 | 18.06.06 | 366958 |  |  | Comp.
29 | Civil | 8.8.05 | 31.5.05 | Imp to back lane by RMC from C-159 to C-142 in C block NIA PH-I in W.NO 128/KBZ | 495300 | EE-I | 128 | 323/05.12.05 | M/s Kuldeep Singh | 06.03.06 | 12.05.06 | 460426 |  |  | Comp.
30 | Civil | 8.8.05 | 7.7.05 | Imp to road by C.C. from E-277 to E-292, in E block , Naraina Vihar in C-128/KBZ | 188500 | EE-I | 128 | 27/05.05.06/EE-I | M/s Raj Builders | 16.05.06 | 20.07.06 | 142343 |  |  | Comp.
31 | Civil | 8.8.05 | 7.7.05 | Const of Gate of park opp E-253, E block Naraina Vihar in C-128/KBZ | 197700 | EE-I | 128 | 268/21.10.05/EE-I | M/s P.R .Const.Co | 21.10.05 | 20.06.06 | 148751 |  |  | Comp.
32 | Civil | 8.8.05 | 7.7.05 | Const of Gate of park ( Apna park) opp Union Bank of India in E block Naraina Vihar in C-128/KBZ | 198900 | EE-I | 128 | 491/23.01.06/EE-I | M/s Amit Consts. | 04.09.06 | 26.12.06 | 139374 |  |  | Comp.
33 | Civil | 8.8.05 | 7.7.05 | Imp to road by inter locking tiles from E-242 to E-248 E-249 to E259 E-203 to E-210 and E221 to E233 in E block Naraina Viahar in C-128/KBZ | 420500 | EE-I | 128 | 319/05.12.05/EE-I | M/s Kuldeep Singh | 05.12.05 | 07.01.06 | 336810 |  |  | Comp.
34 | Civil | 8.8.05 | 7.7.05 | Imp to B/wall of park near Z-180, Loha Mandir in C-128/KBZ | 270800 | EE-I | 128 | 321/05.12.05/EE-I | M/s Kuldeep Singh | 05.12.05 | 23.01.06 | 270733 |  |  | Comp.
35 | Civil | 8.8.05 | 7.7.05 | Imp to lane by C.C from Z-195/1 to Z174 in Z block Loha Mandir in C-128/KBZ | 195200 | EE-I | 128 | 172/05.09.05/EE-I | M/s Jaswinder Gulati | 03.03.06 | 21.11.06 | 195180 |  |  | Comp.
36 | Civil | 8.8.05 | 12.7.05 | Imp to lane by C.C from Z-145 to Z-173 in Z block Loha Mandi in C-128 | 197700 | EE-I | 128 | 185/05.09.05/EE-I | M/s R.S Const.CO | 02.03.06 | 12.01.07 | 197700 |  |  | Comp.
37 | Civil | 8.8.05 | 12.7.05 | Imp to lane by C.C form Z-82/1 to Z-106 in Z block Loha Mandi in c-128 | 195300 | EE-I | 128 | 215/20.09.05/EE-I | M/s Plan-Up-Consts. | 02.03.06 | 31.07.06 | 194942 |  |  | Comp.
38 | Civil | 9.8.05 | 7.7.05 | Imp to lane by pg C.C and drainage from 6/9 to 6/88 in Old Rajinder Nagar C-127 A | 264000 | EE-I | 128 | 351/14.12.05/EE-I | M/s Kishore & Co. | 09.01.06 | 16.03.06 | 179598 |  |  | Comp.
39 | Civil | 9.8.05 | 7.7.05 | Imp to lane from 7/1 to 7/46 by pg C.C and drainage system in old Rajender Nagar C-127 A | 262500 | EE-I | 128 | 16/05.05.06/EE-I | M/s Raj Builders | 12.05.06 | 22.09.06 | 197339 |  |  | Comp.
40 | Civil | 9.8.05 | 7.7.05 | Imp to lane and by lanes from H.No 11 A/4 to 11 A/6 and 11 A/13 to 11 A/18 by pdg C.C and drainage in Old Rajinder Nagar W.No 127 A | 186000 | EE-I | 128 | 406/30.12.05 | M/s Shiv Kumar Gupta | 05.01.06 | 08.04.06 | 128038 |  |  | Comp.
41 | Civil | 9.8.05 | 7.7.05 | Imp to drainage and berms of road from H.No 700 to 710 and near 716 in Double storey New Rajender Nagar in C-127 A | 199600 | EE-I | 128 | 298/21.11.05/EE-I | M/s Raj Builders | 01.12.05 | 14.02.06 | 165984 |  |  | Comp.
42 | Civil | 9.8.05 | 7.7.05 | Imp to lane by pdg C.C. from H.No 23/1 to 23/6 in Old Rajender Nagar in W.No C-127 A | 129900 | EE-I | 128 | 292/11.11.05/EE-I | M/s Inder Entp. | 12.11.05 | 16.12.05 | 117018 |  |  | Comp.
43 | Civil | 9.8.05 | 7.7.05 | Imp to drainage system at Crossing , R-736 , R-724 , and R-685 in New Rajender Nagr W.No 127 A | 144500 | EE-I | 128 | 296/21.11.05/EE-I | M/s Raj Builders | 01.12.05 | 14.02.06 | 129720 |  |  | Comp.
44 | Civil | 9.8.05 | 7.7.05 | Imp to lane by pdg C.C. and drainage from H.No R-806, to R-800 in R block , New Rajender Nagar W.No 127 A | 328700 | EE-I | 128 | 25/05.05.06/EE-I | M/s Sunil Enterprises | 10.06.06 | 01.08.06 | 251134 |  |  | Comp.
45 | Civil | 9.8.05 | 7.7.05 | Imp to footpath and side berms near B/wall of Salwan School Mkt in Old Rajinder Nagar in W.No 127 A | 65000 | EE-I | 128 | 255/10.10.05/EE-I | M/s S.P Consts. | 12.10.05 | 19.01.06 | 64834 |  |  | Comp.
46 | Civil | 9.8.05 | 7.7.05 | Imp to footpath & drainage on Shankar road from odean park to 35 block, old Rajender Nagr in W.No 127 A | 199600 | EE-I | 128 | 334/14.12.05 | M/s Ma Bhoomika Enterprises | 19.12.05 | 28.02.06 | 125290 |  |  | Comp.
47 | Civil | 18.8.05 | 7.7.05 | Imp to back lane of 35 block by pdg C.C. & drainage from Shanker road to water tank in old Rajender Nagar W.No 127 A | 261500 | EE-I | 128 | 461/18.01.06 | M/s Shiv Kumar Gupta | 28.01.06 | 27.04.06 | 182994 |  |  | Comp.
48 | Civil | 18.8.05 | 7.7.05 | Imp to side berm by C.C from Bara Bagar Marg to Salwan Public School in old Rajinder Nagar W.No 127 A | 154600 | EE-I | 128 | 29/05.05.06/EE-I | M/s Inder Entp. | 13.06.06 | 01.08.06 | 116278 |  |  | Comp.
49 | Civil | 20.9.05 | 29.8.05 | Imp to lane by pdg RMC from D/S 670 to D/s -681 in New Rajender Nagar C-127 A/KBZ | 343500 | EE-I | 128 | 437/03.01.06/EE-I | M/s Inder Entp. | 12.01.06 | 24.03.06 | 250920 |  |  | Comp.
50 | Civil | 20.9.05 | 29.8.05 | Imp to B/Wall of park between R- block & J-block New Rajender Nagar w.no 127 A K.B.Z | 247200 | EE-I | 128 | 550/20.03.06/EE-I | M/s Vikas Const.CO | 12.05.06 | 24.06.06 | 188567 |  |  | Comp.
51 | Civil | 20.9.05 | 15.9.05 | Imp to lane of 4 D block by C.C form 4D/13 to 4 D/48 and 4D/29 to 4D/64 in Old Rajender Nagr W.No 127 A K.B.Z. | 261300 | EE-I | 128 | 499/27.01.06/EE-I | M/s Vikas Const.CO | 27.02.06 | 13.07.06 | 183540 |  |  | Comp.
52 | Civil | 20.9.05 | 10.9.05 | Imp to back lane and front lane by pdg drainage and C.C from ,H.NO 17/11 to 17/16 in Old Rajinder Nagr in C-127 A/KBZ | 198600 | EE-I | 128 | 549/20.03.06/EE-I | M.s Amit Consts. | 29.08.06 | 04.05.09 | 111335 |  |  | Comp.
53 | Civil | 20.9.05 | 10.9.05 | Imp to drainage system and berm from Shop No-27 to Shop no 52 in Market Old Rajender Nagar C-127 A/KBZ | 161300 | EE-I | 128 | 444/09.01.06 | M/s Raj Builders | 19.01.06 | 28.03.06 | 103753 |  |  | Comp.
54 | Civil | 20.9.05 | 10.9.05 | Pdg walkway of park opp R-876 in R-block New Rajender Nagar in C-127A/KBZ | 235900 | EE-I | 128 | 433/03.01.06/EE-I | M/s Kuldeep Singh | 05.01.06 | 18.02.06 | 164057 |  |  | Comp.
55 | Civil | 20.9.05 | 10.9.05 | Imp to lane by pg RMC and drainage from H.NO D/S 685 to 697 in Double storey in New Rajender Ngar in C-127 A/KBZ | 226200 | EE-I | 128 | 503/27.01.06 | M/s Vikas Const.CO | 07.03.06 | 02.05.06 | 167423 |  |  | Comp.
56 | Civil | 18.1.05 | 19.7.05 | Resurfacing of carriageway from Behel Nursing home toB-96 in B-block Naraina in KBZ (By pdg B.M. and mix seal) | 725000 | EE-I | 128 | 52/10.02.06 | M/s Sanjeev Kumar & Bros. | 08.05.06 | 12.05.06 | 695587 |  |  | Comp.
57 | Civil | 14.11.05 | 11.11.05 | Imp to foot path by kota stone along Sindhu Samaj in Old Rajinder Nagr W.NO-127 A K.B.Z | 262800 | EE-I | 128 | 523/23.02.06 | M/s Raj Builders | 28.02.06 | 3.04.06 | 152011 |  |  | Comp.
58 | Civil | 21.11.05 | 21.11.05 | Imp to lane by c.c. and drainage from WZ-114 to 110 C in Naraina Village in C-128/KBZ | 140860 | EE-I | 128 | 472/18.01.06/EE-I | M/s Shah Builders | 15.03.06 | 05.05.06 | 95699 |  |  | Comp.
59 | Civil | 21.11.05 | 21.11.05 | Imp to lane by RMC from B-104/5 B-103 in B block NIA ( Naraina Indl Area )PH-I in C-128/KBZ | 336428 | EE-I | 128 | 511/07.02.06/EE-I | M/s Kuldeep Singh | 27.02.06 | 04.04.07 | 336281 |  |  | Comp.
60 | Civil | 21.11.05 | 21.11.05 | Imp to drainage system by open Surface drain from B-104/1 to B-103/1 in B block Naraina Indl area Ph-I in C-128/KBZ (Rs. 220464/-) |  | EE-I | 128 | Work Cancelled as desired by area MLA vide letter dated 05.02.07 and approved by CE-IV dated 29.03.07
61 | Civil | 21.11.05 | 10.9.05 | Imp to B/wall of park along pump Hs in c block Naraina vihar in W.NO 128/KBZ by pdg B/work & grit wash) | 331442 | EE-I | 128 | 514/07.02.06/EE-I | M/s Vikas Const.CO | 27.02.06 | 20.06.06 | 331300 |  |  | Comp.
62 | Civil | 1.12.05 | 11.11.05 | Const of Shed in Raj Guru park in Rajendra park W.NO-127A/ KBZ | 384500 | EE-I | 127A | 557/23.03.06/EE-I | M/s Inder Entp. | 18.05.06 | 01.07.06 | 219557 |  |  | Comp.
63 | Hort | 21.21.05 | 20.9.05 | P/F of CPA at park infront of H.no. R 616 and R 687 in New Rajinder Nagar in W.o. 127 KBZ | 109410 | ADH KBZ | 127 | 37/30.05.06 | M/s Mayur Enterprises | 30.05.06 | 12.06.06 | 109410 |  |  | Comp.
64 | Civil | 28.12.05 | 16.12.05 | Imp to lane by pdg CC and Drainage system H.no. 15/1 to 15/21 in 15-Block, Old Rajinder Nagar w.no. 127A KBZ | 287700 | EE-I | 127A | 556/23.03.06/EE-I | M/s Kishore & Co. | 20.04.06 | 12.06.06 | 205998 |  |  | Comp.
65 | Civil | 28.12.05 | 16.12.05 | Imp to lane by pdg CC and Drainage from H.n. 15/64 to 15/84 in 15 Block. Old Rajinder Nagar in W.no. 124A KBZ | 290900 | EE-I | 127A | 08/05.05.06/EE-I | M/s Raj Builders | 13.05.06 | 22.07.06 | 219175 |  |  | Comp.
66 | Civil | 2.1.06 | 12.09.05 | Imp to B/wall of I -block in Narinan Vihar in C128 KBZ by pdg B/wall, Grill near H.no. I-183. | 131400 | EE-I | 127B | 30/16.05.06/EE-(R-I) | M/s J.S Consts. | 28.07.06 | 24.08.06 | 130967 |  |  | Comp.
67 | Civil | 2.1.06 | 1.9.05 | Imp of B.wall of I block by pdg fixing Iron Grill near I 127, In I block Narain vihar, in C 128 KBZ | 170300 | EE-I | 127B | 85/02.08.06/EE-I | M/s Vikas Const.CO | 12.08.06 | 10.11.06 | 133792 |  |  | Comp.
68 | Civil | 08.03.06 | 16.12.05 | Imp of lane by pdg. C.c. and drainage from H.NO. 15/71 to 15/8 in 15-block old Rajinder Nagar in W.NO. 127/KBZ | 215500 | EE-I | 127A | 60/01.06.06/EE-I | M/s Raj Builders | 05.06.06 | 22.07.06 | 162751 |  |  | Comp.
69 | Civil | 08.03.06 | 16.12.05 | Imp of lane by pdg. C.c. and drainage from H.NO. 15/15 to 15/78 in old Rajinder Nagar in W.NO. 127A/KBZ | 222700 | EE-I | 127A | 56/01.06.06/EE-I | M/s Raj Builders | 05.06.06 | 22.07.06 | 167497 |  |  | Comp.
70 | Civil | 08.03.06 | 29.08.05 | Pdg. C.C from H.NO. WZ-133 to WZ-463 (upto end) in Dusghara Village in W.NO. 127B/KBZ | 182600 | EE-I | 127A | 45/22.05.06/EE-I | M/s Sahil Consts. | 12.07.06 | 14.08.06 | 182509 |  |  | Comp.
|  |  |  | Total | 17720497 | [6 empty] | 14018418
Remarks:- No. of works booked=70, No. of works cancelled=2

## AC-68
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06
Karol Bagh
Municipal Corporation of Delhi
|  | Name Of MLA |  | Sh. S.P. Ratwal |  |  | year 2005-06 |  | Allocation | 154.34 lacs |  | Dated:-
|  | Name of Constituency |  | Karol Bagh | AC-68
|  | Ward Nos and Names |  | 129, Bidanpura 130 Dev Nagar
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Div. | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Civil | 1.8.05 | 27.7.05 | Imp to intersection on B.C Marg W.E.A by pdg chequrred tiles in C-129 B/KBZ. | 160000 | XXIX | 129 | 125/XXIX/6.9.05 | M/S Shiv Shankar Gupta | 6.9.05 | 28.9.05 | 147536 | Camp.
2 | Civil | 1.8.05 | 27.7.05 | Imp to foot path at New Rohtak road from Faiz road to Ramjas road in C-129 A KBZ. | 396582 | XXIX | 129 | 144/28.09.05/XXIX | M/s Ved Pal Bhatia | 28.09.05 | 20.10.05 | 396440 | Comp
3 | Civil | 18.8.05 | 27.7.05 | Imp to lanes from T/2421, to, T/2405, T/2402, T/2413 to to T/2316, T/2412 to T/2402, T/2397 to T/2435 , T/2445 to T/2423 by pdg c.c. pav in Subhash Nagar in C-129 /KBZ | 406800 | XXIX | 130 A | 440/16.05.06/EE-XXIX | M/s Malhotra Const.Co | 16.02.06 | 29.03.06 | 384316 | Comp.
4 | Civil | 18.8.05 | 27.7.05 | Imp to lanes from H.No T/2424 to T/2431 . T/2506 T/2396 T,/2474 to T/2489,T/2492 To 2506,T/2477 to T/2487 by pdg c.c. pav in Subhash Nagar in C-129 A/KBZ | 436900 | XXIX | 130 A | 407/10.02.06 | M/s Raj Builders | 15.02.06 | 30.03.06 | 417716 | Comp.
5 | Civil | 18.8.05 | 27.7.05 | Imp to road by pdg C.C pav from H,No 13 a /119 to 13 a/103, 13 a/79 to 13 a/33, 13 a/71 to 13 a/41 in 13 A block WEA ( slum qtrd) in C-129 A/KBZ | 326000 | XXIX | 130 A | 430/15.02.06 | M/s Narender Singh Dhankar | 24.02.06 | 10.04.06 | 317746 | Comp.
6 | Civil | 18.8.05 | 27.7.05 | Pdg Mastic ashphalt on Hardyan Singh road at Guru Nanak Rd E-ing in c-130/KBZ | 263500 | XXIX | 130 A | 189/24.11.05/XXIX | M/s Kapoor Bros. | 05.01.06 | 18.01.06 | 254392 | Comp.
7 | Civil | 18.8.05 | 27.7.05 | Imp to road by pdg mastic on Padam Singh road & Viahnu Mandir Marg X-ing in C-130 /KBZ | 262240 | XXIX | 130 A | 187/14.11.05/XXIX | M/s D.K.Enterprises | 13.12.05 | 15.12.05 | 253587 | Comp.
8 | Civil | 18.8.05 | 27.7.05 | Imp to lane from H.No 6A/Z upto H.NO 6A/66,by pdg c.c. pav in WEA in C-129 A/KBZ | 327600 | XXIX | 129 A | 367/23.01.06 | M/s Amit Const. | 23.01.06 | 25.04.06 | 323851 | Comp.
9 | Civil | 24.8.05 | 27.7.05 | Imp to lane from H.No 8621 to Rattan Nagar by pdg c,c, flooring in c-129B | 274250 | XXIX | 129 | 204/13.11.05/XXIX | M/s Som Const.Co | 09.12.05 | 30.01.06 | 273643 | Comp.
10 | Civil | 24.8.05 | 27.7.05 | Imp to gali no -8 remaining portion by pdg c.c. pav in 5 A block WEA C-129 KBZ | 123692 | XXIX | 130 | 241/13.12.05/EE-XXIX | M/s Chirag Const.Co | 01.05.06 | 01.06.06 | 122358 | Comp.
11 | Civil | 24.8.05 | 27.7.05 | Imp to X-ing of Saraswati Marg & Arya Samaj road by pdg Mastic in C-129 | 256810 | XXIX | 130 | 153/28.09.05/XXIX | M/s Bhvuk Const.Co | 19.10.05 | 21.10.05 | 255761 | Comp.
12 | Civil | 24.8.05 | 27.7.05 | Pdg Mastic ashphalt on X-ing of Guru Ravi Das Marg and Tank road in C-130 | 256742 | XXIX | 130 | 190/24.11.05/XXIX | M/s A & N Bros. | 05.01.06 | 17.01.06 | 256394 | Comp.
13 | Civil | 24.8.05 | 27.7.05 | Pdg Mastic asphalt on X-ing of Padam Singh road and road No-4 in C-130 | 257658 | XXIX | 130 | 186/14.11.05/EE-XXIX | M/s N.C & Co. | 19.12.06 | 24.12.06 | 256779 | Comp.
14 | Civil | 24.8.05 | 27.7.05 | Imp to road by pdg Mastic Asphalt on Rattan Nagar main road opp DCM& Sr. Sec School in c-129 | 195710 | XXIX | 130 | 126/XXIX/6.9.05 | M/s Aggarwal & Co | 6.10.05 | 10.10.05 | 195601 | Comp
15 | Civil | 24.8.05 | 27.7.05 | Imp to road by pdg Mastic asphalt from New Rohtak Road towards 67 block in c-129 | 190545 | XXIX | 129 | 154/28.09.05/XXIX | M/s Balaji Associates | 14.10.05 | 18.10.05 | 190412 | Comp.
16 | Civil | 24.8.05 | 27.7.05 | Imp to foot path at Arya Samaj road from R/A to Gurudwara road in C-129A/KBZ (by pdg Chequrred tiles) | 197480 | XXIX | 129 | 149/28.09.05/XXIX | M/s Amir Const.Co | 10.11.05 | 23.12.05 | 197477 | Comp.
17 | Civil | 24.8.05 | 27.7.05 | Imp to Joshi road by pdg Metalling & premixing from H.No 847 upto Joshi Hospital in c-129 | 198927 | XXIX | 129 | 139/21.09.05 | M/s Tyagi Associates | 21.09.05 | 18.10.05 | 198728 | Comp.
18 | Civil | 24.8.05 | 27.7.05 | Imp to Joshi road by pdg metalling premixing from D.B. gupta road upto H.No 847 in C-129 A | 199572 | XXIX | 129 | 159/06.10.05/EE-XXIX | M/s J.S Const. | 16.10.05 | 08.12.05 | 198153 | Comp.
19 | Civil | 24.8.05 | 27.7.05 | Imp to faiz road by C.c. in C-129/KBZ | 268711 | XXIX | 129 | 227/07.12.05/EE-XXIX | M/s M.G.Const.Co | 16.12.05 | 08.03.06 | 268407 | Comp.
20 | Civil | 26.8.05 | 27.7.05 | Imp to road by pdg mastic from H.NO-5C/22 (Nav.Hind school ) Upto Gurdwara in C-129/B/KBZ ( on New Rohtak Road) (Rs.486100/-) | - | XXIX | 130 | Work Cancelled as desired by area MLA vide letter dated 10.10.08 and approved by CE-II dated 14.11.08
21 | Civil | 26.8.05 | 27.7.05 | Imp to walkway passage in the park behind cremation ground ( Sat Nagr ) in WEA in C-129/KBZ | 264200 | XXIX | 131 | 494/10.03.06/EE-XXIX | M/s Pawan Kumar | 15.06.06 | 25.08.06 | 169700 | Comp.
22 | Civil | 26.8.05 | 17.8.05 | Imp to road No-6 pdg mastic from round abant up to Sai Baba mandir in C-129/B K.B.Z(in Dev Nagar) | 447700 | XXIX | 132 | 314/06.01.06/EE-XXIX | M/s Star Enterprises | 27.02.06 | 02.05.06 | 343998 | Comp.
23 | Civil | 26.8.05 | 17.8.05 | Imp to Joshi road by pdg mastic from D.B.Gupta road X-ing upto gali no-18 in C-129/KBZ | 575600 | XXIX | 133 | 490/10.03.06/EE-XXIX | M/s Maman Chand Bansal | 11.01.07 | 22.02.07 | 399309 | Comp.
24 | Civil | 26.8.05 | 17.8.05 | Imp to Joshi road by pdg mastic from round abant to gali no-6 in C-129./KBZ | 592700 | XXIX | 134 | 313/06.01.06/EE-XXIX | M/s Star Enterprises | 27.02.06 | 04.05.06 | 455388 | Comp.
25 | Civil | 26.8.05 | 17.8.05 | Imp to Johsi road by pdg masic from gali NO-18 to round abant in C-129/KBZ | 588400 | XXIX | 135 | 315/06.01.06/EE-XXIX | M/s Star Enterprises | 27.02.06 | 25.04.06 | 452113 | Comp.
26 | Civil | 26.8.05 | 17.8.05 | Imp to road NO-6 by pdg mastic from Sai Baba Mandir upto X-ing D.B Gupta road in C-126 B/KBZ Dev Nagr. (Rs.469000/-) | - | XXIX | 136 | Work Cancelled as desired by area MLA vide letter dated 10.10.08 and approved by CE-II dated 14.11.08
27 | Civil | 26.8.05 | 17.8.05 | Imp to Joshi road by pdg mastic from gali NO-6 to New Rohtak road in C-129/KBZ | 597000 | XXIX | 137 | 452/24.02.06/EE-XXIX | M/s Maman Chand Bansal | 10.01.07 | 22.02.07 | 456996 | Comp.
28 | Civil | 26.8.05 | 17.8.05 | Impt o road by pdg premix carpet from X-ing Gaushala marg ( Rattan Nagar ) upto Nallah in C-129/KBZ | 260700 | XXIX | 138
29 | Elect | 13.9.05 | 27.7.05 | Pro and Installation testing & Commissioning of 16M high mast in Ajmal Khan prk infront of gangeshwar Dham in C-129 under K.BZ | 286037 | XXIX | 139 | 228/02.01.06/EE(E)-VII | M/s Himanshu Enterprises | 02.01.06 | 16.01.06 | 277857 | Comp.
30 | Civil | 13.9.05 | 27.7.05 | Impt o foot path ( remaining poriton) in Tikona park in C-130/KBZ by Red Sand stone. | 175610 | XXIX | 140 | 219/1.12.05/EEXXIX | M/sSehgal Bros | 8.12.05 | 31.1.06 | 175459 | Comp.
31 | Civil | 13.9.05 | 17.8.05 | Imp to back lane from H.NO 12 A/5 to B.C Marg & road No-10 WEA in C-129 A (by pdg C.C) | 220255 | XXIX | 141 | 143/XXIX/28.9.05 | M/s R& T Entp | 28.9.05 | 1.15.02 | 218484 | Comp
32 | Civil | 13.9.05 | 17.8.05 | Imp to X-ing of Saraswati Marg & Hardhyan Singh road by pdg mastic in C-129 | 257898 | XXIX | 142 | 209/30.11.05/XXIX | M/s Ashok Kumar Gupta | 18.01.06 | 02.02.06 | 257792 | Comp.
33 | Civil | 13.9.05 | 17.8.05 | Imp to foot path at Faiz road in C-129 A/KBZ | 174965 | XXIX | 143 | 142/28.09.05 | M/s R.S & Co. | 28.09.05 | 01.12.05 | 174867 | Comp
34 | Civil | 13.9.05 | 17.8.05 | Imp to foot path Manas Mandir on D.B Gupta road in C-129/KBZ | 67386 | XXIX | 144 | 240/13.12.05 | M/s Sanjeev Const. | 22.12.05 | 20.03.06 | 67321 | Comp.
35 | Civil | 13.9.05 | 17.8.05 | Imp to road by pdg mastic ashphalt of remaining portion in 65 block ,New Rohtak road C-129/KBZ | 160000 | XXIX | 145 | 195/24.11.05/XXIX | M/s Anil Const. | 28.11.05 | 29.11.05 | 158446 | Comp.
|  |  |  | Total | 9668170 | [6 empty] | 8517027
Remarks:- No. of works booked=35, No. of works cancelled=2

## AC-70
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06
Karol Bagh
Municipal Corporation of Delhi
|  | Name Of MLA |  | Sh Rajesh Lilothia |  |  | year 2005-06 |  | Allocation | 177.16 Lacs
|  | Name of Constituency |  | Baljeet Nagar | AC-70
|  | Ward Nos and Names |  | C-133 Kishan Ganj C-134 Anand Parvat
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Civil | 21.7.05 | 18.7.05 | Imp to drainage system and pdg c.c pavement in Basant Nagr near Hno 49 in C-133 A K.B.Z | 134107 | XXIX | 133 | 87/XXIX/3.8.05 | M/s Manish & Assoc. | 4.8.05 | 3.9.05 | 134086 | Comp.
2 | Civil | 21.7.05 | 18.7.05 | Imp to gali no 3 & 5 Bagh kare Khan by pdg c.c. pavement in c-133, K.B.Z | 141779 | XXIX | 133 | 92/XXIX/10.8.05 | M/s Shiv Kumar Gupta | 11.8.05 | 9.9.05 | 141011 | Comp.
3 | Civil | 21.7.05 | 18.7.05 | P/l c.c. pave. Along Service road Kishan Ganj Mkt. From shop NO 42 to 72 and Adj in remaing portion in C-133 B KBZ | 172435 | XXIX | 133 | 130/13.9.05 | M/s Manchanda Consts | 22.9.05 | 6.12.05 | 172371 | Comp.
4 | Civil | 21.7.05 | 18.7.05 | Imp to lane in Indl. Area Anand parbat from factory No P_10 to approach road in c-133 KBZ by pdg c.c. pavement | 172071 | XXIX | 133 | 86/XXIX | M/s Aggarwal & Co. | 5.8.05 | 31.8.05 | 172023 | Comp.
5 | Civil | 21.7.05 | 18.7.05 | P/l C.C pave along HNO 176 to 190 & 62 and Kota stone in back lane in Vivekanand puri in C-133/KBZ | 166455 | XXIX | 133 | 151/28.09.05/XXIX | M/s Bansal Consts | 07.10.05 | 06.01.06 | 164807 | Comp.
6 | Civil | 21.7.05 | 18.7.05 | P/l C.C pavement & drainage system along HNO 211/4 Padam Nagr in C-133 A /KBZ | 139713 | XXIX | 133 | 120/29.8.05 | M/s Vipin Gupta | 20.9.05 | 18.11.05 | 139034 | Comp.
7 | Civil | 21.7.05 | 18.7.05 | Imp to drainage system at Bhagat Singh road from old Rohatak road to main gate of Rama park on both side in C-133/K.BZ | 164514 | XXIX | 133 | 138/21.09.05/XXIX | M/s Som Const.CO | 30.09.05 | 21.11.05 | 163080 | Comp.
8 | Civil | 21.7.05 | 18.4.05 | pdg drainage system in Anand Parbat from Gadodea road to M.C pry School Anand Parbat (Khadewala) in C-133 B/KBZ | 141613 | XXIX | 133 | 123/29.08.05/XXIX | M/s M.G.Const.Co | 07.09.05 | 06.12.05 | 141389 | Comp.
9 | Civil | 21.7.05 | 18.4.05 | P/l drainage system at Old Rohtak road from Gita Bhawan Mandir to Gali no-2 Padam nagar in the remaining portion in c-133/KBZ | 169256 | XXIX | 133 | 88/XXIX/3.8.05 | M/s Manish & Assoc. | 4.8.05 | 31.8.05 | 167404 | Comp.
10 | Civil | 21.7.05 | 18.4.05 | P/l c.c. pavement in gali no 4 from factory NO 290/2 to 4/51 in remianing portion APIA in c-133/KBZ | 173475 | XXIX | 133 | 133/13.9.05 | M/s Kritika Const | 31.8.05 | 19.113.05 | 172666 | Comp.
11 | Civil | 1.8.05 | 20.7.05 | Imp to S.W drain by pdg RCC Slab from HNO 196/7C to turn of gali no 6 and along Satya Narayan Mandir in Jhan singh Nagr on C-134 A KBZ | 195098 | XXIX | 133 | 147/28.09.05/XXIX | M/s Ved Pal Bhatia | 03.10.05 | 22.10.05 | 193422 | Comp.
12 | Civil | 21.7.05 | 18.4.05 | Pdg Mastic Ashphaltic Concrete Surfacing from gali no 10 towards DB Gupta road on Military road in C-134 A K>B.Z | 235400 | XXIX | 133 | 132/XXIX/13.9.05 | M/s Shiv Kumar Gupta | 6.9.05 | 14.9.05 | 232909 | Comp.
13 | Civil | 1.8.05 | 18.7.05 | Const of footpath in the C.P Hostel in Tealher & lane Nai Bastic Anand Parbat in C-133 A/KBZ | 218387 | XXIX | 133 | 184/11.11.05/XXIX | M/s R & I Enterprises | 12.11.05 | 24.12.05 | 216115 | Comp.
14 | Civil | 6.10.05 | 5.10.05 | Imp to lane by C.C flooring near H.NO T-45 and T-607 J-96 and adj. In Baljeet Nagr in C-134 B/KBZ | 128412 | XXIX | 133 | 10/22.05.06 | M/s M.G.Const.Co | 24.05.06 | 27.06.06 | 127891 | Comp.
15 | Civil | 6.10.05 | 5.10.05 | Imp to lane by C.C flooring near H.NO BNB-790 and BNB 793 and Adj in Baljeet Nagr in C-134 B/KBZ | 135690 | XXIX | 134 | 402/06.02.06/EE-XXIX | M/s Shiv Kumar Gupta | 07.02.06 | 09.03.06 | 135638 | Comp.
16 | Civil | 6.10.05 | 5.10.05 | Imp to lanes by drainage System & C.C flooring near H.NO T-482/2 B , T-482/2E5 and Adj. In Baljeet Nagar in C-134/B/KBZ | 135144 | XXIX | 134 | 395/31.01.06/XXIX | M/s M.G.Const.Co | 07.02.06 | 10.03.06 | 135100 | Comp.
17 | Civil | 6.10.05 | 5.10.05 | Imp to lane by drainage system & c.c. flooring from H.NO 17/111 to H.NO 17/114 at Gali no -1 Nehru Nagr in C-134 B/KBZ | 127176 | XXIX | 134 | 406 / 6.2.06 EEXXIX | M/s Shiv Kumar Gupta | 4.3.06 | 26.03.06 | 126992 | Comp.
18 | Civil | 6.10.05 | 5.10.05 | Const of S.W drain near H.NO T-289, T-287, T-29/F and T-29/k and adj in Baljeet Nagr in c-134 B/KBZ | 175500 | XXIX | 134
19 | Civil | 6.10.05 | 5.10.05 | Imp to lanes by drainage system & C.c flooring near H.NO A t-53/1A,AR-52/2E AT-50/1 and adj in Baljeet Nagr in C-134 B/KBZ | 178369 | XXIX | 134 | 258/13.12.05/XXIX | M/s Ansal Const.Co. | 14.12.05 | 09.01.06 | 178332 | Comp.
20 | Civil | 6.10.05 | 5.10.05 | Imp to lanes by drainage system & C.C flooring near H.NO ,AT 50/1 T-1799/A and adj in Baljeet Nagar in C-134 B/KBZ | 178144 | XXIX | 134 | 259/13.12.05/XXIX | M/s Ansal Const.Co. | 14.12.05 | 09.01.06 | 178056 | Comp.
21 | Civil | 6.10.05 | 5.10.05 | Imp to lane by drainage system & C.C flooring fron H.NO 17/109 to H.NO 17/87 at Gali No-1,Nehru Nagar in C-134 A/KBZ | 163543 | XXIX | 134 | 423/10.02.06/EEXXIX | M/s Shiv Kumar Gupta | 11.2.06 | 15.03.06 | 163079 | Comp.
22 | Civil | 18.11.05 | 24.10.05 | P/l c.c. flooring on cement road from gali no-6 to teachers lane in C-133 KBZ | 462101 | XXIX | 134 | 11/22.05.06/EE-XXIX | M/s Raj Builders | 30.05.06 | 14.08.06 | 460847 | Comp.
23 | Civil | 18.11.05 | 24.10.05 | P/l c.c. flooring on lane from teachers lane to ramjas no-2 school in C-133/KBZ | 451135 | XXIX | 134 | 12/22.05.06/EE-XXIX | M/s Rakesh Bansal | 31.05.06 | 30.08.06 | 451135 | Comp.
24 | Civil | 18.11.05 | 24.10.05 | P/l cement concrete pavement from new Rohtak road to F.NO-92 in gali no -11 Anand parkbat industrial Area in C-133/KBZ | 508017 | XXIX | 134 | 13/22.05.06/EE-XXIX | M/s D.K Const.Co | 31.05.06 | 17.08.06 | 507853 | Comp.
25 | Civil | 18.11.05 | 24.10.05 | Pdg c.c. & drainage system in gali no -4 Nai Basti Anand Parbat in C-133/KBZ | 169974 | XXIX | 134 | 62/11.08.06/EE-XXIX | M/s Manish & Assoc. | 12.08.06 | 14.10.06 | 169969 | Comp.
26 | Civil | 18.11.05 | 24.10.05 | P/l C.c. pavment from Gadodia road to coal depat Anand parbat C-133/KNZ | 464734 | XXIX | 134 | 14/22.05.06/EE-XXIX | M/s Rakesh Bansal | 31.05.06 | 30.08.06 | 464360 | Comp.
27 | Civil | 18.11.05 | 24.10.05 | P/l c.c. pavement from coal depat to Ramjas pry school in Anand Parbat in C-133/KBZ | 460652 | XXIX | 134 | 15/22.05.06/EE-XXIX | M/s Rakesh Bansal | 31.05.06 | 30.08.06 | 460030 | Comp.
28 | Civil | 18.11.05 | 24.10.05 | P/l c.c. pavement from Ramjas Prymary School to Ramjas Public Nursury deptt. In Anand Parbat in C-133 KBZ | 455573 | XXIX | 134 | 71/28.08.06/EE-XXIX | M/s Tyagi Associates | 29.08.06 | 06.12.06 | 455573 | Comp.
29 | Civil | 18.11.05 | 24.10.05 | P/l c.c. pavement from Ramjas Nursury deptt. Towards faridpuri in Anand Parbat in C-133/KBZ | 452851 | XXIX | 134 | 72/28.08.06/EE-XXIX | M/s Tyagi Associates | 29.08.06 | 06.12.06 | 452851 | Comp.
30 | Civil | 24.11.05 | 14.11.05 | P/l cement concrete pavementalong Auto kinks starting from New Rohtak Rd Service road towards Railway line in Harijan Basti in C-133 K.B.Z | 230910 | XXIX | 134 | 16/22.05.06/EE-XXIX | M/s Shah Builders | 31.05.06 | 30.08.06 | 226093 | Comp.
31 | Civil | 6.1.06 | 24.12.05 | Imp to lane by Drainge ssytem in Gali NO. 10, Than Singh Nagar in C 134A KBZ | 386462 | XXIX | 134A | 17/22.05.06/EE-XXIX | M/s Bansal Enterprises | 25.05.06 | 31.07.06 | 386065 | Comp.
32 | Civil | 6.1.06 | 24.12.05 | Imp0 to lanes by Drainag system and CC flooring near H.no. 660/7, 657/3 and adj in Gail No. 1, Punjabi Basti Anand parbat in C 134A KBZ | 304990 | XXIX | 134A | 18/22.05.06/EE-XXIX | M/s Bansal Enterprises | 06.06.06 | 28.07.06 | 303683 | Comp.
33 | Civil | 6.1.06 | 24.12.05 | Imp to lane sby Drainage system in Gali no 2 Than Singh Nagar inC 134A KBZ | 227992 | XXIX | 134A | 08/12.05.06 | M/s Harish Kumar | 19.05.06 | 24.07.06 | 227755 | Comp.
34 | Civil | 6.1.06 | 24.12.05 | Imp to lane by Drainage system in Gali no. 1, Than Singh Nagar in C 134A KBZ | 246057 | XXIX | 134A | 09/12.05.06 | M/s Harish Kumar | 19.05.06 | 24.07.06 | 245934 | Comp.
35 | Civil | 6.1.06 | 24.12.05 | Imp to lanes by Drainage system in Gali no 11, Than singh Nagar in C 134A KBZ | 517800 | XXIX | 134A | 19/22.05.06/EE-XXIX | M/s Shah Builders | 26.05.06 | 28.08.06 | 367773 | Comp.
36 | Civil | 20.03.06 | 18.07.05 | P/F Grill/Barbed fencing out the To wall at Park Anand Parbat in C-133/KBZ | 63100 | XXIX | 134A | 07/12.05.06/EE-XXIX | M/s Markanda Consts. | 22.05.06 | 21.08.06 | 62889 | Comp.
|  |  |  | Total | 8848629 | [6 empty] | 8498215
Note on J46: R.P.S