## Smt.Anjali Rai
STATUS REPORT OF MLA FOR THE YEAR 2005-06 UPTO 16.11.07
Municipal Corporation of Delhi
S.P.ZONE
|  | Name Of MLA |  | Smt Anjali | AC-57 |  | year 2005-06 |  | Allocation | 100
|  | Name of Constituency |  | Paharganj
|  | Ward Nos and Names |  | C-108 , PaharGauj C-107, Bazar Sita Ram
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Div. | W.no | Work order no with date | Name of Agency | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14
1 | Civil | 1.12.05 | 1.12.05 | Imp of gail Fazal Hussain & its lane by CC Pv in C 107 SPZ | 190491 | EE-III | 107 | 414/29.12.05/EE-III | M/s Deepak Kumar | 10.01.06 | 09.03.06 | 190372 |  |  | Comp.
2 | Civil | 1.12.05 | 1.12.05 | Imp to rd from Slum store to GB Road school by CC pav in C 107 SPZ | 183376 | EE-III | 107 | 418/29.12.05/EE-III | M/s V.K.Associates | 28.12.05 | 25.01.06 | 183203 |  |  | Comp.
3 | Civil | 1.12.05 | 1.12.05 | Imp top gali Ravi dass and its adj lanes by CC pav in C 107, SPZ | 198327 | EE-III | 107 | 528/03.03.06/EE-III | M/s Rajesh Const.Co | 07.03.06 | 20.04.06 | 198287 |  |  | Comp.
4 | Civil | 1.12.05 | 1.12.05 | Imop to gali Jaungli Kauan and its adj lanes by CC pav in C 107 Spz | 199032 | EE-III | 107 | 450/24.01.06/EE-III | M/s Puneet Nayyar | 08.02.06 | 04.04.06 | 198434 |  |  | Comp.
5 | Civil | 1.12.05 | 1.12.05 | Imp to FP by pdg Iterlcokcing tiles at hauz Qauji to Chori walan Chowk in C 107 SPZ | 196592 | EE-III | 107 | 408/29.12.05/EE-III | M/s Bajaj Const.Co. | 10.01.06 | 25.03.06 | 196419 |  |  | Comp.
6 | Civil | 1.12.05 | 1.12.05 | Impt to gali Phatak Teleiyan and its adj lanes by CC pav in C 107 SPZ | 198748 | EE-III | 107 | 398/19.12.05/EE-III | M/s Som Dutt Duevedi | 28.12.05 | 06.02.06 | 198145 |  |  | Comp.
7 | Civil | 1.12.05 | 1.12.05 | Imo to gali Sapru rd its adj lanes by CC Pav in C 107 SPZ | 195215 | EE-III | 107 | 458/24.01.06/EE-III | M/s Manish Nayyar | 08.02.06 | 15.04.06 | 195058 |  |  | Comp.
8 | Civil | 1.12.05 | 1.12.05 | Imp tord from Turkman Gate to towards Uchi Masjid by CC pav in C 107 SPZ | 195745 | EE-III | 107 | 547/20.03.06/EE-III | M/s Rajesh Const.Co | 17.04.06 | 22.05.06 | 195654 |  |  | Comp.
9 | Civil | 1.12.05 | 1.12.05 | Imp to lanes from Bazar Sita Ram road to Anuuman chowk by CC Pav in C 107 SPZ | 191113 | EE-III | 107 | 405/22.11.06/EE-III | M/s Prem Const.Co | 24.11.06 | 28.01.07 | 191077 |  |  | Comp.
10 | Civil | 1.12.05 | 1.12.05 | Imp to gali Bansi Koyala and Uchi masjid by pdg Interlocking tiles in C 107 SPZ | 178542 | EE-III | 107 | 449/24.01.06/EE-III | M/s Puneet Nayyar | 08.02.06 | 04.04.06 | 178437 |  |  | Comp.
11 | Civil | 1.12.05 | 1.12.05 | Imp to gali Lajpat and its ajd lanes by CC pav in C 107 SPZ | 196609 | EE-III | 107 | 445/19.01.06/EE-III | M/s Arya & Co | 10.02.06 | 25.03.06 | 196276 |  |  | Comp.
12 | Civil | 1.12.05 | 1.12.05 | Imp to roads from Dispensary to MC Pry school (Chori walan) by pdg CC Pav in C 107 SPz | 196996 | EE-III | 107 | 413/29.12.05/EE-III | M/s Deepak Kumar | 10.01.06 | 23.03.06 | 196870 |  |  | Comp.
13 | Civil | 6.12.05 | 6.12.05 | Imp to gali katra Sharif Bagh by pdg CC Bazar Sita Ram in C 108 SPZ | 192600 | EE-III | 108 | 401/21.12.05/EE-III | M/s Ved Pal Bhatia | 26.12.05 | 22.02.06 | 192025 |  |  | Comp.
14 | Civil | 6.12.05 | 6.12.05 | Imp to lane by pdg CC from Shop NO. 700 to 731 side by lane in Kundawalan in C 108 SPZ | 198400 | EE-III | 108 | 406/29.12.05/EE-III | M/s Bajaj Const.Co. | 31.12.05 | 24.02.06 | 197823 |  |  | Comp.
15 | Civil | 6.12.05 | 6.12.05 | Imp to gali Shish Mahal by pdg CC in Kucha Patti Ram in C 108 SPZ | 190600 | EE-III | 108 | 453/24.01.06/EE-III | M/s Neel Traders | 03.02.06 | 17.04.06 | 190189 |  |  | Comp.
16 | Civil | 6.12.05 | 6.12.05 | Imp to Gali Kashimiriyan & Mohalla Imli From H.no. 1945 to 834 by pdg CC in Kucha Pati Ram I C 108 SPZ | 195700 | EE-III | 108 | 447/24.01.06/EE-III | M/s Manish Nayyar | 03.02.06 | 22.04.06 | 194188 |  |  | Comp.
17 | Civil | 6.12.05 | 6.12.05 | Imp to lane by CC Hotel PG To Community Centre at Kucha Pati Ram in C 108 SPZ | 194700 | EE-III | 108 | 407/29.12.05/EE-III | M/s Bajaj Const.Co. | 30.12.05 | 20.02.06 | 194221 |  |  | Comp.
18 | Civil | 6.12.05 | 6.12.05 | Imp to gali Lodhan by pdg CC from H.no. 552 to 647 and adj lanes b Kucha Pati Ram in C 108 SPZ | 191900 | EE-III | 108 | 396/19.12.05/EE-III | M/s Som Dutt Duevedi | 21.12.05 | 22.02.06 | 191471 |  |  | Comp.
19 | Civil | 6.12.05 | 6.12.05 | Imp to lane by CC from Hotel Dhawni to 3214 in Pahar Ganj in C 108 SPZ | 195400 | EE-III | 108 | 464/24.01.06/EE-III | M/s Deepak Kumar | 30.01.06 | 23.03.06 | 194736 |  |  | Comp.
20 | Civil | 6.12.05 | 6.12.05 | Imp to lane by CC Shop no. 3 to Pergo Behind Thapar Chamber at Pahar Ganj in C 108 SPZ | 194900 | EE-III | 108 | 443/19.01.06/EE-III | M/s Arya & Co | 06.02.06 | 28.05.06 | 194306 |  |  | Comp.
21 | Civil | 6.12.05 | 6.12.05 | Imp to gali Bandook wali by pdg CC pav at Ajmeiri Gate in C 108 SPZ | 195300 | EE-III | 108 | 454/24.01.06/EE-III | M/s Neel Traders | 30.01.06 | 28.04.06 | 194960 |  |  | Comp.
22 | Civil | 6.12.05 | 6.12.05 | Imp to lane by pdg CC from 731 to 792 and 782 to 782A in Kundein walan in C 108 SPZ | 199000 | EE-III | 108 | 422/05.01.06/EE-III | M/s Sumit Const.Co | 12.01.06 | 30.03.06% | 198812 |  |  | Comp.
23 | Civil | 6.12.05 | 6.12.05 | Imp to gali Inder Wali by CC from Hn.o. 913 to 924 and adj lanes from Kucha Pati Ram in C 108 SPZ | 196400 | EE-III | 108 | 399/21.12.05/EE-III | M/s Ved Pal Bhatia | 28.12.05 | 25.02.06 | 196007 |  |  | Comp.
24 | Civil | 6.12.05 | 6.12.05 | Imp to lane by pdg CC from 664 to 606 ad side by lanes in Kucha Pati Ram in C 108 SPZ | 197700 | EE-III | 108 | 549/24.01.06/EE-III | M/s Prem Const.Co | 25.01.06 | 26.04.06 | 196870 |  |  | Comp.
25 | Civil | 6.12.05 | 6.12.05 | Imp to lane by pdg CC from H.no. 747 to Atma Ram School and Atma Ram School to Urinial Block in Kundewalan in C 108 SPZ | 195100 | EE-III | 108 | 421/05.01.06-EE-III | M/s Prem Const.Co | 10.01.06 | 25.03.06 | 194608 |  |  | Comp.
26 | Civil | 6.12.05 | 6.12.05 | Imp to lane by pdg CC from 550 to 505 and adj lanes in Kucha Pati Ram in C 108 SPz | 191600 | EE-III | 108 | 548/20.03.06/EE-III | M/s Rajesh Const.Co | 22.03.06 | 26.06.06 | 190969 |  |  | Comp.
27 | Civil | 6.12.05 | 6.12.05 | Imp to lane by pdg CC from 827 to 550 in Kucha Pati Ram in C 108 SPZ | 199300 | EE-III | 108 | 452/24.01.06/EE-III | M/s Essco Traders | 25.01.06 | 28.04.06 | 198540 |  |  | Comp.
28 | Civil | 8.12.05 | 8.12.05 | Impt o lane by Pdg CC from 505 to Sita Ram Bazar and Gali Nai Basti in Kucha Pati Ram in C 108 SPZ | 192800 | EE-III | 108 | 457/24.01.06/EE-III | M/s Manish Nayyar | 06.02.06 | 29.04.06 | 192244 |  |  | Comp.
29 | Civil | 8.12.05 | 8.12.05 | Imp to lane by CC from 3240 to 3259 behind Commuinty Centre at Pahar ganj in C 108 SPZ | 191500 | EE-III | 108 | 465/24.01.06/EE-III | M/s Deepak Kumar | 27.01.06 | 24.03.06 | 191077 |  |  | Comp.
30 | Civil | 8.12.05 | 8.12.05 | Imp to lane by cC from Gupta Traders to D B Gupta road behind Thapar Chambers at Pahar Ganj in C 108 SPZ | 194500 | EE-III | 108 | 417/29.12.05/EE-III | M/s V.K.Associates | 30.12.05 | 10.03.06 | 193820 |  |  | Comp.
31 | Civil | 8.12.05 | 7.12.05 | Imp of road from narang road ways Shop to Jai Ambe Resturant by pdg CC pav at SN Marg in C 107 SPZ | 199440 | EE-III | 107 | 415/29.12.05/EE-III | M/s V.K.Associates | 07.02.06 | 06.03.06 | 199440 |  |  | Comp.
32 | Civil | 8.12.05 | 7.12.05 | Imp to road from CSE store to dispensary (MCD) by pdg CC pavment and near GB Road in C 107 SPZ | 199871 | EE-III | 107 | 400/21.12.05/EE-III | M/s Ved Pal Bhatia | 28.12.05 | 16.02.06 | 199635 |  |  | Comp.
33 | Civil | 8.12.05 | 7.12.05 | Imp to road from Transformer to Ashok Traderes and Engineers by prd CC pav in Ajmeri Gate in C107 SPZ | 199617 | EE-III | 107 | 394/19.12.05/EE-III | M/s Som Dutt Duevedi | 28.12.05 | 06.02.06 | 199473 |  |  | Comp.
34 | Civil | 8.12.05 | 7.12.05 | Imp of road from Nath Brothers to Fawaz Medical Centre by pdg CC pav at in C 107 SPZ | 199783 | EE-III | 107 | 460/24.01.06/EE-III | M/s Neel Traders | 08.02.06 | 10.04.06 | 199656 |  |  | Comp.
35 | Civil | 8.12.05 | 7.12.05 | Imp of road from Shop no. 4577 to 4566 (Community Centre) by CC pav in Mohala shatava in C 107 SPZ | 194378 | EE-III | 107 | 423/05.01.06/EE-III | M/s Prem Const.Co | 09.01.06 | 25.03.06 | 194330 |  |  | Comp.
36 | Civil | 8.12.05 | 7.12.05 | imp to road by Ratan Kumar to Harshika Communication shop by CC Pav in Bazar Sita Ram in C 107 SPZ | 196227 | EE-III | 107 | 442/19.01.06/EE-III | M/s Arya & Co | 07.02.06 | 29.03.06 | 195774 |  |  | Comp.
37 | Civil | 8.12.05 | 7.12.05 | Imp of road from PIO to Bharat Oil Depot Shop by pdg CC pav in Kucha Pandit in C 107 SPZ | 195323 | EE-III | 107 | 451/24.01.06/EE-III | M/s Essco Traders | 10.2.06 | 08.04.06 | 195243 |  |  | Comp.
38 | Civil | 8.12.05 | 7.12.05 | Imp to road opoosite Hauz Qazi Poilce Station by Pdg CC Pav at Hauz Qazi in C 107 SPZ | 193186 | EE-III | 107 | 448/24.01.06/EE-III | M/s Puneet Nayyar | 10.02.06 | 07.04.06 | 193104 |  |  | Comp.
39 | Civil | 8.12.05 | 7.12.05 | Imp to gali Vakil by pdg CC in Kucha Pandit in C 107 SPZ | 198332 | EE-III | 107 | 437/12.01.06/EE-III | M/s Rajesh Const.Co | 10.01.06 | 10.03.06 | 198332 |  |  | Comp.
40 | Civil | 8.12.05 | 7.12.05 | Imp of orad from Katra Dina Nath Sita Ram Bazar towards Shop Multe Beds 2038 by pdg CC Pav in C 107 SPZ | 197046 | EE-III | 107 | 424/05.01.06/EE-III | M/s Sumit Const.Co | 08.01.06 | 25.03.06 | 196914 |  |  | Comp.
41 | Civil | 8.12.05 | 7.12.05 | Imp of road between GB Road and Fazil road by pdg CC pav in C 107 SPZ | 179145 | EE-III | 107 | 409/29.12.05/EE-III | M/s Bajaj Const.Co. | 10.01.06 | 25.03.06 | 179098 |  |  | Comp.
42 | Civil | 8.12.05 | 7.12.05 | Imo its side brems at Hauz Qazi Chowk nerar Metro Station by pdg CC pav in C 107 SPZ | 185833 | EE-III | 107 | 395/19.12.05/EE-III | M/s Som Dutt Duevedi | 28.12.05 | 06.02.06 | 185532 |  |  | Comp.
43 | Civil | 8.12.05 | 7.12.05 | Imp to gali NalBadhab by pdg CC pav at Shahganh in C 107 SPZ | 198448 | EE-III | 107 | 416/29.12.05/EE-III | M/s V.K.Associates | 07.02.06 | 27.02.06 | 197879 |  |  | Comp.
44 | Civil | 8.12.05 | 7.12.05 | Imp of road from Metro Hardware to AN Welding and Machine by pdg CC pav in Ajmeri Gate in C 107 SPZ | 198611 | EE-III | 107 | 444/19.01.06/EE-III | M/s Arya & Co | 10.02.06 | 25.03.06 | 198503 |  |  | Comp.
45 | Civil | 8.12.05 | 8.12.05 | Imp to gali Bari wali from H.no. 895 to 1124 Kucha Herjasmal and adj lnaes by pdg CC in C 108 SPZ | 199900 | EE-III | 108 | 456/24.01.06/EE-III | M/s Essco Traders | 02.02.06 | 20.04.06 | 199381 |  |  | Comp.
46 | Civil | 8.12.05 | 8.12.05 | Imp to lane by pdg CC from H.no. 1945 to 1126 Kucha Harjasmal and adj lanes in C 108 SPZ | 192600 | EE-III | 108 | 455/24.01.06/EE-III | M/s Manish Nayyar | 02.02.06 | 20.04.06 | 192259 |  |  | Comp.
47 | Civil | 28.12.05 | 9.9.05 | Imp to lane by pdg CC from 3885 to 4089 in Kesru Walan in C 108 SPZ | 305500 | EE-III | 108 | 95/12.05.06/EE-III | M/s Sonu Builders | 21.05.06 | 06.10.06 | 223858 |  |  | Comp.
48 | Civil | 28.12.05 | 9.9.05 | Imp to lane by pdg CC from 4060 to Sr. Sec school in Kesruwalan at C 108 SPZ | 309100 | EE-III | 108 | 594/31.03.06/EE-III | M/s Ved Pal Bhatia | 04.04.06 | 22.05.06 | 225375 |  |  | Comp.
49 | Civil | 28.12.05 | 9.9.05 | Imp ot lane by pdg CC from 8952 to 8932 in Multani Dhanda in C 108 SPZ | 318700 | EE-III | 108
50 | Civil | 28.12.05 | 9.9.05 | Imp ot lane by pdg CC from H.no. 9140 to 9149 in Multani Dhanda in C 108 SPZ | 298200 | EE-III | 108
51 | Civil | 28.12.05 | 9.9.05 | Imp to lane by pdg CC from 8826 to 8855 in Multani Dhanda in C 108 SPZ | 291300 | EE-III | 108 | 672/09.02.07/EE-III | M/s Islam-uddin | 05.02.07 | 30.03.07 | 212975 |  |  | Comp.
52 | Civil | 28.12.05 | 9.9.05 | Imp to lane by pdg CC from 9107 to 9078 in Multani Dhanda in C 108 SPZ | 296600 | EE-III | 108 | 670/09.02.07/EE-III | M/s Islam-uddin | 12.02.07 | 21.03.07 | 216089 |  |  | Comp.
53 | Civil | 28.12.05 | 9.9.05 | Imp to lane by pdg C from H.no. 8923 to 8897 in Multani Dhanda in C 108 SPZ | 307300 | EE-III | 108 | 595/31.03.06/EE-III | M/s Ved Pal Bhatia | 03.04.06 | 20.05.06 | 224245 |  |  | Comp.
54 | Civil | 28.12.05 | 9.9.05 | Imp to lane by pdg CC from 8329 to 8299 in Multani Dhanda in C 108 SPZ | 308900 | EE-III | 108 | 25/08.05.06/EE-III | M/s Sehgal Contractors | 15.05.06 | 04.07.06 | 225153 |  |  | Comp.
55 | Civil | 31.03.06 | 20.12.05 | Imp of lane by pdg cc from Quality Hotel to elect. Transformer, in W.no 108 SP Zone | 323300 | EE-III | 108 | 208/11.08.06/EE-III | M/s Sonu Builders | 11.08.06 | 06.10.06 | 236345 |  |  | Comp.
56 | Civil | 31.03.06 | 20.12.05 | Imp to shahganj road from G.B.Road to gali Masjid wali by pdg Mastic in W.no 107/SPZ | 597500 | EE-III | 107 | 821/28.03.07/EE-III | M/s Arora Const.Co | 28.04.07 | 20.06.07 | 597500 |  |  | Comp.
57 | Civil | 31.03.06 | 20.12.05 | Imp to road from Himmat Garj upto gali Shankar School by pdg Mastic in W.no 107/SPZ | 598400 | EE-III | 107 | 645/05.02.047/EE-III | M/s Arora Const.Co | 08.03.07 | 16.04.07 | 557994 |  |  | Comp.
58 | Civil | 31.03.06 | 05.12.05 | Imp to lane by pdg cc from Hotel nest to Kabeer to Hotel M.Shine In W.no 108/SPZ | 304600 | EE-III | 108 | 252/07.09.06/EE-III | M/s Kalra Const. | 24.08.06 | 30.11.06 | 222454 |  |  | Comp.
59 | Civil | 31.03.06 | 05.12.05 | Imp to lane by pdg cc in gali Ram Nath Patwa in C-108/SPZ | 287000 | EE-III | 108 | 122/01.06.06/EE-III | M/s Ved Pal Bhatia | 05.06.06 | 02.08.06 | 206918 |  |  | Comp.
60 | Civil | 31.03.06 | 21.12.05 | Imp to lane by pdg cc from 8307 to 8375 in Multani Dhanda in C-108/SPZ | 287500 | EE-III | 108 | 116/01.06.06/EE-III | M/s Ganesh Builders | 02.06.06 | 12.07.06 | 222337 |  |  | Comp.
|  |  |  | Total | 13789826 | [6 empty] | 12310894

## Sh. Rajesh jain
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06 UPTO 16.11.07
Municipal Corporation of Delhi
S.P.ZONE
|  | Name Of MLA |  | Sh Rajesh Jain | AC-64 |  | year 2005-06 |  | Allocation | 100
|  | Name of Constituency |  | Sadar Bazazr
|  | Ward Nos and Names |  | C-121 Subzi Mandi C-122, Sadar Bazazr
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agency | D.O.S. As per | D.O.C. As per | First Running | Second running | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  | 13 | 16
1 | Civil | 5.7.05 | 4.7.05 | Imp to road by P/L c.c. from Bara Hindu Rao xing to Nai Bastic at P.D. road in W.No 122 A/S.PZ | 183372 | EE-III | 122 A | 257/8.8.05 | M/s Islmuddin | 23.06.05 | 13.9.05 |  |  | 183251 | Comp.
2 | Civil | 5.7.05 | 4.7.05 | Imp to road by P/L C.C. From Police booth to BSES Transformer Sheesh Mahal Hathi Khana at B.G. road in W.NO 122 A/S.P.Z | 181562 | EE-III | 122 A | 256/8.8.05 | M/s Islmuddin | 23.06.05 | 13.9.05 |  |  | 181419 | Comp.
3 | Civil | 29.7.05 | 26.7.05 | Imp to round about providing marble stone flooring at Roshanara road in C-121/S.PZ | 155959 | EE-III | 121 | 531/03.03.06/EE-III | M/s Shree Mahadev Builders | 06.03.06 | P |  |  | 118575 | In Prog.
4 | Civil | 29.7.05 | 26.7.05 | Imp of round about by providing red stand stone flooring at Sanjay Nagar road in C-121 B SPZ | 157478 | EE-III | 121-B | 387/14.12.05/EE-III | M/s D.K.Const.Co | 19.12.05 | 23.03.06 |  |  | 157283 | Comp.
5 | Civil | 29.7.05 | 26.7.05 | Imp to fountain by pdg Marble stone flooring at Roshanara Roundabout Circle in C-121 SPZ | 153178 | EE-III | 121 | 532/03.03.06/EE-III | M/s Shree Mahadev Builders | 06.03.06 | 10.06.06 |  |  | 152597 | Comp.
6 | Civil | 29.7.05 | 26.7.05 | Imp to PVT Katra No 3577 in Gali Bonwali & P/L c.c. at 3566 gali Hanuman At G.T. road in C-121 A SZP | 181074 | EE-III | 121 | 847/28.03.07/EE-III | M/s United Const.Co. | 15.05.07 | 06.07.07 |  |  | 180567 | Comp.
7 | Civil | 29.7.05 | 4.7.05 | Imp to road by P/l c.c. pavement in gali Bahuji in W.No -122 SPZ | 183310 | EE-III | 122 | 80/31.05.05 | M/s Islmuddin | 25.6.05 | 5.9.05 |  |  | 183171 | Comp
8 | Civil | 9.8.05 | 4.7.05 | Imp to pav block & Marble flooring in chowk and water fiting & imp to entreace gate Kartr (p) 4418 Chatterpartap singh gali Bahuji in W.No 122 A SPZ | 323113 | EE-III | 122A | 293/08.09.05/EE-III | M/s.Som Dutt Duevedi | 08.9.05 | 16.12.05 |  |  | 323013 | Comp.
9 | Civil | 7.10.05 | 4.10.05 | Imp to Pvt. Katra No 3244,3248 in Arya pura & Imp to Pvt No 7821 in Maula Bux at R.A . Road in C-121/SPZ(by pdg c.c. & drainge system) SPZ | 295575 | EE-III | 121 | 29/08.05.06/EE-III | M/s D.K.Const.Co | 10.05.06 | 28.06.06 |  |  | 295158 | Comp.
10 | Civil | 7.10.05 | 4.10.05 | Imp to lane by providing c.c. from Ladha Rajput Chopal to Baba Balalknath Temple in Arya pura in C-121 A/SPZ | 346660 | EE-III | 121A | 868/30.03.07/EE-III | M/s J.P Const.CO | 29.03.07 | 07.05.07 |  |  | 346255 | Comp.
11 | Civil | 7.10.05 | 4.10.05 | Imp to lane by providing c.c from Mata Mandir Chowk Balmiki Baba to Baba Balaknath temple in C-121/SPZ | 237932 | EE-III | 121 | 251/07.09.06/EE-III | M/s J.P Const.CO | 15.09.06 | 10.11.06 |  |  | 237386 | Comp.
12 | Civil | 24.10.05 | 23.10.05 | P/L C.C pavement from H.No 4456 to 4430 in gali Hera Wali in W.No-121 A/SPZ | 220276 | EE-III | 121 A | 523/20.02.06/EE-III | M/s R.P.Enterprises | 20.02.06 | 16.03.06 |  |  | 219568 | Comp.
13 | Civil | 23.11.05 | 30.8.05 | P/L CC in gali Bagchee Acheegi in Bara Hindu Rai in W.no. 122A SP | 199595 | EE-III | 122 A | 467/24.01.06/EE-III | M/s Rajesh Const.Co. | 25.01.06 | 25.03.06 |  |  | 199386 | Comp.
14 | Civil | 25.11.05 | 22.11.05 | Imp ot road surface to the road by MP at old Rohtak Rd near Azad mkt in w.no. 122B SPZ | 187200 | EE-III | 122 B | 403/23.12.05/EE-III | M/s Essco Traders | 28.12.05 | 30.01.06 |  |  | 186924 | Comp.
15 | Civil | 5.12.05 | 14.11.05 | Imp to lab block of qtrw no. 193 to 216 in Vasudev nagar in C 121 A (By pdg CC and Ceramic Tiles etc) SPZ | 216800 | EE-III | 121 A | 487/02.02.06/EE-III | M/s M.C.Aren | 02.02.06 | 11.03.06 |  |  | 216762 | Comp.
16 | Civil | 5.12.05 | 14.11.05 | Imp to CC flooring from H.no. 1781 to 1790 in Ram Gali andadj lanes in Pahar ganj C 121 SPZ | 230977 | EE-III | 121 | 486/02.02.06/EE-III | M/s M.C.Aren | 02.02.06 | 11.03.06 |  |  | 230939 | Comp.
17 | Civil | 19.12.05 | 19.12.05 | Imp to lane by P/L CC from H>no. 10884 to 10879 and 10913 to 10915 at Amrit Puri in C 121A SPZ | 197800 | EE-III | 121A | 426/12.01.06/EE-III | M/s.Bajaj const.co. | 13.02.06 | 08.02.06 |  |  | 197190 | Comp.
18 | Civil | 19.12.05 | 19.12.05 | IIMp to lane by pdg Lying CC from H.no. 10861 to 1086 and 10916 to 10917 in Amrit Puri in C 121A SPZ | 199100 | EE-III | 121A | 427/12.01.06/EE-III | M/s V.K.Associates | 13.01.06 | 13.03.06 |  |  | 198460 | Comp.
19 | Civil | 19.12.05 | 19.12.05 | Imp to lane by pdg cc from Katra NO. 1818 in Anar Kothi at Malka Ganj in C 121A SPZ | 199130 | EE-III | 121A | 591/31.03.06/EE-III | M/s Sumit Const.CO. | 18.04.06 | 28.06.06 |  |  | 198664 | Comp.
20 | Civil | 19.12.05 | 19.12.05 | Imp to lane by P/L CC in gali Kumar Wali H.no. 1985 to 1989 at Malka ganj rd in C 121A SPZ | 199300 | EE-III | 121A | 461/24.01.06/EE-III | M/s Essco Traders | 28.01.06 | 29.05.06 |  |  | 198939 | Comp.
21 | Civil | 19.12.05 | 19.12.05 | Imp to lane by P/L CC in gali Mitra H.no. 4516 to 4509 at Arya Pura in C 121A SPZ | 198742 | EE-III | 121A | 439/19.01.06/EE-III | M/s Rajesh Const.Co. | 20.01.06 | 15.04.06 |  |  | 197608 | Comp.
22 | Civil | 19.12.05 | 19.12.05 | Imp to lane by P/L CC in gali Dharamshala wali H.no. 1388 to 1597 in Shora Kothi in C 121A SPZ | 197200 | EE-III | 121A | 436/12.01.06/EE-III | M/s Prem Const.Co. | 20.01.06 | 20.03.06 |  |  | 196820 | Comp.
23 | Civil | 19.12.05 | 19.12.05 | Imp to lane by P/L CC in gali Jai Puria mIll H.no. 1175 to 1147 at Shora Kothi in C 121A SPZ | 195880 | EE-III | 121A | 504/07.02.06/EE-III | M/s Vedpal Bhatia | 07.02.06 | 10.05.06 |  |  | 195396 | Comp.
24 | Civil | 19.12.05 | 19.12.05 | Imp to lane by P/L CC gali no. 18 Amrit PURi from H.no. 265 to 280 and 217 to 231 in C 121A SPZ | 198000 | EE-III | 121A | 462/24.01.06/EE-III | M/s Essco Traders | 30.01.06 | 29.05.06 |  |  | 197438 | Comp.
25 | Civil | 19.12.05 | 17.12.05 | P/L CC from Shop NO. 9 to Nashta Corner in Gali no. 2 in Hathi Khana in C 122 SPZ | 199936 | EE-III | 122 | 433/12.01.06/EE-III | M/s Punit Nayyar | 15.01.06 | 28.03.06 |  |  | 199422 | Comp.
26 | Civil | 19.12.05 | 17.12.05 | P/L CC in lanes from 10307 to 10321, 10322 to 10325 and 9398 to 9405 at Tokri walan in C 122B SPZ | 146447 | EE-III | 122B | 435/12.01.06/EE-III | M/s Deepak Kumar | 03.02.06 | 07.03.06 |  |  | 146447 | Comp.
27 | Civil | 19.12.05 | 17.12.05 | P/L CC from 1583-84 and 1622 to 1600 in gali no. 1 Hathi Khara in C 122 SPZ | 199502 | EE-III | 122 | 430/12.01.06/EE-III | M/s Neel Traders | 15.01.06 | 28.03.06 |  |  | 199471 | Comp.
28 | Civil | 19.12.05 | 17.12.05 | P/L CC Pav in gali Med wali from 9525 to 9578 and 9599 to 9611 to Tokri Walan in C 122B SPZ | 185176 | EE-III | 122 | 431/12.01.06/EE-III | M/s Rajesh Const.Co. | 27.01.06 | 11.04.06 |  |  | 183940 | Comp.
29 | Civil | 19.12.05 | 17.12.05 | P/L CC pav in Gali Ram Gali from 9230 to 9244 and 9508 at Tokri Walan IN C 122B SPZ | 104169 | EE-III | 122 B | 434/12.01.06/EE-III | M/s Manish Nayyar | 31.01.06 | 31.03.06 |  |  | 103573 | Comp.
30 | Civil | 19.12.05 | 17.12.05 | Imp the road from 93055 to 9484 gali Dorwali 9276 to 9279 behind Mandir and 9256 to 9258 gali Mata Wali by pdg CC Tokri Walan in C 122B SPZ | 176766 | EE-III | 122 B | 432/12.01.06/EE-III | M/s Sumit Const.CO. | 13.01.06 | 24.03.06 |  |  | 176153 | Comp.
31 | Elect | 20.12.05 | 1.12.05 | P/O Lighting arrangment at Round about Roshan pura road under SP Z | 195264 | EEE-I | 121 | 263/27.03.06/EE(E)-I | M/s Repair Shop | 06.04.06 | 22.04.06 |  |  | 134535 | Comp.
32 | Elect | 20.12.05 | 1.12.05 | P/O street lighting arrangment in lanes of Sadar Bazar and Subzi Mandi in W.no. 121 & 122 SPZ | 199986 | EEE-I | 121 & 122 | 256/24.03.06/EE(E)-I | M/s S.K Enterprises | 02.04.06 | 25.05.06 |  |  | 131620 | Comp.
33 | Civil | 27.12.05 | 26.12.05 | pdg laying CC Pavyment from shop no. 1 to 6 and H.no. 1 to 6 in Lehna singh Mkt at RA Road C 121A SPZ | 199360 | EE-III | 121 A | 491/02.02.06/EE-III | M/s Arya & Co. | 14.02.06 | 27.03.06 |  |  | 198817 | Comp.
34 | Civil | 28.12.05 | 28.12.05 | P/L CC in gali Aziz ganj in Hathi Khana in W.n. 122B SPZ | 90000 | EE-III | 122 B | 469/30.01.06/EE-III | M/s Bajaj Const.Co | 09.02.06 | 28.02.06 |  |  | 89778 | Comp.
35 | Civil | 28.12.05 | 28.12.05 | Imp of gali Bhahogi by pdg CC in Pahari Dheeraj C 122A SPZ | 186700 | EE-III | 122 A | 490/02.02.06/EE-III | M/s Arya & Co. | 20.02.06 | 04.03.06 |  |  | 184888 | Comp.
36 | Civil | 28.12.05 | 28.12.05 | Imp of Gali Shyamji in Telewara by pdg CC Pav in Wno. 122B SPZ | 199500 | EE-III | 122 B | 483/30.01.06/EE-III | M/s Punit Nayyar | 02.03.06 | 28.03.06 |  |  | 199236 | Comp.
37 | Civil | 28.12.05 | 28.12.05 | Imp of rd by pdg CC from 1622 to Plot No. 12 in Hathi Khana w.no. 122B SPZ | 197800 | EE-III | 122 B | 481/30.01.06/EE-III | M/s Manish Nayyar | 02.02.06 | 28.03.06 |  |  | 197116 | Comp.
38 | Civil | 28.12.05 | 28.12.05 | P/L CC from Plot no. 19 to Goyal Enterprises and adj lanes and 1742 to 41 at Hathi Khana C 122B SPZ | 193830 | EE-III | 122 B
39 | Civil | 28.12.05 | 28.12.05 | P/L CC from Shop no. 35 to 37 and adj lanes in Hathi Khana in C 122BSPZ | 197600 | EE-III | 122 B | 478/30.01.06/EE-III | M/s Neel Traders | 31.01.06 | 31.03.06 |  |  | 197082 | Comp.
40 | Civil | 3.1.06 | 22.10.05 | Pdg CC at the entrarance of Gali Thaley Wali, 3082, gali Budha wali and gali Nathan wali in C 121A SPZ | 190303 | EE-III | 121 A | 151/07.07.06/EE-III | M/s Sanjeev Builders | 14.07.06 | 12.09.06 |  |  | 190245 | Comp.
41 | Elect | 12.1.06 | 9.12.05 | P/O semi High mast Lighting arrangment near 1373 to 1384 way in Gulabi Bagh qtrs w.no. 121 SPZ | 181329 | EEE-I | 121 | 261/27.03.06/EE(E)-I | M/s Repair Shop | 06.04.06 | 22.04.06 |  |  | 148920 | Comp.
42 | Elect | 12.1.06 | 9.12.05 | P/O semi High mast Lighting arrangment near 1457 to 1468 way in Gulabi Bagh qtrs w.no. 121 SPZ | 182410 | EEE-I | 121 | 262/27.03.06/EE(E)-I | M/s Repair Shop | 06.04.06 | 22.04.06 |  |  | 148487 | Comp.
43 | Elect | 12.1.06 | 9.12.05 | P/O semi High mast Lighting arrangment at Choudhary Nand Lal Marg, Pratap Nagar, w.no. 121 SPZ | 182230 | EEE-I | 121 | 289/31.03.06/EE(E)-I | M/s Gyan Enterprises | 01.04.06 | 12.04.06 |  |  | 139340 | Comp.
44 | Civil | 16.2.06 | 16.2.06 | P/L marble flooring infront of Nurrudin park form Masjid to main road ( R.J road ) in C-122 B /S.P. Zone | 228731 | EE-III | 122 B | 170/04.07.06/EE-III | M/s Nitin Gupta | 20.07.06 | 18.10.06 |  |  | 228006 | Comp.
[5 empty] | 8676252 | [8 empty] | 8189845

## Sh. M.L. Sodhi
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06 UP TO 16.11.07
Municipal Corporation of Delhi
S.P.ZONE
|  | Name Of MLA |  | Sh. M.L. Sodhi | AC-69 |  | year 2005-06 |  | Allocation | 100
|  | Name of Constituency |  | Ram Nagar
|  | Ward Nos and Names |  | C.131 Kadam Singh C-132, Manak Pura
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Divis-ion | W.no | Work order no with date | Name of Agency | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Civil | 11.5.05 | 10.5.05 | P/l C.C. pavement in Gali no 2 Shyam Ji Mal lane in C-1312 B SPZ | 246300 | EE-III | 131 | 276/25.08.05/EE-III | M/s Rakesh Kumar | 02.01.06 | 21.04.06 | 221228 | Comp.
2 | Civil | 3.6.05 | 2.5.05 | P/L C.C. in shyam ji Mal lanes gali no 1 from H.No 10578/41 to 10579 and adjoing lanes in c-131 SPZ | 182460 | EE-III | 131 | 369/11.11.05/EE-III | M/s Sachin Builders | 21.06.06 | 26.02.07 | 181939 | Comp.
3 | Civil | 3.6.05 | 2.5.05 | P/L C.C. in shyam ji Mal lanes gali no 1 from H.No 10578/29 to 10579/46 and adjoing lanes in c-131 SPZ | 184075 | EE-III | 131 | 78/11.05.06/EE-III | M/s Kapoor Const.Co | 23.05.06 | 18.08.06 | 184031 | Comp.
4 | Civil | 3.6.05 | 2.5.05 | P/L C.C. in shyam ji Mal lanes gali no 1 from H.No 10578/29 to 10578/41 and adjoing lanes in c-131 SPZ | 188757 | EE-III | 131 | 368/11.11.05/EE-III | M/s Sachin Builders | 09.12.06 | 31.05.07 | 188222 | Comp.
5 | Civil | 3.6.05 | 20.4.05 | P/L C.C an Jhandawalan road from shop NO 10753 to Shop no 10787 in C-131 SPZ | 476801 | EE-III | 131 | 345/24.10.05/EE-III | M/s Som Dutt Duevedi | 02.11.05 | 29.03.06 | 476221 | Comp.
6 | Civil | 3.6.05 | 20.4.05 | P/L C.C in Jhandawalan road from shop no 10719 to Shop no 10753 in c-131 SPZ | 460073 | EE-III | 131 | 601/31.03.06/EE-III | M/s Ganesh builders | 10.04.06 | 15.05.06 | 459389 | Comp.
7 | Civil | 3.6.05 | 20.4.05 | P/l of C.C on Jhandewalan road from Idgaha road to shop 10719 in c-131 SPZ | 470287 | EE-III | 131 | 357/07.11.05/EE-III | M/s Kapoor Const.Co | 17.11.05 | 28.02.06 | 469110 | Comp.
8 | Civil | 3.6.05 | 2.5.05 | P/L C.C in shyam JI Mal lane gali no-2 from H.No 10578/41 to H.No 10579 & in adjoing lanes in C-131 SPZ | 181535 | EE-III | 131 | 352/31.10.05/EE-III | M/s Deepak Traders | 08.11.05 | 03.04.06 | 181147 | Comp.
9 | Civil | 3.6.05 | 2.5.05 | P/L c.c. in Ram Nagar Gali no -I from H.No 7578 to H.No 7570 and in adjoing lanes C-131 SPZ | 175355 | EE-III | 131
10 | Civil | 3.6.05 | 2.5.05 | P/L C.C in Ram Nagar near gali no-1 from Old Barajkahana to H,NO 7575 and adjoing lanes in c-131 SPZ | 181346 | EE-III | 131 | 359/07.11.05/EE-III | M/s.Sehgal Contractor | 05.01.06 | 08.02.06 | 181080 | Comp.
11 | Civil | 3.6.05 | 1.3.05 | Imp Gali no 2 by providing c.c. from H.NO 7770 top 7788 and adjoing lanes from H.No 7679 to 7678 and 7872 to 7770 in Ram Nagar C-131 SPZ | 182671 | EE-III | 131 | 327/06.10.05/EE-III | M/s.Shree Madhav Builders | 05.01.06 | 30.01.06 | 182002 | Comp.
12 | Civil | 3.6.05 | 1.3.05 | Imp to lanes by Providing C.C from H.No 7697/20 to 7703 7695 to 7694,7690 to 7788 ,7683 to 7682,7762 to school 7756 ti 7756 (A) in Ram Nagar SPZ | 182905 | EE-III | 131 | 358/07.11.05/EE-III | M/s.Shree Madhav Builders | 09.01.06 | 08.02.06 | 182822 | Comp.
13 | Civil | 3.6.05 | 2.5.05 | Imp to Gali No-2 by providing c.c. from Kutabroad to H.No 7789 and adjoing lanes from H.No 7767 to 7764 and 7759 to 7759 (A) in Ram Nagar C-131 SPZ | 174645 | EE-III | 131
14 | Civil | 6.6.05 | 1.6.05 | P/L c.c. pavement in form 6127 Jhandawalan road to 6147 and adjoing lanes in C-131 SPZ | 220500 | EE-III | 131 | 708/09.02.07/EE-III | M/s Islamuddin | 10.02.07 | 26.03.07 | 195801 | Comp.
15 | Civil | 6.6.05 | 1.6.05 | P/L C.C in Krishna Basti from H.No A-519 to H.No A521 and adjoing lanes in C-131 SPZ | 174369 | EE-III | 131
16 | Civil | 6.6.05 | 1.6.05 | P/L C.C. ar Tail Mill road from Girls Se Sec School Ram Nagar to H.No 7408 and in adjoing lanes in C-131 SPZ | 167501 | EE-III | 131 | 365/11.11.05/EE-III | M/s Sachin Builders | 22.05.06 | 09.06.06 | 83941 | Comp.
17 | Civil | 6.6.05 | 1.6.06 | P/L C.C on tail mill road from H.No 7408 to H.No 7450 and in adjoing lanes in C-131 SPZ | 172359 | EE-III | 131
18 | Civil | 6.6.05 | 14.4.06 | P/L C.C in Pvt Katra NO A-519 to A-521 Kacha Rasta in W.No 131 SPZ | 185864 | EE-III | 131 | 569/27.03.06/EE-III | M/s Chuadhary Const.Co | 08.04.06 | 20.05.06 | 185766 | Comp.
19 | Civil | 6.6.05 | 1.6.05 | P/L C.C in Marwari Basti from H.No BB-74 Gali no 2 and adjoing lanes in W-131 SPZ | 171769 | EE-III | 131 | 363/11.11.05/EE-III | M/s Ravi Kumar Malhotra | 29.11.05 | 30.06.06 | 92261 | Comp.
20 | Civil | 6.6.05 | 1.6.05 | P/L c.c. in chinot Bastic from H.No C-235 to H.No C-268 and in Adjoing lanes in W.No-131 SPZ | 246100 | EE-III | 131 | 243/07.09.06/EE-III | M/s Nitin Gupta | 05.10.06 | 06.01.07 | 191653 | Comp.
21 | Civil | 6.6.05 | 1.6.05 | P/L c.c. in Gali Gurudwara (Himmat Singh) Tail mill road along with Gali no 1 and adjoing lanes in c-131 SPZ | 186823 | EE-III | 131 | 566/17.03.06/EE-III | M/s D.K Builders | 12.04.06 | 22.06.06 | 186172 | Comp.
22 | Civil | 6.6.05 | 1.6.05 | Imp to lane by Providing c.c. flooring from 6552 Near (Nand Band) to 6441 factory road Pradhan chowk in c-131 SPZ | 245400 | EE-III | 131 | 580/30.03.06/EE-III | M/s D.K.Const.Co | 07.04.06 | 25.05.06 | 192993 | Comp.
23 | Civil | 6.6.05 | 1.6.05 | Imp to lane by providing c.c. flooring from Idgah road to Shankar pio at Cheerch road and adjoing lanes in c-131 SPZ | 245500 | EE-III | 131 | 562/27.03.06/EE-III | M/s D.K Builders-I | 03.05.06 | 30.06.06 | 191574 | Comp.
24 | Civil | 6.6.05 | 1.6.05 | Imp to lane by providing C.C. flooring from Pradhan chowk along park upto shankar Marg in Nabi Karim c-131 SPZ | 193313 | EE-III | 131 | 563/27.03.06/EE-III | M/s D.K Builders-I | 17.04.06 | 28.06.06 | 192681 | Comp.
25 | Civil | 29.6.05 | 6.6.05 | P/L C.C in Aram Nagar Amar Puri form H.No A-130 to H.No A-261 and in adjoing lanes in W.No-131 SPZ | 200478 | EE-III | 131 | 409/23.10.07/EE-III | M/s Islamuddin | 29.10.07 | 05.12.07 | 200372 | Comp.
26 | Civil | 29.6.05 | 6.6.05 | P/L c.c. in Ashoka Basti from H.NO BB-300 to H.No BB-270 and adjoing lanes in W.No-131 SPZ | 171527 | EE-III | 131 | 817/28.03.07/EE-III | M/s Kaushal Bharat | 18.04.07 | 15.06.07 | 171057 | Comp.
27 | Civil | 29.6.05 | 6.6.05 | P/L C.C in Siddarth Nagar from H.No c-100/4 to H.Nop 7513 and in adjoing lanes in W.No-131 SPZ | 208236 | EE-III | 131 | 289/21.09.06/EE-III | M/s Neel Traders | 23.10.06 | P | 20805700%
28 | Civil | 29.6.05 | 6.6.05 | P/L M/P in Multani Dhanda gali No-13 from Mother Dariry of H.No 6971 /13 in C-131 SPZ | 274300 | EE-III | 131 | 280/21.09.06/EE-III | M/s Naveen Const. | 08.11.06 | 28.11.06 | 217055 | Comp.
29 | Civil | 29.6.05 | 6.6.05 | P/L C.C. in Siddarth Nagar from H.No 7513 to H.No AB-328 and in adjoing lanes W-131 SPZ | 207476 | EE-III | 131 | 190/26.07.06/EE-III | M/s Rakesh Bansal | 25.08.06 | 22.09.06 | 206494 | Comp.
30 | Civil | 29.6.05 | 6.6.05 | P/L C.C. in Siddarth Nagar from H.No AB-328 to H.No AB-427/3 and in adjoing lanes in W-131 SPZ | 168587 | EE-III | 131 | 818/28.03.07/EE-III | M/s Kaushal Bharat | 27.04.07 | 16.06.07 | 168306 | Comp.
31 | Civil | 29.6.05 | 6.6.05 | P/L M/P premixing in Multani Dhanda from H.NO 8048 to H.No 8005/11 in C-131 SPZ | 270400 | EE-III | 131 | 281/21.09.06/EE-III | M/s Naveen Const. | 20.11.06 | 29.11.06 | 214180 | Comp.
32 | Civil | 29.6.05 | 6.6.05 | P/L C.C in Amar Puri foarm H.No AB-02 to H.No AB-32, H.No AB-63 to H.Nmo AB-37 and in Adjoing lanes in W-131 SPZ | 165503 | EE-III | 131 | 816/28.03.07/EE-III | M/s Kaushal Bharat | 17.04.07 | 15.06.07 | 165128 | Comp.
33 | Civil | 29.6.05 | 6.6.05 | P/L C.C. in Krishan Bastic from H.No A-803 to H.No A-583 and H.No A-374 to H.No A-460 and in Adjoing lanes in W-131 SPZ | 203474 | EE-III | 131 | 408/23.10.07/EE-III | M/s Sajid Khan | 02.11.07 | 05.12.07% | 203254 | Comp.
34 | Civil | 29.6.05 | 6.6.05 | P/L C.C in Chinot Basti from H.No C-365 to H.No C-328 and in adjoing lanes in W-131 SPZ | 265300 | EE-III | 131 | 290/21.09.06/EE-III | M/s Manish Nayyar | 25.09.06 | P | 200538 | In Prog.
35 | Civil | 29.6.05 | 6.6.05 | Imp to foot path by chequred tiles infront of Hari Mandir School from Slaughter Hs to Shop to 10824 in W.NO-131SPZ | 210856 | EE-III | 131 | 875/30.03.07/EE-III | M/s Naveen Const. | 03.04.07 | P | 208253 | In Prog.
36 | Civil | 25.7.05 | 1.6.05 | P/L C.C. in Laxman Puri from H.No L-243 to H.No L-255 and in Adjoing lanes C-131SPZ | 228345 | EE-III | 131 | 908/30.03.07/EE-III | M/s Amit Kumar | 30.06.07 | 05.09.07 | 226557 | Comp.
37 | Civil | 25.7.05 | 2.6.05 | P/L C.C. in Yogmaya from H.No MSC-72 to H.No MSC-245 and in adjoing lanes in c-131 SPZ | 224044 | EE-III | 131 | 804/05.03.07/EE-III | M/s Neel Traders | 16.03.07 | P | 220644 | Prog.
38 | Civil | 25.7.05 | 2.6.05 | P/L C.C. in Shyam JI Mal lane from Jhandewalan road to gali no-2 urinal in c-131 SPZ | 230519 | EE-III | 131 | 152/07.07.06/EE-III | M/s Sanjeev Builders | 24.07.06 | 07.09.06 | 229851 | Comp.
39 | Civil | 25.7.05 | 2.6.05 | P/L c.c. in Multani Dhanda Gali no 12 from H.No 9535 to H.No 9483 and in Adjoing lanes in c-131 SPZ | 213071 | EE-III | 131
40 | Civil | 25.7.05 | 2.6.05 | P/L C.C in Bagichi Allanddin gali no-1 from H.No 10404 to H.No 10417 and in Adjoing lanes in W.No 131 SPZ | 226058 | EE-III | 131 | 150/07.07.06/EE-III | M/s Sanjeev Builders | 31.07.06 | 21.09.06 | 225856 | Comp.
41 | Civil | 25.7.05 | 2.6.05 | P/L C.C. in Bagichi allanddin Gali no 3 form H.No 10463 to H.No 10468 and in adjoing lanes in C-131 SPZ | 239760 | EE-III | 131 | 155/07.07.06/EE-III | M/s Rajesh Const.Co | 14.07.06 | 28.09.06 | 239048 | Comp.
42 | Civil | 25.7.05 | 2.6.05 | P/L c.c. in 52 Qtrs from H.No 9512 to H.No 9532 and adjoing lanes in W.No-131SPZ | 222464 | EE-III | 131 | 907/30.03.07/EE-III | M/s Amit Kumar | 19.06.07 | 11.08.07 | 220799 | Comp.
43 | Elect | 2.8.05 | 26.7.05 | P/O lighting arrangement in w.No131 Laxman Puri, Nabi Karim and adjoing area under S.P.ZSPZ | 199702 | EEE-I | 131 | 153/01.12.05/EEE-I | M/s Miglani Electricals | 09.12.05 | 06.01.06 | 185494 | Comp.
44 | Elect | 2.8.05 | 19.7.05 | P/O lighting arrangement in w.No132S.P.Z (LIG,MIG, flats motia khan and gali no 6&8 Motia Khan under S.P.Z | 199568 | EEE-I | 132 | 158/05.12.05/EEE-I | M/s Miglani Electricals | 14.12.05 | 12.01.06 | 185035 | Comp.
45 | Elect | 2.8.05 | 26.7.05 | P/O lighting arrangement in W.No 131 Ram Nagar ( Old& New) Prem Nagar and Kadam Sharif under S.P.Z | 199933 | EEE-I | 131 | 156/01.12.05/EEE-I | M/s Miglani Electricals | 10.12.05 | 07.01.06 | 185508 | Comp.
46 | Elect | 2.8.05 | 26.7.05 | P/o lighting arrangement in W.No 132 Manak pura, and adjoing area S.P.Z ( Model Bastic, Katra Chajju Mal Pandit & Doro walan SPZ | 199585 | EEE-I | 132 | 155/01.12.05/EEE-I | M/s Miglani Electricals | 10.12.05 | 08.01.06 | 184787 | Comp.
47 | Elect | 2.8.05 | 26.7.05 | P/O Focus light at D.B Gupta road near Jhandawalan Mandir W.No-132 S.P.Z | 191452 | EEE-I | 132 | 154/01.12.05/EEE-I | M/s Miglani Electricals | 10.12.05 | 08.01.06 | 191299 | Comp.
48 | Civil | 4.10.05 | 17.8.05 | P/L C.C. on Qutab road from Shop No 6542 to Shop No.7203 and in Adj lanes in C-131 | 182500 | EE-III | 131 | 371/30.11.05/EE-III | M/s Arya & Co. | 02.12.05 | 18.01.06 | 181891 | Comp.
49 | Civil | 4.10.05 | 17.8.05 | P/L C.C on Qutab road from Khewajan Dargah Baki Billa to shop no 5646 and in adj lanes in c-131. SPZ | 183800 | EE-III | 131 | 463/24.01.06/EE-III | M/s E & Co.traders | 01.09.06 | P | 102649 | In Prog.
50 | Civil | 4.10.05 | 17.8.05 | P/l C.C. and Qutab road from Shop No 7203 to shop no 7219 and in adj lanes in w.no 131. SPZ | 190500 | EE-III | 132 | 356/16.10.06/EE-III | M/s Sumit Const CO. | 30.11.06 | 10.02.07 | 190119 | Comp.
51 | Civil | 4.10.05 | 17.8.05 | P/l C.C in Shankar Marg Balmiki Mandir from shop no 6596/1 to shop no 6671 and in adj lanes in w.no-131 SPZ | 191600 | EE-III | 132 | 406/22.11.06/EE-III | M/s sumit Const CO. | 09.12.06 | 10.01.07 | 191319 | Comp.
52 | Civil | 4.10.05 | 17.8.05 | P/L C.C in Shankar Marg from shop No 7203 to Shop no 6596/1 and in adj lanes in w.no-131 SPZ | 195400 | EE-III | 132 | 397/19.12.05/EE-III | M/s Som Dutt Duevedi | 14.01.06 | 27.03.06 | 194802 | Comp.
53 | Civil | 10.10.05 | 6.10.05 | Imp to footpath by providing interlocking tiles o Desh Raj Bhatia Marg from Hari Mandir school to Slaughta Hs and in adj lanes in c-131/SPZ | 194700 | EE-III | 132 | 370/30.11.05/EE-III | Ms/ Arya & Co. | 02.12.05 | 20.01.06 | 194156 | Comp.
54 | Civil | 10.10.05 | 6.10.05 | Imp to fooppath by providing interlocking tiles of Desh Raj Batia Marg from Shop no 10599 to hs main gate of hari Mandir school and in adj lanes in C-131 SPZ | 195500 | EE-III | 132 | 360/7.11.05/EE-III | M/s sumit Const CO. | 28.11.05 | 21.12.05 | 195325 | Comp
55 | Civil | 16.11.05 | 16.11.05 | P/l C.C. pavement in Arya Ngr in Bagh Rooji from H.No T-935 to T-955 and adj lanes in C-132 A SPZ | 246166 | EE-III | 132 | 542/06.03.06/EE-III | M/s D.K.Const.Co | 16.02.06 | 17.03.06 | 226378 | Comp.
56 | Civil | 5.12.05 | 8.9.05 | Imp to FP by pdg Kota Stone along Jhande Walan Temple in C 132 SPZ | 198000 | EE-III | 132B | 319/27.09.05/EE-III | M/s Manish Nayyar | 30.09.05 | 27.12.05 | 197949 | Comp.
57 | Civil | 5.12.05 | 5.12.5 | P/L CC In block A 22 to 228 from Gurudwara and adj lane in C 132B SPZ | 199500 | EE-III | 132B | 320/27.09.05/EE-III | M/s Neel Traders | 30.09.05 | 28.12.05 | 198435 | Comp.
58 | Civil | 14.12.05 | 14.12.05 | P/L cc in A block from A 225 to 249 Mitia Khan LIG Flats adj lanes in C 132 SPZ | 189800 | EE-III | 132 | 412/29.12.05/EE-III | M/s Deepak Kumar | 20.02.06 | 15.03.06 | 188841 | Comp.
59 | Civil | 30.03.06 | 08.09.05 | P/L cc in Block C10 to C25 D/S Motia Khan and adj. Lanes in C-132 (B)/SPZ | 192000 | EE-III | 132B | 484/30.01.06/EE-III | M/s Puneet Naiyer | 18.03.06 | 28.3.06 | 191349 | Comp.
60 | Civil | 30.03.06 | 08.09.05 | P/L cc in B block from B11 to B40 D/S Qtrs. Motia Khan and adj. Lanes in C-132(B)/SPZ | 193200 | EE-III | 132B | 485/30.01.06/EE-III | M/s Puneet Naiyer | 14.03.06 | 28.3.06 | 192797 | Comp.
61 | Civil | 30.03.06 | 08.03.06 | Imp to road by cc from inst. Opp. Chowk of Udasheen Ashram in Aram Bagh in C-132(B)/SPZ | 197500 | EE-III | 132B | 39/10.05.06/EE-III | M/s Bajaj Const.Co | 28.05.06 | 17.08.06 | 197500 | Comp.
62 | Elect | 31.03.06 | 10.08.05 | P/O lighting arrangment in W.no 132 near Jhandwalan Mandir opp. Main gate in SPZ | 191452 | EE(E)-I | 132 | 155/01.12.06/EE(E)-I | M/s M.J Electricals & Electronics | 10.12.06 | 08.01.07 | 160252 | Comp.
63 | Elect | 31.03.06 | 28.11.05 | P/o lighting arrangment in area of Ambedkar Bhawan in W.no.132/SPZ | 199838 | EE(E)-I | 132 | 102/05.10.06/EE(E)-I | M/s Pragati Engineers | 14.10.06 | 13.11.06 | 133098 | Comp.
64 | Elect | 31.03.06 | 30.11.05 | P/o semi high mast light near Dargha near Varun Nalya buiding C-132/SPZ | 150913 | EE(E)-I | 132 | 136/13.11.06/EE(E)-I | M/s Sechdeva Electricals | 13.11.06 | 28.11.06 | 102016 | Comp.
|  |  |  | Total | 13709715 | [6 empty] | 11916481
in C-