## 17
STATUS REPORT FOR THE MLA FUND YEAR 2005-06
MUNICIPAL CORPORATION OF DELHI
Rohini zone
Name of MLA :- Sh. Anil Bhardwaj |  |  |  | A.C. No. 17 | Year :- 2005-06
Name of Constituency :- Tri Nagar
S.No | Depptt. | Date of Booking | Date of Consent | Name of Work | Amount | Div. | Ward no. | Work order No. with Date | Name of Agency | A.D.O.S. | A.D.O.C. | Expenditure | Phy Target | Phy. Ach. | Remarks
Total
1 | Civil | 16.6.06 | 26.5.05 | P/L CC fromH.no. 2745 to 2748/248 in Onkar Nagar in C-27 RZ | 100241 | R-I | 27 | 432/21.11.05/EE®-I | M/s Roshan Lal Builders-II | 28.11.05 | 27.02.06 | 98019 |  |  | Comp.
2 | Civil | 16.6.06 | 21.5.054 | C/O FP from Rly xing Onkar Nagar upto Rohtak Rd near Ashoka park in C 27 RZ | 142300 | R-I | 27 | 199/29.6.05 | M/s RL Builders | 1.7.05 | 28.11.05 | 141903 |  |  | Comp.
3 | Civil | 16.6.06 | 24.5.05 | Cosnt of FP in lane no 5n Jai Mata Mkt in C 27 RZ | 188500 | R-I | 27 | 196/29.6.05 | M/s Pankaj Builders | 9.7.05 | 31.10.05 | 185774 |  |  | Comp.
4 | Civil | 27.6.05 | 21.5.05 | Imp to B/wall of Tikona Park by Marbel Wash near Preshu Ram Chowk on Lal Lajpat Rai Marg in Tri Nagaer C-27 RZ | 334664 | R-I | 27 | 662/08.03.06/EE(R)-I | M/s Anil Kumar | 08.03.06 | 09.06.06 | 334479 |  |  | Comp.
5 | Civil | 27.6.05 | 21.5.05 | Const of Free U-Turn road and Side FP under Zakhira Fly Voer in C27 | 172500 | R-I | 27 | 223/14.07.05/EE(R)-I | M/s Govind Gupta | 18.07.05 | 23.01.06 | 172395 |  |  | Comp.
6 | Civil | 27.6.05 | 24.5.05 | P/L CC from H.No. 4498/11 to 4489/11 in Jai Mata Mkt in C 27m RZ | 398898 | R-I | 27 | 680/17.03.06 | M/s Anil Kumar | 18.03.06 | 24.06.06 | 398750 |  |  | Comp.
7 | Civil | 27.6.05 | 26.5.05 | P/L CC around Joor Bagh Chopal in C -27 RZ | 108427 | R-I | 27 | 227/14.07.05 | M/s Pankaj Singh | 23.07.05 | 21.11.05 | 108106 |  |  | Comp.
8 | .CSE | 2005-06-30 | 2005-06-24 | Imp of Drainage system by pdg RCC pipes in fornt of Golden park at Rohtak road in w.no. 271 RZ | 197650 | CSE/RZ | 27 | 31/27.7.05 | M/s Raj Const Co. | 10.08.05 | 30.8.05 | 178919 |  |  | Comp
9 | Civil | 2005-06-30 | 2005-05-21 | Imp to berms from H.no. 43 to 52 and P/L C C from H.no. 73 to 81 in Ashoka Park in C -27. | 297741 | R-I | 27 | 682/17.03.06/EE(R )-I | M/s Anil Kumar | 18.03.06 | 24.06.06 | 297199 |  |  | Comp.
10 | Civil | 2005-06-30 | 2005-05-24 | Const of B.wall near Marble side and P/F MS grills along passage in Mam Chand park Rampura village in C -27 | 334226 | R-I | 27 | 386/19.10.05 | M/s Nimit Const co. | 27.10.05 | 27.01.06 | 311150 |  |  | Comp
11 | Civil | 2005-06-30 | 2005-05-24 | P/L CC near H.no.c 1689 to 1688 in Shanti Nagar in C 27. | 109444 | R-I | 27 | 226/14.7.05 | M/s Bajaj Enterprises | 15.7.05 | 5.10.05 | 104344 |  |  | Comp
12 | Civil | 2005-06-30 | 2005-05-26 | Imp of FP with Red Sand Stone from Dahav Marg toParshu Ram Chowk on Lajpat Rai marg in C 27. | 365879 | R-I | 27 | 585/31.01.06/EE(R )-I | M/s Singhal builders | 07.02.06 | 08.06.06 | 364625 |  |  | Comp
13 | Civil | 2005-06-30 | 2005-05-26 | P/L S W Drianage on Agarsen marg rom kanhiya Nagar Drain to H.no. 3424/2 in Tri nagar in C 27. | 370739 | R-I | 27 | 683/17.03.06/EE(RD)-I | M/s Anil Kumar | 25.03.06 | 24.06.06 | 370629 |  |  | Comp.
14 | Civil | 2005-06-30 | 2005-05-26 | P/L SW Drainage from Railway xing upto Rohtak rd near Goden Park in C -27. | 350058 | R-I | 27 | 681/17.03.06/EE(R )-I | M/s Anil Kumar | 18.03.06 | 24.06.06 | 349931 |  |  | Comp.
15 | Civil | 2005-07-06 | 2005-05-10 | Imp of road by pdg RMC between G .30 and G 40/3 at Dr. Lohiya Indil ara. At C 28. | 656361 | R-I | 28 | 668/09.03.06/EE(R.D)-I | M/s Vijay Builders | 19.03.06 | 04.08.06 | 655820 |  |  | Comp.
16 | Civil | 2005-07-13 | 2005-05-21 | P/L CC in lane no 32 from 36/7 to 191/9 in Onkar Nagar in Tri nagar in C 27 | 197749 | R-I | 28 | 406/03.11.05 | M/s Mukesh Kumar Bansal | 05.11.05 | 06.02.06 | 197627 |  |  | Comp.
17 | Civil | 2005-07-15 | 2005-05-18 | Const of B./wall at Ramleela Park at Shree nagar at C 28. | 541750 | R-I | 28 | 473/09.12.05/EE-(R-I) | M/s Anil Kumar | 09.12.05 | P | 380550 |  |  | In Prog.
18 | Civil | 2005-07-19 | 2005-05-10 | Const of Walkway in Central park of MIG Flats Ram Pura at C 28 | 306682 | R-I | 28 | 521/29.12.05 | M/s Vijay Builders | 02.01.06 | 24.02.06 | 306479 |  |  | Comp.
19 | Civil | 2005-07-19 | 2005-05-10 | Const of Drain and FP along MIG Flat Rampura Mohalla at C 28. (Rs.422798/-) | - | R-I | 28 | Work cancelled as desired by area MLA and technical reasons explanied by EE-(R )-I and approved by DC Rohini Zone, dated 22.12.06.
20 | Civil | 2005-07-19 | 2005-05-10 | Const of B/wall with Grill at MIG Flat Rampura Mohalla at C 28. | 151037 | R-I | 28 | 535/02.01.06 | M/s Pritam Lal | 12.01.06 | 28.03.06 | 150847 |  |  | Comp.
21 | Civil | 2005-07-19 | 2005-05-10 | Imp of Drainand main lane at Janta Flats Rampura at C 28 (Rs.335085/-) | - | R-I | 28 | Work cancelled as desired by area MLA and technical reasons explanied by EE-(R )-I and approved by DC Rohini Zone, dated 17.01.07.
22 | Civil | 2005-07-19 | 2005-05-10 | Imp to drain and main lane at B 2 Pkt flats, Keshav Puram, C 28. | 388012 | R-I | 28 | 399/26.10.05 | M/s Vinod Associates | 05.11.05 | 28.04.06 | 388012 |  |  | Comp.
23 | Civil | 2005-07-19 | 2005-05-18 | Imp to main lane and drain in C 5 Pkt Keshav Puram C 28. | 364304 | R-I | 28 | 400/26.10.05 | M/s Mehandi Ratta Traders | 06.11.05 | 03.03.06 | 363924 |  |  | Comp.
24 | Civil | 2005-07-19 | 2005-05-21 | Stg of B/wall along Metro Rail Line from C 6 Pkt Corner to C 8 Pkt Corner at Keshav Pura, C 28. (Rs=414427/-) | - | R-I | 28 | Work cancelled as desired by area MLA and technical reasons explanied by EE-(R )-I and approved by DC Rohini Zone, dated 11.01.07.
25 | Civil | 2005-07-19 | 2005-05-10 | Imp to drain on road near G 30 and G 40/3 in Dr Lohiya Indl Area at C 28. | 445203 | R-I | 28 | 401/26.10.05 | M/s Vijay Builders | 5.11.05 | 20.01.06 | 444175 |  |  | Comp
26 | Civil | 2005-07-21 | 2005-07-20 | P/L CC From H.no. 599/38 to 602/38 in Joor Bagh 430/1 to 35/7 in Onkar nagar B & 1427/1 to 1407/96 in Ganesh Pura, C 27. | 199395 | R-I | 27 | 287/18.08.05 | M/s Mohan Lal & Co. | 22.08.05 | 26.11.05 | 183537 |  |  | Comp
27 | Civil | 2005-07-25 | 2005-05-18 | Imp to lane and Drainage system of C 4 Pkt at Keshav Puram, C 28. | 478944 | R-I | 28 | 504/23.12.05/EE(RD)-I | M/s Gupta & Company | 03.01.06 | 12.11.06 | 478609 |  |  | Comp.
28 | Civil | 2005-07-25 | 2005-05-21 | Stg of Centre Verge and xing at Madhav marg from C block Indl. Area turning to NDPL office at Keshav Puram. C 28. | 603398 | R-I | 28 | 538/31.01.06 | M/s R.S Building Mate.& Supp. | 12.01.06 | 28.03.06 | 602377 |  |  | Comp.
29 | Civil | 2005-07-25 | 2005-05-21 | Stg of Center Verge and xing at Madhav Marg from C 2 Pkt xing to C 4 Pkt xing at Keshav Puram, C 28. | 580520 | R-I | 28 | 398/26.10.05 | M/s D.R.Builders | 28.10.05 | 07.02.06 | 579856 |  |  | Comp.
30 | Civil | 2005-07-25 | 2005-05-21 | Stg of Cetre verge and xing at Madhav Marg from C 4 Pkt to C 8 Pkt xing at Keshav Puram, C 28. | 585897 | R-I | 28 | 369/11.10.05 | M/s C.B.Gupta & Co | 21.10.05 | 26.04.06 | 585614 |  |  | Comp.
31 | Civil | 2005-07-25 | 2005-05-21 | Stg of C/V and xing at 100' Rd from Rd no 37 to Narang Cly chowk, Keshav Puram, C 28 | 726350 | R-I | 28 | 627/28.02.06 | M/s Vijay Builders | 02.03.06 | 30.05.06 | 725990 |  |  | Comp.
32 | Civil | 2005-07-25 | 2005-07-21 | Imp to alnes by Pdg CC from 3177 to 3128 & 3128 to 3167 and 3175 to 3253 to 3262, 376 to 3134 and adj lane at Mahender Park at C 28. | 274181 | R-I | 28 | 502/23.12.05 | M/s Ravinder Const.Co | 02.01.06 | 28.03.06 | 274102 |  |  | Comp.
33 | Civil | 2005-07-27 | 2005-05-24 | Const of entrance gates of Vardhman Vatika Park in C 27 RZ | 560129 | R-I | 27 | 527/02.01.06 | M/s Satish & Co. | 05.01.06 | 21.06.06 | 533524 |  |  | Comp.
34 | Civil | 2005-08-01 | 2005-05-18 | Imp to D/Sys and FP on main rd form Madhav Mar gto C 4 Pkt xing at Keshav Puram at C 28. | 443239 | R-I | 28 | 657/08.03.06/EE(RD)-I | M/s Vijay Builders | 18.03.06 | 16.11.06 | 442963 |  |  | Comp.
35 | Civil | 2005-08-01 | 2005-05-18 | Const of Designer gate at C 4 and C 7 Pkt Park at Keshav Puaram C 28. | 412144 | R-I | 28 | 402/28.10.05 | M/s A&T Const. | 01.11.05 | 09.02.06 | 411928 |  |  | Comp.
36 | Civil | 2005-08-01 | 2005-05-18 | Const of Designer gate at Ram Leela Park ande Tikona park at main bazar road of Raja Park in C 28 | 546853 | R-I | 28 | 440/21.11.05 | M/s Aand T Const. | 01.12.05 | 08.03.06 | 546743 |  |  | Comp.
37 | Elect. | 2005-08-05 | 2005-06-25 | Prov of 43 nos Street light arrangment in Tri nagar, Keshav Puram and Shakur pur village C no 17 under RZ | 198818 | EEE-VII | 27,28 | 68/24.10.05 | M/s Farward Engineers | 27.10.05 | 21.11.05 | 195283 |  |  | Comp
38 | Civil | 2005-08-05 | 2005-05-18 | Const of Drian on Railway line rd from C 4 to C 5 Pkt xing at Keshav Puram C 28. | 785702 | R-I | 28 | 520/28.12.05 | M/s C.B.Gupta & Co | 30.12.05 | 20.05.05 | 785392 |  |  | Comp
39 | Civil | 2005-08-26 | 2005-07-21 | Imp of alne by CC from 3585 to 3575 Raja Park and at Mina Bazar of Raj park in C 28. (Rs=597600/-) | - | R-I | 28 | Work cancelled as desired by area MLA and technical reasons explanied by EE-(R )-I and approved by DC Rohini Zone, dated 28.02.07.
40 | Civil | 2005-08-26 | 2005-07-21 | Upliftment and Imp of C 7 Mkt at Keshav Puram in C 28. | 301211 | R-I | 28 | 519/27.12.05 | M/s Arun Builders | 06.01.06 | 01.03.06 | 300785 |  |  | Comp.
41 | Civil | 2005-08-26 | 2005-07-21 | Imp of lane by CC in C 8 Pkt enar C 8/43 lane and C 8/41 to 86 and adj lane at keshav Puram inC 28. | 286641 | R-I | 28 | 594/03.02.06/EE®-I | M/s Manoj Builders | 13.02.06 | P | 237948 |  |  | In Prog.
42 | Civil | 19.9.05 | 12.9.05 | Const of entrance boundary gate of Mamchand park in Rampura village in C 27 | 133751 | R-I | 27 | 458/20.11.05/EE®-I | M/s Manoj Builders | 07.12.05 | 31.08.06 | 105922 |  |  | Comp.
43 | Civil | 19.9.05 | 12.9.05 | P/L CC in lane No. 43 from H.no. 1905 to 1910 in Ganesh Pura, Tri nagar in C 27 RZ | 122683 | R-I | 27 | 567/27.01.06/EE®-I | M/s R.L Builders | 30.01.06 | 05.05.06 | 110828 |  |  | Comp.
44 | Civil | 5.1.06 | 12.9.05 | Stg of road of C-4 to C-8 Pkt by pdg (Dense) BM/AC at Keshav Puram, in C -28 | 2387261 | R-I | 28 | 109/11.09.06/EE( R)-I | M/s Sanjeev Kumar & Bros. | 20.09.06 | 15.11.06 | 2387261 |  |  | Comp.
45 | Civil | 6.2.06 | 31.1.06 | P/L CC from H.no. 1042-169 to 1050/69 in Deva Ram Park, 487/36 to 523/36 in Onkar Nagar and 417/5 to 468/19 in Jai Mata Mkt in Tri Nagar in C 21 RZ | 426804 | R-I | 27 | 755/31.03.06/EE(R )-I | M/s Naresh Enterprises | 08.04.06 | 08.07.06 | 426694 |  |  | Comp.
46 | Civil | 13.2.06 | 31.1.06 | Const of FP on Aggersen Marg from H.no. 2523/193 to 617/2004 in Tri Nagar in C 27 | 346330 | R-I | 27 | 766/31.03.06/EE-(R )-I | M/s Rakesh Kumar Goel | 04.04.06 | 22.07.06 | 333160 |  |  | Comp.
47 | Civil | 13.2.06 | 1.02.06 | Const of FP on Old Bus stand along Vishram Nagar in Tri Nagar in C 27 | 374913 | R-I | 27 | 30/03.05.06/EE(R )-I | M/s Rakesh Kumar Goel | 05.05.06 | 10.08.06 | 363948 |  |  | Comp.
48 | Civil | 27.2.06 | 31.1.06 | Const of Planter at Narang colony Chowk near Subzi Mkt in Tri Nagar in C 27 | 234460 | R-I | 27 | 16/25.04.06/EE®-I | M/s SeeKay Enterprises | 01.05.06 | 27.09.06 | 234204 |  |  | Comp.
[5 empty] | 17531989 | [6 empty] | 17150325
Remarks:- No. of works booked=48, No. of works cancelled=4

## 18
STATUS REPORT FOR THE MLA FUND YEAR 2005-06
MUNICIPAL CORPORATION OF DELHI
Rohini zone
[7 empty] | Budget | Allocation | Vide Letter No |  | Dated
Name of MLA :- Sh. Dr. S.C. Vats |  |  |  | A.C. No. 18 | Year :- 2005-06 |  |  | i. 66.63 lacs ii. 33.37 lacs iii. 84.00 lacs iv. 3.27 lacs Total 187.27 | 140 233 330 CE-III/E-258 | Savings pre.yrs | 23.7.04 29.9.04 28.12.04 25.1.05
v. (-) 7.62 Booked for 04-05 in 03-04
Name of Constituency :- Shakurpur | [7 empty] | Net 179.65 lacs
S.No | Depptt. | Date of Booking | Date of Consent | Name of Work | Amount | Div. | Ward no. | Work order No. with Date | Name of Agency | A.D.O.S. | A.D.O.C. | Expenditure | Phy. Tar. | Phy. Ach. | Remarks
Total
1 | Civil | 2005-08-04 | 2005-08-02 | imp of back lane by CC from H.no. C 23 to C 34 in New Multan nagar in C 30 | 350800 | R-I | 30 | 528/02.01.06 | M/s Raghav Const. | 02.01.06 | 10.04.06 | 264850 | 264850 |  | Comp.
2 | Civil | 2005-08-04 | 2005-08-02 | Imp to ane by pdg CC from h.no. 677 to 545 in Rishi Nagar in C 30 | 226083 | R-I | 30 | 481/09.12.05/EE(RD)-I | M/s Surender Pal Singh | 07.06.06 | 27.11.06 | 187273 |  |  | Comp
3 | Civil | 2005-08-04 | 2005-08-02 | Imp to lane by pdg CC from H.no. 6 to 14, 47 to 52 and 101 to 102 in Hari Singh Park in C 30 | 271400 | R-I | 30 | 499/23.12.05 | M/s V.K.Gupta | 23.12.05 | 30.03.06 | 249009 |  |  | Comp.
4 | Civil | 2005-08-04 | 2005-08-02 | Imp to SW Drain and Road side berms by interlocking pavers fromH.nolD 28 to 31(Both side) and Imp to lane along District park in New Multan Nagar in C 30. | 397200 | R-I | 30 | 717/27.03.06/EE(RD)-I | M/s Surender Pal Singh | 21.07.06 | 27.11.06 | 267460 |  |  | In Prog.
5 | Civil | 2005-08-04 | 2005-08-02 | Imp to rd sid berms by P/L Interlocking paver from Bnnu Biradari Apptt. To Parwana ed (both side) in H 4/5 in C 30. | 561800 | R-I | 30 | 595/03.02.06/EE(RD)-I | M/s Manoj Builders | 20.02.06 | 09.06.09 | 249187 |  |  | Comp.
6 | Civil | 2005-08-04 | 2005-08-02 | Imp of SW drain & Rd side berms (both side) by interlocking paver from Brij Vihar Society to Parwana rd in H 4/5 inC 30. | 389321 | R-I | 30 | 479/09.12.05/EE-(R-I) | M/s Surender Pal Singh | 08.12.05 | P | 349829 |  |  | In Prog.
7 | Civil | 2005-08-04 | 2005-08-02 | Imp of SW Drain back side at Brij Vihar Society to Bal Bharti Public School in H 4/5 C 30. | 362100 | R-I | 30 | 542/28.11.05 | M/s Friends const and Bldg Ma Supplier | 28.11.05 | 26.12.05 | 362091 |  |  | Comp
8 | Civil | 2005-08-04 | 2005-08-02 | Imp of lane by pdg CC from H.no. 1424 to 1402, 1674 to 1655, 1675 to 1687 in Ram Singh in C 30. | 290404 | R-I | 30 | 480/09.12.05/EE(RD)-I | M/s Surender Pal Singh | 08.05.06 | 29.05.06 | 241279 |  |  | Comp
9 | Civil | 2005-08-04 | 2005-08-02 | Imp of back lane by CC form D 1 to 22 and laong D 11 in Pushpanjali Encl in C 30. | 543100 | R-I | 30 | 678/17.03.06/EE(R )-I | M/s Shri Vinayak Enterprises | 17.03.06 | 24.06.06 | 504088 |  |  | Comp.
10 | Civil | 2005-08-04 | 2005-08-02 | Imp of drainge system &Rd Side berms by interlocking paver opp H.no. C 432 to C 447 in Saraswati Vihar in C 30. | 248931 | R-I | 30 | 653/08.03.06/EE®-I | M/s Satyam Const.CO | 08.03.06 | 14.07.06 | 248931 |  |  | Comp.
11 | Civil | 2005-08-18 | 2005-08-04 | Imp of 45' ROW rd fromH.no. 82 to 146 in Rajdhani Encl in C 29. | 573400 | R-I | 29 | 677/17.03.06/EE(R )-I | M/s Anil Kumar | 26.03.06 | 21.06.06 | 531987 |  |  | Comp.
12 | Civil | 2005-08-18 | 2005-08-04 | Imp of 45' Rd by pg RMC from Rd no. 43 to 81 in Rajdhani Encl in C 29. | 545200 | R-I | 29 | 497/23.12.05/EE(R )-I | M/s Subhash Chander-III | 01.01.06 | 14.08.06 | 402168 |  |  | Comp.
13 | Civil | 2005-08-18 | 2005-08-04 | Imp of 45' Rd by pdg RMC from H.no. 157 to 235 in Rajdhani Encl in C 29. | 582200 | R-I | 29 | 542/09.01.06/EE (R )-I | M/s Dua Broth. | 18.01.06 | 27.07.06 | 430639 |  |  | Comp.
14 | Civil | 2005-08-18 | 2005-08-04 | Imp to space by pdg CC outside MC Pry school G block (MGH rd) and along opark in G block Shakur Pur in C-29. | 108150 | R-I | 29 | 349/23.09.05 | M/s Om Mark Buider | 03.10.05 | 23.01.06 | 108071 |  |  | Comp.
15 | Civil | 2005-08-18 | 2005-08-04 | Imp/Const of walkway in park infront of I-1 in JJ Cly Shakur pur in C 29. | 169913 | R-I | 29 | 547/12.01.06/EE(R )-I | M/s Neeraj Const.Co | 21.01.06 | P | 130604 |  |  | In Prog.
16 | Civil | 2005-08-18 | 2005-08-04 | Imp to rd side berms in front of H.no. 23 Rohit Kunj to Mkt in Rohit Kunj in C 29-II in (Interlocking tiles) | 266100 | R-I | 29 | 393/20.10.05 | M.s Subhash singh | 30.10.05 | 14.12.05 | 144887 |  |  | Comp
17 | Civil | 2005-08-18 | 2005-08-04 | Const of passage in park opp H.no. 234 & Gurudwara in Kohat Encl in C 29-II | 169400 | R-I | 29 | 405/3.11.05 | M.s KP Associates | 3.11.05 | 27.11.05 | 150435 |  |  | Comp
18 | Civil | 2005-08-18 | 2005-08-04 | Imp of intenal road by Premixing Carpet in Gate No 3 in MP encl in C 29 | 177650 | R-I | 29 | 464/01.12.05 | M/s Vijay Bansal | 10.12.05 | 03.03.06 | 177128 |  |  | Comp
19 | Civil | 2005-08-18 | 2005-08-04 | Imp to Drainge system near I-464, I-569 to Kabir Dass margf along MC school I block Shakur Pur JJ Cly C 29. | 356907 | R-I | 29 | 456/29.11.05 | M/s Manoj Builders | 08.12.05 | 07.03.06 | 343926 |  |  | Comp
20 | Civil | 2005-08-23 | 2005-08-04 | Stg of internal rds by Mix Seat in Rohit Kunj & Sandesh Vihar in C 29.(Rs.479200) |  | R-I | 29 | Work Cancelled as desired by area MLA vide letter dated 30.10.07 & Approvsd by Commissioner dated 05.02.08
21 | Civil | 2005-08-23 | 2005-08-04 | Const of passage in park opp H.no. 64 in Rohit Kunj inC 29. | 275100 | R-I | 29 | 629/28.02.06 | M./s Surender & Co. | 09.03.06 | 25.05.06 | 177451 |  |  | Comp.
22 | Civil | 2005-08-23 | 2005-08-04 | Imp to kabristan in G block Shakurpur JJ cly in C 29. | 193900 | R-I | 29 | 524/30.12.05 | M/s Jasvinder Gulati | 08.01.06 | P | 71578 |  |  | In Prog
23 | Civil | 2005-08-23 | 2005-08-04 | Imp to Open Space by RMC along Park opp H.No. G 1106 in Shakurpur, JJ Cly in C 29. | 323700 | R-I | 29 | 507/23.12.05 | M/s Rakesh Kr Goel | 24.12.05 | 23.1.06 | 246421 |  |  | Comp
24 | Civil | 2005-08-30 | 2005-08-04 | Imp of rd by pdg CC Pav alogn H.no. 110, 159 in Rajdhani Encl in c 29 | 751900 | R-I | 29 | 563/18.01.06 | M/s Surander & Company | 27.01.06 | 22.05.06 | 531783 |  |  | Comp
25 | Civil | 2005-08-30 | 2005-08-04 | Imp to rd by Dense Carpetting from Raj Nagar rd to Rd no 44 in C 29.(Rs. 669400) |  | R-I | 29 |  | Work Cancelled as desired by area MLA vide letter dated 30.10.07 & Approvsd by Commissioner dated 05.02.08
26 | Elect. | 26.9.05 | 2.9.05 | Prov. Of 12mtr long High Mast Pole Raising and lowering type with Flood Light fixtuer in Mpl park opp, H.no. G 280, Shakurpru JJ Cly under RZ | 280400 | EEE-VII | 29
27 | Civil | 28.12.05 | 4.12.05 | C/o Toilet in E block Shakurpur JJ Cly C-29. | 396200 | R-I | 29 | 722/27.03.06/EE(R )-I | M/s Sharma & Co. | 05.04.06 | P | 260488 |  |  | In Prog.
28 | Civil | 13.1.06 | 27.9.05 | P/L CC on road side berms and P/L CC Slab no F P o approach rd to Pundrik Vihar from Parwana Rd to Back of JJ Cluster in C 30 | 491221 | R-I | 30 | 718/27.03.06/EE®-I | M/s Chauhan Const.CO | 30.03.06 | 27.12.06 | 491221 |  |  | Comp.
29 | Civil | 13.1.06 | 27.9.05 | P/L CC on road side berm and P/L CC Slab FP fromParwnan rd to NDPL Transformer alogn Harvard Public School in C 30 | 434679 | R-I | 30 | 11/10.04.06/EE®-I | M/s Sharma & Co. | 23.06.06 | 04.10.06 | 392469 |  |  | Comp.
30 | Civil | 13.1.06 | 4.1.06 | Remodelling SW Drainf rom H.no. 113 to 120 in Shakti Vihar on Mahatma Hans Raj marg in C 30. | 441100 | R-I | 30 | 711/27.03.06/EE®-I | M/s Vijay Kumar Gupta & Co. | 13.06.06 | 11.10.06 | 319015 |  |  | Comp.
[5 empty] | 10178259 | [6 empty] | 7834268
Remarks:- No. of works booked=30, No. of works cancelled=2

## 19
STATUS REPORT FOR THE MLA FUND YEAR 2005-06
MUNICIPAL CORPORATION OF DELHI
Rohini zone
Name of MLA :- Sh. Ravinder Nath Bansal |  |  |  | A.C. No. 19 | Year :- 2005-06
Name of Constituency :- Shalimar Bagh
S.No | Department | Date of Booking | Date of Consent | Name of Work | Amount | Div. | Ward no. | Work order No. with Date | Name of Agency | A.D.O.S. | A.D.O.C. | Expenditure | Phy. Tar. | Phy.Ach. | Remarks
1 | Civil | 17.5.05 | 31.12.04 | Const of Walkway in the park opp. H.no,. 362 & 121 in SD Block Pitampura C -32. | 196060 | RD-I | 32 | 239/22.7.05 | M./s Kanhiya Lal | 23.2.05 | 14.10.05 | 195757 |  |  | Comp
2 | Civil | 25.5.05 | 18.5.05 | Strong thening of Approach rd of singal pur Village Chowk near 102 in font of 100,110,105 chowk near 105 near 106 chowk along 121,121 to 114 chowk near DJB Pump House 58 to 46 in AD block 15 to 27, 44 to 58, 1023 to 91 and 109 to 123 in BL block and 110 t | 1076600 | RD-I | 31 | 539/09.01.06/EE(R )-I | M/s Dhingra Const.Co | 12.05.06 | P | 830873 |  |  | In Prog.
3 | Elect. | 26.5.05 | 28.4.05 | P/o Semi High Mast Lights in opark Situated between AD & AE block and on the back side of Sarvodya Vidyalaya B block A 4 block and on the one side of AF block Shalimar Bagh under RZ | 172552 | EEE-VII | 31 | 108/16.11.05 | M/s Sushma Etecticals | 21.11.05 | 30.11.05 | 164808 |  |  | Comp.
4 | Elect. | 26.5.05 | 30.4.05 | Prov. Of Semi High Mast light in park opposite Sad Guru Dham Mandir UP block Pitampura under RZ | 173097 | EEE-VII | 32 | 186/06.12.05 | M/s Perfect Elect. Works | 08.12.05 | 20.12.05 | 165397 |  |  | Comp.
5 | Elect. | 26.5.05 | 21.4.05 | Prov of Semi High Mast light in park near H.no. BC-8(West) Shalimar bagh under RZ | 172806 | EEE-VII | 31 | 107/16.11.05 | M/s Sri Bala ji Electricals | 18.11.05 | 29.11.05 | 172257 |  |  | Comp.
6 | Elect. | 26.5.05 | 23.4.05 | Prov. Of Semi High Mast Light in park near H.no. BL-7 (West) Shalimar Bagh RZ | 173439 | EEE-VII | 31 | 120/16.11.05 | M/s Siwach Engineers & Traders | 18.11.05 | 29.11.05 | 171382 |  |  | Comp.
7 | Elect. | 03.06.05 | 20.4.05 | Prov of Semi High Mast light in park in near H.no. BM-108(West) Shalimar bagh under RZ | 172172 | EEE-VII | 31 | 112/16.11.05 | M/s Khanna Sales Corp. | 17.11.05 | 22.11.05 | 172111 |  |  | Comp.
8 | Elect. | 3.6.05 | 1.5.05 | Prov. Of Semi High Mast Light in park adj Central Schoool TP block, Pitampura under RZ | 173439 | EEE-VII | 32 | 113/16.11.05 | M/s ST Electic Co. | 24.11.05 | 19.12.05 | 167286 |  |  | Comp.
9 | Elect. | 3.6.05 | 25.04.05 | Prov. Of Semi high Mast light in park Opp H.No. AA-86, AA Block, Shalimar Bagh, under RZ | 172045 | EEE-VII | 31 | 146/22.11.05 | M/s Sangwan Electricals | 24.11.05 | 30.11.05 | 172045 |  |  | Comp.
10 | Elect. | 3.6.05 | 29.04.05 | Prov. Of Semi High Mast Light in park situated behind Petrol Pump in BU block Pitampura RZ | 172210 | EEE-VII | 32 | 185/6.12.05 | M/s Prince Engg. Works | 8.12.05 | 19.12.05 | 172160 |  |  | Comp.
11 | Elect. | 3.6.05 | 25.4.05 | Prov of Semi High Mast Light in parks near Situated on the back side of MCD Pry School, AB Block shalimar Bagh under RZ | 172679 | EEE-VII | 31 | 226/23.12.05 | M/s Pragati Engineers | 31.12.05 | 12.01.06 | 165409 |  |  | Comp.
12 | Civil | 3.6.05 | 31.5.05 | Argumentation of Water Supply by P/L GI Pipe line in park in AG block and AN Blcok in Shalimar Bagh in C-31 RZ | 78700 | RD-I | 31 | 301/24.08.05 | M/s Modeen Bldg. Matarial Suppilers | 24.08.05 | 31.10.05 | 73689 |  |  | Comp.
13 | Elect. | 9.6.05 | 3.6.05 | Prov. Of Lighting arrangment in Mpl park opp flat no 587-A BN-C(Poorvi) block, Shalimar bagh under RZ | 154401 | EEE-VII | 31 | 64/21.9.05 | M/s Khanna Sales Corp. | 22.9.05 | 30.9.05 | 127679 |  |  | Comp
14 | Civil | 10.06.05 | 25.5.05 | Imp of lane by pdg Drianage and RMC from H.no. 47 to 62 front & Bacl in AG block in Shalimar Bagh C-31.RZ-I | 414472 | RD-I | 31 | 364/29.9.05 | M/s Supreme const. | 29.9.05 | 20.04.05 | 413780 |  |  | Comp
15 | Civil | 10.6.05 | 25.5.05 | Imp. Of Drainage System from H.no. 31 to 82 and 154 to 97 in AA block Shalimar Bagh, Delhi | 575790 | RD-I | 31 | 465/5.12.05 | M/s Chauhan Const Co. | 5.12.05 | 12.03.06 | 575790 |  |  | Comp
16 | Civil | 10.6.05 | 25.5.05 | Const of Walkway in the park in BC (West) block in Shalimar Bagh in C-31 RZ | 104492 | RD-I | 31 | 254/29.7.05 | M/s Supreme const. | 29.7.05 | 16.9.05 | 104458 |  |  | Comp
17 | Civil | 10.6.05 | 10.5.05 | Resurfacing of Existing Walkway by Red Sand Stone flooring in park Situated between AD & AE block in Shalimar Bagh C-31 RZ | 325200 | RD-I | 31 | 763/31.03.06 | M/s Anil Kumar | 07.04.06 | 31.03.08 | 252857
18 | Elect. | 10.6.05 | 17.2.05 | Imp of Semi High Mast Lights in Mpl parks in Shalimar bagh & PUItampura C-19 under RZ | 199696 | EEE-VII | 31/32 | 58/24.08.05 | M/s G.S Elect. | 25.08.05 | 12.09.05 | 158060 |  |  | Comp.
19 | Civil | 2005-07-06 | 2005-06-07 | P/F barded wire fencing in "SD" blcok, Pitampura C 32 | 112329 | RD-I | 32 | 455/29.11.05 | M/s Manoj Builders | 02.12.05 | 16.01.06 | 101107 |  |  | Comp.
20 | Civil | 2005-07-06 | 2005-06-07 | Const of Walkway in the park opp H.no. LP-23A in LP Block Pitmapura in C 32. | 89579 | RD-I | 32 | 342/20.0.9.05 | M/s Pankaj Cost co. | 22.9.05 | 26.11.05 | 89513 |  |  | Comp
21 | Civil | 2005-07-06 | 2005-06-07 | Imp to lane by pdg CC along Central School in TP block from 1A to 8A in 4 P block and side of mkt in YP block Pitampura in C 32. | 332400 | RD-I | 32 | 764/31.03.06/EE(RD)-I | M/s Anil Kumar | 03.04.06 | 05.07.06 | 267764 |  |  | Comp.
22 | Civil | 2005-07-06 | 2005-06-07 | Const of Walkwa in the park opp H.no. 83A WP block, Pd grit wash (Inner Portion) and gate in parks opp 32A and 83A in WP block and Pdg and fixing of grill on B.wall of park opp H.no. 54 A in YP block Pitampura in C 32. | 167565 | RD-I | 32 | 407/09.11.05/EE( R)-I | M/s Laxmen Const.Co | 02.01.06 | 03.08.06 | 158025 |  |  | Comp.
23 | Civil | 2005-07-06 | 2005-06-28 | Const of Walkway in DU blcok park near H.no. 85 in Pitampura in C 32. | 119174 | RD-I | 32 | 409/09.11.05/EE(R )-I | M/s Laxmen Const.Co | 02.01.06 | 03.07.06 | 107501 |  |  | Comp.
24 | Civil | 2005-07-06 | 2005-07-05 | Imp of rd from 127 to 140 and 20 to 1 in NP block Pitampura in C 32(By MP) | 109400 | RD-I | 32 | 295/22.8.05 | M/s Anil Kr Gupta | 25.8.05 | 30.11.05 | 109311 |  |  | Comp
25 | Civil | 2005-07-19 | 2005-06-28 | Imp to open space by KSF of SU block Mkt in Pitampura in C 32. | 245468 | RD-I | 32 | 416/09.11.05 | M/s Vinod Associates | 11.11.05 | 20.02.06 | 245332 |  |  | Comp
26 | Civil | 2005-07-19 | 2005-06-28 | Imp ot D/system from Corner of MC Pry school CP block to opp H.no. 132 in CP block Pitampura in C 32. | 295769 | RD-I | 32 | 371/11.10.05 | M/s Satish Gupta & Co | 15.10.05 | 30.01.06 | 295632 |  |  | Comp
27 | Civil | 2005-07-19 | 2005-07-05 | Imp to D/system and lane from 99 to 104 and 126 to 121 and opp Jain Sthanak inNP block and 56 to 88 in PP block Pitampura in C 32 | 191758 | RD-I | 32 | 372/11.10.05 | M/s Satish Gupta & Co | 15.10.05 | 12.12.05 | 191591 |  |  | Comp
28 | Civil | 2005-07-20 | 2005-07-05 | Imp ot Drainage sytem from H.no. 48 to 40, 31 to 39, 11 to 19, 28 to 20 and 51 to 59 in FD block, Pitampura inC 32. | 361200 | RD-I | 32 | 590/03.02.06 | M/s Manoj Kumar Gupta | 08.02.06 | 25.08.06 | 223232 |  |  | Comp.
29 | Civil | 2005-07-20 | 2005-07-05 | P/F bateed wire fencing along Dda park in BN & BM (Poorvi ) and B K-2 Block in Shalimar Bagh C 31. | 99800 | RD-I | 31 | 461/01.12.05/EE(RD)-I | M/s Chauhan Const Co. | 01.12.05 | 08.02.06 | 99800 |  |  | Comp.
30 | Civil | 2005-07-29 | 2005-07-11 | Imp of lane by pdg RMC from H.no. 90 to 99 in AM block in Shalimar Bagh in C 31 | 466732 | RD-I | 31 | 376/14.10.05 | M/s Ess Kay Const co. | 14.10.05 | 20.01.06 | 466620 |  |  | Comp
31 | Civil | 2005-08-02 | 2005-07-22 | Imp ot D/system from 105A to 109A, 128A to 121A, 120 A to 117A, 140A to 143A, 129A to 145A 141A to park & 116 A to 114A in U & V block in Shalimar Bagh in C 32. | 437006 | RD-I | 32 | 503/23.12.05/EE(R )-I | M/s Ravinder Const.Co | 03.05.06 | 16.11.06 | 436904 |  |  | Comp.
32 | Civil | 2005-08-02 | 2005-07-22 | Imp of D/system from H.no. 1 to 45 & 155 to 46 in FU block Pitampura | 280700 | RD-I | 32 | 591/03.02.06 | M/s Manoj Kumar Gupta | 08.02.06 | 05.08.06 | 171560 |  |  | Comp.
33 | Civil | 2005-08-02 | 2005-07-22 | Imp to D/system from H.no. 111A to Park 110A to 46A, 140A to 11A, and 124A to 12A in VP blcok, Pitampura . | 645400 | RD-I | 32 | 589/03.02.06 | M/s Manoj Kumar Gupta | 08.02.06 | 25.08.06 | 425575 |  |  | Comp.
34 | Elect. | 2005-08-08 | 2005-07-06 | p/O Semi High Mast light in MCD parkl situated in LK (New ) Block, Pitampura under Rz | 155809 | EEE-VII | 32 | 207/19.12.05 | M/s Malhotra Elect. | 27.12.05 | 12.01.06 | 146221 |  |  | Comp.
35 | Elect. | 2005-08-08 | 2005-07-16 | Prov. Of semi high mast light opp Man Singh Sewa sadan KP Block Community Centre, Pitam pura under RZ | 182403 | EEE-VII | 32 | 115/16.11.05 | M/s Himanshu Enterprises | 17.11.05 | 25.11.05 | 180133 |  |  | Comp.
36 | Civil | 2005-08-08 | 2005-07-22 | P/F barbed wire ofacneing in Vaishali opp H. no. 230 to 222 and to 138 and C/o B/wall opp no. 150(Near Mkt ) in Viahshali, Pitampura in RZ | 75800 | EEE-VII | 32
37 | Elect. | 2005-08-23 | 2005-08-10 | Prov of Semi High Mast Lights in MPl park opp Govt Sarvodya School FU block Pitampura unnder RZ | 189723 | EEE-VII | 32 | 150/22.11.05 | M/.s S.K. Enterprises | 1.12.05 | 30.12.05 | 180051 |  |  | Comp
38 | Elect. | 2005-08-23 | 2005-08-11 | Prov of Semi High Mast Light in Mpl park adj LU Block Mkt, Pitam pura under RZ | 189381 | EEE-VII | 32 | 184/06.12.05 | M/s Pragati Engineers | 14.12.05 | 09.01.06 | 178277 |  |  | Comp
39 | Elect. | 31.8.05. | 25.8.05 | P/O Semi Hgih Mast light in MCD park adj H.no. BT-44, Shalimar bagh RZ | 182534 | EEE-VII | 31 | 322/14.03.06 | M/s Saksham Elect.& Electronic | 16.03.06 | 31.03.06 | 134457 |  |  | Comp
40 | Elect. | 31.8.05. | 27.8.05 | Pro. Of Semi High Mast ligth inj MCD park adj House No. BK-I,/192,, shalimar Bagh under Rz | 183832 | EEE-VII | 31 | 308/07.03.06 | M/s Khanna Sales Corp. | 08.03.06 | 16.03.06 | 133777 |  |  | Comp
41 | Elect. | 20.10.05 | 6.10.5 | P/O Semi High Mast Light in MCD park Situated in AJ block, Shaliamrg Bagh, RZ | 183001 | EEE-VII | 31 | 307/07.03.06 | M/s Khanna Sales Corp. | 08.03.06 | 16.03.06 | 133256 |  |  | Comp
42 | Civil | 23.11.05 | 22.11.05 | P/F MS Grills flowers bneds along DAV School at Shaheed Udham singh Marg in Shalimar Bagh in C -31. | 64850 | RD-I | 31 | 50/22.06.06/EE®-I | M/s Pawan Kumar | 04.07.06 | 21.02.07 | 64735 |  |  | Comp.
43 | Civil | 13.1.06 | 13.12.05 | Pdg Red Sand Stone on outer face of Shelter in BD-FD park G & JV Park and HP Block park in Pitampura C 32 | 131400 | RD-I | 32 | 676/17.03.06/EE(R )-I | M/s Pee Kay Const. | 05.05.06 | 19.06.06 | 84354 |  |  | Comp.
44 | Civil | 3.2.06 | 2.2.06 | Pdg Kota Stone Floorig inOpen space of MP Block Market in Pitampura in C 32 | 238232 | RD-I | 32 | 10/10.04.06/EE(R )-I | M/s Lalit Const.Co | 15.06.06 | 18.07.06 | 221555 |  |  | Comp.
45 | Civil | 3.2.06 | 2.2.06 | Pdg RMC from H.no. C V -53 to CU-104 & opposite CV -44 (along park) and oppsoite CU 40 to CU 37 in CU Block Pitampura in C 32. | 147700 | RD-I | 32 | 22/25.04.06/EE(R )-I | M/s Manoj Kumar Gupta | 02.06.06 | 08.09.06 | 142190 |  |  | Comp.
46 | Civil | 3.2.06 | 2.2.06 | Remodelling to Drainage system and pdg CC on side berms from SU Block park corner to RU 169 in Pitam,pura in C 32. | 596900 | RD-I | 32 | 765/31.03.06 | M/s Rakesh Kumar Goel | 03.05.06 | 26.06.06 | 428208 |  |  | Comp.
47 | Civil | 14.2.06 | 2.2.06 | Pdg RMC in opne space and Kota Stone Flooring in Passage of CUI block kota in Pitampura in C 32 | 1165867 | RD-I | 32 | 29/03.05.06/ EE ( R) -I | M/s Lalit Const.Co | 21.06.06 | 08.12.06 | 1105383 |  |  | Comp.
48 | Civil | 20.02.06 | 16.2.06 | Const of back lane from H.no. 54 ti 67,67 to 70 in LU Bloc in Pitampura in C 32 | 198100 | RD-I | 32 | 743/31.03.06/EE(R )-I | M/s Shree Balaji Const.Co | 18.05.06 | 19.07.06 | 140007 |  |  | Comp.
[5 empty] | 12519662 | [6 empty] | 10917869

## 20
STATUS REPORT FOR THE MLA FUND YEAR 2005-06
MUNICIPAL CORPORATION OF DELHI
Rohini zone
Name of MLA :- Sh. Jai Bhagwan Aggarwal |  |  |  | A.C. No. 20 | Year :- 2005-06
Name of Constituency :- Badli
S.No | Department | Date of Booking | Date of Consent | Name of Work | Amount | Div. | Ward no. | Work order No. with Date | Name of Agency | A.D.O.S. | A.D.O.C. | Expenditure | Phy. Tar. | Phy. Ach. | Remarks
Total
1 | Elect. | 17.5.05 | 9.9.04 | Prov. Of Semi High Mast Lights in Mpl park opp. Aggarwal Bhawan, G-5,S ect-16,R Z | 172082 | EEE-VII | 33 | 51/12.8.05 | M/s Master Electric Store | 17.8.05 | 26.8.05 | 140670 |  |  | Comp.
2 | Elect. | 9.6.05 | 2.6.05 | Prov. Of Semi High Mast Lights in Mpl park at H-1/H-2 Block, Sector-16, R Z | 145089 | EEE-VII | 33 | 50/12.805 | M/s Master Electric Store | 16.8.05 | 26.8.05 | 119630 |  |  | Comp.
3 | Elect. | 9.06.05 | 2.6.05 | Prov. Of Semi High Mast Lights in park at F-17, Sect-8, RZ | 174482 | EEE-VII | 33 | 59/24.8.05 | M/s SG Enterprises | 26.8.05 | 5.9.05 | 143280 |  |  | Comp.
4 | Elect. | 9.06.05 | 2.6.05 | Prov. Of Semi High Mast Lights in Mpl park at G-2 Block, Sec-16, RZ | 173216 | EEE-VII | 33 | 52/12.805 | M/s Bansal Electric Store | 13.8.05 | 29.8.05 | 145590 |  |  | Comp.
5 | Civil | 2005-07-01 | 2005-06-27 | construction of ahatas by providing interlooking pavers of H.No.165 to 172,H.No. 143 to 150 & near 199 in pkt. B-5 sec-V Rohini C-33 R-II. (Rs.180800/-) | - | R-II | 33 | Work cancelled as desired by area MLA vide his letter dated 11.02.08 and approved by SE(RZ) on dated 14.02.08
6 | Civil | 2005-07-01 | 2005-06-27 | Const. Of Ahatas by providing interlocking pevers of H.No.37 to 54 and H.No. 173 to 179 in pkt. B-5 sec-V, Rohini C-33 R-II. | 186600 | R-II | 33 | 172/20.07.05/EE(R )-II | M/s Amandeep Consts. Co | 22.07.05 | 30.07.06 | 186500 |  |  | Comp.
7 | Civil | 2005-07-01 | 2005-06-27 | Const. Of back lane & side berms by blg. Interlocking tiles from H.No. 1to6 in pkt. H-4 Sec-II, Rohini C-33 R-II. | 171700 | R-II | 33 | 167/20.07.05 | M/s Khatri Const oc. | 5.8.05 | 8.10.05 | 151927 |  |  | Comp
8 | Civil | 2005-07-01 | 2005-06-27 | Const. Of Parking Area & berms by blg. Interlocking tiles in the surrounding of E-Block Prashant Vihar Market in Prashant Vihar C-33 R-II. | 161400 | R-II | 33 | 166/20.07.05/EE(R )-II | M/s Vikas Bansal | 04.08.05 | 02.01.06 | 161248 |  |  | Comp.
9 | Civil | 2005-07-01 | 2005-06-15 | Imp. of Ahatas by interlocking paversfrom H.No. 301 to 314 & 293 to 300 in pkt. D-II sec-7 Rohini in C-33 R-II. | 150820 | R-II | 33 | 176/27.7.05 | M/s Vijay Bansal | 7.8.05 | P | 150288 |  |  | Comp.
10 | Civil | 2005-07-01 | 2005-06-15 | Const of lane by pd RMC near H NO 30 in E-4 Sect. 11 Rohini C-33 R II | 521117 | R-II | 33 | 370/22.11.05 | M/s Vijay Kumar-II | 23.11.05 | 14.03.06 | 521037 |  |  | Comp.
11 | Civil | 2005-07-01 | 2005-06-15 | Imp of park by quit wash & M.S grill near H No 23 in E -4 sec. 11 Rohini C-33 R II | 132200 | R-II | 33 | 481/09.03.06/EE( R)-II | M/s A.D Const.Co | 14.04.06 | 27.06.06 | 103180 |  |  | Comp.
12 | Civil | 2005-07-01 | 2005-06-22 | Const of Ahatas by i/ locking pavers of H No 361 to 378 & 211 to 224 in pkt Pkt E-16 sec 7 Rohini in C-33 R II | 267128 | R-II | 33 | 326/21.10.05 | M/s Ajay Enterprises | 2.11.05 | P | 265764 |  |  | comp
13 | Civil | 2005-07-01 | 2005-06-22 | Const of Ahatas by pdg i/locking prefeb parvers of H No 37 to 48 & 85 to 96 in pkt A -3 ,sec 7 Rohini C-33 R II | 283781 | R-II | 33 | 357/18.11.05 | M/s Surander Kumar verma | 14.12.05 | 25.02.06 | 283278 |  |  | comp
14 | Civil | 2005-07-01 | 2005-06-22 | Const of Ahatas by pdg i/locking prefeb parvers of H No 9 to 22 & 95 to 112 in pkt E -16,sec 8 Rohini in C-33 R II | 271060 | R-II | 33 | 310/11.10.05 | M/s Hindustan Const Co. | 20.10.05 | 10.02.06 | 270105 |  |  | comp
15 | Civil | 2005-07-01 | 2005-06-22 | Const of Ahatas by pdg i/locking prefeb parvers of H No 49 to 60 pkt A-3 sec 7 & H No 383 to 396 pkt D -11,sec 7 Rohini in C-33 R II | 280265 | R-II | 33 | 349/16.11.05 | M/s Anil Goel | 17.11.05 | 06.02.06 | 279070 |  |  | comp
16 | Civil | 2005-07-01 | 2005-06-22 | Const of Ahatas by pdg i/locking prefeb parvers of H No 9 to 22 in pkt D -16,pkt -21 sec 7 Rohini in C-33 R II | 261359 | R-II | 33 | 343/16.11.05 | M/s Hindustan Const Co. | 20.11.05 | 12.12.05 | 260771 |  |  | Comp
17 | Civil | 2005-07-01 | 2005-06-22 | Const of Ahatas by pdg i/locking prefeb parvers of H No 9 to 22 &40 to 54 in pkt B -4 sec 8 Rohini in C-33 R II | 369800 | R-II | 33 | 297/5.10.05 | M/s Bhagwati Const co. | 6.10.05 | 8.12.05 | 265993 |  |  | Comp
18 | Civil | 2005-07-01 | 2005-06-22 | Const of Ahatas by pdg i/locking prefeb parvers of H No 1 to 12 & 13 to 24 in pkt A -3 sec 7 Rohini in C-33 R II | 392900 | R-II | 33 | 298/06.10.05 | M/s Ajay Enterprises | 28.11.05 | 26.12.05 | 284313 |  |  | comp
19 |  |  |  | Cancelled |  |  |  | Work cancelled as desired by area MLA vide his letter dated 27/11/06 and approved by CE-V on dated 30/11/06
20 | Civil | 2005-07-05 | 2005-06-23 | Const of B/ wall with M.S Girll and grit wash of park near H no G-9 /172 sector 16 , Rohini in C-33 II | 291250 | R-II | 33 | 307/10.10.05 | M/s Anil Goel | 21.10.05 | 27.02.05 | 290713 |  |  | Comp
21 | Civil | 2005-07-05 | 2005-06-23 | Const of B/ wall with M.S Girll and grit wash of park near H no G-8/113 in sector 16 , Rohini in C-33 II | 400700 | R-II | 33 | 306/10.10.05 | M/s Anil Goel | 20.10.05 | 27.02.06 | 286383 |  |  | Comp
22 | Civil | 2005-07-05 | 2005-06-23 | Const of B/ wall with M.S Girll and grit wash of park near H no G-3/50 in sector 16 , Rohini in C-33 II | 401700 | R-II | 33 | 305/10.10.05 | M/s Anil Goel | 22.10.05 | 27.02.06 | 288504 |  |  | Comp.
23 | Civil | 2005-07-06 | 2005-06-04 | I/S of 8.5 metre Row lane by pdg RMC H NO 75 to 84 . 99 to 108in PKt A -3 sector 11 Rohini. | 514900 | Br-IV | 33 | 30/20.10.05 | M/s Sajjan Engineers & Builders | 1.11.05 | 28.12.05 | 466298 |  |  | Comp.
24 | Civil | 2005-07-07 | 2005-05-30 | Imp/stg of 9 mtr. Row internal lanes by pgdin B-4 block RMC sector 11 Rohini H No33 | 1126400 | Br-IV | 33 | 40/22.02.06 | M/s Sunil Enterprises | 20.02.06 | 24.05.06 | 1035764 |  |  | Comp.
25 | Civil | 2005-07-25 | 2005-07-02 | Const of Park in Pkt C-11 sector 5 by grit wash and Plaster and providing C-C in Pkt C-11 Sector 5 Rohini in C-33 R II (Rs.471200.00) |  | R-II | 33 |  | Work cancelled as desired by area MLA vide his letter no.08/35 dated 24.01.08 and approved by DC (Rohini Zone) on dated 25.01.07
26 | Civil | 2005-07-25 | 2005-07-02 | Const of walkway by i/l prefeb pervers in the park in front of Navyug Apptt. In Sector 9 Rohini in C-33 R II (Rs.427000/-) | - | R-II | 33 |  | Work cancelled as desired by area MLA vide his letter dated 11.02.08 and approved by DC(RZ) on dated 14.02.08
27 | Civil | 2005-07-25 | 2005-07-04 | Const of B/Wall of Park by grit wash of M.S grill opp. H No 94 in Pkt A-1 sec 8 Rohini in C-33 R II | 471500 | R-II | 33 | 488/09.03.06/EE(R )-I | M/s S.S Rana Const.Co | 17.04.06 | p | 297775 |  |  | In Prog.
28 | Civil | 2005-07-25 | 2005-07-13 | Imp. of lane by pdg RMC from H No 19 to 24 in Pokt G-8 sec 11 Rohini in C-33 R II | 370000 | R-II | 33 | 442/03.02.06 | M/s Rajeev Gupta | 04.02.06 | 07.03.06 | 346172 |  |  | Comp.
29 | Civil | 2005-08-04 | 2005-07-12 | Cost of drain L.H.S on Sizra road village Libas pur from Khasra No9/12 to Khasra No 5/18 in C-34 I R II | 752449 | R-II | 34 | 325/21.10.05 | M/s Raja Const.Co | 28.10.05 | 05.03.06 | 599127 |  |  | Comp.
30 | Civil | 2005-08-04 | 2005-07-12 | Imp. to drainage system by pdg O.S drain in village samaipur from Laxmi Dharam Kanta to H no 11 (both sides) in C-34 (R) II | 199200 | R-II | 34 | 227/25.8.05 | M/s Shri Varshnay Const co. | 3.9.05 | 2.12.05 | 191903 |  |  | Comp
31 | Civil | 2005-08-04 | 2005-07-12 | Imp to road by M/P from Auchandi road to H No 10 in Samai pur Villae in C-34 I (R) II | 199900 | R-II | 34 | 223/25.08.05 | M/s Anil Goel | 03.09.05 | 28.12.05 | 197503 |  |  | Comp
32 | Elect. | 2005-08-08 | 2005-07-30 | Provision of Semi high mast lights in mpl park opp. H NO E-25 , Prashant Vihar under R .T | 177935 | EEE-VII | 33 | 121/16.11.05 | M/s Kamal Electrical | 24.11.05 | 22.12.05 | 177860 |  |  | Comp
33 | Civil | 9.11.05 | 26.10.05 | Imp of road & drainage from H;no. 152 to 162 in Block H-1 in Sec-11 Rohini by pdg RMC | 270000 | Br-IV | 33 | 64/31.03.06 | M/s D.R.builders | 10.04.06 | 15.06.06 | 218775 |  |  | Comp.
34 | Civil | 9.11.05 | 26.10.05 | Imp of rd and driange from H.no. 55 to 62 and 72 to 80 in Block H-3, in Sec-11 Rohini by pdg RMC | 500000 | Br-IV | 33 | 65/31.03.06 | M/s D.R.builders | 10.04.06 | 20.06.06 | 405025 |  |  | Comp.
35 | Elect. | 9.11.05 | 26.10.05 | Prov. Of Semi High Mast light in park near RG Compex, Sector 14, RZ | 178939 | EEE-VII | 33 | 245/12.1.06 | M/s Master Electric Store | 13.1.06 | 16.1.06 | 170710 |  |  | Comp
36 | Elect. | 9.11.05 | 25.8.05 | P/O Semi High Mast light park, Pkt F 24, Sctor 7,R Z | 185978 | EEE-VII | 33 | 246/12.1.06 | M/s Master Electric Store | 131.06 | 16.1.06 | 174322 |  |  | Comp
37 | Civil | 3.1.06 | 21.11.05 | Const of lane by RMC & drainage system from G 182 to G 191 in Prashant vihar in C 33-I | 260109 | R-II | 33 | 517/17.03.06/EE(R )-II | M/s Krishna Const.Co | 07.04.06 | 04.07.06 | 259989 |  |  | Comp.
38 | Civil | 3.1.06 | 21.11.05 | Const of Lane by pdg RMC and Drainage system from E -25 to end of | 287822 | R-II | 33 | 514/17.03.06 | M/s Friends Const. & B.M.Suppliers | 08.04.06 | 24.06.06 | 287603 |  |  | Comp.
39 | Civil | 3.1.06 | 21.11.05 | Const of berms by pdg inter locking tiles and Drainage system from A -1 /60 to PWD road in Sec-8 in C 33-I | 190200 | R-II | 33
40 | Civil | 3.1.06 | 21.11.05 | Const of lane by pdg inter locking tiles and Drainage system from A -1/60 to PWD road in Sec-8 in C -33-I | 266777 | R-II | 33 | 22/17.04.06/EE(R )-II | M/s Konark Const.Co | 27.04.06 | 30.06.06 | 266419 |  |  | Comp.
41 | Civil | 3.1.06 | 21.11.05 | Const of lane by pdg RMC & Drainage system from E -13 to E -18 and adj lane in Parshant Vihar in C 33-I | 257336 | R-II | 33 | 09/17.04.06/EE(R )-II | M/s Mukesh Kumar Bansal | 20.04.06 | 28.06.06 | 257159 |  |  | Comp.
42 | Civil | 3.1.06 | 21.11.05 | Const of Berms by pdg CC & Inte lociing toel from D 14/72 in C infront of PWD road in Sector-8, RZ | 230707 | R-II | 33 | 04/13.04.06 | M/s Konark Const.Co | 30.04.06 | 25.06.06 | 230531 |  |  | Comp.
43 | Civil | 3.1.06 | 21.11.05 | Const of berm by pdg CC & Intelocking tiles & Drainage system along vikas sheet apptt in sector -9,R Z | 213899 | R-II | 33 | 01/13.04.06/EE(R )-II | M/s Krishna Const.Co | 23.04.06 | 20.07.06 | 213449 |  |  | Comp.
44 | Civil | 3.1.06 | 21.11.05 | Const of road & side berms by pdg PMP and I/l tiles along Jhang Aptt. In Sector 13 RZ | 592050 | R-II | 33 | 24/17.04.06/EE( R)-II | M/s Krishna Const.Co | 30.04.06 | 02.09.06 | 427796 |  |  | Comp.
45 | Civil | 3.1.06 | 21.11.05 | Const of Ahatas by I/l prefeb pavers from H.n o. 1 to 8,37 to 54, and 83 to 90 in pkt D 8, Secto-6, RZ | 104684 | R-II | 33 | 126/26.05.07/EE-R-I/ | M/s Chauhan Const.Co | 28.05.06 | P | 51990 |  |  | In Prog.
46 | Civil | 3.1.06 | 21.11.05 | Const of Ahatas by I/l prefeb pavers from H.n o. 19 to 27 & 277 to 288 in pkt D 6, Secto-6, RZ | 199200 | R-II | 33 | 125/26.05.06/EE(R )-II | M/s Chauhan Const.Co | 02.09.06 | P | 97273 |  |  | In Prog.
47 | Civil | 3.1.06 | 21.11.05 | Const of Ahatas by I/l prefeb pavers from H.n o. 247 to 265 & 99 to 112 in pkt G-22 sec-7, RZ | 108102 | R-II | 33 | 101/11.05.06/EE(R )-I | M/s Krishna Const.Co | 21.05.06 | 12.08.06 | 108092 |  |  | Comp.
48 | Civil | 3.1.06 | 21.11.05 | Const of Ahatas by I/l prefeb pavers from H.n o. 391 to 399 & 241 to 251 in pkt D-6 sec-6, RZ | 198000 | R-II | 33 | 116/24.05.06/EE(R )-I | M/s R.B Builders & Consts. | 30.06.06 | P | 95970 |  |  | In Prog.
49 | Civil | 3.1.06 | 21.11.05 | Const of Ahatas by I/l prefeb pavers from H.n o. 391 to 399 & 241 to 251 in pkt D-6 sec-6, RZ (Rs.199000/-) | - | R-II | 33 | Work cancelled as desired by area MLA vide his letter dated 11.02.08 and approved by SE(RZ) on dated 14.02.08
50 | Civil | 3.1.06 | 21.11.05 | Const of Ahatas by I/l prefeb pavers from H.n o. 181 to 192 & 343 to 354 in pkt D-6 sec-6, RZ | 107142 | R-II | 33 | 100/11.05.06/EE(R )-II | M/s Krishna Const.Co | 20.05.06 | 17.07.06 | 107137 |  |  | Comp.
51 | Civil | 3.1.06 | 21.11.05 | Const of Ahatas by I/l prefeb pavers from H.n o.367 to 378 in pkt A-1, Sect-6, & 301 to 312 in pkt D 6, sec-6, RZ | 106665 | R-II | 33 | 128/29.05.06/EE(R )-II | M/s Krishna Const.Co | 08.06.06 | 26.07.06 | 106456 |  |  | Comp.
52 | Civil | 3.1.06 | 21.11.05 | Const of Ahatas by I/l prefeb pavers from H.n o.61 to 72 in Pkt B-6 Sect 5 & 443 to 456 i in Pkt D -16 , sec-7, RZ | 106773 | R-II | 33 | 103/12.05.06/EE(R )-II | M/s Krishna Const.Co | 22.05.06 | 30.06.06 | 106724 |  |  | Comp.
53 | Civil | 3.1.06 | 21.11.05 | Const of Two Umbrella in park in Pkt G 20 & G 22 in Sect 7, RZ | 295044 | R-II | 33 | 508/17.03.06/EE(R )-II | M/s Pushpa Builder | 26.03.06 | 24.06.06 | 294123 |  |  | Comp.
54 | Civil | 3.1.06 | 21.11.05 | Const of walkway in Central park of F 24 Sect 7 RZ | 302000 | R-II | 33 | 02/13.04.06/EE(R )-II | M/s Krishna Const.Co | 23.04.06 | P | 177182 |  |  | In Prog.
55 | Civil | 3.1.06 | 21.11.05 | Const berms by I/l Preferb pavers near h.n o. 1 to Pkt B-1 & along park in Prashant Vihar in C 33-I (Rs.124300/-) | - | R-II | 33 | Work cancelled as desired by area MLA vide his letter dated 11.02.08 and approved by SE(RZ) on dated 14.02.08
56 | Civil | 3.1.06 | 21.11.05 | Const of lane by Har Lal Mkt by RMC in Village Naharpur in C 33-1 | 532987 | R-II | 33 | 70/25.04.06/EE(R )-II | M/s Sarthak Const.Co | 07.05.06 | 01.07.06 | 529652 |  |  | Comp.
57 | Civil | 3.1.06 | 21.11.05 | const of Ahata by I/l Perfeb pavers H.n. 291 to 296 & H.n. 223 to 230 in Pkt B 6, Sect-7 Rohini | 198500 | R-II | 33 | 123/26.05.06/EE(R )-II | M/s J.M.D Const.Co | 10.07.06 | P | 103852 |  |  | In Prog.
58 | Civil | 3.1.06 | 21.11.05 | const of Ahata by I/l Perfeb pavers 327, H.n. 121 to 127, 144 to 150 & 254 tp 260 in Pkt B 6, Sect-7 Rohini | 126726 | R-II | 33 | 124/26.05.06/EE(R )-II | M/s J.M.D Const.Co | 30.05.06 | 31.07.06 | 126136 |  |  | Comp.
59 | Civil | 3.1.06 | 21.11.05 | const of Ahata by I/l Perfeb pavers 327, H.n. 231 to 237, 91 to 97, 114 top 120 in Pkt B 6, Sect-7 Rohini | 126986 | R-II | 33 | 139/07.06.06/EE( R)-II | M/s J.M.D Const.Co | 08.06.06 | 31.07.06 | 126350 |  |  | Comp.
60 | Civil | 3.1.06 | 18.10.05 | Const of Arya Samaj Mandir road by C C in Pkt C 7, Sector 7, RZ | 134150 | R-II | 33 | 542/29.03.06/EE(R )-II | M/s Om Const.Co | 10.04.06 | 22.08.06 | 133722 |  |  | Comp.
61 | Elect. | 27.2.06 | 13.10.05 | P/O 40 nos HPSV Stree Light arrangement in Secot -6 and 8, Rohini under RZ | 142715 | EEE-VII | 33 | 383/31.03.06 | M/s Bansal Electric Store | 31.03.06 | 05.05.06 | 98460 |  |  | Comp.
62 | Elect. | 27.2.06 | 13.10.05 | P/O 40 nos HPSV Stree Light arrangement in Secot -7, Rohini under RZ | 177482 | EEE-VII | 33 | 380/31.03.06 | M/s Bansal Electric Store | 31.03.06 | 04.05.06 | 124055 |  |  | Comp.
63 | Elect. | 27.2.06 | 13.10.05 | P/O 50 nos HPSV Stree Light arrangement in Block A, B and C, Prashant Vihar under Rohini under RZ | 180261 | EEE-VII | 33 | 379/31.03.06 | M/s Bansal Electric Store | 31.03.06 | 05.05.06 | 127260 |  |  | Comp.
64 | Elect. | 27.2.06 | 13.10.05 | P/O 50 nos HPSV Stree Light arrangement in Secot-8, Rohini under RZ | 177752 | EEE-VII | 33 | 378/31.03.06 | M/s Bansal Electric Store | 31.03.06 | 04.05.06 | 123500 |  |  | Comp.
65 | Elect. | 27.2.06 | 13.10.05 | P/O 40 nos HPSV Stree Light arrangement in village Naharpur and Rajapur , Rohini,. under RZ | 148668 | EEE-VII | 33 | 381/31.03.06 | M/s Prince Engg.Works | 07.04.06 | 05.05.06 | 102690 |  |  | Comp.
66 | Elect. | 27.2.06 | 13.10.05 | P/O 50 nos HPSV Stree Light arrangement in Block A, B and C, Sector-5, Rohini under RZ | 180967 | EEE-VII | 33 | 382/31.03.06/EE(E)-VII | M/s Maya Elect. | 08.04.06 | 02.05.06 | 101820 |  |  | Comp.
67 | Elect. | 27.2.06 | 13.10.05 | P/O 50 nos HPSV Stree Light arrangement in Sector-5, Rohini under RZ | 177752 | EEE-VII | 33 | 384/31.03.06/EE(E)-VII | M/s Master Electric Store | 31.03.06 | 04.05.06 | 123360 |  |  | Comp.
68 | Elect. | 27.2.06 | 13.10.05 | Prov. Of HPSV 70w Street light arrangement in Swaroop Nagar & Yadav Nagar ni W.no. 34 Under RZ | 148114 | EEE-VII | 34 | 385/31.03.06/EE(E)-VII | M/s Maya Elect. | 06.04.06 | 13.04.06 | 84992 |  |  | Comp.
69 | Elect. | 27.2.06 | 13.10.05 | Prov. Of HPSV 70w Street lights arrangement in Block A, B , C and D block Sector-15, Rohini | 165103 | EEE-VII | 34 | 387/31.03.06/EE(E)-VII | M/s Seth Const. | 06.04.06 | 13.04.06 | 106940 |  |  | Comp.
70 | Elect. | 27.2.06 | 13.10.05 | Prov. Of HPSV 70w Street lights arrangement in village Badli under Rohini Zone | 181216 | EEE-VII | 34 | 386/31.03.06/EE(E)-VII | M/s Seth Const. | 06.04.06 | 13.04.06 | 114930 |  |  | Comp.
[5 empty] | 16781739 | [6 empty] | 14095090
Remarks: 70-6(NO.19 is Cancelled)= 64

## 21
STATUS REPORT FOR THE MLA FUND YEAR 2005-06
MUNICIPAL CORPORATION OF DELHI
Rohini zone
Name of MLA :- Sh. Kulawant Rana |  |  |  | A.C. No. 21 | Year :- 2005-06
Name of Constituency :- Shahbad Daulatpur
S.No | Department | Date of Booking | Date of Consent | Name of Work | Amount | Div. | Ward no. | Work order No. with Date | Name of Agency | A.D.O.S. | A.D.O.C. | Expenditure | Phy. Tar. | Phy.Ach | Remarks
Total
1 | Civil | 6.6.05 | 31.5.05 | const of D/System & main lane by CC in Sanjay Mkt village Mangolpur Kalan in C 35 R_II | 165950 | R-II | 35 | 103/20.6.05 | M/s SM Const Co. | 5.9.05 | 28.10.05 | 162273 |  |  | Comp
2 | Civil | 6.6.05 | 31.5.05 | Pdg CC pav in damaged lane from H.no 40 to 48 & 57 to 49 in B block Sanjay Mkt Mangolpur Kalan C-35. | 192500 | R-II | 35 | 104/20.6.05 | M/s Gobinda Enterprises | 10.9.05 | 27.9.05 | 191954 |  |  | Comp
3 | Civil | 6.6.05 | 31.5.05 | Pdg CC pav in damaged lane from H.no 1 to 10 and H.no. 11 to 20 in B block Sanjay Mkt Mangolpur Kalan C-35. | 190700 | R-II | 35 | 105/20.06.05 | M/s Parkash Const. | 16.09.05 | P | 126765 |  |  | In Prog.
4 | Civil | 6.6.05 | 6.6.05 | Pdg CC pav in damaged lane from H.no 1 to 30 and H.no. 31 to 39 in B block Sanjay Mkt Mangolpur Kalan C-35. | 177200 | R-II | 35 | 102/20.6.05 | M/s Trimurti Trading | 10.9.05 | 26.9.05 | 176277 |  |  | Comp
5 | Elect. | 2005-07-27 | 2005-05-01 | P/O boring with submersible pump set of physical centre in vill pooth kalan in ward no 36 under R Z | 176035 | EEE-VII | 36 | 242/04.01.06 | M/s V.V Enterprises | 04.01.06 | 21.01.06 | 172124 |  |  | Comp
6 | Elect. | 2005-08-05 | 2005-07-05 | Provision of 39 Nos street light arrangement in Vijay Vihar Ph II under R Z | 198791 | EEE-VII | 35 | 98/07.11.05 | M/s Kamal Electriclas | 14.11.05 | 12.12.05 | 195783 |  |  | Comp.
7 | Elect. | 2005-08-05 | 2005-07-05 | Provision of 39 Nos street light arrangement at karman panna, Mahajan panna near Kanjhawala road pooth kalan ward no 36 under Rohini Zone | 198914 | EEE-VII |  | 71/24.10.05 | M/s Repair Shop | 25.10.05 | 7.11.05 | 195558 |  |  | Comp
8 | Elect. | 2005-08-05 | 2005-07-04 | Provision of 39 Nos street light arrangement on phirni road , pooth kalan , ward no 36 under R Z | 198914 | EEE-VII | 36 | 101/7.11.05 | M/s Punjab Eletric Co. | 8.11.05 | 14.11.05 | 195515 |  |  | Comp.
9 | Elect. | 2005-08-05 | 2005-07-07 | Provision of 39 Nos street light arrangement in shah bad Daulatpur Village , ward no 36 under R Z | 199100 | EEE-VII | 36 | 149/22.11.05 | M/s Sheela Electric Works | 30.11.05 | 19.12.05 | 195606 |  |  | Comp.
10 | Elect. | 2005-08-05 | 2005-07-08 | Provision of 39 Nos street light arrangement in prahladpur village ward no 36 under R Z | 199100 | EEE-VII | 36 | 143/22.11.05 | M/s MJ Electricals & Electronics | 24.11.05 | 20.12.05 | 195606 |  |  | Comp
11 | Elect. | 2005-08-05 | 2005-07-08 | Provision of 39 Nos street light arrengement in Rithala village ward no 35 , under R Z | 198976 | EEE-VII | 35 | 118/16.11.05 | M/s Krishna Eletricals | 18.11.05 | 30.11.05 | 195405 |  |  | Comp.
12 | Elect. | 2005-08-05 | 2005-07-06 | Provision of 39 Nos street light arrengement in Barwala village ward no 36 under R Z | 199100 | EEE-VII | 36 | 114/16.11.05 | M./s Kamal Electicals | 23.11.05 | 22.12.05 | 195567 |  |  | Comp
13 | Elect. | 2005-08-05 | 2005-07-11 | Provision of 39 Nos street light arrengement in Vir Singh Colony Azad Colony ,Shiv Colony and Chandu Lal Colony ,Budh Vihar Ph II under R Z | 199409 | EEE-VII | 35 | 119/16.11.05 | M/s Bansal Eletric store | 18.11.05 | 12.12.05 | 195963 |  |  | Comp
14 | Elect. | 2005-08-05 | 2005-07-06 | Provision of 39 Nos street light arrargement in Vijay Vihar Phase I under R Z | 198791 | EEE-VII | 35 | 158/06.12.05 | M/s Paras Const.CO | 12.12.05 | 12.01.06 | 195241 |  |  | Comp.
15 | Elect. | 2005-08-05 | 2005-07-06 | Provision of 39 Nos street light arragement in Harsh Dev Park , Mange Ram Park and Jaswant Colony, Budh Vihar Phase II undr R Zone | 199409 | EEE-VII | 35 | 126/16.11.05 | M/s AK Electricals | 24.11.054 | 22.12.05 | 195963 |  |  | Comp
16 | Elect. | 2005-08-05 | 2005-07-04 | Provision of 39 Nos street light arragement in Mangolpur Kalan Village under R Zone | 199162 | EEE-VII | 35 | 69/24.10.05 | M/s Bansal Eletric store | 25.10.05 | 2.11.05 | 195819 |  |  | Comp.
17 | Elect. | 2005-08-05 | 2005-07-07 | Provision of 39 Nos street light arragement in A to Y Block ,Budh Vihar Phase I under R Zone | 199223 | EEE-VII | 35 | 125/16.11.05 | M/s Sakshma Electricals * Electonics | 17.11.05 | 22.11.05 | 195819 |  |  | Comp.
18 | Elect. | 2005-08-05 | 2005-07-08 | Provision of 39 Nos street light arragement in A-1 to Y-1 Block ,Budh Vihar Phase I under R Zone | 199223 | EEE-VII | 35 | 116/16.11.05 | M/s Sakahsm Electricals & Electronics | 17.11.05 | 22.11.05 | 195863 |  |  | Comp.
19 | Elect. | 2005-08-05 | 2005-07-07 | Provision of 39 Nos street light arragement in Rithala Extension ward no 35 under R Zone | 198976 | EEE-VII | 35 | 122/16.11.05 | M/s Gyan Enterprises | 24.11.05 | 22.12.05 | 195323 |  |  | Comp.
| Elect. | 2005-08-05 | 2005-07-04 | Provision of 39 Nos street light arragement in Dada Bhaiya Mandir Road , pooth Kalan ward No36 under R Zone | 199285 | EEE-VII | 36 | 84/27.10.05 | M/s S.G. Enterprises | 3.11.05 | 30.11.05 | 195906 |  |  | Comp.
21 | Elect. | 2005-08-05 | 2005-07-05 | Provision of 39 Nos street light arragement in Sector 26,Rohini under R Zone. | 199162 | EEE-VII | 36 | 70/24.10.05 | M/s Sangwan Eletricals | 2.11.05 | 30.11.05 | 195863 |  |  | Comp.
22 | Elect. | 2005-08-05 | 2005-07-07 | Provision of 39 Nos street light arragement in Pidhotia Mohalla pooth Kalan , ward No 36 under R Zone | 199285 | EEE-VII | 36 | 85/27.10.05 | M/s Oberio Electicals | 28.10.05 | 5.11.05 | 195927 |  |  | Comp.
23 | Elect. | 2005-08-05 | 2005-07-12 | Provision of 39 Nos street light arragement in Sharma colony Budh Vihar Phase II under R Zone | 199223 | EEE-VII | 35 | 97/7.11.05 | M/s Neeraj Electricals | 14.11.05 | 9.12.05 | 195857 |  |  | Comp.
24 | Elect. | 2005-08-05 | 2005-07-06 | Provision of 39 nos street light arrangement in Mangolpur Khurd village ward no 35 under R Zone | 198976 | EEE-VII | 35 | 123/16.11.05 | M/s Vivek Electricals | 23.11.05 | 19.12.05 | 195558 |  |  | Comp.
25 | Civil | 14.9.05 | 13.9.05 | Imp of chowk by CC near Old Well in Village Shahbad Daulatpur in C 36 RZ | 160210 | R-II | 36 | 282/30.09.05/EE(R )-II | M/s Majdoor Const.Co | 02.12.05 | 23.02.06 | 160203 |  |  | Comp.
26 | Civil | 14.9.05 | 13.9.05 | Imp of lane by CC from SH. Ram Kishan house to Ayurvdic Disp and adj lane in village Shahbad Daulatpur in C 36 RZ | 183750 | R-II | 36 | 284//30.09.05 | M/s Shiv Shankar Gupta | 11.10.05 | 05.12.05 | 183723 |  |  | Comp.
27 | Civil | 18.11.05 | 12.11.05 | Imp of lane by CC pavement from Sh. Krishan House to Sh. Rajender House in village Barwala in 36 R II | 165393 | R-II | 36 | 422/06.12.05/EE(R )-II | M/s Kumar N & Sons | 04.05.06 | 09.08.06 | 165329 |  |  | Comp.
28 | Civil | 18.11.05 | 12.11.05 | Imp of lane by CC pavement from Sh.Bhim Singh House to marain Singh House and Chandgi Saini to Gurudayal House in village :Barwala in C-36 Rohini II | 180497 | R-II | 36 | 454/13.02.06/EE( R)-II | M/s Govind Gupta | 02.06.06 | 24.08.06 | 179279 |  |  | Comp.
29 | Civil | 18.11.05 | 12.11.05 | Imp of lane by CC and drainge from recreation centre to main road and vikas Tailor to Satish Hose in village Barwala in C-36 R II | 199973 | R-II | 36 | 446/03.02.06/EE(R )-II | M/s Tri Murti Trading Co. | 01.06.06 | 24.08.06 | 198916 |  |  | Comp.
30 | Civil | 18.11.05 | 12.11.05 | Imp of lane by CC from Jeet Ram House to Ram dhan House Iswar House to Ved Bhawan and A-70 t oKuldeep Rana House in Village Shah bad Daulatpur | 87429 | R-II | 36 | 421/26.12.05/EE(R )-II | M/s Surya Kant Sharma | 16.01.06 | 03.06.06 | 86562 |  |  | Comp.
31 | Civil | 18.11.05 | 12.11.05 | Imp of lane by CC from Ranbir Singh House to Rakesh Tele Centre and Parmanand House tro Umrao House in village Preladpur in C-36 R II | 143831 | R-II | 36 | 425/26.12.05/EE(R )-II | M/s Amar Chauhan | 01.06.06 | 26.07.06 | 143189 |  |  | Comp.
32 | Civil | 18.11.05 | 12.11.05 | Imp of lane by CC pavement from Shri Ram polt to Prabha Dayal Kiryana store and adjacent lane in village Pralad pur in C36 R II | 171161 | R-II | 36 | 423/26.12.05 | M/s Hari Jain Const.Co | 26.12.05 | P | 169591 |  |  | In Prog.
33 | Civil | 18.11.05 | 12.11.05 | Imp of lane by CC pavement from Pape house to Chand SinghHouse in village Parlad pur inC-36 R II | 140747 | R-II | 36
34 | Civil | 18.11.05 | 12.11.05 | Imp of lane by pdg.CC and drainage system from Sh Dariyab Singh House to Sh. Bhoopender House in village Pralad pur in C-36 R II | 184350 | R-II | 36
35 | Civil | 5.12.05 | 12.11.05 | Imp. of lane by CC pavement and drain from Sh. Tika Ram house to phirni Road in village Barwala in C-36 R II | 470150 | R-II | 36 | 487/09.03.06/EE(R )-II | M/s Konark Const.Co | 18.03.06 | 28.08.06 | 342489 |  |  | Comp.
36 | Civil | 5.12.06 | 12.11.06 | Imp of lane by CC pavement from Girish factory to Naresh factory Pt Dayanand House to Dewan House and from Rajender house to Zile Singh house in village Barwala C-36 R II | 406500 | R-II | 36 | 486/09.03.06/EE(R )-II | M/s Konark Const.Co | 18.03.06 | 28.06.06 | 289527 |  |  | Comp.
37 | Civil | 5.12.07 | 12.11.07 | Imp of lane by RMC from Sh. Devan singh house to Sh. Anand house in village Barwala in C-36 R II | 576003 | R-II | 36 | 375/08.01.07/EE®-II | M/s S.Kumar & Bros. | 08.01.07 | 28.03.07 | 574595 |  |  | Comp.
38 | Civil | 5.12.08 | 12.11.08 | Imp of lane by pdg CC from Chopal to Sushil Rana house and near Raj Roop House in village Shahbad Dulatpur in C-36 R II | 455700 | R-II | 36 | 485/09.03.06/EE®-II | M/s Konark Const.Co | 14.03.06 | 09.08.06 | 322511 |  |  | Comp.
39 | Elect. | 5.12.08 | 20.10.05 | P/O 38 nos Street Light in A -I Block, Krsihan Viarh Under Rz | 196667 | EEE-VII | 36 | 304/07.03.06 | M/s Khanna Sales Corporation | 09.03.06 | 31.03.06 | 115848 |  |  | Comp.
40 | Elect. | 5.12.08 | 24.10.05 | P/O 39 nos HPSV streeet light in JS Block, Krishans Vihar under RZ | 196264 | EEE-VII | 36 | 303/07.03.06 | M/s Khanna Sales Corporation | 08.03.06 | 31.03.06 | 128529 |  |  | Comp.
41 | Civil | 2.1.06 | 15.12.05 | Const of Two Gates at Park Mangol Pur Kalan and Mangol pur Khurd Rd no. 3, C 35. | 469800 | EEE-VII | 35 | 513/17.03.06/EE(R )-I | M/s Konark Const.Co | 07.07.06 | 13.09.06 | 389885 |  |  | Comp.
42 | Civil | 2.1.06 | 17.12.05 | Const of Two Gates at Pkt A1 & A2 park in Sector 4, Rohini C 35. | 468100 | R-II | 35 | 511/17.03.06/EE(R )-II | M/s Pushpa Builder | 19.05.06 | 26.07.06 | 391731 |  |  | Comp.
43 | Civil | 12.1.06 | 21.11.05 | Pdg and laying RMC from Sh. Rajender Pradhan hs to Nidhan Hs on Main road in villaeg Shahbad Daulatpur in C 36 R-II | 648241 | R-II | 36 | 119/24.05.06/EE( R)-II | M/s Rajeev Mittal | 05.06.06 | 30.10.06 | 648107 |  |  | Comp.
44 | Civil | 2.1.06 | 21.11.05 | Const of lane by RMC from main Auchandi Rd to Satbir Rana hs in village Shahbad Daulatpur in C 36 R-II | 1281704 | R-II | 36 | 115/23.05.06/EE( R)-II | M/s Rajeev Mittal | 05.06.06 | 30.10.06 | 1281434 |  |  | Comp.
[5 empty] | 11471874 | [6 empty] | 10318983

## 53
STATUS REPORT FOR THE MLA FUND YEAR 2005-06
MUNICIPAL CORPORATION OF DELHI
Rohini zone
Name of MLA :- Sh. Mange Ram Garg |  |  |  |  | Year :- 2005-06
A.C. No. 53
Name of Constituency :-
S.No | Department | Date of Booking | Date of Consent | Name of Work | Amount | Div. | Ward no. | Work order No. with Date | Name of Agency | A.D.O.S. | A.D.O.C. |  | Phy.Tar. | Phy Ach. | Remarks
Total
1 | Elect. | 17.5.05 | 02.03.05 | P/O Lighting arrangment with post top lantern in parks of SFS flats near flat No 214 and near SFS mkt and near B & C mkt Ashok Vihar Ph-IV & With 10 mtr pole in the park of B-3 block Ashok Vihar Ph-II RZ | 199310 | EEE-VII | 100 | 55/12.8.05 | M/s Kawatra Eletric Works | 17.8.05 | 30.9.05 | 192637 |  |  | Comp.
2 | Elect. | 17.5.05 | 3.03.05 | P/O Post Top Lighting in the parks of Nimri Cly near H.nos. 338 and near H.no. 348 in W.no. 99 RZ | 148778 | EEE-VII | 99 | 128/16.11.05 | M/s Paras Const.Co | 18.11.05 | 12.12.05 | 143264 |  |  | Comp.
3 | Elect. | 17.5.05 | 4.3.05 | P/O Post Top Lighting in the parks of SFS flat s near flat no 153, Ashok Vihar Ph-IV in W.no. 99 RZ | 195265 | EEE-VII | 99 | 54/12.8.05 | M/s Kawatra Eletric Works | 17.8.05 | 30.9.05 | 189029 |  |  | Comp.
4 | Elect. | 17.5.05 | 5.3.05 | P/O Post Top Lighting in the parks of Ashok Vihar Ph-III near Hs no A-60 in W.no. 99 RZ | 166779 | EEE-VII | 99 | 130/16.11.05 | M/s Paras Const.Co | 18.11.05 | 12.12.05 | 160942 |  |  | Comp.
5 | Elect. | 17.5.05 | 6..03.05 | Prov of Boring with Subermsible pump set at park in B-3 Block, Ashok Vihar Ph-II in W.no. 100 RZ | 197781 | EEE-VII | 100 | 129/16.11.05 | M/s Paras Const.Co | 25.11.05 | 20.12.05 | 186299 |  |  | Comp.
6 | Civil | 20.5.05 | 9.3.05 | Cosnt of Walkway in park infront of H.no. D-110 in AV, Ashok Vihar Ph-I C-100 RZ | 259600 | RD-I | 100 | 258/02.08.05 | M/s Supreme Const. | 11.8.05 | 12.9.05 | 215548 |  |  | Comp.
7 | Civil | 20.5.05 | 9.3.05 | Imp of lane by RMC from H.no. L-70 to L-92 JJ Cly Wazirpur in C-99 RZ | 199900 | RD-I | 99 | 173/20.06.05 | M/s Anhal Const.Asso. | 21.06.05 | P | 179323 |  |  | In Prog
8 | Civil | 20.5.05 | 9.3.05 | Const of walkway infront park in H.no. E-48 in Satyawati Cly in Ashok Vihar Ph=-III | 259600 | RD-I | 99 | 308/25.8.05 | M/s AB Builders | 26.8.05 | 8.10.05 | 218409 |  |  | Comp
9 | Civil | 20.5.05 | 9.3.05 | Const of Umberella in F block park in JJ cly wazirpur in C-99 RZ | 198700 | RD-I | 99 | 339/20.09.05 | M/s Raminder Const.Co | 20.09.05 | 22.11.05 | 185276 |  |  | Comp.
10 | Civil | 20.5.05 | 9.3.05 | Const of Umberalla in C block park in JJ cly Wazirpur in C-99 RZ | 198700 | RD-I | 99 | 328/12.09.05 | M/s Nishant Const.Co | 13.09.05 | 05.11.05 | 185970 |  |  | Comp.
11 | Civil | 20.5.05 | 9.3.05 | Const of Umberalla in H block park in JJ cly Wazirpur in C-99 RZ | 198700 | RD-I | 99 | 271/10.8.05 | M/s Gujral Const. | 11.8.05 | 13.10.05 | 186133 |  |  | Comp.
12 | Civil | 20.5.05 | 9.3.05 | Const of Umberalla in j-III block park (Behind Mandir) in JJ Cly Wazirpur in C-99 RZ | 198700 | RD-I | 99 | 300/24.8.05 | M/s Rakesh Kr Goel | 24.8.05 | 1.11.05 | 186401 |  |  | Comp.
13 | Civil | 20.5.05 | 9.3.05 | Imp of lane by pdg RMC from H.no. L-103 to L-166 and L-201 to L-212 in JJ Cly Wazirpur-RZ | 80000 | RD-I | 99 | 299/24.8.05 | M/s Rakesh Khanna Goel | 25.8.05 | 18.9.05 | 73478 |  |  | Comp.
14 | Civil | 20.5.05 | 9.3.05 | Imp of park near flat no B-4/73, B4/37, B4/25, B4/26A in B4 block in Ahsok Vihar Ph-II by Grit Wash | 144821 | RD-I | 100 | 15/4.8.05 | M/s Surender Const co. | 4.8.05 | 4.10.05 | 144148 |  |  | Comp.
15 | Civil | 20.5.05 | 9.03.05 | Cosnt of Umberalla in park near DTC Stand (Bus Stand) Bharat Nagar in C-99 RZ | 199000 | RD-I | 99 | 340/20.09.05 | M/s Ravinder Const.Co | 20.09.05 | 25.11.05 | 186669 |  |  | Comp.
16 | Civil | 20.5.05 | 14.03.05 | Const of B/wall of Open Sapce near H.no. A-172 and H-344 by block Masonery in JJ Wazirpur C-99. | 263700 | RD-I | 99 | 259/2.8.05 | M/s Harish Const Co. | 11.8.05 | 4.10.05 | 263700 |  |  | Comp.
17 | Civil | 14.6.05 | 14.03.05 | Imp of lane by pdg CC flooring along super bazar in Ashok Vihar PH-II C-100. | 92369 | RD-I | 100 | 190/28.6.05 | M/s Subhash Singh | 7.7.05 | 16.9.05 | 92343 |  |  | Comp.
18 | Civil | 20.6.05 | 13.06.05 | Imp of side berms by RMC along park near H.no. B-45 in Satyawati Cly in C-99 RZ | 199904 | RD-I | 99 | 195/29.6.05 | M/s BMB Enterprises | 8.7.05 | 26.11.05 | 184042 |  |  | Comp.
19 | Civil | 20.6.05 | 13.06.05 | Raising/Imp of B/wall from Corner of Maharaj Aggersain Public School to DTC Stand in Neemari Cly C-99 RZ | 199238 | RD-I | 99 | 143/28.11.05/EE (Br)-III | M/s Ravinder Const.Co | 29.11.05 | 03.02.06 | 167735 |  |  | In Prog
20 | Civil | 2005-06-27 | 14.3.05 revaledated 19.5.05 | Imp of drainage system from ch Gulab Singh Marg to corner of Kulachi Hant Raj School along Pocket A in Ashok Vihar Ph III C-100 R Z | 175915 | RD-I | 100 | 144/28.11.05 | M/s Ravinder Const.Co | 06.12.05 | 06.12.05 | 175915 |  |  | Comp
21 | Civil | 2005-06-27 | 14.3.05 revaledated 19.5.05 | Imp of B/Wall and room in park in afront of Pragati Market in C-2 Block in Ashok Vihar Ph II C 100 | 199800 | RD-I | 100 | 40/8.9.05 | M/s Gaurav Const Co. | 20.09.05 | 20.10.05 | 199800 |  |  | Comp
22 | Civil | 2005-06-27 | 2005-06-23 | Imp of ope spaceby intrerlocking parers in front of flat No 6 in M.I.G flats Ashok Vihar IV C 100 R Z | 198600 | RD-I | 100 | 45/12.09.05 | M/s Surya Kant Sharma | 23.09.05 | 29.03.06 | 188499 |  |  | Comp
23 | Civil | 2005-06-27 | 9.3.05 revaledated 19.5.05 | Imp of roads by M/P in B-4 Pkt from B-4 /73A to 76 A,36A to 22A 1A to 8Aand 30 A to 24 A in Ashok Vihar Ph II C 100 | 199972 | RD-I | 100 | 138/25.11.05 | M/s Mittal Traders | 21.12.05 | 12.01.06 | 199588 |  |  | Comp.
24 | Civil | 2005-06-27 | 9.3.05 revaledated 19.5.05 | Stg. of internal roads in SFS flatsby BM with mix seal inAshok Vihar (Shakti Apptt.) Ph III in C 99 RD I | 549022 | RD-I | 99 | 105/09.11.05/EE-(R-I) | M/s Vinod Kumar | 20.06.06 | P | 547305 |  |  | In Prog
25 | Civil | 2005-07-01 | 14.3.05 revaledated 19.5.05 | Imp of out fall drain from Deep Cinema Roa to C 3 Block in A.V Ph- II C100 RZ (Ashok Vihar) | 490584 | RD-I | 100
26 | Civil | 2005-07-06 | 2005-07-04 | Imp of back lane by cc flooring from H No B 4/109 to B4/91 and 8A to 1A in B4 pocket Ashok Vihar Ph II C100 R Z | 199996 | RD-I | 100 | 28/30.08.05/EE(Br)-III | M/s Pankaj Builders | 10.09.05 | 09.11.05 | 199996 |  |  | Comp.
27 | Elect. | 2005-07-12 | 2005-06-08 | P/O semi high mast light in the park near house no B129 Ashok Vihar Phase I underRohini Zone | 187300 | EEE-VII | 100 | 257/06.02.06 | M/s Aman Electriclas | 10.02.06 | 28.02.06 | 179261 |  |  | Comp.
28 | Elect. | 2005-07-12 | 2005-06-08 | P/o stg arrrangement in park near Sanatan Dharam Mandir Ph II in park of B Block Ph I Ashok Vihar and in park of central market Ashok Vihar Ph I under Rohini Zone | 197197 | EEE-VII | 100 | 124/16.11.05/EE(E)-VII | M/s Illuminator & Circuiters | 22.11.05 | 05.12.05 | 180194 |  |  | Comp
29 | Elect. | 2005-07-12 | 2005-06-08 | P/O semi high mast light in the park near house no B-195 Ashok Vihar Phase I underRohini Zone | 184582 | EEE-VII | 100 | 67/24.10.05 | M/s Sachdeva Electricals | 24.10.05 | 4.11.05 | 158610 |  |  | Comp
30 | Civil | 2005-07-25 | 2005-07-22 | Imp to approach road by M/P of H.G drain in JJ Colony wazirpur C-99 R Z | 199100 | RD-I | 99 | 57/22.09.05 | M/s Globe Const. | 23.09.05 | P | 188479 |  |  | Comp.
31 | Civil | 2005-07-25 | 2005-07-22 | C/O walary & Imp to park near E-27 Satyawati Colony C99 R Z | 197700 | RD-I | 99 | 22/22.8.05 | M/s Hari Jain Cosnt.Co. | 25.8.05 | 22.10.05 | 197700 |  |  | Comp
32 | Civil | 2005-07-25 | 2005-07-22 | Widening of road byM/P along park near K Block dalao in wazir pur C99 R Z | 197600 | RD-I | 99 | 19/22.08.05 | M/s Aggarwal Builders | 24.08.05 | 10.12.05 | 197176 |  |  | Comp.
33 | Civil | 2005-07-29 | 9.3.05 revaledated 19.5.05 | Imp to lane by i/locking brick pavers in L.I.G flats no 57 A to 51 A 74 A 63 A to 68 A , 68 A to 45 A in J Bolck Ashok Vihar Ph I C100 | 199930 | RD-I | 100 | 61/29.9.05 | M/sAmar Chaukar | 9.10.05 | 30.10.05 | 199918 |  |  | Comp
34 | Civil | 2005-07-29 | 9.3.05 revaledated 19.5.05 | Imp of lanes by i/lockin parvers from central park to 44 A and 75 A to 80A in L.I.G flats in J Block Ashok Vihar Ph I C100 | 199800 | RD-I | 100 | 41/09.09.05 | M/s Mahesh Const.& Co | 20.09.05 | 28.10.05 | 199774 |  |  | Comp.
35 | Civil | 2005-07-29 | 2005-07-05 | Imp of roads side berms. By i/locking parvers from H noB 3 Block Ashok Vihar Ph II C100 R Z | 198700 | Br-III | 100 | 52/20.9.05 | M/s Gaurav Associates | 30.9.05 | 29.11.05 | 198673 |  |  | Comp
36 | Civil | 2005-07-29 | 2005-06-26 | Making Add. Water arrangement in M.C primeryschool . Sawan park in C 99 R Z | 28150 | Br-III | 99 | 60/29.9.05 | M/s S.M. Const | 24.9.05 | 15.10.05 | 27425 |  |  | Comp
37 | Elect. | 2005-08-18 | 2005-06-08 | P/O Lighting arrangement in park near H no B38 Ashok Vihar Ph I under R Z | 115697 | EEE-VII | 100 | 223/23.12.05 | M/s ACE Engineers Bureau | 23.12.05 | 23.1.06 | 105311 |  |  | Comp
38 | Elect. | 2005-08-18 | 2005-06-08 | P/o boring with submersible pump set at park opposite H NO H 185 Ashok Vihar Ph I in ward No 100 under Rohini Zone | 170159 | EEE-VII | 100 | 161/06.12.05 | M/s Tyagi Elect & Trading Co | 09.12.05 | 12.01.06 | 158594 |  |  | Comp
39 | Elect. | 2005-08-18 | 2005-06-08 | P/o boring with submersible pump set at park central market, Ashok Vihar Ph I in ward No 100 under Rohini Zone | 171910 | EEE-VII | 100 | 222/23.12.05 | M/s Seth Const | 26.12.05 | 23.1.06 | 161965 |  |  | Comp
40 | Civil | 2005-08-18 | 14.3.05 revaledated 19.5.05 | Imp to drainage system in B 2 Bolck behind mandir in Ashok Vihar Ph II C100 R Z | 785131 | EEE-VII | 99 | 03/07.04.06/EE-(Br)-III | M/s Gupta Brothrs. | 20.05.06 | 14.08.06 | 782750 |  |  | Comp.
41 | Civil | 2005-08-18 | 2005-08-10 | Imp of site by kota flooring in front of Patherwala park in JJ Colony wazir pur in C 99 RZ | 124098 | Br-III | 99 | 142/28.11.05 | M/s Pankaj Const co. | 29.11.05 | 24.01.06 | 123789 |  |  | Comp
42 | Civil | 2005-08-18 | 2005-08-10 | Imp to road side berm by into paversfrom K -17 to Gujrati Mndir in wazir pur JJ Colony C 99 RZ | 150456 | Br-III | 99 | 100/26.10.05 | M/s Prakash Traders | 28.10.05 | 27.12.05 | 150456 |  |  | Comp
43 | Civil | 2005-08-18 | 2005-08-10 | C/o umbrella in D Block park in wazirpur JJ Colony C 99 RZ (near D 70) | 196327 | Br-III | 99 | 81/11.10.05 | M/s Prakash Traders | 13.10.05 | 26.11.05 | 196239 |  |  | Comp
44 | Civil | 2005-08-18 | 2005-08-10 | Imp to B/wall & C/o walkway in F Block park wazirpur JJ Colony C99 RZ near F 270 | 137143 | Br-III | 99 | 126/21.11.05 | M/s Satish Gupta & Co. | 22.11.05 | 25.01.06 | 136978 |  |  | Comp
45 | Civil | 2005-08-18 | 2005-08-10 | Imp to B/wall by stone guit finish near C17 to near A 10 in satyawati colony C99 RZ | 179543 | Br-III | 99 | 133/25.11.05 | M/s Pankaj Const co. | 27.11.05 | 07.03.06 | 179305 |  |  | Comp
46 | Civil | 2005-08-18 | 2005-08-10 | Imp to B/wall by guit wash near H No A 11 to mandir in satyawati colony C99 Rz | 179934 | Br-III | 99 | 134/25.11.05 | M/s Pankaj Const co. | 27.11.05 | 07.03.06 | 179930 |  |  | Comp
47 | Civil | 2005-08-18 | 2005-08-10 | C/o B/wall by brick Masonary in font of C 31 Satyawati Colony C99 RZ | 198771 | Br-III | 99 | 96/20.10.05 | M/s Vijay Kumar-II | 21.10.05 | 21.07.06 | 198718 |  |  | Comp
48 | Civil | 2005-08-18 | 2005-08-10 | Imp of B/wall bystone grit finish of park near C17 in satya wati colony C 99 Rz | 204209 | Br-III | 99 | 82/11.10.05 | M/s Vijay Kumar-II | 20.10.05 | 17.12.05 | 203596 |  |  | Comp
49 | Civil | 2005-08-19 | 2005-08-04 | Imp to drainage system from H No D12 to D 67 in D Bolck in Ashok Vihar Ph II C100 R Z | 598900 | Br-III | 99 | 226/31.01.06/EE(Br)-III | M/s Ashok Kumar gupta | 16.02.06 | 16.05.06 | 402869 |  |  | Comp
50 | Civil | 2005-08-19 | 2005-08-04 | Imp of drainage system from H no D 68 to D 203 in D Block in Ashok Vihar Ph I C 100 RZ | 581100 | Br-III | 99 | 254/02.03.06/EE(Br.)-III | M/s Ashok Kumar gupta | 11.03.06 | 10.06.06 | 402366 |  |  | Comp.
51 | Civil | 2005-08-19 | 2005-08-04 | Imp of drainage system from H No F 136 to F 149 in F Block in Ashok Vihar Ph I C 100 RZ | 391596 | Br-III | 100 | 116/17.11.05 | M/s Rajan Builders | 26.11.05 | 06.02.06 | 391502 |  |  | Comp
52 | Civil | 2005-08-19 | 2005-08-04 | Imp of drainage system from H No 108 to 136 Ph F Block in Ashok Vihar Ph I C 100 RZ | 583900 | Br-III | 100 | 229/06.02.06/EE(Br)-III | M/s K.K.Enterprises | 03.03.06 | 10.05.06 | 396397 |  |  | Comp
53 | Civil | 2005-08-19 | 2005-08-04 | Imp of drainage system rom H No E 151 to E Block school in E Block in Ashok Vihar Ph I C 100 RZ | 391496 | Br-III | 100 | 163/14.12.05 | M/s Pankaj Const co. | 15.01.06 | 19.03.06 | 391403 |  |  | Comp
54 | Civil | 2005-08-19 | 2005-08-04 | Imp of drainage system from H No B218 to B 226 in B Bolck Ashok Vihar Ph I C 100 RZ | 359405 | Br-III | 100 | 120/17.11.05 | M/s RM Auto Centre | 30.11.05 | 4.1.06 | 359405 |  |  | Comp
55 | Civil | 2005-08-19 | 2005-08-04 | Imp of drainage system from H no 42 to 71 on main road in A bolck in Ashok Vihar Ph II C 100 RZ | 598100 | Br-III | 100 | 230/06.02.06/EE(Br)-III | M/s K.K.Enterprises | 03.03.06 | 10.05.06 | 404143 |  |  | Comp
56 | Civil | 2005-08-30 | 2005-08-25 | Const of walkway and Imp of Radha Kunj park in Satya wati colony in C 99 RZ | 176189 | Br-III | 99 | 174/28.12.05/EE(Br.)-III | M/s Neeraj Const.Co | 29.12.05 | 02.08.06 | 175706 |  |  | Comp
57 | Civil | 2005-08-30 | 2005-08-24 | Imp of draimage system fromvH NI E II to corner of E Bolck school on main road E Block Ashok Vihar Ph I C 100 | 294012 | Br-III | 100 | 145/28.11.05 | M/s Krishna Const.Co | 20.01.06 | 09.03.05 | 293903 |  |  | Comp
58 | Civil | 2005-08-30 | 2005-08-24 | Imp of roads by mix seal in K C Block in Ashok Vihar Ph I C 100 RZ | 198600 | Br-III | 100
59 | Civil | 2005-08-30 | 2005-08-24 | Imp of internal roads by mix seal in B.A Block in Ashok Vihar Ph I C 100 RZ | 195100 | Br-III | 100
60 | Civil | 12.9.05 | 25.8.05 | Imp of rd by Premix Carpet from H.no. 39 to Park near H.n. 395 and upto H.no. 411 in Nimri Cly, in C 99 RZ | 195856 | Br-III | 99 | 121/17.11.05 | M/s Prakash Traders | 26.11.05 | 27.12.05 | 195082 |  |  | Comp
61 | Civil | 12.9.05 | 8.9.05 | C/o of Footpat at T-Point of GS Marg & SN Nagar (Swami Nayyar marg) in C 99 RZ | 256960 | Br-III | 99 | 70/7.10.05 | M/s Sajjan Engg. & Builders | 10.10.05 | 26.11.05 | 254191 |  |  | Comp
62 | Civil | 12.9.05 | 22.9.05 | Imp fo B./wall by pdg Grit wash & grill 48 DDA mkt, near Sanatan dharam Mandir infront G block in Wazirpur in C 99 | 118045 | Br-III | 99 | 127/21.11.05 | M/s Rakesh Kumar Goel | 22.11.05 | 28.1.06 | 118045 |  |  | Comp
63 | Civil | 7.10.05 | 5.10.05 | Imp of B.wall of park by Brick Masonary & Imp to walkway in front of E-16 Wazirpur JJ Cly in C 99. | 143194 | Br-III | 99 | 162/14.12.05 | M/s Dhruv Const. | 23.12.05 | P | 107074 |  |  | In Prog.
64 | Civil | 10.10.05 | 6.10.05 | Widening of rd at T point of Swami Narayan marg & GS Marg in W.no. 99 | 189929 | Br-III | 99 | 150/2.12.05 | M/s Subhash Singh | 2.12.05 | P | 149917 |  |  | inprog.
65 | Civil | 19.10.05 | 18.10.05 | C/o Walkway in oark infront of 109 Nimri Cly C 99 | 197132 | Br-III | 99 | 212/27.01.06 | M/s Vashista const.Co | 28.01.06 | P | 196677 |  |  | Comp
66 | Civil | 5.12.05 | 18.10.05 | imp to B/Wall of park by Brick masonry in front of H No 448 Nimri Colony in C 99 RZ | 199855 | Br-III | 99 | 170/21.12.05 | M/s B.M.B.Enterprises | 23.12.05 | 01.03.06 | 199654 |  |  | Comp.
67 | Civil | 5.12.05 | 18.10.05 | Imp of parking by interlocking tiles in C pocket Ashok Vihar Ph III in C99 RZ | 195967 | Br-III | 99 | 211/27.01.06 | M/s Praveen Kumar Garg | 27.01.06 | 21.03.06 | 195805 |  |  | Comp.
68 | Civil | 5.12.05 | 18.10.05 | C/o B/Wall of demolished lav Block Space by brick masonary near B-107 & in F Block Wazirpur JJ Colony C99 RZ | 199100 | Br-III | 99 | 207/27.01.06/EE(Br)-III | M/s M.P Associates | 28.01.06 | 03.04.06 | 187559 |  |  | Comp.
69 | Civil | 5.12.05 | 21.11.05 | Const of walkway in park in front of H no 367 &369 in Nimri Colony in C99 RZ | 199975 | Br-III | 99 | 208/27.01.06 | M/s Baba & Co. | 28.01.06 | 15.06.06 | 199975 |  |  | Comp.
70 | Civil | 5.12.05 | 21.11.05 | Imp to lane by cement Concrete pavements near House No 357 to 367 and 345 to 355 Nimri Colony in C 99 R Z | 199680 | Br-III | 99 | 191/05.01.06/EE(Br)-III | M/s Jatin Const. | 07.01.06 | 25.03.06 | 198800 |  |  | Comp.
71 | Civil | 5.12.05 | 21.11.05 | Imp to lane by cement Concrete pavements near House No 325 to 335 and 337 to Mandir in Nimri Colony in C 99 R Z | 199153 | Br-III | 99 | 167/21.12.05/EE(Br.)-III | M/s Mittal Traders | 22.12.05 | 13.09.06 | 199028 |  |  | Comp.
72 | Civil | 5.12.05 | 21.11.05 | Imp to lane by RMC from H no D 539 to D-560 and D 625 to D 646 in JJ Colony Wazir pur R Z | 198392 | Br-III | 99 | 216/27.01.06/EE(Br.)III | M/s Kumar Const.co. | 28.01.06 | P | 170748 |  |  | In Prog.
73 | Civil | 5.12.05 | 21.11.05 | Imp of road by RMC from Sanatan Dharam Mandir to MC pry School Sawan Park in C99 R Z | 199910 | Br-III | 99 | 213/27.01.06/EE(Br)-III | M/s Prakash Const.Co | 04.02.06 | 31.05.06 | 199910 |  |  | Comp.
74 | Civil | 5.12.05 | 21.11.05 | Imp of road by M/p from Railway X-ing to Sawan Park in C99 R Z | 199690 | Br-III | 99 | 189/05.01.06/EE(Br)-III | M/s Surya Kant Sharma | 10.01.06 | P | 198381 |  |  | In Prog.
75 | Civil | 5.12.05 | 21.11.05 | Imp of B/ Wall with B/M of park near Bharat Nagar Bus Stand in C-99 R Z | 199852 | Br-III | 99 | 209/27.01.06 | M/s Om Const.Co | 28.01.06 | P | 199852 |  |  | Comp
76 | Civil | 5.12.05 | 21.11.05 | Imp to open Space by interlocking tiles in front of House No 485 to 445 Nimri Colony in C-99 RZ | 199406 | Br-III | 99 | 214/27.01.06 | M/s Surjit Kumar | 27.01.06 | 06.03.06 | 198805 |  |  | Comp.
77 | Civil | 5.12.05 | 21.11.05 | Imp to open Space by interlocking tiles in front of House No 443 and 523 Nimri Colony in C-99 RZ | 199447 | Br-III | 99 | 215/27.01.06 | M/s Ancon | 28.01.06 | P | 186246 |  |  | In Prog.
78 | Civil | 9.12.05 | 8.12.05 | Imp to lane by CC pav from H.nl. 315 to 271 Double Storey Bharat nagar in C 99. | 199994 | Br-III | 99 | 210/27.01.06 | M/s Maruti Const. | 28.01.06 | 24.03.06 | 199402 |  |  | Comp.
79 | Civil | 13.12.05 | 10.11.05 | Imp to open space for park pdg B/wall in front of H.n. 17 Bharat Ngar, C 99 | 196193 | Br-III | 99 | 178/27.01.06 | M/s Hari Jain Cosnt.Co. | 02.01.06 | 08.03.06 | 195520 |  |  | Comp.
80 | Elect. | 2.1.06. | 24.10.05 | P/o Semi High mast Light at park in H 48, Ashok Vihar Ph-I, in W.no. 100 RZ | 191627 | EEE-VII | 100 | 04/03.01.06 | M/s Master Elect. Store | 03.01.06 | 09.01.06 | 180144 |  |  | Comp.
81 | Elect. | 2.1.06. | 24.10.05 | P/O boring with Subermsible Pump set at park in Bunkar Colony and laying its line in adjacent park in W.no. 99 RZ | 145493 | EEE-VII | 99 | 05/03.01.06 | M/s Master Elect. Store | 03.01.06 | 09.01.06 | 141711 |  |  | Comp.
82 | Civil | 5.1.06 | 4.1.06 | P/F I/l Precast Pav on central verge on S.N. Marg in W.no. C 99 | 199700 | Br-III | 99 | 221/31.1.06 | M/sMahesh Chand & Co. | 1.02.06 | 14.2.06 | 199511 |  |  | Comp
83 | Civil | 5.1.06 | 4.1.06 | Imp to road by Premix Carpet near H.no. 603 to main road & nar 159 in Nimri Colony in C 99 | 99050 | Br-III | 99 | 252/22.02.06/EE(Br)-III | M/s Surya Kant Sharma | 03.03.06 | P | 98699 |  |  | In Prog.
84 | Civil | 5.1.06 | 15.12.05 | Imp of lane by CC flrooring from H-66 to H 86 and H 87 to H 107 in JJ Colony Wazirpur in C 99 | 199800 | Br-III | 99 | 253/22.02.06/EE(BR)-III | M/s Gaurav Associates | 23.02.06 | 23.06.06 | 199700 |  |  | Comp.
85 | Civil | 5.1.06 | 15.12.05 | Imp to lane by CC flooring from H 173 to H 193 and H 259 to H 279 in JJ cly Wazirpur in C 99 | 199600 | Br-III | 99 | 239/18.02.06/EE(Br.)-III | M/s Esskay Enterprises | 14.02.06 | 20.04.06 | 198981 |  |  | Comp.
86 | Elect. | 24.1.06 | 18.1.06 | P/O Post Top Lantern I the park infont of flat no. C 50, LIG Flats Ashok Vihar Ph-II, In W.n. 100 | 191470 | EEE-VII | 100 | 336/21.03.06/EE(E)-VII | M/s Repairs Shop | 27.03.06 | 13.04.06 | 120023 |  |  | Comp.
87 | Elect. | 24.1.06 | 18.1.06 | P/O Post Top Tantern in the aoprk in fornt of Flat NO. C 10, LIG Flats Ashok Vihar ph-IV in w.no. 100. | 257466 | EEE-VII | 100 | 368/31.03.06 | M/s Seth Const | 31.03.06 | 14.04.06 | 159619 |  |  | Comp.
88 | Elect. | 24.1.06 | 18.1.06 | Prov of Semi High Mast light at park in C block Ashok Vihar Ph-III in w.no. 100 | 196022 | EEE-VII | 100 | 339/21.03.06 | M/s Saksham Elect. & Electronics | 21.03.06 | 29.03.06 | 141002 |  |  | Comp.
89 | Elect. | 24.1.06 | 18.1.06 | Prov of Semi High Mast light near Sindhi Dharamshala, Ashok Vihar Ph-II, w.n. 100 | 190772 | EEE-VII | 100 | 340/21.03.06 | M/s Saksham Elect. & Electronics | 21.03.06 | 29.03.06 | 139377 |  |  | Comp.
90 | Elect. | 24.1.06 | 18.1.06 | P/O Street light arrangement on the road (a) near Laxmi Narayan Mandir, Ashok Vihar Ph-II, and (b) near B-3/25, Ashok Vihar Ph-II and (c) neare DDA Mkt Shakti Nagar Ext in Under RZ | 218837 | EEE-VII | 100 | 369/31.03.06/EE(E)-VII | M/s Kawatra Eletric Works | 06.04.06 | 31.05.06 | 115120 |  |  | Comp.
91 | Civil | 6.2.06 | 4.2.06 | C/o of Island on Swami Narayan Marg in C 99 (New Gulab Singh Marg) | 199907 | Br-III | 99 | 284/21.03.06 | M/s Subhash Singh | 21.03.06 | 30..05.06 | 199890 |  |  | Comp.
92 | Civil | 20.02.06 | 18.1.06 | Imp to Side berms by pdg CC tiles paver near 8A, 11A to 17A to 22a to 18A and 34A in KC block, Ashok Vihar in C 1000 | 199936 | Br-III | 100 | 259/06.02.06 | M/s Shiv Shankar Gupta | 06.03.06 | 30.03.06 | 199929 |  |  | Comp.
93 | Civil | 20.02.06 | 18.1.06 | Imp to drainage system and side berm from A 25 to 27, near A 15, and A 30 in A block, Ph-II, Ashok Vihar in C 100 | 198998 | Br-III | 100 | 261/06.03.06/EE(Br.)-III | M/s Ram Kishore Berwa | 24.04.06 | 26.06.06 | 198989 |  |  | Comp.
94 | Civil | 20.02.06 | 18.1.06 | Imp of Drainage system from A-8 to A 13 and A 18 to A 22 in A block, Ashok ViharPh-II in C 100 | 199748 | Br-III | 100 | 269/09.03.06/EE(Br.)-III | M/s Krishna Const.Co | 20.03.06 | P | 199748 |  |  | In Prog.
95 | Civil | 20.02.06 | 18.1.06 | Const of drain and culvert on Sh. Gulab Singh rd near Dda Park , WP-I Wazirpurvillage, Ashok Vihar Ph-I in C 100. | 199950 | Br-III | 100 | 299/28.03.06/EE(Br.)-III | M/s Anhal Const.Asso. | 29.03.06 | 23.05.06 | 198442 |  |  | Comp.
96 | Civil | 20.02.06 | 4.2.06 | C/o of Island near K block, dalao in Wazirpur in JJ Cly | 99200 | Br-III | 99 | 300/28.03.06 | M/s Shiv Shankar Gupta | 29.03.06 | 22.04.06 | 89597 |  |  | Comp.
97 | Civil | 24.2.06 | 23.02.06 | Imp to lane by CC flooring fro H.no.150 to 129, 107 to 918 & 97 to 118 in F Block, JJ Cly in Wazirpur in C 99 | 199950 | Br-III | 99 | 288/24.03.06 | M/s Mittal Traders | 25.03.06 | 13.09.06 | 199910 |  |  | Comp.
98 | Civil | 28.2.06 | 23.02.06 | Pdg & laying interlocking pavers in Walkway in park near H.no. 385 infornt of Gurudwara in Nimri Cly in C 99 RZ | 33800 | Br-III | 99
[5 empty] | 21695625 | [6 empty] | 19106047