## AC-23
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06 UP TO 16.11.07
Municipal Corporation of Delhi
|  | Name Of MLA |  | Sh. Jai Kishan | AC-23 |  | year 2005-06 |  | Allocation | 163.21 lacs
|  | Name of Constituency |  | Sultanpuri
|  | Ward Nos and Names |  | AC-39 AC-40
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agency | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 16
1 | Civil | 9.6.05 | 7.6.05 | Imp of park by pdg B/wall with MS grill at Sultanpur Mazra Village in Sultanpuri in C-40 | 767989 | XXVIII | 40 | 380/24.01.06 | M/s Trilok Sharma | 01.07.06 | 30.03.07 | 765066 | Comp.
2 | Elect | 24.8.05 | 18.8.05 | P/O Semi High Mast light at L -15, Udhog Nagar under NGZ | 175063 | EEE-III | 40 | 217/28.10.05/EE(E)III | M/s Bhima Electricals | 05.11.05 | 02.12.05 | 172176 | Comp.
3 | Elect | 24.8.05 | 18.8.05 | P/O Semi High Mast light at Sulatan Pur Majra Village under NGZ | 174999 | EEE-III | 40 | 260/03.11.05/EE(E)III | M/s A.K Electronics | 03.11.05 | 17.11.05 | 171849 | Comp.
4 | Elect | 24.8.05 | 18.8.05 | P/O Semi High Mast light at near Bus Terminal Sultanpur under NGZ | 174999 | EEE-III | 40 | 262/03.11.05/EE(E)III | M/s Bindra Motors & Elect. | 04.11.05 | 17.11.05 | 171803 | Comp.
5 | Elect | 24.8.05 | 18.8.05 | P/O Semi High Mast light at Nagin Lake appartment Peera Garhi under NGZ | 174999 | EEE-III | 40 | 368/08.12.05/EE(E)III | M/s Malhotra Elect. | 15.12.05 | 16.01.06 | 170032 | Comp.
6 | Elect | 22.9.05 | 7.9.05 | Prov. Of Street Light at Rd starting from S block Mangolpuri terminal to A -B Ext , Sultanpuri under NG | 274161 | EEE-III | 39 | 509/10.03.06/EE(E)III | M/s Perfect Elect.Work | 12.03.06 | 30.03.06 | 261993 | Comp.
7 | Elect | 22.9.05 | 7.9.05 | Prov. Of Street Light at Sultanpuri Rd from Rly. Xing to East Friends Encl. under NGZ | 374253 | EEE-III | 39 | 505/27.02.06/EE(E)III | M/s Perfect Elect.Work | 28.02.06 | 13.03.06 | 351344 | Comp.
8 | Civil | 30.9.05 | 17.9.05 | Const of Walkway in the park opp H.no. D 2/44 & Pdg Passage near D 1/444 and D 2/228 in Sultanpuri C 40 NGZ | 253988 | XXVIII | 40 | 454/16.03.06/EE-XXVIII | M/s Shiv Kumar Gupta | 17.03.06 | 23.06.06 | 253988 | Comp.
9 | Civil | 30.9.05 | 17.9.05 | Const of Walkway in the park opp H.no. F6/276 in Sultanpuri in C 40 NGZ | 266742 | XXVIII | 40 | 390/06.02.06/XXXIII | M/s Bhagwan Const.Co | 20.02.06 | 31.07.07 | 266742 | In Prog.
10 | Civil | 30.9.05 | 17.9.05 | Const of Walkway in the park opp H.n. E 1/268 and pdg Passage near H.n. E 2/288 and opp Nursury park in Sultanpuri in C 40 NGZ | 317192 | XXVIII | 40 | 381/24.01.06/XXXIII | M/s Bhagwan Const.Co | 20.02.06 | 19.04.06 | 317093 | Comp.
11 | Civil | 30.9.05 | 17.9.05 | Const of Walkway and passage in the park opp H.no. E 7/493 in Sultanpuri C 40 NGZ | 330380 | XXVIII | 40 | 411/10.02.06/EE-XXVIII | M/s K.K.Const.Co-I | 19.02.06 | 04.04.06 | 330380 | Comp.
12 | Civil | 30.9.05 | 17.9.05 | Const of Walkway in the park opp P 4/1 in Sultanpuri in C 40 NGZ | 237018 | XXVIII | 40 | 455/16.03.06/EE-XXVIII | M/s Shiv Kumar Gupta | 23.03.06 | 19.05.06 | 232687 | Comp.
13 | Civil | 30.9.05 | 17.9.05 | Const of walkway in the park opp H.no. E 3/493 and Imp to passage by pdg Red Stone in Sultanpuri in C 40 NGZ | 227348 | XXVIII | 40 | 453/16.03.06/EE-XXVIII | M/s Shiv Kumar Gupta | 17.03.06 | 23.06.06 | 227279 | Comp.
14 | Civil | 30.9.05 | 17.9.05 | to Imp of lane by KSF from H.No. D 6/ to D/E18 and D/E11 to & xing in in Sultanpuri in C 40 NGZ | 166981 | XXVIII | 40 | 410/10.02.06/EE-XXVIII | M/s K.K.Const.Co-I | 19.02.06 | 03.04.06 | 166981 | Comp.
15 | Civil | 30.9.05 | 17.9.05 | Imp of lane by KSF from H.no.D 6/24 to 37, D 6/111 to 142, D 6/36 to 85 and xing in Sultanpuri in C 40 NGZ | 167418 | XXVIII | 40 | 393/06.02.06/XXVIII | M/s Anil Goel | 07.02.06 | 17.02.06 | 167418 | Comp.
16 | Civil | 30.9.05 | 17.9.05 | Const fo walkway in the park near H.no. P3/199 in Sultanpuri in C 40 NGZ | 334061 | XXVIII | 40 | 412/10.02.06/EE-XXVIII | M/s K.K.Const.Co. | 02.03.06 | 24.07.07 | 334061 | In Prog.
17 | Civil | 3.10.05 | 17.9.05 | Imp of park by pdg B/wall with Marble wash and MS grill infornt fo C 8/97 in C 8 block in Sultanpuri in C 40 NGZ | 282407 | XXVIII | 39 | 452/16.03.06/EE-XXVIII | M/s Shiv Kumar Gupta | 03.04.06 | 08.06.06 | 282407 | Comp.
18 | Civil | 3.10.05 | 17.9.05 | Imp of road/lane by pdg RMC from C 8/241 to C 8/288 C 2/228 to C 4/1 & c 7/37 to C 7/27 in Sultanpuri in C 40 NGZ | 498446 | XXVIII | 39 | 502/24.03.06/EE-XXVIII | M/s V.K Chaudhary & Co. | 03.04.06 | 25.10.07 | 496013 | In Prog.
19 | Elect | 7.10.05 | 5.10.05 | Prov. Of Street light in Resettlement colony of Sultanpuri A,B,,C, and D blockUnder NGZ | 199358 | EEE-III | 39 | 263/03.11.05/EE(E)III | M/s Sachdeva Electriclas | 04.11.05 | 11.12.05 | 190908 | Comp.
20 | Elect | 7.10.05 | 5.10.05 | Prov of street light in resettlement colony Sultanpuri harizan Basti Friedns Sultanpuri Harizan Basti 80 sq yds and G,H block Sultanpuri under NGZ | 199358 | EEE-III | 40 | 264/03.11.05/EE(E)III | M/s Sachdeva Electriclas | 04.11.05 | 11.12.05 | 188483 | Comp.
21 | Elect | 7.10.05 | 5.10.05 | Prov of street lightin resettlement Colony Sultanpuri E,F, P-1, P-3 and P-4 block, under NGZ | 199358 | EEE-III | 40 | 371/EE(E)III | M/s Pragati Enginers. | 09.12.05 | 15.12.05 | 191209 | Comp.
22 | Civil | 24.10.05 | 30.9.05 | Imp of park by pdg B/wall with MS grill and Red Sand stone at C 8/36 and C 2/228 Sultanpuri in C 39. | 401963 | XXVIII | 39 | 503/24.03.06/EE-XXVIII | M/s Anil Goel | 02.04.06 | 29.06.06 | 401963 | Comp.
23 | Civil | 24.10.05 | 30.9.05 | Imp of lane by KSF from A5/37 to 48, 13 to 12, 60 to 61, 143 to 121 in A -5 blockand A 2/193 to 180,157 to 228,157 to 324, 72 to 409, 394 to 349, 393 to block Sultanpuri in C 39 NGZ | 398260 | XXVIII | 39 | 501/24.03.06/EE-XXVIII | M/s Vijay Bansal | 19.05.06 | 28.06.06 | 391783 | Comp.
24 | Civil | 24.10.05 | 30.9.05 | Imp of park by Pdg walkway infrong fo C 6/97, C 6 block Sultanpuri in C 39 NGZ | 150744 | XXVIII | 39 | 82/12.05.06 | M/s Nirvan Const.CO | 26.07.06 | 19.08.06 | 150700 | Comp.
25 | Civil | 24.10.05 | 30.9.05 | Imp of walkway of NH Park by pdg CC tiles & other Miscellaneous work at Jalebi Chowk Sultanpuri in C 39 | 524713 | XXVIII | 39 | 449/08.03.06/EE-XXVIII | M/s Ashoka Traders | 15.03.06 | 30.06.06 | 524258 | Comp.
26 | Civil | 2.11.05 | 17.9.05 | Const of Hut in NH Park near Jelabi Chowk Sultanpuir inC 39 NGZ | 461016 | XXVIII | 39 | 465/08.03.06/EE-XXVII | M/s S.S Contractors | 04.04.06 | 23.06.06 | 450270 | Comp.
27 | Civil | 31.1.06 | 12.1.06 | Imp of B/wall of park by pdg Red Sand Stone, Marble Wash & MS Grills opp E 7-336 on main road Sultanpuri in C 40 NGZ | 441006 | XXVIII | 40 | 202/11.09.06/EE-VIII | M/s Naresh Kumar Bansal | 19.10.06 | 30.11.06 | 440684 | Comp.
28 | Civil | 08.03.06 | 03.03.06 | Dev of park & const. Of water body in park near P-3/50 opp. Gurudwara in Sultanpuri C-40/N.G zone | 408823 | XXVIII | 40 | 108/25.05.06/EE-XXVIII | M/s A.S Traders | 01.06.06 | 28.08.06 | 408823 | Comp.
29 | Civil | 08.03.06 | 03.03.06 | Dev of park and const.of water body in park near F-1/97 Sultanpuri C-40 N.G zone | 408823 | XXVIII | 40 | 106/25.05.06/EE-XXVIII | M/s A.S Traders | 01.06.06 | 28.08.06 | 408381 | Comp.
30 | Civil | 08.03.06 | 03.03.06 | Imp. Of lanes by pdg. R.M.C from B-687 to b-806 B-686 to B-619 & Sanatan Dharam Mandir to Jahaj Apartment C-39/N.G zone | 415281 | EE-XXVIII | 39 | 114/25.05.06/EE-XXVIII | M/s Surinder Const.Co | 28.06.06 | 25.08.06 | 414866 | In Prog.
31 | Civil | 08.03.06 | 03.03.06 | Imp. Of lanes by pdg. Kota Stone in C-1 market near bus stand in Sultampuri C-39/N.F zone | 346789 | EE-XXVIII | 39 | 113/25.05.06/EE-XXVIII | M/s A.S Traders | 25.05.06 | 31.08.06 | 346077 | Comp.
32 | Civil | 08.03.06 | 03.03.06 | Const. Of hut in aprk opp. T-46 in T-Block Mangolpuri C-39/N.G zone | 487094 | EE-XXVIII | 39 | 112/25.05.06/EE-XXVIII | M/s A.S Traders | 07.06.06 | 18.08.06 | 485994 | Comp.
33 | Civil | 08.03.06 | 03.03.06 | Const.of hut in Ambedkar Park near B-3 Block Sultanpuri C-39/ N.G zone | 526958 | EE-XXVIII | 40 | 109/25.05.06/EE-XXVIII | M/s Ram Chander Dagar | 05.06.06 | 20.08.06 | 526676 | Comp.
34 | Civil | 08.03.06 | 17.09.05 | Const. Of hut in Hans Park near H.NO E-7/493 in Sultanpuri C-40/N.G zone | 532134 | EE-XXVIII | 40 | 104/25.05.06/EE-XXVIII | M/s Pawan Builders | 04.07.06 | 31.08.06 | 532134 | Comp.
35 | Civil | 08.03.06 | 03.03.06 | Const. Of hut park near H.NO. F-6/277 in Sultanpuri in C-40/N.G zone | 521961 | EE-XXVIII | 40 | 105/25.05.06/EE-XXVIII | M/s Pawan Builders | 04.07.06 | 31.08.06 | 521623 | Comp.
36 | Civil | 17.03.06 | 12.01.06 | Imp of central verge with M.S grill on main Sultan Puri Road from Jalebi Chowk to wards railway x-in in C-40/N.G zone | 623432 | EE-XXVIII | 40 | 356/27.11.06/EE-XXVIII | M/s Shankar Builder | 05.01.07 | 19.02.07 | 622858 | Comp.
37 | Elect | 17.03.06 | 05.01.06 | Provision of street light on main road of Resettelment colony, D-1,D-2,D-3,D-6,D-7,F-6,F-7,P-1 and P-2 Block Sultanpuri and Friends Enclave under N.G zone | 335533 |  |  | 262/04.10.06/EE(E)-III | M/s Suchdeva Electricals | 05.10.06 | 31.10.06 | 327922 | Comp.
38 | Elect | 30.03.06 | 05.01.06 | P/O Lighting arrangment with 2X250 watt flood light fitting on 12 M long street tubular Pall at main road near kali mandir Sultanpuri N.G zone | 163067 | EE(E)-III | 40 | 184/24.07.06/EE(E)-III | M/s Neeraj Electricals | 25.07.06 | 14.08.06 | 157887 | Comp.
|  |  |  | Total | 12944115 | [6 empty] | 12822811

## AC-24
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06 UP TO 16.11.07
Municipal Corporation of Delhi
|  | Name Of MLA |  | Sh. Raj Kumar Chauhan | AC-24 |  | year 2005-06 |  | Allocation | 200.00 lacs |  | Dated:-
|  | Name of Constituency |  | Mangol puri
|  | Ward Nos and Names |  | C-41 C-42
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Civil | 4.7.05 | 30.6.05 | Const of Hut in Indira Gandhi Park in I block Mangolpuri in C-41. | 189548 | XXVIII | 41 | 172/08.08.05/XXVII | M/S Paplaj Const Co | 09.08.05 | 15.11.05 | 454992 | Comp
2 | Civil | 4.7.05 | 30.6.05 | Const of Hut in Centre park near CTC Complex in F block Mangolpuri. | 455037 | XXVIII | 41 | 171/XXVIII | M/S Paplaj Const Co | 9.8.05 | 15.11.05 | 454220 | Comp
3 | Civil | 4.7.05 | 30.6.05 | Const of Hut in park infornt of C 210 in Mangolpuri C-41. | 455037 | XXVIII | 41 | 170/08.08.05/XXVIII | M/S Paplaj Const Co | 10.08.05 | 10.11.05 | 455037 | Comp
4 | Civil | 18.7.05 | 5.7.05 | Pdg MS gate on Kala Mandir ground in Mangolpuri in C42 NGZ | 189548 | XXVIII | 42 | 199/13.09.05/XXVIII | M/s Goela Associates | 14.09.05 | 18.12.05 | 189447 | Comp
5 | Civil | 18.7.05 | 5.7.05 | Imp of berms by RMC near Mother Dairy Booth on G block mangolpuri. | 189718 | XXVIII | 41 | 205/13.09.05/XXVIII | M/s Rajinder Singh Dagar | 14.09.05 | 02.01.06 | 189685 | Comp
6 | Civil | 18.7.05 | 5.7.05 | Imp of berm by RMC from Indira Gandhi Park to balmiki Mandir in I Block Mangolpuri in C-41. | 190327 | XXVIII | 41 | 225/18.10.05/XXVIII | M/s Deep Const Co. | 18.10.05 | P | 181960 | In Prog.
7 | Civil | 18.7.05 | 5.7.05 | Imp of berm by RMC infront of Water Tank to K block Mangolpuri in C-42. | 190567 | XXVIII | 42 | 220/04.10.05/XXVIII | M/s Dabas Const.Co | 05.10.05 | P | 185462 | In Prog.
8 | Civil | 18.7.05 | 5.7.05 | Imp of berms by pdg RMC infront of Mini Mkts S block Mangolpuri in C-42. | 198150 | XXVIII | 42 | 204/13.09.05/XXVIII | M/s Parveen Const. | 14.09.05 | 29.11.05 | 188678 | Comp
9 | Civil | 18.7.05 | 5.7.05 | Pdg MS Grill on FP of Slip way in S block Mangolpuri. | 199900 | XXVIII | 42 | 202/13.09.05/XXVIII | M/s R.S.Const | 23.09.05 | 20.12.05 | 189462 | In Prog.
10 | Civil | 18.7.05 | 5.7.05 | Pdg MS Grill on FP in F 2 block Mangolpuri in C-41. | 189896 | XXVIII | 41 | 198/13.09.05/XXVIII | M/s Pawan Kumar | 14.09.05 | P | 184896 | In Prog.
11 | Civil | 9.8.05 | 19.7.05 | Const of Designer Gate of park near Y block Nursury in Mangolpuri in C-41. | 389585 | XXVIII | 41 | 185/30.08.05/XXVIII | M/s Hari Ram | 08.09.05 | 02.12.05 | 389585 | Comp
12 | Civil | 9.8.05 | 19.7.05 | Const of Designer Gate of park side Petrol Pump along PWD rd in Mangolpuri in C42. | 395812 | XXVIII | 42 | 252/09.11.05/XXVIII | M/s Shree Shamgiri Enter | 09.11.05 | 30.03.06 | 395812 | Comp
13 | Civil | 9.8.05 | 19.7.05 | Const of Hut in J block park near H.no. 1198 inJ block Mangolpuri in C41. | 451736 | XXVIII | 41 | 187/30.08.05/XXVIII | M/s Vinod Dhawan | 30.08.05 | 02.12.05 | 451191 | Comp
14 | Civil | 9.8.05 | 19.7.05 | Pdg Premixing Carpet on road from Water tank to S block Chowk in Mangolpuri in C42. | 147774 | XXVIII | 42 | 200/13.09.05/XXVIII | M/s Hari Ram | 13.09.05 | 29.11.05 | 147710 | Comp
15 | Civil | 9.8.05 | 19.7.05 | Const of Designer Gate of Ambedkar park in M block Mangolpuri in C-42. | 389779 | XXVIII | 42 | 188/30.08.05/XXVIII | M/s Vinod Dhawan | 30.08.05 | 02.12.05 | 389779 | Comp
16 | Civil | 9.8.05 | 19.7.05 | Const of Storm Water Drain infront of Mother Dairy booth to road no 3 G block, Mangolpuri, C-41. | 189723 | XXVIII | 41 | 193/05.09.05/XXVIII | M/s Ajay Kumar | 06.09.05 | 13.12.05 | 189692 | In Prog.
17 | Civil | 9.8.05 | 19.7.05 | Const of strom Water Drain from O block, MC Pry School to LP road, Mangolpuri in C-42 | 189811 | XXVIII | 42 | 191/05.09.05/XXVIII | M/s Gaur Const.Co | 10.09.05 | 12.01.05 | 189775 | In Prog.
18 | Civil | 9.8.05 | 19.7.05 | Const of Strom Water Drain from M-962 to park in Mangolpuri in C-42. | 190242 | XXVIII | 42 | 293/28.11.05/XXVIII | M/s Sehwag Const. | 06.12.05 | 05.02.06 | 190242 | In Prog.
19 | Civil | 9.8.05 | 19.7.05 | Const of Strom Water Drain Ambedkar Park to M 221 in Mangolpuri in C-42. | 190157 | XXVIII | 42 | 203/13.09.05/XXVIII | M/s Shokeen Enterprises | 22.09.05 | 05.02.6 | 190012 | Comp
20 | Civil | 9.8.05 | 19.7.05 | Const of Hut in park near Masjid in Y block Mangolpuri in C-41. | 451736 | XXVIII | 41 | 186/30.08.05/XXVIII | M/s Hari Ram | 30.08.05 | 20.12.05 | 451736 | Comp
21 | Civil | 25.8.05 | 1.8.05 | P/F stone sunk on B/wall of park near petrol pump in Mangolpuri C-42 | 167118 | XXVIII | 42 | 283/28.11.05/XXVIII | M/s P.K.Sharma | 30.11.05 | 28.02.06 | 167118 | Comp
22 | Civil | 25.8.05 | 1.8.05 | P/F stone sunk on B/wall of park infront of M.C pry School C Bolck in Mangolpuri C-42 | 167483 | XXVIII | 42 | 286/28.11.05/XXVIII | M/s Ashok Kumar | 30.11.05 | 28.02.06 | 167479 | Comp
23 | Civil | 25.8.05 | 1.8.05 | P/F stone sunk on B/wall of IndiraGandhi park I Block in Mangolpuri C-41 | 167764 | XXVIII | 41 | 284/28.11.05/XXVIII | M/s R.K.V Co. | 30.11.05 | 28.02.06 | 167729 | Comp
24 | Civil | 25.8.05 | 1.8.05 | P/F stone sunk on B/wall of park near gas Agency in T Block in Mangolpuri C-42 | 167815 | XXVIII | 42 | 287/28.11.05/XXVIII | M/s R.K. Const. | 30.11.05 | 28.02.06 | 167815 | Comp
25 | Civil | 25.8.05 | 1.8.05 | P/F stone sunk on B/wall of infront of B 1202 in Mangolpuri C-42 | 168192 | XXVIII | 42 | 285/28.11.05/XXVIII | M/s R.K. Const. | 30.11.05 | 28.02.06 | 167654 | Comp
26 | Civil | 25.8.05 | 1.8.05 | P/F stone sunk on B/wall of infront of Nirankari Bhawan in Mangolpuri C-42 | 167125 | XXVIII | 42 | 339/19.12.05/XXVIII | M/s R.S.Const | 28.12.05 | 28.02.06 | 167112 | Comp
27 | Civil | 25.8.05 | 1.8.05 | P/F stone sunk on B/wall of infront of B 263 in Mangolpuri C-42 | 166546 | XXVIII | 42 | 340/19.12.05/XXVIII | M/s R.S.Const | 20.12.05 | 28.02.06 | 166546 | Comp
28 | Civil | 25.8.05 | 1.8.05 | P/F stone sunk on B/wall of infront of B 277 in Mangolpuri C-42 | 167815 | XXVIII | 42 | 292/28.1.05/XXVIII | M/s P.K.Sharma | 30.11.05 | 28.02.06 | 167803 | Comp
29 | Civil | 25.8.05 | 1.8.05 | Const of walkway on park back side of Shan Ghar H Bolck Mangolpuri C 41 | 189139 | XXVIII | 41 | 282/31.03.06/XXVIII | M/s Bansal Const | 30.11.05 | 20.012.05 | 189068 | In Prog.
30 | Civil | 25.8.05 | 1.8.05 | Imp. of drain & footpath infront of Indira Gandhi park I Block Mangolpuri C 41 | 190186 | XXVIII | 41 | 226/18.10.05/XXVIII | M/s B.P.Dabas & Bros. | 19.10.05 | 20.12.05 | 190039 | Comp
31 | Civil | 25.8.05 | 1.8.05 | Const. Of hut in H Block nursary park in Mangolpuri C 41 | 450620 | XXVIII | 41 | 350/21.12.05/EE-XXVIII | M/s R.K Enterprises | 28.12.05 | 28.07.06 | 450441 | Comp
32 | Civil | 25.8.05 | 1.8.05 | Imp. of main roads by pdg. M.S grill on foot path , B Block road ,Police station road & Mangolpuri C 41 | 197500 | XXVIII | 41 | 213/26.9.05 | M/s Harish Kumar | 27.9.05. | 22.11.05 | 188008 | Comp
33 | Civil | 25.8.05 | 1.8.05 | Imp. of main roads by pdg. M.S grill on foot path , Sanjay Gandhi road ,L.P road & S.T road Mangolpuri C 42 | 190000 | XXVIII | 42 | 214/26.9.05 | M/s Shree Shamgiri Enter | 27.9.05. | 24.10.05 | 189942 | Comp
34 | Civil | 18.10.05 | 13.10.05 | Const of Walkay ofpark infornt of F 1/174 inMangolpuri C 41 NGZ | 187416 | XXVIII | 41 | 251/09.11.05/EE-XXVIII | M/s Vipin Kumar Dagar | 09.11.05 | 10.02.06 | 186884 | Comp
35 | Civil | 18.10.05 | 13.10.05 | Const of Walkay of park infornt of P 1/84 in Mangolpuri C 41 NGZ | 188982 | XXVIII | 41 | 250/09.1.05/XXVIII | M/s Harish Kumar | 10.11.05 | 13.12.05 | 188933 | Comp
36 | Civil | 2.1.06 | 20.12.05 | Const of Culverts in B block Chowk & Y 1244 in Mangolpuir in C 41 NGZ | 367783 | XXVIII | 41 | 514/28.03.06/EE-XXVIII | M/s K.K Const. Co-II | 06.04.06 | P | 364328 | In Prog.
37 | Civil | 2.1.06 | 20.12.05 | Const of Centra Verge ad FP from Indira Gandhi park to CTC Complex on Police Station rd Mangolpuri in C 41 NGZ | 425439 | XXVIII | 41 | 472/23.03.06/EE-XXVIII | M/s Rama Const.Co | 23.03.06 | 26.06.06 | 424700 | Comp
38 | Civil | 2.1.06 | 20.12.05 | Const of Culverts in S block chowk in Mangolpuri in C 42. | 181451 | XXVIII | 42 | 29/27.04.06/EE-XXVIII | M/s P.K.Sharma | 27.04.06 | 26.07.06 | 181170 | Comp
39 | Civil | 2.1.06 | 20.12.05 | Const of Culverts in Q block Chowk & near Designer Gate in Mangolpuri in C 42 NGZ | 338797 | XXVIII | 42 | 30/27.04.06/EE-XXVIII | M/s Garg Enterprises | 27.04.06 | 14.07.06 | 338772 | Comp
40 | Civil | 2.1.06 | 20.12.05 | Const of walkway of park and MS Gate ifront of D 898 in Mangolpuri in C 41 NGZ | 271213 | XXVIII | 41 | 33/27.04.06/EE-XXVIII | M/s Anil Const.Co | 27.04.06 | 02.08.06 | 271032 | Comp
41 | Civil | 2.1.06 | 20.12.05 | Const of walkway in park infront of G 781 an surrounding pond in Block B, Mangolpuir in C 41 NGZ | 433739 | XXVIII | 41 | 27/27.04.06/EE-XXVIII | M/s K.K Const. Co-II | 27.04.06 | 14.07.06 | 433602 | Comp
42 | Civil | 2.1.06 | 20.12.05 | Const of walkway of park infornt of Q-11/36 in Mangolpuri inC 42 NGZ | 473921 | XXVIII | 42 | 516/28.03.06 | M/s Anil Goyal | 30.03.06 | 28.04.06 | 473837 | Comp
43 | Civil | 2.1.06 | 20.12.05 | Const of Walkway & MS gates infront of B-900, B-421, B 720 and B 840i Mangolpuri in C 42 NGZ | 478061 | XXVIII | 42 | 480/23.03.06 | M/s Anil Goyal | 24.03.06 | 28.04.06 | 477848 | Comp
44 | Civil | 2.1.06 | 20.12.05 | Const of walkway & MS gates on Veer Kumwar Singh Park in Mangolpuri in C 42 NGZ | 486331 | XXVIII | 42 | 26/27.04.06/EE-XXVIII | M/s Harish Kumar | 27.04.06 | 04.08.06 | 485596 | Comp
45 | Civil | 2.1.06 | 20.12.05 | Const of Walkway of park & MS Gate infront of E 770 in Mangolpuri inC 41 NGZ | 475612 | XXVIII | 41 | 25/27.04.06/EE-XXVIII | M/s Indians Apply Agencies | 27.04.06 | 15.12.08 | 475441 | Comp
46 | Civil | 2.1.06 | 20.12.05 | Const of Walkway of park & MS Gate near Mini Mkt R block Mangolpuri in C 42 NGZ | 478488 | XXVIII | 42 | 36/27.04.06/EE-XXVIII | M/s K.K Const. Co-II | 06.05.06 | 24.07.07 | 478116 | In Prog.
47 | Civil | 2.1.06 | 20.12.05 | Const of B/wall of park in block A. Mangolpuri insdustrial area in Mangolpuir in C 42 NGZ | 498237 | XXVIII | 42 | 40/27.04.06/EE-XXVIII | M/s Vinod Associates | 27.04.06 | 07.09.06 | 498237 | Comp
48 | Civil | 2.1.06 | 20.12.05 | Const of Walkway & Pdg MS Gate in F block park infront of F 497 in Mangolpuri in C 41 NGZ | 470459 | XXVIII | 41 | 466/23.03.06/EE-XXVIII | M/s Dev Const. | 23.03.06 | 24.08.06 | 470217 | Comp
49 | Civil | 2.1.06 | 20.12.05 | Const of Walkway of park in Y block <Nursary near (Road no. 3) in Y block in Mangolpuir in C 41 NGZ | 467042 | XXVIII | 41 | 475/23.3.06 | M/s Anil Goyal | 24.03.06 | 28.04.06 | 466923 | Comp
50 | Civil | 2.1.06 | 20.12.05 | Const of Walkway of park infornt of Masjid I block Mangol puri in C 41 NGZ | 426849 | XXVIII | 41 | 35/27.04.06/EE-XXVIII | M/s K.K Const. Co-II | 27.04.06 | 19.07.06 | 419328 | Comp
51 | Civil | 2.1.06 | 20.12.05 | Const of walkway in CRP Park in industrial area Mangolpuri in C 42 NGZ | 481008 | XXVIII | 42 | 116/25.05.06/XXVIII | M/s Indians Apply Agencies | 25.05.06 | 15.12.08 | 444940 | Comp
52 | Civil | 2.1.06 | 20.12.05 | Imp of passage by RMC in A block Mkt back sid eof Dispensary in Mangolpuri in C 41 NGZ | 527230 | XXVIII | 41 | 474/23.03.06/EE-XXVII | M/s Brama Nand | 23.03.06 | 30.06.06 | 527230 | Comp
53 | Civil | 2.1.06 | 20.12.05 | Imp of lane by RMC from I-720 to I -676 in Mangolpuri inC 41 NGZ | 519158 | XXVIII | 41 | 473/23.03.07/EE-XXVIII | M/s Garg Enterprises | 23.03.06 | 22.06.06 | 519149 | Comp
54 | Civil | 2.1.06 | 20.12.05 | Imp of passage by RMC surrounding CTC Complex & Dhalao in I block in Mangolpuri in C 41 NGZ | 518234 | XXVIII | 41 | 471/23.03.06/EE-XXVIII | M/s Garg Enterprises | 23.03.06 | 30.06.06 | 516121 | Comp
55 | Civil | 07.03.06 | 14.12.05 | Imp of B/wall of park by pdg. Stone wall lining near parking & infront of N-480 Mangolpuri C-42/ N.G zone | 1011023 | XXVIII | 42 | 67/10.05.06/EE-XXVIII | M/s Pawan Builders | 11.05.06 | 26.07.06 | 1011023 | Comp
56 | Civil | 07.03.06 | 20.12.05 | Const of B/wall of park in front of R-577 in Mangolpuri C-42 N.G zone | 519374 | XXVIII | 42 | 519/28.03.06/EE-XXVIII | M/s Pawan Builders | 28.03.06 | 09.06.06 | 519374 | Comp
57 | Civil | 07.03.06 | 20.12.05 | Const of B/wall of park in front of R-577 in Mangolpuri C-42 N.G zone | 348312 | XXVIII | 42 | 10/17.04.06/EE-XXVIII | M/s Pawan Builders | 17.04.06 | 09.06.06 | 347500 | Comp
58 | Civil | 23.03.06 | 07.03.06 | Const. Of Snan Ghar and urinal Block near Ramlila Park in R-block in Mangopuri C-42/N.G zone | 191250 | XXVIII | 42 | 05/17.04.06/EE-XXVIII | M/s Lakshay Builders | 17.04.06 | 25.05.06 | 191228 | Comp
59 | Civil | 23.03.06 | 07.03.06 | Const. Of huts in R-block park Mnagolpuri in C-42/N.G zone | 192300 | XXVIII | 42 | 06/17.04.06/EE-XXVIII | M/s Harish Kumar | 17.04.06 | 25.05.06 | 192300 | Comp
60 | Civil | 23.03.06 | 07.03.06 | Const. Of Walkway surounding skirting ring in H-block park in Mangolpuir C-41/N.G zone | 199600 | XXVIII | 41 | 08/17.04.06/EE-XXVIII | M/s Rajeev Const.Co | 17.04.06 | 19.06.06 | 199500 | Comp
61 | Civil | 23.03.06 | 07.03.06 | Pdy passage by precast terrazo tile flooring in park near shan ghar Mnagolpuri C-42/ N.G zone | 187150 | XXVIII | 42 | 07/17.04.06/EE-XXVIII | M/s K.K Const. Co-II | 17.04.06 | 20.07.06 | 187076 | Comp
62 | Civil | 23.03.06 | 07.03.06 | Pdg G.I pipe line on park in front of MC primary School C-blcok Mangolpuri C-42 | 207008 | XXVIII | 42 | 509/28.03.06/XXVIIII | M/s Bramanand | 28.06.06 | P | 206745 | Comp
63 | Civil | 23.03.06 | 07.03.06 | Pdg. G.I pipr line on chatt puja park in P-block in Mangolprui C-42/ N.G zone | 206028 | XXVIII | 42 | 517/28.03.06/XXVIII | M/s Bramanand | 28.03.06 | P | 205770 | Comp
64 | Civil | 23.03.06 | 07.03.06 | Const of B/Wall of Agarsain vatika and passage in S-block in Mangolpuir C-42 | 327755 | XXVIII | 42 | 32/27.04.06/EE-XXVIII | M/s Anil Const.Co | 28.04.06 | 13.07.06 | 327694 | Comp
65 | Civil | 23.03.06 | 07.03.06 | Imp of B/wall of park and Pdg M.S gate on H-block park Crimenation ground Mangolpuri C-41 | 350042 | XXVIII | 41 | 31/27.04.06/EE-XXVIII | M/s K.K Const. Co-II | 27.04.06 | 09.06.06 | 349755 | Comp
66 | Civil | 23.03.06 | 07.03.06 | Const. Of lane from road No. 3 to y-2073 in Mangolpuri C-41 | 514160 | XXVIII | 41 | 28/27.04.06/EE-XXVIII | M/s Garg Enterprises | 27.04.06 | 26.07.06 | 512000 | Comp
67 | Civil | 28.03.06 | 20.12.05 | Imp of road bearn by RMC from 901 B.stand to J-Block X-ing in Mangolpuri C-42 | 514056 | XXVIII | 42 | 34/27.04.06/EE-XXVIII | M/s K.K Const. Co-II | 27.04.06 | 27.03.08 | 513834 | In Prog.
|  |  |  | Total | 21454894 | [6 empty] | 21612330

## AC-25
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06 UP TO 16.11.07
Municipal Corporation of Delhi
|  | Name Of MLA |  | Sh .Bijender Singh | AC-25 |  | year 2005-06 |  | Allocation | 200.00 lacs
|  | Name of Constituency |  | Nangloi Jatt.
|  | Ward Nos and Names |  | C-43 C-44
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 16
1 | Civil | 15.7.05 | 4.7.05 | Pdg RMC from H.no. 281 to H.no. 935 in Vill. Mundka in C-44 NGZ | 568800 | XXVIII | 44 | 357/30.12.05/XXVIII | M/s Surender Kumar Vats | 06.01.06 | 20.03.06 | 552738 | Comp.
2 | Civil | 15.7.05 | 3.7.05 | Pdg RMC from Usha General Store to H.no. 279 in vill Mundka in C-44. | 564300 | XXVIII | 44 | 235/31.10.05/XXVIII | M/s Akshita Builders | 05.11.05 | 03.11.06 | 552956 | Comp.
3 | Civil | 15.7.05 | 5.7.05 | Pdg RMC from Mange Ram Hous to Rohtak Rd I Vill Mundka Vill in C-44. | 569000 | XXVIII | 44 | 231/20.10.05/XXVIII | M/s V.K.Chaudhry | 25.10.05 | 9.01.06 | 550232 | Comp.
4 | Civil | 15.7.05 | 5.7.05 | Pdg RMC from Narain Singh House to DS Saini Hosue Jaipal to Chander Boss Hs, Bharat Singh to Jai Singh Hs, H.no. 722 to Anand hs, Shri Bhagwati to Lalit Hs, Rajender to Jai Bhagwan Hs, Balbir to Partap Hs and Bhim Singh to Dharam Veer Hs in vill Mundka C-44 NGZ | 1914916 | XXVIII | 44 | 374/16.01.06/XXVIII | M/s K.K.Const.Co-II | 17.01.06 | 04.04.06 | 1913240 | Comp.
5 | Civil | 15.7.05 | 5.7.05 | Imp to lane by pdg RMC from Chajju Ram Dharam Kanta to Todar Mal Chowk in Vill Mundka C-44. NGZ | 1510500 | XXVIII | 44 | 361/30.12.05 | M/s Sanjeev Kumar | 15.03.06 | 31.07.07 | 1509923 | Comp.
6 | Civil | 25.7.05 | 5.7.05 | Imp to lane by RMC fromS ita Ram House to Pond & Chander Bhan Hs to Phirni Rd in village Mundka in C-44 NGZ | 761600 | XXVIII | 44 | 392/06.02.06 | M/s Raj Enterprises | 10.03.06 | 14.06.07 | 735821 | Comp.
7 | Elect. | 24.8.05 | 17.8.05 | P/O Street lighting in Kavita Cly rd near Mela Ground Nursury in nangloi Assembly Constituency under NZ | 54861 | EEE-III | 44 | 487/14.02.06/EE(E)III | M/s Akansha Elect. | 15.02.06 | 28.02.06 | 50228 | Comp.
8 | Elect. | 24.8.05 | 17.8.05 | P/O Street lighting in Nangloi Village, Kamruddin nagar connecting rd in Nangloi assembly Constituency under NZ | 273366 | EEE-III | 44 | 442/29.12.05//EE(E)III | M/s Khanna Sales Corp. | 03.01.06 | 27.01.06 | 253534 | Comp.
9 | Elect. | 20.12.05 | 22.11.05 | P/O Street Lighting o n the road frm Nolthi Community Centre to Najafgarh Drain W. o. 44 under NGZ | 480344 | EEE-III | 44 | 82/10.05.06/EE(E)-III | M/s Bansal Elect.Store | 16.05.06 | 15.06.06 | 464032 | Comp.
10 | Elect. | 28.12.05 | 22.11.05 | P/O S treet lighting on the main connecting road Kammrudin Nagar vill to Rhtak Road in W.no. 44 NGZ | 226360 | EEE-III | 44 | 103/10.05.06/EE(E)III | M/s Perfact Electrical Works. | 18.05.06 | 15.06.06 | 216706 | Comp.
11 | Civil | 28.12.05 | 27.9.05 | stg of Carriage way by Dense carpetting from Hari Vatika to Bake Bihar Sweets at Nangloi Najafgarh rd in C 44 NGZ | 2228362 | EEE-III | 44 | 169/25.07.06/EE-XXVIII | M/s Competent Const.Co | 12.10.06 | P | 2187657 | In Prog
12 | Civil | 6.1.06 | 27.10.05 | Pdg Water arrangment in the park of GH -5 and 7, GH-13, GH-14 and Bhera Enclave in Paschim Vihar in C 43 NGZ | 259300 | XXVIII | 43 | 70/12.05.06/EE-XXVIII | M/s Naresh Kumar Bansal | 22.05.06 | 06.06.06 | 221412 | Comp.
|  |  |  | Total | 9411709 | [6 empty] | 9208479

## AC-28
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06 UP TO 16.11.07
Municipal Corporation of Delhi
|  | Name Of MLA |  | Sh.Ranbir Kharb | AC-28 |  | year 2005-06 |  | Allocation | 200.00 lacs |  | Dated:-
|  | Name of Constituency |  | Najafgarh
|  | Ward Nos and Names |  | C-43 C-50
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 16
1 | Civil | 9.5.05 | 7.5.05 | Imp of chowk by pdg CC near Panchahyat Ghar in C 50 vill Mundhela Kalan in C-50 | 197200 | Naj. | 50 | 274/EE.NG /22.7.05 | M/s Satish Kumar & Co | 22.7.05 | 9.9.05 | 187792 | Comp
2 | Civil | 9.5.05 | 7.5.05 | Pdg Drian & CC from Kawal Pahalwan Hs to Zile Singh Hs in vill mundhela Kalan in C-50. | 196400 | Naj. | 50 | 324/EE.NG /8.8.05 | M/s Rana Entep | 8.8.05 | 12.9.05 | 187037 | Comp
3 | Civil | 29.6.05 | 7.5.05 | Imp of lane by CC & Raising of Drain from Bimla Hs to Jain Electronics in Najafgarh, NGZ | 197600 | Naj. | 49 | 438/08.09.05/EE N.G | M/s Suresh Bros. | 10.09.05 | 04.11.05 | 188156 | Comp
4 | Civil | 29.6.05 | 7.5.05 | Imp of lane by pdg CC & Raising of drianf rom ABC Cyber Hills to Arya Samaj mandir Najafgarh, C-49. | 194900 | Naj. | 49 | 296/05.07.05/EE N.G | M/s Deep Const.Co | 03.08.05 | 05.10.05 | 185604 | Comp
5 | Civil | 29.6.05 | 7.5.05 | Imp of lane by CC & Raising of Drain from Om parkash etc to Raju Gipt Hs in Najafgarh in C-49. | 197200 | Naj. | 49 | 293/EE.NG/25.7.05 | M/s Harish Kr. | 26.7.05 | 30.8.05 | 187753 | Comp
6 | Civil | 29.6.05 | 7.5.05 | Imp of lane by CC & Raising of Drain from Ram Mandir to Daya Kaj Baton Shop in Najafgarh C-49. | 199300 | Naj. | 49 | 264/EE.NG/ 22.7.05 | M/s Vipin Kumar Dagar | 23.7.05 | 23.8.05 | 189636 | Comp
7 | Civil | 29.6.05 | 7.5.05 | Imp of laen by CC & Raising of drain from Verma time centre to Mahende Hs in Najafgarh in C-49. | 189500 | Naj. | 49 | 276/EE.NF 25.7.05 | M/s Rajender singh Dagar | 27.7.05 | 23.8.05 | 180442 | Comp
8 | Civil | 29.6.05 | 7.5.05 | Imp of lane by CC & Raising of derainf rom BS singla Hs to Ram Narain hs in Najafgarh in C-49. | 199200 | Naj. | 49 | 316//EE.NG/8.8.05 | M/s Goela Assoc. | 9.8.05 | 18.9.05 | 189706 | Comp
9 | Civil | 30.6.05 | 22.6.05 | Imp of Najafgarh Khaira link road by PMP from Bhal Singh Tmber store Towards Buddha Temple in NGZ | 191754 | VI | 49 | 72/EE-IV/26.9.05 | M/s Gaur Const Co. | 30.8.05 | 29.9.05 | 191370 | Comp
10 | Civil | 30.6.05 | 22.6.05 | Imp of rd by PMP from Kair Village towards Pipe Factory on Mundhela Kair Link rd in NGZ | 193213 | VI | 49 | 78/26.09.05/EE VI | M/s Manish Kumar | 03.10.05 | 29.11.05 | 193094 | Comp
11 | Civil | 30.6.05 | 22.6.05 | Imp of Khaira Najafgarh link road by PMP near by Surya Gas Agency Godwon in NGZ | 191176 | VI | 49 | 108/03.11.05/EE-NG | M/s R.L Builders | 07.11.05 | P | 164221 | In Prog.
12 | Civil | 14.7.05 | 20.6.05 | Imp & Cosnt of Phirni rd of vill Bakkargarh by Pdg MP from Mandir to Pond in NG Z | 794200 | VI | 50 | 112/10.11.05/EE-VI | M/s Rakesh Kumar | 10.11.05 | P | 532918 | In Prog.
13 | Civil | 14.7.05 | 20.6.05 | Const of drain on Phirni rd from H/o Shubram towards H/o Prabhu in vill. Mundhela Khurd in NGZ | 572159 | VI | 50 | 84/05.10.05/EE VI | M/s Sachin Const | 10.10.05 | 12.01.07 | 571678 | Comp
14 | Civil | 14.7.05 | 20.6.05 | Imp and Raising of Phirni rd by PMP from H/o Shubram towards H/o Prabhu in vil Mundhela hurd in NGZ | 478354 | VI | 50 | 83/05.10.05/EE VI | M/s Balvant Singh | 10.10.05 | 10.02.06 | 474845 | Comp
15 | Civil | 14.7.05 | 28.6.05 | Imp/Const of approach road of Cremation Ground by pdg RMC in Ujwa Village in NGZ | 689300 | VI | 50 | 119/23.11.05/EE VI | M/s Puneet Const | 05.12.05 | 27.02.06 | 562368 | Comp
16 | Civil | 21.7.05 | 20.6.05 | Imp of approach rd of vill Mundhela Khurd by pdg RMC from Mungesh pur drain to Tubewell in NGZ | 1722573 | VI | 50 | 120/23.11.05/EE Vi | M/s Ram Kumar Gupta | 24.11.05 | 03.02.06 | 1721960 | Comp
17 | Civil | 21.7.05 | 20.6.05 | Imp of chowk and lane by RMC in Mundhela Khurd in vill. In NGZ | 1694154 | VI | 50 | 122/23.11.05/EE VI | M/s Sunil Enterprises | 28.11.05 | 28.02.06 | 1693022 | Comp
18 | Civil | 29.7.05 | 27.7.05 | Imp of rd by pdg RMC at Najafgarh Gurgaon rd infront of PNB Bank to State Bank Najafgarh in C-49. | 197300 | Naj. | 49 | 421/8.9.05/E.NG | M/s Dabas Const co | 10.9.05 | 26.9.05 | 187888 | Comp
19 | Civil | 29.7.05 | 26.7.05 | Imp of road by MP at Nangloi Najafagrh rd opp Airforece offcie Bapdolla Village in C-49. | 199800 | Naj. | 49 | 383/EE.NG/26.8.05 | M/s Rajender singh Dagar | 29.8.05 | 12.10.05 | 190293 | Comp
20 | Hort. | 1.8.05 | 28.7.05 | p/F of MS Tree garuds on road side at Jaffarpur to Ujwa road in W> no. 50. | 99277 | DDH/Naj | 50 | 60/10.10.05/ADH/N.G | M/s Lucky Enterprises | 10.10.05 | 08.11.05 | 99277 | Comp
21 | Hort. | 1.8.05 | 28.7.05 | P/F MS Tree Garuds on road side at Baker Garh Vill Bakar Garh Border in W.no. 50. | 99277 | DDH/Naj | 50 | 126/02.02.06/ADH.N.G | M/s Lucky Enterprises | 02.02.06 | 06.03.06 | 98843 | Comp
22 | Hort. | 1.8.05 | 28.7.05 | P/F MS Tree Gaurds on road side at Dhans Vill to Dhansa Border in W.no. 50. | 99277 | DDH/Naj | 50 | 127/02.02.06/ADH/N.G | M/s Lucky Enterprises | 02.02.06 | 11.03.06 | 98843 | Comp
23 | Hort. | 1.8.05 | 28.7.05 | P/F MS Tree Gaurds on road side on Mundhela Moar to Mundhela Vill in W.no. 50. | 99277 | DDH/Naj | 50 | 128/02.02.06/ADH/N.G | M/s Lucky Enterprises | 02.02.06 | 06.03.06 | 98843 | Comp
24 | Hort. | 1.8.05 | 28.7.05 | P/F MS Tree Gaurds on road side at Malikpur Phirni approach rd in W>no. 50. | 99277 | DDH/Naj | 50 | 124/02.02.06/ADH/N.G | M/s Lucky Enterprises | 02.02.06 | 10.03.06 | 98843 | Comp
25 | Hort. | 1.8.05 | 28.7.05 | P/F MS Tree Gaurds on road side at main Dhansa Rd Issapur Moar to Dhansa Vill. In W.no. 50. | 99277 | DDH/Naj | 50 | 125/02.02.06/ADH.N.G | M/s Lucky Enterprises | 02.02.06 | 06.03.06 | 98843 | Comp
26 | Hort. | 1.8.05 | 28.7.05 | P/F MS Tree Gaurds on road side at Kher Road Turning to Khar Khari Jat mal vill Turning (Right Hand Side ) in W.n. 49. | 99277 | DDH/Naj | 49 | 131/02.02.06/ADH NZ | M/s Lucky Enterprises | 02.02.06 | 28.03.06 | 98843 | Comp
27 | Hort. | 1.8.05 | 28.7.05 | P/F MS Tree Gaurds on road side at Khera Dabar vill to Way to School in W>no. 49. | 99277 | DDH/Naj | 49 | 56/ADH. N.G. 10.10.05 | M/s Lucky | 10.10.05 | 21.10.05 | 99068 | Comp
28 | Hort. | 1.8.05 | 28.7.05 | P/F MS Tree Gaurds on road side at Khera Moar to Kharkheri Moar (Left Hand Side) in w.no. 49. | 99277 | DDH/Naj | 49 | 130/02.02.06 | M/s Lucky Enterprises | 02.02.06 | 28.03.06 | 98843 | Comp
29 | Hort. | 1.8.05 | 28.7.05 | P/F MS Tree Gaurds on road side at Khera Moar to Khera Vill in W>no. 49. | 99277 | DDH/Naj | 49 | 57/ADH/N.G 10.10.05 | M/s Lucky | 10.10.05 | 25.10.05 | 99068 | Comp
30 | Hort. | 1.8.05 | 28.7.05 | P/F MS Tree Gaurds on road side on Najafgarh Nangloi road (RHS) to Baprola vill. In w.no. 49. | 99277 | DDH/Naj | 49 | 59/10.10.05/ADH/N.G | M/s Lucky Enterprises | 10.10.05 | 31.10.05 | 99277 | Comp
31 | Hort. | 1.8.05 | 28.7.05 | P/F MS Tree Gaurds on road side at Najafgarh to Kakrola Regulator & Nangllhi Dairy Gashipur rd in W>no. 49. | 99277 | DDH/Naj | 49 | 58/10.10.05/ADH/N.G | M/s Lucky Enterprises | 10.10.05 | 28.10.05 | 99277 | Comp
32 | Hort. | 1.8.05 | 28.7.05 | P/F MS Tree Gaurds on road side on road Najafgarh Nangloi rd (LHJS) upto Baprol vill in W>no. 49. | 99277 | DDH/Naj | 49 | 115/30.01.06/ADH/N.G | M/s Lucky Enterprises | 30.01.06 | 01.02.06 | 98843 | Comp
33 | Civil | 2.8.05 | 19.7.05 | Imp of rd by PMP from Pnd to Heigher Sec. School in village Mitrau in C 50. | 199100 | Naj. | 50 | 536/14.11.05/EE. N.G | M/s Goela Assoc. | 14.11.05 | 22.12.05 | 189443 | Comp
34 | Civil | 2.8.05 | 19.7.05 | Imp of road by PMP from Dichau Road near Dichau Vill in C-50.3 | 199000 | Naj. | 50 | 470/14.10.05/EE. N.G | M/s R.S.Const | 14.10.06 | 22.11.05 | 189529 | Comp
35 | Civil | 2.8.05 | 19.7.05 | Imp of rad by PMP on Jharoda Rd near CRPF Camp & near Jharoda Vill. In C-50. | 196000 | Naj. | 50 | 467/14.10.05/EE N.G | M/s Lakshay Builders | 14.10.05 | 29.10.05 | 186619 | Comp
36 | Hort. | 5.8.05 | 28.7.05 | P/F MS Tree Gaurds on orad side at Khakhari nahar (Phirni) vill W.no. 49. | 99277 | DDH/Naj | 49 | 129/02.02.06 | M/s Lucky Enterprises | 02.02.06 | 27.03.06 | 98843 | Comp
37 | Hort. | 24.8.05 | 28.7.05 | P/F MS Tree Gaurds on Phirni rd side of Kharkhari Jatmal in W.no. 49 NZ | 98913 | DDH/Naj | 49 | 103/05.01.06/ADH/N.G | M/s Gurmeet Enterprises | 08.01.06 | 13.01.06 | 92141 | Comp
38 | Hort. | 24.8.05 | 28.7.05 | P/F MS Tree Gaurds on Phirni rd at Khera dabar Village W.no. 49 NZ | 98913 | DDH/Naj | 49 | 102/05.01.06/ADH/N.G | M/s Gurmeet Enterprises | 06.01.06 | 10.01.06 | 92141 | Comp
39 | Hort. | 29.8.05 | 29.7.05 | P/F MS Tree Gaurds on Phirni rd side at Ujwa Village to Kair College in W.no. 49 NZ | 99176 | DDH/Naj | 50 | 85/27.10.05/ADH/N.G | M/s S.K.Enginers & Cond. | 27.10.05 | 08.11.05 | 99060 | Comp
40 | Hort. | 29.8.05 | 29.7.05 | P/F MS Tree Gaurds on Road side at Ujwa Village to Samaspur village in W.no. 50 NZ | 99176 | DDH/Naj | 50 | 83/27.10.05/ADH.N.G | M/s S.K.Enginers & Cond. | 27.10.05 | 08.11.05 | 99060 | Comp
41 | Civil | 14.9.05 | 13.9.05 | Imp of lane by pdg CC & drainj from Birkha hs to Kedar hs upto Tuliram Hs invill Kair in C 50. | 191100 | Naj, | 50 | 472/14.10.05/EE N.G | M/s R.S Const. | 16.10.05 | 23.12.05 | 180550 | Comp
42 | Civil | 14.9.05 | 13.9.05 | Imp of lane by pdg CC & Drain from Chetram Hs to Bhoop Singh hs in vill Kair in C 50 | 198500 | Naj, | 50 | 483/24.10.05/ EE N.G | M/s Bittoo Const. | 24.10.05 | 12.01.06 | 188999 | Comp
43 | Civil | 14.9.05 | 13.9.05 | Pdg CC & Drain from Jai Kishan H sto Balra hs in vil Kair in C 50 | 199700 | Naj, | 50 | 461/14.10.05/EE N.G | M/s Vipin Kumar Dagar | 14.10.05 | 22.11.05 | 190139 | Comp
44 | Civil | 14.9.05 | 13.9.05 | Const of O/S drain both side from Chopal to Shishram Khatri in vill Kair in C 50 | 197500 | Naj, | 50 | 554/24.11.05/EE N.G | M/s Deep Const.Co | 24.11.05 | 23.12.05 | 188077 | Comp
45 | Civil | 14.9.05 | 13.9.05 | Imp to lane by pdg CC & Drain from Jagdish wali gali in vill Kair in C 50 | 131800 | Naj, | 50 | 468/14.10.05/ EE.N.G | M/s Dabas Builders | 14.10.05 | 29.10.05 | 125179 | Comp
46 | Civil | 14.9.05 | 13.9.05 | Imp of rd by PMP from Chopal to Shishram Khatri Hs in vill kair in C 50 | 197700 | Naj, | 50 | 464/EE.NG 14.10.05 | M/s Satish Kumar & Co | 14.10.05 | 29.10.05 | 188881 | Comp
47 | Civil | 14.9.05 | 13.9.05 | Imp of lane by CC and drain fromBus stand to Jhula in vill. Mundhela Khurd in C 50 | 199600 | Naj, | 50 | 485/24.10.05/EE N.G | M/s Sanjeev Kumar & Bros. | 24.10.05 | 19.12.05 | 184690 | Comp
48 | Civil | 14.9.05 | 13.9.05 | Imp of rd by PMP fromChopal to Harijan Basti in Vill kair in C 50 | 199000 | Naj, | 50 | 462/14.10.05/EE N.G | M/s Rana Entep | 14.10.05 | 23.12.05 | 189547 | Comp
49 | Civil | 14.9.05 | 13.9.05 | Imp of lane by pdg CC and drain from Jile Singh hs to Chopal in vill. Kair in C 50 | 198500 | Naj, | 50 | 552/24.11.05/EE N.G | M/s R.K.Enterprises | 24.11.05 | 23.12.05 | 188983 | Comp
50 | Civil | 14.9.05 | 13.9.05 | Imp of lane by pdg CC and drain from Jagdish Hs to Ghirhari in village Kair in C 50 | 193700 | Naj, | 50 | 474/EE.NG/14.10.05 | M/s Apoorv Builders & const | 14.10.05 | 20.11.05 | 184436 | Comp
51 | Civil | 14.9.05 | 13.9.05 | Const of Drain both sides from Chopal to Harijan basti in village Kair in C 50 | 194200 | Naj, | 50 | 484/24.10.05/EE N.G | M/s Vidaya Const. Co | 24.10.05 | 12.01.06 | 184934 | Comp
52 | Civil | 14.9.05 | 13.9.05 | Imp of lane by pdg CC and Drain from Chopal to MC Pry school in village Kair in C 50 | 188200 | Naj, | 50 | 466/EE.NG/14.10.05 | M/s Harish Kr. | 14.10.05 | 20.11.05 | 172734 | Comp
53 | Civil | 14.9.05 | 13.9.05 | Imp of chowk by pdg CC and Drain from Pandit Ramphal hs toPond in vill Mundela Kalan in C 50 | 285000 | Naj, | 50 | 222/04.09.06/EE-NG | M/s Jai Const.CO | 11.09.06 | 12.12.06 | 212308 | Comp
54 | Civil | 14.9.05 | 13.9.05 | Imp of lane by pdg CC and Drain from Hawa Singh hs gto Hoshiyar in village Samaspuri inC 50 | 263300 | Naj, | 50 | 895 |  |  |  | 167298
55 | Civil | 7.12.05 | 5.12.05 | Imp of lane by c.c & drain from Main road to end of road in village Jaffarpur in C-50/NGZ | 199300 | Naj, | 50 | 717/30.01.06/EE(NG) | M/s R.S Const.Co. | 05.02.06 | 15.03.06 | 189746 | Comp
56 | Civil | 7.12.05 | 5.12.05 | Imp of lane by pdg c.c. and drain from chowk to Kharb Niwas in vill Mundela Kalan in C-50/NGZ | 199460 | Naj, | 50 | 635/28.12.05/EE N.G | M/s Satish Kumar & Co | 28.12.05 | 23.01.06 | 189951 | Comp
57 | Civil | 4.1.06 | 22.7.05 | Imp of Lane by CC from Raj Karam Hs to Ram Kishan hs in Kharkhari Nahar in C 49 NGZ | 199600 | EE N.G | 49 | 708/23.01.06/EE N.G | M/s Apoorv Builders & const | 24.01.06 | 10.02.06 | 189851 | Comp
|  |  |  | Total | 14311599 | [6 empty] | 13429633

## AC-29
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06
Municipal Corporation of Delhi
|  | Name Of MLA |  | Sh. Mahabal Mishra | AC-29 |  | year 2005-06 |  | Allocation | 100.00 lacs |  |  | Dated:-
|  | Name of Constituency |  | Nasir pur
|  | Ward Nos and Names |  | C-51 Dabri C-52 Sagar pur
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Civil | 7.6.05 | 4.6.05 | Pdg Drainage System and CC fromH.no. F 206 to F 29 and F 236 to F 440/8 in Sadh Nagar inC 52. | 196400 | Naj. | 52 | 289/25.07.05/ N.G | M/s Ram Kishore Bairwa | 02.08.05 | 02.12.05 | 187034 |  |  | Comp
2 | Civil | 7.6.05 | 4.6.05 | Imp of lane by CC from H.no. RZ F 222/51 to RZ 238/3 in Sadh nagar in C-52. | 169900 | Naj. | 52 | 337/08.08.05/N.G | M/s Subhash Singh | 17.08.05 | 10.09.05 | 161598 |  |  | Comp
3 | Civil | 7.6.05 | 4.6.05 | Pdg Drainage system & CC from RZ-426/51 to RZ 654/6 in Sadh Nagar in C52. | 199700 | Naj. | 52 | 334/08.08.05/N.G | M/s Bansal Const. Co | 17.08.05 | 15.11.05 | 190117 |  |  | Comp
4 | Civil | 7.6.05 | 4.6.05 | Pdg D/System from F 206 to 178A/36 in Sadh Nagar in C-52. | 152700 | Naj. | 52 | 336/08.08.05/N.G | M/s Subhash Singh | 17.08.05 | 10.09.05 | 144090 |  |  | Comp
5 | Civil | 7.6.05 | 4.6.05 | Imp of alne by CC from H.no. 178A/36 to F 206 in Sadh Nagar in C-52 | 188700 | Naj. | 52 | 270/22.07.05/ N.G | M/s Parveen Const.Co | 31.07.05 | 26.10.05 | 179616 |  |  | Comp
6 | Civil | 15.6.05 | 9.6.05 | Imp of alane by CC & Drain from b-100 to R 14 in Mahavir Encl. in C51. | 389113 | Naj. | 52 | 396/EE.NG/29.8.05 | M/s Ishwar Singh Dagar | 30.8.05 | 7.10.05 | 389031 |  |  | Comp
7 | Civil | 23.6.05 | 22.6.05 | Pdg CC from H.no. RZ 20H/6 to RZ 20F/B & MC Pry School to MCW Centre Sagarpur (Main) in C52. | 197800 | Naj. | 52 | 326/EE.NG/ 8/8/05 | M/S Goyal consection | 28.9.05 | 11.11.05 | 188196 |  |  | Comp.
8 | Civil | 23.6.05 | 22.6.05 | Imp of lane by CC from H.no. RZ 47 to RZ 206/5A in main Sagarpur in C 52. | 109300 | Naj. | 52 | 286/25.07.05/N.G | M/s J.K Const.Co | 26.07.05 | 01.11.05 | 104084 |  |  | Comp.
9 | Civil | 23.6.05 | 22.6.05 | Pdg D/system & CC from h.no. 440 J to RZ F 20A in Sadh nagar in C 52. | 199700 | Naj. | 52 | 424/08.09.05/N.G | M/s Rajeev Kumar | 09.09.05 | 15.11.05 | 190099 |  |  | Comp.
10 | Civil | 23.6.05 | 22.6.05 | Pdg D/system & CC from H.no. 448 J to RZ F 29A in Sadh Nagar & RZ 20H/16 to RZ 20F/B in Sagarpur main in C 52. | 199200 | Naj. | 52 | 327 8/8/05 N.G | J.s const | 2005-08-17 | p | 188686 |  |  | Progress
11 | Civil | 30.6.05 | 22.6.05 | Imp of drainage sytem from C 14 to B-111 and B-67 to B 130 in Mahavir Encl in C 51.. | 199000 | Naj. | 51 | 312/08.09.05/N.G | M/s Apoorv Builders & Cont. | 19.08.05 | 15.11.05 | 188985 |  |  | Comp.
12 | Civil | 30.6.05 | 22.6.05 | Imp of lane by CC & Drain from H/1/13 to H 1/10 and H1/24 to H1/26 in Mahavir Encl In C-51. | 198900 | Naj. | 51 | 428/08.09.05/N.G | M/s S.J Const. | 17.09.05 | 12.12.05 | 189304 |  |  | Comp.
13 | Civil | 8.7.05 | 6.7.05 | Imp of lane by CC from Hn.o. RZ 28/29 to RZ 99 in Sagarpur (West) in C-52. | 176000 | Naj. | 52 | 343/22.08.05/N.G | M/s Vipin Kumar Dagar | 31.08.05 | 15.10.05 | 167567 |  |  | Comp.
14 | Civil | 8.7.05 | 6.7.05 | Imp of lane by CC from H.no. RZ 669/8 to RZ 835/3 in Sadh nagar in C 52. | 197500 | Naj. | 52 | 390/26.08.05/N.G | M/s Rana Entps. | 26.08.05 | 30.10.05 | 187991 |  |  | Comp.
15 | Civil | 15.7.05 | 22.6.05 | Imp of lanes by CC from b-111 to RZ C-14 and b 130 to b 67 in Mahavir Encl in C-51. | 199800 | Naj. | 51 | 494/31.10.05 | M/s Bansal Const. Co | 01.11.05 | 07.01.06 | 189709 |  |  | Comp.
16 | Civil | 28.7.05 | 29.6.05 | Imp of laen by RMC from H.no. RZ 20B/1H to RZ 729 in Sagarpur (West ) in C 52. | 559800 | Naj. | 52 | 82/01.05.06 | M/s Daba & Const.Co | 01.05.06 | 19.05.06 | 399967 |  |  | Comp.
17 | Civil | 28.7.05 | 29.6.05 | Imp of lane by CC from H.no. RZ 2/179 to RZ-23 & RZ 17 to RZ 13 A in Durga Park in C52. | 337800 | Naj. | 52 | 581/06.12.05/EE-NG | M/s Aditya Const.CO | 15.12.05 | P | 164459 |  |  | In Prog.
18 | Civil | 2.8.05 | 15.7.05 | Imp of lane by CC & Drain from H.n. RZ 86 to RZ 201 in Vaishali In C-51. | 186000 | Naj. | 51 | 429/08.09.05/N.G | M/s Apoorv Builders & Cont. | 09.09.05 | 15.11.05 | 177025 |  |  | Comp.
19 | Civil | 24.8.05 | 29.6.05 | Pdg. Drainag system & CC from H No RZ 1/266 to 7 A /266 in (w) sagarpur in C52 \N.G.Z | 263400 | Naj. | 52 | 93/12.05.06/EE(NG) | M/s Prem Singh Surhera | 13.05.06 | P | 169632 |  |  | In Prog.
20 | Civil | 24.8.05 | 29.6.05 | Pdg. Drainag system & CC from H No RZ 31/261 to shiv mandir in (w) sagarpur in C52 \N.G.Z | 364500 | Naj. | 52 | 663/03.01.06 | M/s Ved Const.co | 07.01.06 | 08.04.06 | 246530 |  |  | Comp.
21 | Civil | 24.8.05 | 29.6.05 | Pdg. Drainag system & CC from H No RZ A2/30A to RZ 4B in Durga park inC52 \N.G.Z | 265000 | Naj. | 52 | 95/12.05.06/EE(NG0 | M/s Rakesh Kumar Gole | 21.05.06 | 05.07.06 | 177236 |  |  | Comp.
22 | Civil | 24.8.05 | 29.6.05 | Pdg. Drainag system & CC from H No RZ 123/1 in Sagar pur main in C52 \N.G.Z | 372200 | Naj. | 52 | 811/17.02.06/N.G | M/s Bhagwati Pd. Shukla | 26.02.06 | 31.03.06 | 256211 |  |  | Comp.
23 | Civil | 24.8.05 | 29.6.05 | Pdg Drainage system & CC from H.no. 1117 to RZ 1127 and D 84 to C 125/2 in Sadh nagar in C 52 | 281200 | Naj. | 52 | 601/20.12.05/EE-NG | M/s Mukesh Builders | 29.12.05 | P | 166077 |  |  | In Prog.
24 | Civil | 24.8.05 | 29.6.05 | Pdg Drainage system and CC from H.no. 1196A to 1197 in Sadh Nagar in C 52 | 294800 | Naj. | 52 | 600/20.12.06/EE-NG | M/s Prem Singh Surhera | 08.09.06 | P | 139887 |  |  | In Prog.
25 | Civil | 24.8.05 | 6.7.05 | Pdg Drainge System & CC fom H.no. RZ 7B to RZ 20B to RZ C-1/B to RZ 1/97 in Durga Park in C 52. | 371500 | Naj. | 52 | 810/17.02.06 | M/s Suresh Kumar Gupta | 20.02.06 | 15.05.06 | 251884 |  |  | Comp.
26 | Civil | 24.8.05 | 6.7.05 | Pdg Drainge sytem & CC from H.no. RZ 10 to RZ 16A and H.no. RZ 1/63 to RZ 101 A in Durga Park in C 52. | 488200 | Naj. | 52 | 623/21.12.05/N.G | M/s Deepak Const.Co | 30.12.05 | 28.03.05 | 339117 |  |  | Comp.
27 | Civil | 24.8.05 | 6.7.05 | Pdg Drainage System and CC from H.no. RZ 50 to 2/385 in Sagarpur (W) in C 52. | 169700 | Naj. | 52 | 480/14.10.05/N.G | M/s Panwar Const.Co | 23.10.05 | 20.12.05 | 161563 |  |  | Comp.
28 | Civil | 24.8.05 | 6.7.05 | Pdg Drainge system and CC from H.no. RZ 188 t RZ 14B & H.no. 45B/207 to 2/5 in Durga Park in C 52. | 404800 | Naj. | 52 | 809/17.02.06 | M/s Suresh Kumar Gupta | 20.02.06 | 15.05.06 | 274628 |  |  | Comp.
29 | Civil | 29.8.05 | 20.7.05 | Pdg drainage system & CC from H.no. RZ 46/286 to RZ 26/284 & RZ 180/234 to RZ 77/284 in Geetanjali Pak Sagarpuri in C 52 | 392733 | Naj. | 52 | 329/01.11.06/EE-NG | M/s Raj Enterprises | 02.11.06 | 15.12.06 | 392642 |  |  | Comp.
30 | Civil | 29.8.05 | 20.7.05 | Imp of lane by CC from H.no.RZ 42/1 to RZ 10/11 in Geetanjali park Sagarpur in C 52. | 207160 | Naj. | 52 | 132/19.06.06/EE(NG) | M/s Gupta Const.Co | 19.06.06 | 14.08.06 | 207097 |  |  | Comp.
31 | Civil | 29.8.05 | 20.7.05 | Imp of lane by CC and Drainage from H.no. RZ-234/294 to 259/292 & RZ 48/28 to Deep Model School in Geetanjali park in Sagarpur inC 52. | 202802 | Naj. | 52 | 169/21.08.06/EE(NG) | M/s Jai Const.Co | 22.08.06 | 01.11.06 | 202720 |  |  | Comp.
32 | Civil | 29.8.05 | 20.7.05 | Pdg Drainge and CC from H.no. RZ 25/324 to RZ 324 & RZ 29 to RZ 94/116 & RZ 14 to RZ 42C & RZ 6/287 to 271/291 in Geetanjali Park Sagarpur in C 52. | 535100 | Naj. | 52 | 83/01.05.06/EE(NG) | M/s Jai Const.Co | 02.05.06 | 08.08.06 | 370028 |  |  | Comp.
33 | Civil | 29.8.05 | 20.7.05 | Imp of lane by RMC from Tilak Medical Sote to H/o Hiralal in C 52 in Sadh nagar | 396700 | Naj. | 52 | 840/28.02.06/EE(NG) | M/s RSD & Co. | 31.03.06 | 03.06.06 | 296202 |  |  | Comp.
34 | Civil | 29.8.05 | 20.7.05 | Imp of lane by RMC from Pardhan Chowk to Shiv Mandir Gali NO. 14 Sadh Nagar In C 52. | 453600 | Naj. | 52 | 846/01.03.06 | M/s Bhagwati Pd. Shukla | 31.03.06 | 03.06.06 | 337483 |  |  | Comp.
35 | Hort | 14.9.05 | 23.8.05 | P/F of CPA in park Phase-I Mangpapuri near H.no. 422 w.no. 51 NGZ | 97555 | DDH Naj | 52 | 135/03.02.06 | M/s Pahwa Builders | 06.02.06 | 03.04.06 | 93523 |  |  | Comp.
36 | Hort | 14.9.05 | 23.8.05 | P/F of CPA in park Ph-II Manglapuri near H.no. 176 W.n. 51 NGZ | 97555 | DDH Naj | 51 | 133/06.02.06 | M/s Pahwa Builders | 06.02.06 | 03.04.06 | 93520 |  |  | Comp.
37 | Hort | 14.9.05 | 23.8.05 | P/F CPA in park Sarai Sohal village near H.no. 84 Wn.o. 51 NGZ | 97555 | DDH Naj | 51 | 134/06.02.06 | M/s Pahwa Builders | 06.02.06 | 03.04.06 | 93520 |  |  | Comp.
38 | Hort | 14.9.05 | 23.8.05 | P/F of CPA in park mangla puri village (Main rd wala) w.no. 51 NGZ | 97555 | DDH Naj | 51 | 136/06.02.06 | M/s Pahwa Builders | 06.02.06 | 03.04.06 | 93520 |  |  | Comp.
39 | Civil | 6.12.05 | 7.9.05 | C/o built up section Drain from A 4 to G 167 in Mahavir Enclaver in C 51 NGZ | 457600 | Naj. | 51 | 170/21.09.06/ | M/s Jai Const.Co | 22.08.06 | 15.11.06 | 344650 |  |  | Comp.
40 | Civil | 6.12.05 | 7.9.05 | Imp ofl ane by CC & Drain from H.no. H1/43A to H-1/42 and h 31/3 to Dr. Mandip Singh hs in Mahvir Encl in C 51 NGZ | 261216 | Naj. | 51 | 08/04.04.06 | M/s Ishwar Singh Dagar | 05.04.06 | 30.05.06 | 261108 |  |  | Comp.
41 |  |  |  | Cancled on 16.03.06
42 | Civil | 6.12.05 | 7.9.05 | Imp of lane by pdg CC & Drain fromH.no. RZ-51A to RZ 62A in Vashit Park in C 51 in NGZ | 268431 | Naj. | 51 | 05/04.04.06 | M/s R.S.D & Co | 05.04.06 | 30.05.06 | 268157 |  |  | Comp.
43 | Civil | 6.12.05 | 7.9.05 | Imp of lane by CC & Drain frm H.no. RZ 41 to RZ 54 in Dabri Ext in C 51 NGZ | 255396 | Naj. | 51 | 45/20.04.06/EE(NG) | M/s Ishwar Singh Dagar | 21.04.06 | 21.06.06 | 255127 |  |  | Comp.
44 | Civil | 6.12.05 | 7.9.05 | Imp ofane by pdg RMC from H.no. RZ 55 to RZ 1567 I n Vashiali inC 51 NGZ | 362145 | Naj. | 51 | 09/04.04.06/EE(NG) | M/s Ishwar Singh Dagar | 05.04.06 | 23.06.06 | 362136 |  |  | Comp.
45 | Civil | 6.12.05 | 7.9.05 | Pdg Drainage system & CC from RZ 7A to Temple in Dabri Ext. in C 51 NGZ | 414974 | Naj. | 51 | 812/20.02.06 | M/s Rajeev Const.Co | 21.02.06 | 29.04.06 | 414647 |  |  | Comp.
46 | Civil | 6.12.05 | 7.9.05 | Imp of lane by RMC from RZ 30 to RZ 176 in Vaishali in C 51 NGZ | 364682 | Naj. | 51 | 10/04.04.06/EE(NG) | M/s Ishwar Singh Dagar | 05.04.06 | 25.06.06 | 364447 |  |  | Comp.
47 |  |  |  | Cancled on 16.03.06
48 | Civil | 6.12.05 | 7.9.05 | Imp of lane by CC & Drian from H.no. A 19 to G 21 and G 94 to G 94A and A 6 to A 11 in Mahavir Encl niC 51 NGZ | 367773 | Naj. | 51 | 07/04.04.06 | M/s Ishwar Singh Dagar | 05.04.06 | 30.05.06 | 367725 |  |  | Comp.
49 | Civil | 6.12.05 | 7.9.05 | Imp of lane by RMC from RZ 40 to Palam Dabri rd in Vaishali in C 51 NGZ | 429145 | Naj. | 51 | 48/20.04.06/EE(NG) | M/s Jai Const.Co | 21.04.06 | 17.06.06 | 429132 |  |  | Comp.
50 | Civil | 6.12.05 | 7.9.05 | Pdg Draiage system & CC from H.no. RZ -54 to RZ 67A in Dabri Ext in C 51 NGZ | 260916 | Naj. | 51 | 51/20.04.06/EE(NG) | M/s Manish Const.Co | 21.04.06 | 20.06.06 | 260733 |  |  | Comp.
51 | Civil | 6.12.05 | 15.7.05 | Const of outfall Drain in C 55 to B 52 in Sitapuri in C 51 NGZ | 690700 | Naj. | 51 | 882/14.03.06/EE(NG) | M/s Parresh Const.Co | 15.03.06 | 22.06.06 | 599980 |  |  | Comp.
52 | Civil | 6.12.05 | 15.7.05 | Imp of lane by CC & Drain from RZ 49 to RZ 7 in Sitapuri in C 51 NGZ | 292484 | Naj. | 51 | 06/04.04.06 | M/s Ishwar Singh Dagar | 05.04.06 | 30.05.06 | 292457 |  |  | Comp.
53 | Civil | 7.12.05 | 28.11.05 | Imp of Drainge sytem & CC from Palam Railway Station to Indira Park gali no 1 in Sadh Nagar in C 52 NGZ | 198500 | Naj. | 52 | 730/03.02.06/N.G | M/s N.A const | 28.02.06 | 30.03.06 | 188885 |  |  | Comp.
54 | Civil | 7.12.05 | 28.11.05 | Imp ofl ane by CC & Drainge system from Nutan Bal Vidaylaya Nehru Mket to Chutt Mandir in Sagarpur in C 52 NGZ | 196000 | Naj. | 52 | 636/28.12.05/N.G | M/s Apoorv Builders & Cont. | 28.12.05 | 01.03.06 | 186491 |  |  | Comp.
55 | Civil | 7.12.05 | 28.11.05 | Pdg RMC from Railway rd infront of Gali 14 to Immam Chand Patwari in Sadh nagar in C 52 NGZ | 199200 | Naj. | 52 | 729/03.02.06 | M/s Sehwag Const.Co | 29.03.06 | 10.05.06 | 189007 |  |  | Comp.
56 | Civil | 7.12.05 | 10.10.05 | Imp of lane by CC from RZ 27/252 to Masjid in Jagdama Vihar in Sagarpur(W) in C52 NGZ | 199000 | Naj. | 52 | 683/16.01.06/N.G | M/s Jain Entps | 25.01.06 | 04.03.06 | 148816 |  |  | Comp.
57 | Civil | 7.12.05 | 10.10.05 | Imp of lane by CC fro Juice Corner to Shiv Mandir in Sadh Nagar in C 52 NGZ | 156300 | Naj. | 52 | 644/28.12.05/EE(NG) | M/s Bansal Const. Co | 30.12.05 | 04.03.06 | 187326 |  |  | Comp.
58 | Civil | 7.12.05 | 10.10.05 | Pdg Drainage system & CC from H.no. RZ 3/52 to RZ 3/6B & RZ 3/52 to 9/F/178 in Durga Park in C 52 NGZ | 199345 | Naj. | 52 | 681/12.01.06/N.G | M/s Lakshay Builders | 12.01.06 | 28.02.06 | 199208 |  |  | Comp.
59 | Civil | 7.12.05 | 10.10.05 | Pdg Drainage ssytem from H.n. RZ 20B/14 to RZ 729 in Gali no 4 Sagarpur(W) in C 52 NGZ | 198874 | Naj. | 52 | 637/28.12.05/N.G | M/s Daba & Const.Co | 28.12.05 | 08.02.06 | 198800 |  |  | Comp.
60 | Civil | 7.12.05 | 10.10.05 | Pdg Drainage sytem & CC from H.no. RZ 486A/1 to Z 442/C-2 in Gail no. 23 in Sadh Nagar in C 52 NGZ | 184000 | Naj. | 52 | 718/30.01.06/N.G | M/s Deep Const.Co.II | 08.02.06 | 31.03.06 | 164298 |  |  | Comp.
61 | Civil | 14.12.05 | 20.07.05 | Imp of lane by CC fromH.n. Rz 299 to 317 in Sadh Nagar in C 52 NGZ | 290750 | Naj. | 52 | 889/17.03.06 | M/s Gupta Engineers and Construction | 18.03.06 | 27.04.06 | 216152 |  |  | Comp.
62 | Civil | 14.12.05 | 20.07.05 | Imp of lane by pdg Drainage & CC from H.no. 608A/11 to RZ 708/223 & E 225 to RZ 708H Gali no. 16C in Sadh Nagar in C 52 NGZ | 374100 | Naj. | 52 | 842/28.02.06 | M/s Gupta Engineers and Construction | 01.03.06 | 27.04.06 | 252901 |  |  | Comp.
63 | Civil | 14.12.05 | 20.07.05 | Imp of lane by CC from WZ 251 to WZ 162 & WZ 120 to WZ 124 in Sadh Nagar in C 52 NGZ | 350500 | Naj. | 52 | 835/24.02.06 | M/s Gupta Engineers and Construction | 05.03.06 | 08.05.06 | 332865 |  |  | Comp.
64 | Civil | 14.12.05 | 20.07.05 | Pdg Drainage system & CC from WZ 250 to WZ 230 in Sadh Nagar in C 52 NGZ | 569800 | Naj. | 52 | 814/20.02.06 | M/s Ishwar Singh Dagar | 28.02.06 | 31.03.06 | 390062 |  |  | Comp.
65 | Civil | 17.03.06 | 21.02.06 | Imp of lane by RMC from RZ-E-55 to RZ-E-53 and RZ-E-56 to RZ-E-69 in Mahavir Enclave C-51/NG zone | 198400 | Naj. | 51 | 62/20.04.06/EE(NG) | M/s Sehwag Const.Co | 29.04.06 | 05.06.06 | 188255 |  |  | Comp.
66 | Civil | 17.03.06 | 21.02.06 | Imp of lane by RMC & drain from H.NO RZ-185 to RZ-146 in Vaishali in C-51/N.G zone | 196600 | Naj. | 51 | 40/20.04.06/EE(NG) | M/s Sachin Kumar Gupta | 21.04.06 | 15.06.06 | 186602 |  |  | Comp.
67 | Civil | 17.03.06 | 21.02.06 | Pdg drainage system from H.NO C-4E to Dabri Palam Road in Mahvir Enclave in C-51/NG zone | 196200 | Naj. | 51 | 37/20.04.06/EE(NG) | M/s J.S Const.Co | 21.04.06 | 01.07.06 | 186758 |  |  | Comp.
68 | Civil | 30.03.06 | 20.07.05 | Pdg. Drainge and cc from H.NO. WZ 250 to RZ-140 A and RZ C 1 to RZ 22 A in Sadh Nagar in NZ | 290369 | Naj. | 52 | 595/19.12.06/EE-NG | M/s Shri Ram Const.Co | 19.12.06 | 20.02.07 | 290319 |  |  | Comp.
69 | Civil | 30.03.06 | 20.07.05 | Pdg drainge system and cc from WZ 932 to RZ 902 and WZ 770/4 to WZ 933 in Sadh Nagar in C 52 NZ | 382733 | Naj. | 52 | 813/15.02.07/EE(M)-II/NG | M/s Vijay Kumar | 22.02.07 | 23.05.07 | 382625 |  |  | Comp.
70 | Civil | 30.03.06 | 19.11.05 | Imp of lane by RMC from H.NO 59 to RZ J-4 in Sagar pure West in C-52 | 226127 | Naj. | 52 | 230/06.09.06/EE(NG) | M/s Shri Ram Const.Co | 06.09.6 | 01.11.06 | 226105 |  |  | Comp.
71 | Civil | 30.03.06 | 19.11.05 | Imp of lane by Pdg RMC from H.NO RZ 48 A to Bondary Ball in Sagar Pur West in C-52 | 343140 | Naj. | 52 | 247/11.09.06/EE(NG) | M/s Shri Ram Const.Co | 11.09.06 | 01.11.06 | 343123 |  |  | Comp.
|  |  |  | Total | 19286328 | [6 empty] | 16629475
Remarks:- No. of works booked=71, No. of works cancelled=2

## AC-30
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06
Municipal Corporation of Delhi
|  | Name Of MLA |  | Sh. Dharam Dev Solanki | AC-30 |  | year 2005-06 |  | Allocation | 100.00 lacs |  |  | Dated:-
|  | Name of Constituency |  | Palam
|  | Ward Nos and Names |  | C-53 C-53
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Physical Target | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 16
1 | Civil | 30.6.05 | 27.6.05 | Const of drain & CC near Home of jaipal Rajpal, Nafe Singh wali gali in 20pkt Programme Matiyala in C53. | 198000 | Naj. | 53 | 333/EE.NG/8.8.05 | M/s Nishant Const co | 26.8.05 | 6.9.05 | 189572 |  | Comp
2 | Civil | 30.6.05 | 27.6.05 | Imp of rd by pdg 2 cm Premix from Mandir towards Hasanpur village in C 53. | 186500 | Naj. | 53 | 292/EE.NG/25.7.05 | M/s Kamal Const co | 4.8.05 | 26.9.05 | 180729 |  | Comp
3 | Civil | 30.6.05 | 27.6.05 | Imp of rd by pdg 2 cm Premix from Pandwalan Phirni towards in C 53. | 187700 | Naj. | 53 | 335/EE.NG/8.8.05 | M/s Bansal const co | 6.9.05 | 26.9.05 | 181593 |  | Comp
4 | Civil | 30.6.05 | 27.6.05 | C/o Drain and Pdg CC in back lane from Aggarwal store to RZ F 762/41 in Raj Nagar -II in C54. | 158700 | Naj. | 54 | 503/31.10.05/NGZ | M/s Manish Kumar and Co. | 08.11.05 | 04.02.06 | 150982 |  | Comp.
5 | Civil | 30.6.05 | 27.6.05 | Pdg Drainge and CC from WZ 423 to Wz 624 and abck lane from WZ 450 to Nirmal Jeweller in Raj nagar -I in C 54. | 197000 | Naj. | 54 | 313/EE.NG/8.8.05 | M/s Sanjeev & Bros | 17.8.05 | 4.10.05 | 187312 |  | Comp
6 | Civil | 30.6.05 | 27.6.05 | PMP from RK Gutpa house to RS Rawat House in Raj Nagar-II in C54. | 474700 | Naj. | 54 | 399/29.08.05/N.G | M/s Ved Const.Co | 31.08.05 | 06.12.05 | 464289 |  | Comp
7 | Civil | 30.6.05 | 27.6.05 | Pdg Drainage and CC from B-113 to NZ 806A and B-128 in Raj nagar -I in C 54. | 573700 | Naj. | 54 | 368/EE.NG/26.8.05 | M/s A.R & Co | 27.8.05 | 18.10.05 | 486081 |  | Comp
8 | Civil | 30.6.05 | 27.6.05 | Imp of lane by CC and Drian from RZ 133 to RZ -D 120 in Raj nagar-II in C 54. | 303400 | Naj. | 54 | 400/29.08.05/N.G | M/s R.K.Const.Co III | 06.09.05 | 05.12.05 | 275951 |  | Comp
9 | Civil | 30.6.05 | 27.6.05 | C/o FP infront of MC Pry. School Palam Village in C 54. | 199500 | Naj. | 54 | 410/31.8.05/N.G | M/s Panwar Const co | 8.9.05 | 20.10.05 | 189999 |  | Comp
10 | Civil | 30.6.05 | 27.6.05 | C/o Drainf rom Community Hall to D 277 in JJ Cly Sector-7, Dwarka in C 54 | 363900 | Naj. | 54 | 371/26.8.05.N.G | M/s Suresh kr. & Co | 29.8.05 | 6.10.05 | 356251 |  | Comp
11 | Civil | 6.7.05 | 4.7.05 | PMP of road in Kiran Garden enar Kahender Hs in C53. | 185410 | Naj. | 53 | 645/28.12.05/EE-NG | M/s Mittal & Co. | 30.01.06 | P | 176497 |  | In Prog
12 | Civil | 6.7.05 | 4.7.05 | Pdg MP of rd near MCD Primary School, Tajpur Vill,. In C53. | 186500 | Naj. | 53 | 440/08.09.05/EE-NG | M/s Shiva Trading Co. | 17.09.05 | 16.12.05 | 180854 |  | Comp.
13 | Civil | 6.7.05 | 4.7.05 | Const of Open surface drain in village Pindwalan Kalan near Bus stand in C53. | 197800 | Naj. | 53 | 418/31.08.05/N.G | M/s Mukesh Builders | 17.09.05 | 07.11.05 | 191006 |  | Comp.
14 | Civil | 6.7.05 | 4.7.05 | Pdg Brick Flooring near Mandir in Goela Dairy in C-53. | 199700 | Naj. | 53 | 411/31.08.05/N.G | M/s Panwar Const co | 20.09.05 | P | 191192 |  | In Prog
15 | Civil | 6.7.05 | 4.7.05 | Pdg CC & Drainage in Bhagawali glai in vill Palam in C53. | 170420 | Naj. | 53 | 407/31.08.05/N.G | M/s Subhash Singh | 19.11.05 | 09.12.05 | 165457 |  | Comp.
16 | Civil | 6.7.05 | 4.7.05 | Pdg CC in Dalal wali gali in Palam vill, in C53. | 195900 | Naj. | 53 | 314/8.8.05 | M/s SanjeevKr. & Bros | 7.10.05 | 18.10.05 | 188984 |  | Comp
17 | Civil | 15.7.05 | 4.7.05 | PMP of Phirni rd in village Ambrahi from DDA flat to Ram Singh Hs in C53. | 186065 | Naj. | 53 | 415/31.08.05/N.G | M/s Vidaya Cosnt.Co | 28.09.08 | P | 180598 |  | In Prog
18 | Civil | 15.7.05 | 4.7.05 | PMP of rd in village Matiyala from Shiv Mandir to matrix Pharmacticals on Phirni in C53. | 186700 | Naj. | 53 | 435/08.09.05/NG | M/s Vijay Bansal | 28.09.05 | 28.10.05 | 180006 |  | Comp.
19 | Civil | 15.7.05 | 4.7.05 | pdg Brick flooring Kakrola Dairy C 53 /NG near Park from 18 to 57. | 199700 | Naj. | 53 | 510/02.11.05/N.G | M/s Goyal Const.Co | 09.11.05 | 06.01.05 | 193739 |  | Comp
20 | Hort. | 11.8.05 | 28.7.05 | P/F of MS Tree gards on Phirni rd of Khakhari Rond vill in w.no. 53. | 100000 | DDH Naj. | 53 | 55/1010.05 | M/s S.K. Engg Const | 10.10.05 | 19.10.05 | 99950 |  | Comp
21 | Hort. | 11.8.05 | 28.7.05 | P/F of MS Tree gards on Pindwala Kalan More to Kharkhari Rodn vill in w.no. 53. | 100000 | DDH Naj. | 53 | 50/ADH N.G | M/s S.K Engineer & Cont. | 10.10.05 | 15.10.05 | 96542 |  | Comp
22 | Hort. | 11.8.05 | 28.7.05 | P/F of MS Tree gards on Phirni rd of Galibpur vill in w.no. 53. | 100000 | DDH Naj. | 53 | 54/10.10.05/ADH N.G | M/s S.K. Engg Const | 10.10.05 | 22.10.05 | 96542 |  | Comp
23 | Hort. | 11.8.05 | 28.7.05 | P/F of MS Tree gards on main road of Rewla mopre to Rewla Khampur vill in C-53. | 100000 | DDH Naj. | 53 | 52/10.10.05/ADH N.G | M/s S.K. Engg Const | 10.10.05 | 20.10.05 | 96542 |  | Comp
24 | Hort. | 11.8.05 | 28.7.05 | P/F of childern play apprants in D& E block park opp H.no. D 123 & E-20, Sec-I JJ Dwarka w.no. 54. | 99867 | DDH Naj. | 54 | 94/13.12.05/ADH N.G | M/s M.S Entps | 13.12.05 | 27.12.05 | 99867 |  | Comp.
25 | Hort. | 11.8.05 | 28.7.05 | P/F of childern play apprants in park near Kali Mandir & opp. H.no. A 185 Sec7 JJ Dwarka in W>no. 53. | 99867 | DDH Naj. | 54 | 93/13.12.05/ADH N.G | M/s M.S Entps | 13.12.05 | 01.02.06 | 99867 |  | Comp.
26 | Hort. | 11.8.05 | 28.7.05 | P/F of childern play apprants in park opp H.no. A77. A 79, 88 in Mansa Ram Cly in W>no. 53. | 99867 | DDH Naj. | 53 | 97/13.12.05 | M/s M.S Entps | 13.12.05 | 28.12.05 | 99867 |  | Comp.
27 | Hort. | 11.8.05 | 28.7.05 | P/F of childern play apprants in park opp H.no. A-21, 299 in Kakrol Complex in W.n. 53 | 99867 | DDH Naj. | 53 | 100/13.12.05/ADH NG | M/s M.S Entps | 13.12.05 | 28.12.05 | 99867 |  | Comp.
28 | Hort. | 11.8.05 | 28.7.05 | P/F MS tree Garuds on main road of Goyla Diary Ph-I in .wno. 53. | 100000 | DDH Naj. | 53 | 51/10.10.05/ADH N.G | M/s S.K Engineer & Cont. | 10.10.05 | 26.10.05 | 96542 |  | Comp.
29 | Hort. | 11.8.05 | 28.7.05 | P/F MS tree Garuds on internal road of Mansa Ram park Cly in W.n. 53. | 100000 | DDH Naj. | 53 | 53/10.10.05/ADH N.G | M/s S.K Engineer & Cont. | 10.10.05 | 28.10.05 | 96542 |  | Comp.
30 | Hort. | 29.8.05 | 6.6.05 | P/F Tree gaurds on Phirni rd of Pochanpur Village W.no. 63 NGZ | 100000 | DDH Naj. | 53 | 108/30.01.06/NG | M/s Jai Enterprises | 30.01.06 | 22.03.06 | 96421 |  | Comp.
31 | Hort. | 29.8.05 | 6.6.05 | P/F of Tree Gaurds on Phini rd of Amrahi Village W.no. 53 NGZ | 99800 | DDH Naj. | 53 | 110/30.01.06/ADH NG | M/s Jai Enterprises | 30.01.06 | 23.03.06 | 96421 |  | Comp.
32 | Hort. | 29.8.05 | 6.6.05 | P/F of tree garuds on Lodhi Chowk, Palam to Harizan basti rd W.no. 53. | 99800 | DDH Naj. | 53 | 109/30.01.06/DDH(NG) | M/s Jai Enterprises | 15.02.06 | 31.07.06 | 95938 |  | Comp.
33 | Hort. | 29.8.05 | 6.6.05 | P/F Tree gaurds on Doda Dev mandir rd Palam W.no. 53 NGZ | 99800 | DDH Naj. | 53 | 111/30.01.06/ADH NG | M/s Jai Enterprises | 15.02.06 | 03.08.06 | 95938 |  | Comp.
34 | Hort. | 29.8.05 | 6.6.05 | P/F Tree gaurds on Palam Chowk to Harizan Basti rd W.no. 54 NGZ | 99800 | DDH Naj. | 54 | 112/30.01.06/ADH NG | M/s Jai Enterprises | 30.01.06 | 25.03.06 | 96421 |  | Comp.
35 | Hort. | 29.8.05 | 6.6.05 | P/F Tree gaurds on rd between MLA office and MC Pry school Palam in W>no. 53 NGZ | 99800 | DDH Naj. | 54 | 113/30.01.06/DDH(NG) | M/s Jai Enterprises | 15.02.06 | 07.08.06 | 95938 |  | Comp.
36 | Hort. | 29.8.05 | 6.6.05 | P/F Tree gaurds on Internal roads of Raj Nagr rd W.no. 54 NGZ | 99800 | DDH Naj. | 54 | 114/30.01.06/DDH(NG) | M/s Jai Enterprises | 15.02.06 | 10.08.06 | 95938 |  | Comp.
37 | Civil | 23.9.05 | 20.9.05 | Pdg Metalling premixing of rd from Professional Properties towards DDA alternative park in Ambrahi Village in C52 NGZ | 199000 | Naj. | 53 | 535/14.11.05/N.G | M/s Kamal Const co | 26.11.05 | 14.12.05 | 189418 |  | Comp.
38 | Civil | 23.9.05 | 20.9.05 | Pdg CC from Shiv mandir Palam to Ganga Ram Wli Gali in Palam C 53 | 197460 | Naj. | 53 | 502/31.10.05/EE-NG | M/s Sehrawat Const.Co-I | 07.11.05 | P | 183140 |  | In Prog
39 | Civil | 23.9.05 | 20.9.05 | pdg MP of road from Sweet Corner at matiyuala rd to Gurudwara in Kiran Garden in C 53 NGZ | 199700 | Naj. | 53 | 538/14.11.05/N.G | M/s Dabo & Const Co. | 05.12.05 | 12.01.06 | 188627 |  | Comp.
40 | Civil | 23.9.05 | 20.9.05 | Pdg Brick Flooring on road from Jain Sweet to Shcook in Village Pochanpur in C 53 NGZ | 192175 | Naj. | 53 | 532/14.11.05/N.G | M/s Parveen Const.Co | 03.01.06 | 20.02.06 | 182160 |  | Comp.
41 | Hort. | 3.10.05 | 17.9.05 | P/F Children Play appratus in MC park near Hanuman Mandir, Raj Nagar w.no. 54 NGZ | 98539 | Adh | 54 | 01/05.06.06/DDH(NG) | M/s Greenage Entps. | 05.06.06 | 27.06.06 | 92350 |  | Comp.
42 | Civil | 30.03.06 | 24.03.06 | Pdg CC from WZ-40 to WZ-40 71 in Harizan Basti in C-54 NGZ | 198700 | Naj. | 54 | 32/20.04.06/EE(NG) | M/s RSD & Co. | 28.04.06 | 25.07.06 | 188845 |  | Comp.
43 | Civil | 30.03.06 | 24.03.06 | C/o nalla from old Mehrauli road to RZ 403 in Raj Nagar-II in C-54 NGZ | 199900 | Naj. | 54 | 35/20.04.06/EE(NG) | M/s Dabas Builders | 03.06.06 | 24.06.06 | 189725 |  | Comp.
44 | Civil | 30.03.06 | 24.03.06 | C/o nalla from 444/ E to E60 in Raj Nagar II in C-54 NGZ | 199900 | Naj. | 54 | 33/20.04.06/EE(NG) | M/s Appoorva Builders & Contractor | 20.04.06 | 28.07.06 | 190218 |  | Comp.
45 | Civil | 30.03.06 | 24.03.06 | Pdg M/P from B-176 to C-7 in J.J Colony Sec-I in C-54 NGZ | 198700 | Naj. | 54 | 23/17.04.06/EE(NG) | M/s Puneet Sehrawat & Co. | 18.04.06 | 14.07.06 | 189165 |  | Comp.
46 | Civil | 30.03.06 | 24.03.06 | Pdg Drainage from WZ-70 to WZ-36 and WZ-23 in Harijan Basti in C-54 in NGZ | 199900 | Naj. | 54 | 22/17.04.06/EE(NG) | M/s Rajinder Singh Dagar | 20.04.06 | 24.07.06 | 190080 |  | Comp.
47 | Civil | 30.03.06 | 24.03.06 | Pdg CC and drainage in Back lane of Sanjay Hospital in pooran Nafar in C-54 in NGZ | 99600 | Naj. | 54 | 41/20.04.06/EE(NG) | M/s Ram Chander Degra | 24.04.06 | 28.06.06 | 94596 |  | Comp.
48 | Civil | 30.03.06 | 24.03.06 | C/o Drain and pdg CC from H-416 to RZ-408 and RZ-118 A in Raj Nagar II in C-54 NGZ | 199100 | Naj. | 54 | 24/17.04.06/EE(NG) | M/s Sehruwat Const.Co | 20.04.06 | 14.07.06 | 189231 |  | Comp.
49 | Civil | 30.03.06 | 24.03.06 | C/o Drain and pdg CC from Restogi Gen Stone to lal Clinic in Raj nagar II in C-54 NGZ | 599100 | Naj. | 54 | 223/04.09.06/EE(NG) | M/s Jai Dada Budha Const.Co | 05.09.06 | 30.09.06 | 458985 |  | Comp.
50 | Civil | 30.03.06 | 24.03.06 | Pdg CC in Back and Front lave from WZ-24A to Chawdgi Raw H.S in Raj Nagar-II C-54 in NGZ | 199300 | Naj. | 54 | 36/20.04.06/EE(NG) | M/s P.K & Co | 27.04.06 | 27.05.06 | 189594 |  | Comp.
51 | Civil | 30.03.06 | 24.03.06 | Pdg RMC from STD shop to E-30 in Raj Nagar II in NGZ | 199600 | Naj. | 54 | 65/20.04.06/EE(NG) | M/s Ashish Const.Co | 03.07.06 | 22.07.06 | 189907 |  | Comp.
[5 empty] | 9430237 | [6 empty] | 8872276

## AC-31
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06
Municipal Corporation of Delhi
|  | Name Of MLA |  | Sh Vijay Singh Lochav | AC-31 |  | year 2005-06 |  | Allocation | 190.00 lacs |  |  | Dated:-
|  | Name of Constituency |  | Mahipal pur
|  | Ward Nos and Names |  | C-55 Bijwasan C-Mahipal pur
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Civil | 6.7.05 | 26.6.05 | Pdg Drainage system from Rishi Hs to Manoj Hs in Mahipal Pur in C56. | 199900 | NG | 56 | 561/24.11.05/N.G | M/s Om Parkash Mittal | 03.12.05 | 19.02.06 | 189189 |  |  | Comp.
2 | Civil | 28.7.05 | 5.7.05 | Const of Phirni rd by MP of vill Bijwasan Between Palam Vihar NGZ | 282200 | EE-VI | 55 | 8/05.10.05/EE VI | M/s Sonu Const.Co | 26.10.05 | P | 277088 |  |  | In Prog.
3 | Civil | 28.7.05 | 5.7.05 | C/o Road and drian on the Phirni rd of vill Kanganheri rom H/o Khem Chand to Pond in NGZ | 291700 | EE-VI | 55 | 192/09.01.06/EE-VI | M/s Ajit Singh | 20.05.06 | 14.06.07 | 289233 |  |  | Comp.
4 | Civil | 28.7.05 | 6.7.05 | Pdg CC on the Phirni rd of vill Bamnouli from MCD school to H/o Sh Azad Singh in NGZ | 990800 | EE-VI | 55 | 123/23.11.05/EE VI | M/s Sehrawat Const.Co | 28.11.05 | 01.02.06 | 976879 |  |  | Comp
5 | Civil | 12.8.05 | 8.8.05 | pdg CC and Channel from Shankar to Suraj Bhan hs Ishwar Hs to Bijwasan Rd and Kishan Hs to Phirni in Villaeg Chhawla in C 55 | 194900 | Naj | 55 | 493/31.10.05//N.G | M/s A.K Const.Co | 04.11.05 | 07.01.06 | 183183 |  |  | Comp
6 | Civil | 12.8.05 | 8.8.05 | Const of Covered drain from Jaage hs Naresh hs on Khati Mohalla rd in Vill Kapashere inC 55 | 198700 | Naj | 55 | 463/14.10.05/N.G | M/s Rana Entps | 17.10.05 | 28.11.05 | 188003 |  |  | Comp
7 | Civil | 12.8.05 | 8.8.05 | Pdg RMC from Hari Kishan hs upto Bank on rd in front of MLA hs in village Bamnoli in C 55. | 388900 | Naj | 55
8 | Hort. | 24.8.05 | 22.7.05 | p/F of Children Play Apptt inpark of C 8 opp. F.no. 8262, 8555 Vasant Kunj in W.no. 56. | 99867 | DDH Naj | 56 | 98/13.12.05/ADH N.G | M/s M.S Enterprises | 13.12.05 | 26.12.05 | 99866 |  |  | Comp
9 | Hort. | 24.8.05 | 22.7.05 | p/F of Children Play Apptt inpark of C 9 opp. F.no. 9554, 9472 Vasant Kunj in W.no. 56. | 99867 | DDH Naj | 56 | 95/13.12.05/ADH N.G | M/s M.S Enterprises | 13.12.05 | 23.12.05 | 99866 |  |  | Comp
10 | Hort. | 24.8.05 | 22.7.05 | p/F of Children Play Apptt inpark of B 4 opp. F.no. 3014 Vasant Kunj in W.no. 56. | 99867 | DDH Naj | 56 | 92/13.12.05/ADH NG | M/s M.S Enterprises | 13.12.05 | 05.01.06 | 99866 |  |  | Comp
11 | Hort. | 24.8.05 | 22.7.05 | p/F of Children Play Apptt inpark of D 7 opp. F.no. 7130, 7353 Vasant Kunj in W.no. 56. | 99867 | DDH Naj | 56 | 96/13.12.05/ADH NG | M/s M.S Enterprises | 13.12.05 | 02.01.06 | 99866 |  |  | Comp
12 | Hort. | 24.8.05 | 22.7.05 | p/F of Children Play Apptt inpark of D 3 opp. F.no. 3307, 3196 Vasant Kunj in W.no. 56. | 99867 | DDH Naj | 56 | 99/13.12.05/ADH NG | M/s M.S Enterprises | 13.12.05 | 04.01.06 | 99866 |  |  | Comp
13 | Hort. | 14.9.05 | 22.8.05 | P/F MS tree Gaurds onMainr d Bamnoli More to Bijwasan Vill W.no. 55 | 99176 | DDH Naj | 56 | 86/27.10.05/ADH N.G | M/s S.K Engineer & Cont. | 27.10.05 | 26.12.05 | 99060 |  |  | Comp
14 | Hort. | 14.9.05 | 22.8.05 | P/F of MS tree Gaurds on rd side at main rd Chhawla vill to Jhatikra More (RHS) in W.no. 55 NGZ | 99176 | DDH Naj | 56 | 88/27.10.05/ADH N.G | M/s S.K Engineer & Cont. | 27.10.05 | 23.12.05 | 99060 |  |  | Comp
15 | Hort. | 14.9.05 | 22.8.05 | P/F of MS tree Gurads on rd from MC pry school Bijwasant o kapashere village W.n. 55 | 99176 | DDH Naj | 55 | 87/27.10.05/ADH N.G | M/s S.K Engineer & Cont. | 27.10.05 | 26.12.05 | 99060 |  |  | Comp
16 | Hort. | 14.9.05 | 22.8.05 | P/F of MS tree Gurads on rd Kaganheri vill to Badu sarai vill (RHS) w.no. 55 NGZ | 99176 | DDH Naj | 55 | 84/27.10.05/ADH N.G | M/s S.K Engineer & Cont. | 27.10.05 | 22.12.05 | 99060 |  |  | Comp
17 | Hort. | 14.9.05 | 22.8.05 | P/F of MS tree Gurads on rd Kanganheir village to Chhawla vill (RHS) w.n. 55 NGZ | 99176 | DDH Naj | 55 | 89/27.10.05/ADH N.G | M/s S.K Engineer & Cont. | 27.10.05 | 23.12.05 | 99060 |  |  | Comp
18 | Civil | 28.9.05 | 26.8.05 | pdg RMC from Phirni to Bijwasan rd near Khazan hs in vill Bijwasan in C 55 NGZ | 529657 | Naj | 55 | 927/30.03.06/EE(NG) | M/s Raj Entps. | 07.04.06 | 08.07.06 | 528512 |  |  | Comp.
19 | Civil | 28.9.05 | 26.8.05 | Pdg RMC from Jai Chand Hs to gali no 8 onKhati Mohalla rd in village Kapashere in C 55. | 486599 | Naj | 55 | 813/20.02.06/N.G | M/s Raj Entps. | 27.01.06 | 28.06.06 | 484970 |  |  | Comp.
20 | Civil | 28.9.05 | 26.8.05 | Pdg RMC from Ram, Saroop hs tochowk Rajeshhs to main rd in vill. Chhawala in C 55. | 286088 | Naj | 55 | 926/30.03.06/EE(NG) | M/s Raj Entps. | 03.04.06 | 06.07.06 | 282723 |  |  | Comp.
21 | Civil | 28.9.05 | 26.8.05 | Pdg RMC from Baljit hs to Chander Hs & Chander Bhan hs to Bishma Chowk in Vill Bijwasan in C 55 | 337340 | Naj | 55 | 925/30.03.06/NG | M/s Raj Entps. | 06.04.06 | 15.05.06 | 335404 |  |  | Comp.
22 | Civil | 28.9.05 | 26.8.05 | pdg CC from Mahender Hs to Rajroop Hs and Pardhan Wali in Vill Kapashere in C 55 | 254108 | Naj | 55 | 743/06.02.06/N.G | M/s Halash Kumar | 07.02.06 | 21.03.06 | 254108 |  |  | Comp.
23 | Civil | 28.9.05 | 26.8.05 | Pdg RMC & Drain from Kohli Building to Najafgarh Bijwasan Rd in vill Bijwasan in C 55 | 450509 | Naj | 55 | 729/13.02.06/NG | M/s Raj Entps. | 14.02.06 | 28.04.06 | 449267 |  |  | Comp.
24 | Civil | 28.9.05 | 26.8.05 | PDG RMC from Kanwar Singh Yadav hs to main rd back side of MC pry school (B) in Vill Kapashere in C 55 | 199000 | Naj | 55 | 556/24.11.05/N.G | M/s Jain Entps | 26.11.05 | 04.02.06 | 189489 |  |  | Comp.
25 | Civil | 28.9.05 | 26.8.05 | Pdg RMC & Drain in laen in back side of MCD Disp. And Baljit Plot wali gali in Vill Bijwasan in C 55 | 197100 | Naj | 55 | 613/20.12.05/N,G | M/s Ajay Kumar | 21.12.05 | 04.02.06 | 186911 |  |  | Comp.
26 | Civil | 28.9.05 | 26.8.05 | Pdg RMC & Drain from Sh. Khazan hs to Surajmal School in Vill Bijwasan | 280650 | Naj | 55 | 794/13.02.06 | M/s Raj Entps. | 20.02.06 | 14.04.06 | 280538 |  |  | Comp.
27 | Civil | 28.9.05 | 26.8.05 | Pdg RMC & Drain from Red Cross centre to Naresh hs in village Jhatikra in C 55. | 197500 | Naj | 55 | 555/24.11.05/N.G | M/s Madanlal Gupta | 25.11.05 | 30.12.05 | 185355 |  |  | Comp
28 | Civil | 28.9.05 | 26.8.05 | Pdg RMC from Bhagwan Singh hs to Jai Parkash Hs in vill Bijwasan in C 55. | 198100 | Naj | 55 | 553/24.11.05/N.G | M/s Shokeen Entps | 01.12.05 | 07.01.06 | 188356 |  |  | Comp
29 | Civil | 28.9.05 | 26.8.05 | Pdg RMC & Drain from Chopal to Poppal Shop in village kapashere in C 55 NGZ | 194000 | Naj | 55 | 615/20.12.05/EE(NG) | M/s Mittal & Co | 27.12.05 | 09.06.06 | 184699 |  |  | Comp.
30 | Civil | 28.9.05 | 26.8.05 | Pdg RMC from Ramniwas Hs to Sunder Hs and Raman Hs to Juglal hs in village Bijwasan in C 55 | 452894 | Naj | 55 | 793/13.02.06/EE(NG) | M/s Raj Entps. | 20.02.06 | 15.05.06 | 450557 |  |  | Comp.
31 | Civil | 28.9.05 | 26.8.05 | Pdg RMC & Drain from Sh. Sat Parkash X.MLA old Hs to Chowk near Mange Ram Hs & CC & Chhannel from Baljit Dhoopan Hs to Sat Parkash Wali gali ni village Bijwasan in C 55 | 347689 | Naj | 55 | 747/06.02.06/NG | M/s Raj Entps. | 08.02.06 | 14.04.06 | 347464 |  |  | Comp.
32 | Civil | 28.9.05 | 8.8.5 | Pdg RMC from Mam chand hs near MC Pry school (G) to Old NG-8, Mata chowk to Old NG-8, Yadav Hs to main rd and SW drain & RMC from Sewa Ram Hs to Sarjit Hs and CC in Sibba Harizan wali gali in vill Kapashere C 55. | 571123 | Naj | 55 | 923/30.03.06/EE(Ng) | M/s Chend Singh | 01.04.06 | 01.07.06 | 568819 |  |  | Comp.
33 | Civil | 28.9.05 | 8.8.5 | Pdg RMC from Dharam Singh Hs to Phirni RMC from Shookeen Hs to Chowk Rajiv Hs to Vinod Hs Rajesh Hs to Main rd near Harizen Basti and Onkar Hs to Phirni in village Chhawala in C 55 NGZ | 585956 | Naj | 55 | 746/06.02.06/Ng | M/s Raj Entps. | 07.02.06 | 14.04.06 | 582880 |  |  | Comp
34 | Civil | 6.10.05 | 27.9.05 | C/o Rd by MP on the Phirni rd of village Kangan heri from main Nanakheri rd to H/o Sh Jagdish in NGZ | 479798 | EE-VI | 55 | 243/08.02.06/EE-VI | M/s Ajit Singh | 20.06.06 | P | 478354 |  |  | In Prog
35 | Civil | 23.11.05 | 2.11.05 | Const of drain on the Phirni rd of vill Badu Sarai frok Mandir to Culvert on Kangan Heri Rd in C 55 NGZ | 411491 | EE-VI | 55 | 36/08.02.06/EE-VI | M/s Ajit Singh | 20.06.06 | P | 411454 |  |  | In Prog
36 | Civil | 24.1.06 | 21.12.05 | Const of Drain from Kalwati hs to EP-51, EP 21 to Phirni & Pardhan Hs to Harijan Basti in vill Badu Sarai in C 55 NGZ | 186432 | N.G | 55 | 762/07.02.06/N.G | M/s Rana Entps | 11.02.06 | 12.05.06 | 186101 |  |  | Comp.
37 | Civil | 24.1.06 | 21.12.05 | Pdg CC and Drain from Sh Chiranjipal hs to Bheem Hs in village Bijwasan in C 55 NGZ | 189507 | N.G | 55 | 759/07.02.06/NG | M/s Madanlal Gupta | 11.02.06 | 01.04.06 | 185586 |  |  | Comp.
38 | Civil | 24.1.06 | 21.12.05 | Pdg RMC from Azad hs to Phirni in village Bijwasan in C 55 NGZ | 185805 | N.G | 55 | 772/10.02.06/EE(NG) | M/s Rajender Singh Dagar | 17.02.06 | 05.05.06 | 183764 |  |  | Comp.
39 | Civil | 24.1.06 | 4.11.05 | Const of outfall Drain from pond to Phirni in Village Bamnoli I C 55 NGZ | 499096 | N.G | 55 | 171/21.08.06/EE-NG | M/s Jai Const.CO | 28.08.06 | 13.11.06 | 495853 |  |  | Comp.
40 | Civil | 24.1.06 | 4.11.05 | Pdg RMC & Drian from Sh. Malkhan Singh Hs to Sh. Bharat Singh hs & Drain from hs. Bhagwan Singh hs to Sh Birham Singh hs & Sh. Ompal hs to Sh Nafe Singh hs in Village Hassanpur in C 55 NGZ | 218591 | N.G | 55 | 50/20.04.06/EE-NG | M/s Jai Const.CO | 08.06.06 | P | 216175 |  |  | In Prog
41 | Elec | 08.03.06 | 06.03.06 | P/o lighting arrangment in sector -A pocket-B Park Vasany Kunj in W.NO-56 under NGZ | 169865 | EE(E) III | 56 | 123/18.05.06/EE(E)-III | M/s Saksham Electricals & Electronics | 18.05.06 | 24.05.06 | 164785 |  |  | Comp.
[5 empty] | 11451213 | [6 empty] | 10920329
Note on E54: R.P.S: