## AC-22
STATUS REPORT OF MLA FOR THE YEAR 2005-06
Municipal Corporation of Delhi
Narela Zone
|  | Name Of MLA |  | Sh. Surender Kumar | AC-22 |  | year 2005-06 |  | Allocation | 200 |  |  | Dated:-
Name of Constituency
|  | Ward Nos and Names |  | C-37 Bawana C-38,Kanjhawla
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agency | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14
1 | Elect | 10.6.05 | 28.4.05 | P/o Street light fittings on Existing poles in village Bawana, pooth khurd bultan pur and Chand puri Majra under Narela Zone W.No-37 | 199833 | EE(E)-II | 37 | 53/6.9.05/EEE-II | M/s Perfect Elect.works | 14.9.05 | 5.10.05 | 184769 |  |  | Comp.
2 | Elect | 10.6.05 | 28.4.05 | P/o Street light fittings on Existing poles in village Darya pur Nangal Thakran & Bajit pur under Narela Zone W.No-37 | 199970 | EE(E)-II | 37 | 49/6.9.05/EEE-II | M/s Bansal Elect store | 12.9.05 | 5.10.05 | 181406 |  |  | Comp.
3 | Elect | 10.6.05 | 28.4.05 | P/o Street light fittings an existing poles in village Auchandi Harwali w.No-37 NZ | 199885 | EE(E)-II | 37 | 54/6.9.05/EEE-II | M/s Perfect Elect.works | 14.9.05 | 5.10.05 | 183436 |  |  | Comp.
4 | Elect | 10.6.05 | 28.4.05 | P/o Street light fittings on existing poles in village Mungesh pur Qutab Garh, Jatkhor, Punjab Khore. W.No-37 under Narela Zone | 199885 | EE(E)-II | 37-I | 55/8.9.05/EEE-II | M/s S.G Enterp. | 16.9.05 | 7.10.05 | 183615 |  |  | Comp.
5 | Elect | 10.6.05 | 28.4.05 | P/o Street light fittings an existing poles in village Kanjhawla Lad pur, Jounti Gandhi Randla & Nizam pur W.No-38 NZ | 199730 | EE(E)-II | 38 | 48/6.9.5/EEE-II | M/s Bansal Elect store | 12.9.05 | 5.10.05 | 183354 |  |  | Comp
| Civil | 20.6.05 | 14.6.05 | Additional booking :- Imp to gali from Chopal to Zile singh House in village Nizam pur C-38 -I Narela Zone. | 88409 | EE(Pr) R | 38-I | 163/24.08.05/EE-Narela | M/s Khatri Const.Co. | 09.09.05 | 18.02.06 | 87409 |  |  | Comp
6 | Civil | 5.7.05 | 6.5.05 | Imp to lane by RMc from Hari singh Hs to Chopal in village Bawana W.No-37, Narela | 563583 | EE(Pr) R | 37 | 92/30.12.05/EE(Pr)R | M/s Vijay Bansal | 05.01.06 | 27.02.06 | 563402 |  |  | Comp.
7 | Civil | 5.7.05 | 6.5.05 | Imp to the road berms portion by RMC between road and drain from canal to culvort on Delhi road in village Bawana in W.No-37 NZ | 519207 | EE(Pr) R | 37 | 84/28.12.05/EE(Pr)R | M/s Vijay Kumar II | 26.12.05 | 30.03.06 | 518172 |  |  | Comp.
8 | Civil | 5.7.05 | 6.5.05 | Imp to the lane of Ram singh & Brahm Prakash by providing brick flooring in village Mungesh pur C-37 NZ | 315000 | EE(Pr) R | 37 | 53/19.10.05/EE(Pr)R | M/s Naresh Kumar Garg | 19.10.05 | 03.01.06 | 279282 |  |  | Comp.
9 | Civil | 5.7.05 | 6.5.05 | C/o B/Wall & beautification of park infront of Ram singh Hs in village Harwali w.No-37 NZ | 392000 | EE(Pr) R | 37 | 64/07.12.05/EE(Pr)R | M/s Naresh Kumar Garg | 08.12.05 | 08.02.06 | 320601 |  |  | Comp.
10 | Civil | 28.7.05 | 25.7.05 | C/o culvert at Dadi Sati Mandir Marg in village Mangal thankran in C-37-I NZ | 179500 | EE-Narela | 37 | 161/11.08.05/EE-Narela | M/s Khatri Const.Co. | 20.08.05 | 19.10.05 | 173811 |  |  | Comp.
11 | Civil | 18.8.05 | 1.8.05 | Providing C.C Opp M.C Primary School in village Mandan pur Dabas W.No-38/Narela | 198802 | EE(Pr) R | 38 | 91/30.12.05/EE(Pr.)Rural | M/s R.L Builders | 06.03.06 | 30.06.06 | 197097 |  |  | Comp.
12 | Civil | 18.8.05 | 1.8.05 | Imp to road by PMP from Gyani Hs to Trasnformer in village Nizam pur W.No 38 | 418600 | EE(Pr) R | 38 | 74/15.12.05/EE(Pr)R | M/s Naresh Kumar Garg | 24.12.05 | 15.03.06 | 338304 |  |  | Comp.
13 | Civil | 18.8.05 | 1.8.05 | C/o drain from Phirni road to Gyani Hs in village Nizam pur W.No-38 | 364300 | EE(Pr) R | 38 | 65/07.12.05/EE(Pr)R | M/s Naresh Kumar Garg | 09.12.05 | 11.02.06 | 282076 |  |  | Comp.
14 | Civil | 18.8.05 | 1.8.05 | Providing C.C from Jai Singh Hs to Baljet Hs in village Ladpur W.No-38. | 201522 | EE(Pr) R | 38 | 76/15.12.05/EE(Pr)R | M/s Raj Engineers & Builders | 15.12.05 | 13.03.06 | 201522 |  |  | Comp.
15 | Civil | 26.8.05 | 1.8.05 | Imp to Gali by providing brick pavement from Mahar Singh Hs to Ajit Singh Hs and from well to sh Tarif singh Advocate plot in village Khanjhawla in c-38(I)NZ | 331838 | EE ( N) | 38 | 313/20.01.06/EE-Narela | M/s Nishan Traders | 23.01.06 | 25.04.06 | 329708 |  |  | Comp.
16 | Civil | 26.8.05 | 1.8.05 | Imp of Gali pdg brick pavement and open surface drain from Bed Prakash to Jagbir Hs in village Khanjhawla C-38-I | 448444 | EE ( N) | 38 | 340/27.01.06/EE-Narela | M/s Satish Const.Co | 07.02.06 | 27.03.06 | 447899 |  |  | Comp.
17 | Civil | 26.8.05 | 1.8.05 | Imp of lane by providing C.C pavement and open Surface drain friam Rameshwar Hs to Balwan Hs in village Nizam pur in c-38 (I) | 419401 | EE ( N) | 38 | 328/23.01.06/EE-Narela | M/s Atul Gupta | 27.01.06 | 10.05.06 | 418857 |  |  | Comp.
18 | Civil | 26.8.05 | 1.8.05 | Imp of lane by providing C.C. pavement and open surface drain from Dilbagh Singh Hs to Hoshyar Hs in village Nizam pur C-38-I NZ | 99300 | EE ( N) | 38-I | 197/25.10.05/EE-Narela | M/s Khatri Const.Co. | 17.11.05 | 16.02.06 | 93515 |  |  | Comp.
19 | Civil | 26.8.05 | 1.8.05 | Imp to lane by providing c.c. pavement & o/s drain from Praham singh Hs to Dayanad Hs in village Nizam pur in C-38 NZ | 123850 | EE ( N) | 38
20 | Civil | 26.8.05 | 1.8.05 | Imp to lane by providing c.c. pav and O/s drain from MCD Pry School to BudhRam Hs and lane upto RamPhal Hs in Village Ladpur in C-38 NZ | 356200 | EE ( N) | 38 | 339/27.01.06/EE-Narela | M/s Satish Const.Co | 31.01.06 | 11.05.06 | 352676 |  |  | Comp.
21 | Civil | 26.8.05 | 1.8.05 | Imp of lane by providing brick pavement from Azad Hs to Bhagwan singh Plot and lane along PyreHs , Anil Hs and Prem Plot in village ladpur C-38 NZ | 390655 | EE ( N) | 38 | 315/20.01.06/EE(N) | M/s Jitender Gaur | 24.01.06 | 11.03.06 | 390286 |  |  | Comp.
22 | Civil | 26.8.05 | 1.8.05 | Imp of lanes by providing c.c pavement O/s drain from Bhoop Singh Hs to Darampal Hs and Ajit singh hs to Raghbir Singh Hs and lane upto Randhir Hs in village Ladpur C-38-I NZ | 296649 | EE ( N) | 38 | 316/20.01.06/EE-Narela | M/s Dev Const. Co | 24.01.06 | 30.03.06 | 292393 |  |  | Comp.
23 | Civil | 26.8.05 | 1.8.05 | Imp of lanes by providing c.c pavement O/s drain from Ram Chander Hs to Jagroop Hs in village Jaunti C-38-I NZ | 392600 | EE ( N) | 38 | 245/13.12.05/EE-Narela | M/s B.K.Builders | 11.01.06 | 29.03.06 | 378481 |  |  | Comp.
24 | Civil | 26.8.05 | 1.8.05 | Imp of lanes by providing c.c. pavement and open Surface drain from Satbir Hs to Dharmvir Hs and its link lane upto Chander Bhan Hs in village Jaunti in c-38-I NZ | 293579 | EE ( N) | 38 | 395/07.03.06/EE-Narela | M/s Gaj Raj Singh | 16.03.06 | 10.07.06 | 293273 |  |  | Comp.
25 | Civil | 26.8.05 | 1.8.05 | Imp of lanes by providing c.c. pave farom Roop chand Hs to Jagdish Hs and brick pav form umed Hs to Mulitab Hs in village Ladpur C-38 | 337201 | EE ( N) | 38 | 348/06.02.06/EE-Narela | M/s A.K Const.Co-II | 08.02.06 | 30.03.06 | 336491 |  |  | Comp.
26 | Civil | 2.9.05 | 25.8.05 | C/o drain from Om Parkash Hs to Chowk in village Nithari in C-38/Narela. | 313522 | EE(Pr.) Rural | 38 | 87/30.12.05/EE (Pr)R | M/s Joginder Saroha | 08.01.06 | 03.03.06 | 289186 |  |  | Comp.
27 | Civil | 2.9.05 | 25.8.05 | Imp of road by M/P from Chowk to opp M.C Pry School in village ithari in C-38/Narela | 314158 | EE(Pr.) Rural | 38 | 96/16.01.06/EE(Pr.)Rural | M/s Balwan Singh | 16.02.06 | 30.06.06 | 263970 |  |  | Comp.
28 | Civil | 2.9.05 | 25.8.05 | Pro C.C in lane of Meer Singh in village Lad pur in C-38/ Narela | 278741 | EE(Pr.) Rural | 38 | 72/15.12.05/EE(Pr)R | M/s Naresh Kumar Garg | 22.12.05 | 13.03.06 | 278418 |  |  | Comp.
29 | Civil | 2.9.05 | 25.8.05 | Pro C.C in lanes of Jile Singh, Ram Kishan , Kehar and Amar Singh in village Nizampur C-38/Narela | 271272 | EE(Pr) R | 38 | 93/02.01.06/EE(Pr)R | M/s Dev Const. Co | 2.01.06 | 17.03.06 | 270601 |  |  | Comp.
30 | Civil | 6.9.05 | 1.8.05 | Imp of lane by Prov C.C pavement from Naresh to sat Narayan Hs in village Harawali in C-37-II/Narela NZ | 199700 | EE(N) | 37-II | 200/25.10.05/ EE Narela | M/s Rakesh Kumar | 27.10.05 | 10.12.05 | 193319 |  |  | Comp.
31 | Civil | 6.9.05 | 1.8.05 | Pro C.C. pavement and drain from Sh. Dalel Singh Hs to Jat Ram Hs and Kekh Ram to Shishpal hs in village Sultanpur Dabas C-37-I/ Narela | 165800 | EE(N) | 37-II | 199/25.10.05/EE(N) | M/s Gobind Gupta | 08.11.05 | 02.01.06 | 160644 |  |  | Comp.
32 | Civil | 6.9.05 | 1.8.05 | Pdg C.C. pavement from Karan Singh to Bijender , Bal Kishan to Rajinder and Dayanand Mahavir wali gali in village Bajit Pur in C-37-I/Narela | 99200 | EE(N) | 37-II | 201/25.10.05/EE(N) | M/s Ankit Associates | 08.11.05 | 02.01.06 | 96155 |  |  | Comp.
33 | Civil | 6.9.05 | 1.8.05 | Imp of lane by providing c.c. pavement and O/s drain fraom Santra Sukhla Hs to Kuldeep Hs and Hari Singh to Ghanshyam Hs in village Karala in C-38-II/Narela | 84400 | EE(N) | 38 | 203/25.10.05/EE-Narela | M/s Bittu Const.Co | 12.12.05 | 24.01.06 | 81874 |  |  | Comp.
34 | Civil | 8.9.05 | 24.8.05 | Imp to lanes from Jagbir Singh Hs to Prem Singh Hs and Kishan Hs to Ram Kishan hs by providing M/P & drain in village Bawana in C-37/Narela | 459932 | EE(Pr) R | 37
35 | Civil | 8.9.05 | 1.8.05 | Imp to road surface by M/P and c.c along the walls of park an Mukhtyar Singh Marg in village Bawana C-37/Narela | 190537 | EE(Pr)-R | 37 | 83/26.12.05/EE(Pr.)R | M/s Vijender Bhardwaj | 04.01.06 | 07.07.06 | 171081 |  |  | Comp.
36 | Civil | 8.9.05 | 1.8.05 | Imp to Chowk at Punjabi pana ( Takia) by Kota stone flooring & drain in village Bawana in c-37/Narela | 140600 | EE(Pr)-R | 37 | 69/12.12.05/EE(Pr)R | M/s K.C.Builders | 13.12.05 | 14.02.06 | 86229 |  |  | Comp.
37 | Civil | 15.9.05 | 1.8.05 | Imp of lane by providing brick pavement and O/s drain from Jeet Ram Hs to Hari Singh Hs via park and lane from Mange Ram Hs to Daya Nand Hs in Vill. Karala C-38-II.Narela Zone | 388519 | EE/Narela | 38 | 322/20.01.06/EE-Narela | M/s Raj Associates | 24.01.06 | 20.03.06 | 387715 |  |  | Comp.
38 | Civil | 15.9.05 | 1.8.05 | Imp of gali by providing c.c. pave and open surface drain from Ganga Ram Hs to Niranjan Hs Via Raju Pehlwan in village Majri C-38-II/Narela | 608376 | EE/Narela | 38 | 345/06.02.06/EE-Narela | M/s Barawal Builders | 05.04.06 | 08.06.06 | 597541 |  |  | Comp.
39 | Civil | 15.9.05 | 1.8.05 | Imp of gali by Providing c.c. pavment from Jagdish (ASI) Hs to Karan Singh Hs in vill Karala in C-38-II/Narela | 354339 | EE/Narela | 38 | 335/23.01.06/EE-Narela | M/s Rajesh Dabas | 30.01.06 | 30.05.06 | 353590 |  |  | Comp.
40 | Civil | 15.9.05 | 1.8.05 | Imp of Gali by pdg c.c. pavement and o/s drain from Kishan Hs to Sansar Public School in village karala C-38-II NZ | 339882 | EE/Narela | 38 | 344/06.02.06/EE-Narela | M/s Ankur Associates | 08.02.06 | 03.06.06 | 338414 |  |  | Comp.
41 | Civil | 15.9.05 | 1.8.05 | Imp of gali by providing c.c. pav and open surface drain farom Ramesh Mathur Hs to Ajit Hs to village Karala C-38-II/Narela | 330444 | EE/Narela | 38 | 309/20.01.06/EE-Narela | M/s Ankit Associates | 15.02.06 | 29.03.06 | 330322 |  |  | Comp.
42 | Civil | 15.9.05 | 1.8.05 | Imp of lane by providing c.c. pave and o/s drain from Mehar Chand Khanna Hs to Azad Hs in village Karala C-38-II Narela | 346248 | EE/Narela | 38 | 319/20.01.06/EE(N) | M/s Mehboob Const.Co | 21.01.06 | 10.03.06 | 344749 |  |  | Comp.
43 | Civil | 21.11.05 | 24.8.05 | Imp of lane by prov brick flooring of Pardhan Balwan singh & ornamental lane of vill Darya pur in c-37/Narela | 84407 | EE/(Pr)Rural | 37 | 116/20.02.06/EE(Pr.)R | M/s Parvesh Const.Co | 27.02.06 | 01.06.06 | 84335 |  |  | Comp.
44 | Civil | 21.11.05 | 1.8.05 | Imp to lane from Gotu Hs to Mir Singh Hs by RMC in village Darya pur in C-37/Narela | 473000 | EE/(Pr)Rural | 37 | 125/11.03.06/EE(Pr)R | M/s Jai Kumar | 21.03.06 | 14.04.06 | 385907 |  |  | Comp.
45 | Civil | 21.11.05 | 1.8.05 | Imp to road by Providing M/P and RMC on Berms from Umesh kumar Sharma Hs to Khanjawala la Banwana road in Ishawar coloney , Bawna in C-37/Narela | 382207 | EE/(Pr)Rural | 37 | 21/27.06.06/EE (Pr)R | M/s Anil Kumar | 03.07.06 | 08.09.06 | 382175 |  |  | Comp.
46 | Civil | 21.11.05 | 1.8.05 | Imp to lane by RMC & drain fron Balbir Hs to Sheela Hs & Harigobind Hs in Iswarh Coloney Bawnana C-37/Narela | 430400 | EE/(Pr)Rural | 37 | 138/22.03.06/EE(Pr)R | M/s Bharadwaj Const.Co | 29.03.06 | 14.07.06 | 350440 |  |  | Comp.
47 | Civil | 21.11.05 | 1.8.05 | Imp to lane by RMC & drain front Chander Bhan Hs to chopal in village Bawana in C-37/Narela | 420200 | EE/(Pr)Rural | 37 | 127/11.03.06/EE(Pr)R | M/s Anil Kumar | 18.03.06 | 20.06.06 | 383593 |  |  | Comp.
48 | Civil | 21.11.05 | 1.8.05 | C/o drain from Dhani Ram Hs to Mohan hs in village Bawna in C-37/Narela | 259282 | EE/(Pr)Rural | 37
49 | Civil | 21.11.05 | 1.8.05 | Imp to road from Mahivdev Singh hs to Raj Singh hs and Ravider hs to Jaipal Hs in village Bawana C 37 NZ | 377093 | EE/(Pr)Rural | 37 | 111/14.02.06/EE(Pr)R | M/s Bajaj Const.Co | 15.02.06 | 23.06.06 | 376914 |  |  | Comp.
50 | Civil | 21.11.05 | 1.8.05 | C/o drain from Mahiinder Singh Hs to Raj Singh Hs and Ravinder Hs to Jaipul Hs in vill Bawana in C-37/Narela | 450906 | EE/(Pr)Rural | 37-I | 124/11.03.06/EE(Pr.)R | M/s Sudeh Kumar | 20.03.06 | 20.07.06 | 394752 |  |  | Comp.
51 | Civil | 21.11.05 | 2.9.05 | Pdg C.c. pavement and drain from Phool Singh hs to Singh Ram Hs and pl Chopal to Muni Ram and Jiya Ram wali gali in vil. Bawana in c-37-I/Narela | 191200 | EE/Narela | 37-I | 291/16.01.06/EE-Narela | M/s Sujit Kumar | 21.01.06 | 08.03.06 | 186042 |  |  | Comp.
52 | Civil | 21.11.05 | 16.9.05 | Pdg C.C.pavement from Sameer Singh hs to Chander Parkesh and Jagdish wali glai in vill Auchandir in C-37/Nareala | 132100 | EE/Narela | 37-I | 295/16.01.06/EE-Narela | M/s Jagdamba Trading Co. | 18.01.06 | 06.03.06 | 127870 |  |  | Comp.
53 | Civil | 21.11.05 | 16.9.05 | C/o O/s drain Transtermer to Sohatemor ( main road) in vill Qutab garh in C-37/Narela | 199600 | EE/Narela | 37-I | 296/16.01.06/EE-Narela | M/s Raj Associates | 25.01.06 | 14.02.06 | 193391 |  |  | Comp.
54 | Civil | 21.11.05 | 1.8.05 | Pro B/P from Khadark Singh Hs to Mahander singh , Gyanverden to Om parkash Hs and adj lane in vill Mengesh pur in C-37-II/Narela | 364672 | EE/Narela | 37-I | 391/02.03.06/EE-Narela | M/s Devinder Kumar | 06.03.06 | 22.05.06 | 364155 |  |  | Comp.
55 | Civil | 21.11.05 | 1.8.05 | Pdg C.C. pavement & drain from Om Parkash Hs to Suresh Hs in vill Qutab garh inC-37-II/Narela | 275192 | EE/Narela | 37-I | 325/23.01.06/EE(N) | M/s D & G Const.Co | 30.01.06 | 21.03.06 | 274737 |  |  | Comp.
56 | Civil | 21.11.05 | 1.8.05 | Imp to lane by pdg C.C, pavement farom Ganga Elect shop to Chandan, Lakhmi to Sureat, Jai Bhagwan to Tara Chan and Sureder to Ashok hs in vill Harwali in C-37-II/Narela | 193564 | EE/Narela | 37-I | 326/23.01.06/EE(N) | M/s D & G Const.Co | 30.01.06 | 21.03.06 | 193238 |  |  | Comp.
57 | Civil | 21.11.05 | 1.8.05 | Pdg M/P and drain from Mahavir Hand on main road to Om Parkash S/o Chander Singh Hs in vill Chand pur Kalan in C-37/Narela | 653361 | EE/Narela | 37-II | 409/08.03.06/EE-Narela | M/s Om Const.Co | 15.03.06 | 26.06.06 | 652710 |  |  | Comp.
58 | Civil | 21.11.05 | 1.8.05 | Pdg c.c. pavement and drian from Raghbir to Jasbir Hs via Jagdish , Mehender to Rattan, Ramphel to Raghunath Bhard waj and link gali in vill Pooth Khurd in C-37-/Narela | 497225 | EE/Narela | 37-II | 334/23.01.06/EE(N) | M/s Raj Associates | 30.01.06 | 23.03.06 | 496778 |  |  | Comp.
59 | Civil | 21.11.05 | 1.8.05 | Pdg c.c. pavement and drain farom Jai Karn Hs to Chattan Singh and main prem Pio road to Hawa Singh Balmikji Hs in village Sultanpur Dabas in C-37-/Narela | 324263 | EE/Narela | 37-II | 400/08.03.06/EE-Narela | M/s Deep Const.Co | 16.03.06 | 19.06.06 | 324124 |  |  | Comp.
60 | Civil | 21.11.05 | 1.8.05 | Pdg c.c. pavement and drain farom Rati Ram to Dayanand via Bhim Singh , Rambhaj to Nanhu ram Balmik , Pratap singh lane Ram pha to Balbir Singh Om Prakash lane in vill Pooth Khurd in C-37/Narela | 299086 | EE/Narela | 37-II | 406/08.03.06/EE_narela | M/s D & G Const.Co | 10.03.06 | 12.05.06 | 298846 |  |  | Comp.
61 | Civil | 21.11.05 | 1.8.05 | Pdg c.c pavement and drain from Bhoop Singh to Chander Bhan Hs and Surajmal to Hoshyar Singh Hs in vill Salahpur Majra in c-37/Narela | 190922 | EE/Narela | 37-II | 324/23.01.06/EE_narela | M/s D & G Const.Co | 03.02.06 | 04.04.06 | 190758 |  |  | Comp.
62 | Civil | 21.11.05 | 1.8.05 | C/o O/s drain from Ajit Singh Hs to Pt Ram Kumar Hs in village Slahpur Majra in C-37-I/Narela | 227050 | EE/Narela | 37-II | 407/08.03.06/EE-Narela | M/s D & G Const.Co | 13.03.06 | 14.06.06 | 226785 |  |  | Comp.
63 | Civil | 21.11.05 | 1.8.05 | Imp to lane by providing c.c.pavement from Rambir Hs to Rajender Hs in village Bajit pur in C-37/-I/Narela | 215340 | EE/Narela | 37-II | 405/08.03.06/EE-Narela | M/s D & G Const.Co | 17.03.06 | 14.08.06 | 214963 |  |  | Comp.
64 | Civil | 21.11.05 | 2.9.05 | Imp of drainge system from Khanjhwala Rd upto outfall drain in Village Bawana C-37 -I Narela | 391520 | EE/Narela | 37-I | 390/02.03.06/EE-Narela | M/s Devinder Kumar | 09.03.06 | 15.06.06 | 390986 |  |  | Comp.
65 | Civil | 23.11.05 | 3.10.05 | Pdg M/P from Pry school to Mubarakpur rd in village Kirari C 38 NZ | 586000 | EE(Pr)Rural | 38 | 144/27.03.06/EE(Pr)R | M/s Raj Engg.& Builders | 05.04.06 | 24.04.07 | 467172 |  |  | Comp.
66 | Civil | 23.11.05 | 3.10.05 | Const of Drain from Laxmi Shop to Culvert in villag Kirari in C 38NZ | 431343 | EE(Pr)Rural | 38 | 113/14.02.06/EE(Pr)R | M/s Rajesh Kumar | 16.02.06 | 27.03.06 | 402431 |  |  | Comp.
67 | Civil | 4.1.06 | 3.1.06 | Pdg RCC pipe culvert on main road of Nizampur in village Jounti in C 38 NZ | 89000 | EE(Pr)Rural | 38 | 117/20.02.06/EE(Pr)R | M/s Raj Engineers & Builders | 20.02.06 | 15.03.06 | 78332 |  |  | Comp.
68 | Civil | 9.1.06 | 1.8.05 | Imp of gali by pdg Brick Pavment from Kulveer singh Hs to Balwant hs in Village karala in C 38 NZ | 266500 | EE(Narela) | 38 | 453/31.03.06/EE-Narela | M/s Kaushik Enterprises | 05.04.06 | 19.05.06 | 195841 |  |  | Comp.
69 | Civil | 9.1.06 | 14.10.05 | Const of drain from Maha Rishi Daya Nand school to S.O.S. in village Bawana C 37 NZ | 593220 | EE(Pr)Rural | 37 | 14/15.05.06/EE (Pr)R | M/s Rajesh Kumar | 22.05.06 | 03.08.06 | 582840 |  |  | Comp.
70 | Civil | 9.1.06 | 14.10.05 | Const of drain from Rajiv Dabas tent Hs to Pole NO. 08/19/02/05 in village Majra Dabas C 37 NZ | 194560 | EE(Pr)Rural | 37 | 143/27.03.06/EE(Project)R | M/s Rajesh Kumar | 05.04.06 | 28.09.07 | 193810 |  |  | Comp.
71 | Civil | 16.1.06 | 13.1.06 | Imp to lane by RMC and drain from pandit Chaju Hs to Dada Bhaiya Chowk in village Bawana in C 37 NZ | 196800 | EE(Pr)Rural | 37 | 142/27.03.06/EE(Project)R | M/s Jai Kumar | 02.04.06 | 03.05.06 | 179565 |  |  | Comp.
72 | Civil | 16.1.06 | 13.1.06 | Const of Culvert on pjhirni rd of village Pooth Khurd from Shivan Propertioes to MCD Store (Pooth Khurd) C 37 NZ | 248634 | EE(Pr)Rural | 37 | 08/01.05.06/EE(Pr.)South | M/s Shyam Lal Gupta | 27.09.06 | 07.11.06 | 245472 |  |  | Comp.
73 | Civil | 22.2.06 | 8.2.06 | Pdg CC In berms on Tau Bihari Rd and cost of Drain near Crimation Ground in vIllage Lad Pur C 38, Narela | 522200 | EE(Pr)Rural | 38 | 07/01.05.06/EE (Pr) R | M/s Shyanti Lal Gupta | 08.05.06 | 08.08.06 | 381834 |  |  | Comp.
|  |  |  | Total | 22776460 | [6 empty] | 20676439

## AC-54
STATUS REPORT OF MLA FOR THE YEAR 2005-06
Municipal Corporation of Delhi
Narela Zone
|  | Name Of MLA |  | Sh. C.S. Kandera | AC-54 |  | year 2005-06 |  | Allocation | 200 |  |  | Dated:-
|  | Name of Constituency |  | Narela
|  | Ward Nos and Names |  | C-101 , Narela C-102 Alipur
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agency | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14
1 | Civil | 2.6.05 | 24.5.05 | Pro. C.C from Transformer to oriental Bank of Commerce in village Holambi Khurd C-102-I NZ | 155200 | Narela | 102-I | 118/16.6.05 | M/s D.& G Const co. | 22.6.05 | 11.8.05 | 150351 |  |  | Comp
2 | Civil | 2.6.05 | 24.5.05 | Pdg B/P and O/s drain from Sh. Ishwar Singh Hs to MED Singh Hs in Apni colony Alipur Garhi in C-102-I NZ | 186600 | Narela | 102-I | 119/16.6.05 | M/s Rakesh Kumar | 22.6.05 | 22.8.05\ | 180909 |  |  | Comp
3 | Civil | 2.6.05 | 24.5.05 | Pdg B/P and O/s drain from chandhary dilip singh Pardhan Hs in village Khera Khurd Garhi in C-102-I NZ | 282100 | Narela | 102-I | 214/25.2.05 | M/s Pushp Const CO. | 25.10.05 | P | 122665 |  |  | Inprog.
4 | Civil | 2.6.05 | 24.5.05 | Pdg B/P and drain form Poultry farm to Rajinder Hs and Kasturi Hs to Pyre lal hs in village Khera Khurd C-102 NZ | 308816 | Narela | 102-I | 185/07.10.05/EE-Narela | M/s Rajinder Singh Dahiya | 07.10.05 | P | 308541 |  |  | In Prog.
5 | Civil | 2.6.05 | 24.5.05 | Pdg B/P and drain from Prem Raj Hs to Silas Ekka Hs in village Khera Khurd in c-102-I NZ | 330800 | Narela | 102-I | 186/07.10.05/EE-Narela | M/s Rajinder Singh Dahiya | 15.10.05 | 12.01.06 | 247953 |  |  | Comp.
6 | Civil | 2.6.05 | 24.5.05 | Pdg B/P and drain from Michacl Minge to Amar Singh Hs and Silas Ekka to Sabertian House in Village Khera Kherd C-102-I NZ | 199400 | Narela | 102-I | 120/16.6.05 | M/s Vipin kumar Dagar | 24.6.05 | 22.8.05 | 193361 |  |  | Comp.
7 | Civil | 2.6.05 | 24.5.05 | Pdg C.C pavement around the temple streets in village Holambi Kalan in c-102-I NZ | 176900 | Narela | 102-I | 115/16.06.05/EE-Narela | M/s R.B.Traders | 25.07.05 | 12.12.05 | 171565 |  |  | Comp.
8 | Civil | 2.6.05 | 31.5.05 | Imp of road by PMP from Gas Agency office to police chowki in Metro vihar in c-102 NZ | 199200 | Narela | 102-I | 125/16.6.05/Narela | M/s Trimurti trading Co. | 23.6.05 | 15.10.05 | 193288 |  |  | Comp
9 | Civil | 2.6.05 | 24.5.05 | Pdg M/P and drain from Pt Shiv Raj Shastri to Sh Nanak Hs in village Khera Khurd in C-102 NZ | 591900 | Narela | 102-I | 212/25.10.05/EE-Narela | M/s Pushp Const CO. | 25.10.05 | P | 397857 |  |  | In Prog.
10 | Civil | 2.6.05 | 24.5.05 | PMP and drain foarm Pratap Singh Hs to Mahepal Hs and Balmiki chowpal to OM parakash hs in village Naya Bans in c-102-I NZ | 233116 | Narela | 102-I | 188/11.10.05/EE Narela | M/s Rakesh Kumar | 11.10.05 | 7.1.06 | 232842 |  |  | Comp
11 | Civil | 8.6.05 | 20.5.05 | Providing B/P and drain from Nani Singh Hs to Chander Hs Dharam Singh and Same Singh in village Sunger pur C-102 NZ | 542526 | Narela | 102-I | 190/11.10.05/EE Narela | M/s Jagdamba Trading CO. | 11.10.05 | 9.1.06 | 540633 |  |  | Comp
12 | Civil | 8.6.05 | 20.5.05 | Pdg C.C pav and drain from OM Parkash Hs Mandir to Zile Singh Hs in village Singhu in c-102 NZ | 327553 | Narela | 102-I | 229/21.11.05/EE Narela | M/s Sahil Builiders | 21.11.05 | 12.1.06 | 327494 |  |  | Comp
13 | Civil | 8.6.05 | 20.5.05 | Providing B/P and drain from Anil Hs Ram Singh Hs and and Upto Charan singh Hs in village Sunger pur C-102 NZ | 284163 | Narela | 102-I | 213/25.10.05/EE(N) | M/s Pushp Const CO. | 25.10.05 | 15.02.06 | 284118 |  |  | Comp
14 | Civil | 8.6.05 | 20.5.05 | Pdg C.C in the lanes from Het Ram Hs to towards Attar Singh Hs in village Tiggipur C-102 -IINZ | 262867 | Narela | 102-I | 215/8.11.05/EE Narela | M/s Gupta Const co.-II | 8.11.05 | 1.2.06 | 262353 |  |  | comp
15 | Civil | 8.6.05 | 20.5.05 | Pdg C.C pav and drain from Madan Hs towards Rattan Hs and upto Dulichud Hs and adjoing lanes in village Bakoli in c-102-IINZ | 260004 | Narela | 102-I | 191/13.10.05/Narela | M/s Deep Const co. | 13.10.05 | 17.12.05 | 260004 |  |  | comp
16 | Civil | 8.6.05 | 20.5.05 | Pdg C.C in the lames fsorm Darshan singh to Reedy Singh Uttam Singh to Joginder and side lanes of Balbir Hs in village Jhingola C-102-IINZ | 258595 | Narela | 102-I | 217/8.11.05/Narela | M/s Gupta Const co.-II | 8.11.05 | 18.1.06 | 257794 |  |  | comp
17 | Civil | 8.6.05 | 20.5.05 | Raising of lanes by C.C from M.C. School upto Bishme Hs and Adjoing lanes in vilage Jhirgola C-102/II NZ | 479955 | Narela | 102-I | 303/.20.01.06/EE-Narela | M/s Deep Const co. | 20.03.06 | 29.03.06 | 479260 |  |  | Comp,
18 | Civil | 8.6.05 | 20.5.05 | Raising of lane by C.C. from Balwant Hs to wards Ram Niwas Hs and adjoing lanes in village Palla in c-102-II NZ | 363878 | Narela | 102-I | 189/11.10.05/EE-Narela | M/s S.S.Engg. | 11.10.05 | 31.01.06 | 362620 |  |  | Comp.
19 | Civil | 8.6.05 | 3.6.05 | Imp of lane by providing brick pavement and c/o O/s drain faorm Ramesh Hs to Balmiki Chopal in Landless colony Singhu in c-102 NZ | 409500 | EE(Pr.)R | 102 | 59/07.12.05/EE(Pr)R | M/s Jagdamba Trading CO. | 14.12.05 | 06.02.06 | 315315 |  |  | Comp.
20 | Civil | 8.6.05 | 3.6.05 | C/o O/s drain from Munder to Kartar Singh Hs upto Transfermer in Landless Colony Singhu in c-102 NZ | 792200 | EE(Pr.)R | 102 | 18/31.05.06/EE(Pr.)R | M/s Puneet Const.Co | 31.05.06 | 17.07.06 | 599424 |  |  | Comp.
21 | Civil | 8.6.05 | 3.6.05 | Imp of lane of Providing B/Promt and c/o O/s drain form Jagbir Hs to M.C Pry School in landless coloney Singhu c-102 NZ | 162500 | EE(Pr.)R | 102 | 123/11.03.06/EE(Pr.)R | M/s Dev Const.Co. | 11.03.06 | 09.06.06 | 122551 |  |  | Comp.
22 | Civil | 10.6.05 | 9.6.06 | Imp of lane by providing CC Pavment from Coner of park to H. no. 93 in Punjaby Coloney in c-101 NZ | 198070 | Narela | 101-II | 236/13.12.05/Narela | M/s Sahil Builiders | 20.12.05 | 16.1.06 | 139378 |  |  | Comp
23 | Civil | 10.6.05 | 9.6.05 | Imp of lane by providing C.C pav and O/s drain from Pandit Jai Kishan Hs to Shyam Singh Hs near Phirni in village Sanooth in c-101 NZ | 371100 | Narela | 101-II | 237/13.12.05/EE-Narela | M/s Sahil Builiders | 16.12.05 | 24.02.06 | 272665 |  |  | Comp
24 | Civil | 10.6.05 | 9.6.05 | Imp of lane by pdg C.C pav from Phirni road to shri Kishan Hs and lane along Zile Singh Hs and Ashok Hs in viilage Ghoga in c-101 NZ | 301700 | Narela | 101-II | 218/08.11.05/EE(N) | M/s Gupta Const co.-II | 21.11.05 | 14.02.06 | 217766 |  |  | Comp
25 | Civil | 5.7.05 | 24.5.05 | C/o road by PMP premixing from Kishan S/o Maxmi chand Hs to Anil Bariwala ( on Phirni road) in Alipur C-102 NZ | 470746 | Narela | 101-II | 238/03.12.05/EE(N) | M/s Rakesh Kumar | 22.12.05 | 03.03.06 | 470746 |  |  | Comp
26 | Civil | 7.7.05 | 24.5.05 | Pdg M/P and drain from Prem Singh Hs to Nandu Hs in village Khera Khurd in C-102 NZ | 258051 | Narela | 101-II | 216/08.11.05/EE-Narela | M/s Gupta Const co.-II | 08.11.05 | 15.02.06 | 257142 |  |  | Comp
27 | Civil | 11.7.05 | 1.7.05 | Imp of road by M/P from Sannoth drain to Mill on Holambi Kalan Sannoth road in C-102 -II NZ | 199200 | Narela | 101-II | 155/26.07.05/EE-Narela | M/s Suresh Bros. | 04.08.05 | 24.02.06 | 191770 |  |  | Comp
28 | Civil | 4.10.05 | 20.5.05 | Pdg C.C. Pav.& drain from Sr. Sec School towards Om Shanti Near Chopal & adj. Lanes in vill Bakatawarpur in C-102/II , Narela Zone. | 509781 | Narela | 102-II | 377/21.02.06/EE-Narela | M/s Om Const.Co. | 21.02.06 | 30.03.06 | 509781 |  |  | Comp
29 | Civil | 4.10.05 | 2.8.05 | Providing C.C. pave & drain from Radhey Hs to Rajpal Via Inder Singh Hs in vill Tajpur in C-102/-II N.Z | 199800 | Narela | 102-II | 292/16.01.06/EE-Narela | M/s Prem Brothers | 16.01.06 | 20.04.06 | 193640 |  |  | Comp.
30 | Civil | 4.10.05 | 2.8.05 | Providing C.C. pave & drain from Pala Ram to Jai Bhagwan , Ram Gopal to Ram Sharan & Balber to Sukh Lal Hs in Vill Tajpur in C-102-II NZ | 218551 | Narela | 102-II | 404/08.03.06/EE-Narela | M/s D.& G Const co. | 08.03.06 | 01.05.06 | 218551 |  |  | Comp.
31 | Civil | 7.11.05 | 7.11.05 | C/o drain from Phirni to Jai Bhagwan fectory and Satpal Hs in vill Sanoth in C-101-II N.Z | 140500 | Narela | 102-II | 305/20.01.06/EE-Narela | M/s Popular Enterprises | 23.01.06 | 16.02.06 | 104851 |  |  | Comp.
32 | Civil | 7.11.05 | 7.11.05 | C/o Culvert near Transfermar and M.c School in vill Sanoth in C-102-II/N.Z | 181914 | Narela | 102-II | 31/01.06.06/EE-Narela | M/s Ankit Associates | 09.06.06 | 31.07.06 | 180468 |  |  | Comp.
33 | Civil | 7.11.05 | 7.11.05 | Imp of road by providing M/P from Bawana road to Sanoth vill in C-102-II/NZ | 419000 | Narela | 102-II | 327/23.01.06/EE-Narela | M/s Popular Enterprises | 24.1.06 | 24.02.06 | 305527 |  |  | Comp.
34 | Civil | 7.11.05 | 7.11.05 | C/o Culvert in Pujabi coloney in C-102-II/NZ | 302900 | Narela | 102-II | 386/27.02.06/EE(N) | M/s Shanker Const.Co. | 20.02.06 | P | 244211 |  |  | In Prog.
35 | Civil | 8.11.05 | 7.11.05 | Pdg C.C. from Prem Singh Hs Towards Phool Singh hs in vill. Hiranki in C-102/NZ | 281263 | Narela | 102-II | 331/23.01.06/EE-Nareal | M/s Govind Gupta | 23.01.06 | 22.03.06 | 281262 |  |  | Comp.
36 | Civil | 8.11.05 | 7.11.05 | Pdg C.C pavement & drain from Dharam pal Hs to Thanu Hs Via Jagdish Hs in vill Tajpur in C-102-II/N.Z | 596400 | Narela | 102-II | 384/21.02.06/EE-Narela | M/s Raj Associates | 21.02.06 | 30.03.06 | 432172 |  |  | Comp.
37 | Civil | 10.11.05 | 7.11.05 | C/o drain from Jas Ram Sweets Corner to Sant Gaganeshwar Public school in Vill Khampur in C-102-II/N.Z | 191800 | Narela | 102-I | 293/16.01.06/EE-Narela | M/s Atul Gupta | 16.01.06 | 21.03.06 | 185600 |  |  | Comp.
38 | Civil | 10.11.05 | 7.11.05 | Pdg C.C and drain from Sukhbir Hs to Rai Singh Hs in vill Khera Kalan in C-102-II?N.Z | 161100 | Narela | 102-I | 294/16.01.06/EE(N) | M/s Om Const.Co. | 16.01.06 | 18.02.06 | 154595 |  |  | Comp.
39 | Elect | 22.11.05 | 27.9.05 | P/o Semi High Mast light at shah pur garhi near park Chauraha w.no. 102 Narela | 150576 | EEE-II | 102 | 251/24.03.06/EE(E)-II | M/s Bansal Electrci Store | 02.04.06 | 25.05.06 | 120275 |  |  | Comp.
40 | Civil | 23.11.05 | 7.11.05 | Pdg RMC and Drain from Vijay pal hs to Sukhbir hs on Prhnir rd in village khera kalan in C102 I Nz | 454223 | Narela | 102-I | 387/27.02.06/EE-Narela | M/s Khatri Const.Co | 27.02.06 | 30.05.06 | 454223 |  |  | Comp.
41 | Civil | 23.11.05 | 7.11.05 | Imp of Drian from Kanwar singh hs to China Ram Hs in village khera Kalan C 102 I NZ | 280800 | Narela | 102-I | 90/06.09.06/EE-Narela | M/s Raj Associates | 06.09.06 | 15.11.06 | 212254 |  |  | Comp.
42 | Civil | 23.11.05 | 7.11.05 | Pdg CC and drain from Ravi to Kali Ram via Banwari Hs and side lanes in village Bakhtawar pur C 102 II NZ | 455961 | Narela | 102-II | 425/16.03.06/EE-Narela | M/s Mehboob Const.Co | 16.03.06 | 20.05.06 | 455961 |  |  | Comp.
43 | Civil | 23.11.05 | 7.11.05 | Pdg M/P along MC School in village Jind pur C 102 I NZ | 230500 | Narela | 102-I | 50/05.07.06/EE(Narela) | M/s Ajay Assos. | 14.07.06 | P | 175330 |  |  | In Prog.
44 | Civil | 23.11.05 | 7.11.05 | Pdg M/P on Bakoli - Hamid pur road in C 102 II NZ (Link Road) | 485855 | Narela | 102-II | 433/16.03.06/EE-Narela | M/s Dev Const.Co. | 16.03.06 | 26.06.06 | 485548 |  |  | Comp.
45 | Civil | 23.11.05 | 7.11.05 | Imp of lane by pdg Dry Brick Flooring and O/S drain from Yamin Hs to Rajbir HS and its parallel lanes in Punjabi Cly in c 101 II NZ | 536300 | Narela | 101-II | 411/08.03.06/EE-Narela | M/s Shanker Const.Co. | 10.03.06 | 29.03.06 | 405048 |  |  | Comp.
46 | Civil | 5.12.05 | 7.11.05 | Imp of lane (small lanes) by pdg CC Pav in Bagri Mohalla in Panna Udyhan in Narela in C 101 -I, NZ | 290000 | Narela | 101-I | 415/08.03.06/EE-Narela | M/s Ankit Associates | 18.03.06 | 28.04.06 | 202956 |  |  | Comp.
47 | Civil | 7.12.05 | 7.11.05 | Pdg CC and brick pavment and drain from Mukesh saini to Horam and Vijay to Mahender Hs in village Bakoli C 102-II, NZ | 464680 | Narela | 102-II | 436/22.03.06/EE-Narela | M/s Om Const.Co. | 22.03.06 | 20.06.06 | 463622 |  |  | Comp.
48 | Civil | 8.12.05 | 7.11.05 | Const of rd by pdg M/P from GT road to Anil Factory on phirni rd in viillage Alipur in C 102-I,NZ | 1052332 | Narela | 102-I | 192/16.11.06/EE-Narela | M/s Bajaj Const.Co | 16.11.06 | 20.02.07 | 1052100 |  |  | Comp.
49 | Civil | 14.12.05 | 7.11.05 | C/o Phirni rd by M/P from Meer Singh Hs to Mahender Hs in village Jindpur in C 102-I, NZ | 989600 | Narela | 102-I | 22/10.05.06/EE-Narela | M/s Khatri Const.Co | 10.05.06 | 13.09.06 | 846927 |  |  | Comp.
50 | Civil | 16.12.05 | 7.11.05 | Pdg M/P on Phrni rd from Jai Parkash HS to Community Centre in village Akbar Pur Majra in C 102-II, NZ | 598200 | Narela | 102-II | 398/07.03.06/EE-Narela | M/s Dev Const.Co. | 07.08.06 | 17.10.06 | 479393 |  |  | Comp.
51 | Civil | 27.12.05 | 7.11.05 | Pdg CC and drain from Puran Jogi to Ashok via Devender and along shiv mandir in village Bakhtawar Pur in C 102-II, NZ | 429580 | Narela | 102-II | 435/22.03.06/EE-Narela | M/s D & G Const.Co | 22.03.06 | 20.06.06 | 428095 |  |  | Comp.
52 | Elect | 6.1.06 | 24.10.05 | P/OI Semi High Mast light at Holambi Kalan (Near Bus stand) w.no. 102, Narela Zone | 148491 | EEE-II | 102 | 64/05.07.06/EE(E)-II | M/s Master Electric Store | 14.07.06 | 12.08..06 | 138401 |  |  | Comp.
53 | Civil | 6.1.06 | 2.1.06 | Imp to lane by pdg CC pav from Safia Bad turn to Raghunath Mandir in Pana Udyan w.no. 101-I, NZ | 485012 | Narela | 101-I | 452/31.03.06/EE-Narela | M/s P.K Const.Co | 03.04.06 | 06.07.06 | 376263 |  |  | Comp.
54 | Civil | 17.03.06 | 20.01.06 | Imp of lane by Pdg. CC Pav & O/s Drain from Gopi Chand House to Rajinder House in G-Block Punjabi Colony C-101-II/ Narela | 196200 | Narela | 101-II | 439/30.04.06/EE-Narela | M/s Gaj Raj Singh | 05.05.06 | 16.06.06 | 195850 |  |  | Comp.
|  |  |  | Total | 19057959 | [6 empty] | 16863269