## 37-
STATUS REPORT OF MLA FOR THE YEAR 2005-06
Municipal Corporation of Delhi
Shahdra South
|  | Name Of MLA |  | Sh. Braham Pal Singh | AC-37 |  | year 2005-06 |  | Allocation | 100
|  | Name of Constituency |  | Tirlok Puri
|  | Ward Nos and Names |  | 67Trilok Puri, 68 Dallupura
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Div. | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Civil | 20.7.05 | 1.6.05 | Imp of foot path and road side berms on Khudi ram Bose Marg by pdg c.c. pav. From Chilla Chowk to Pdt.-II Gate Mayur Vihar PH-I in Ac-37/67 | 328362 | XXX | 67 | 88/08.11.05/EE-XXX | M/s P.K Builder | 22.11.05 | 31.01.06 | 327326 | Comp.
2 | Elect | 9.8.05 | 5.8.05 | P/o boring with submersible pump set in Mayur vihar Ph-1 Pkt-III Pkt-v Green belt near Raghunath mandir and T.P block-4 Mpl park under Sh.S Zone | 408908 | EE(E)-V | 67 | 221/20.02.06/EE(E)-V | M/s HL-Tech Electriclas | 21.02.06 | 17.03.06 | 344523 | Comp.
3 | Elect | 9.8.05 | 31.7.05 | P/o boring with submersible pump set in T.P. block 30 entra middle park Chilla Chowlk park Mayur vihar Ph-1 Pkt-2.&DDA flat Chilla under Sh.S Zone | 407946 | EE(E)-V | 67 | 126/03.01.06/EE(E)-V | M/s Khana Sales Corporation | 04.01.06 | 09.02.06 | 325720 | Comp.
4 | Elect | 9.8.05 | 28.7.05 | P/o boring with sumbersible pump set in T.P block 2,7, and 10 mpl park under Sh.S Z. | 407946 | EE(E)-V | 68 | 132/04.01.06/EE(E)-V | M/s ACE Engineers Bureau | 06.01.06 | 10.02.06 | 335302 | Comp.
5 | Elect | 9.8.05 | 26.7.05 | P/o boring with submersible pump set in T.P vlock 3,16 and Mahila park under Sh. S Zone | 409870 | EE(E)-V | 68 | 186/20.01.06/EE(E)-V | M/s Repair Shop | 21.01.06 | 18.02.06 | 355078 | Comp.
6 | Elect | 9.8.05 | 4.8.05 | P/o boring with submerssible pump set in T.P block 22,27, and 30 extra Mpl park under Sh. S Zone | 408465 | EE(E)-V | 67 | 130/04.01.06/EE(E)V | M/s Vinaya Kam Enginers & Traders. | 05.01.06 | 11.02.06 | 338237 | Comp.
7 | Elect | 25.8.05 | 30.7.05 | P/o boring with submerisble pump set at mpl park in Mayur vihar ph-I pkt-III opp H.No 411,441 and 359 under sh.S Zone | 407946 | EE(E)-V | 67 | 205/10.02.06/EE(E)-V | M/s M.J Electricals & Electronics | 17.02.06 | 25.05.06 | 333787 | Comp.
8 | Civil | 30.8.05 | 20.7.05 | Imp of lane by pdg c.c pav from 19 B to Mazar near H.No 181 and const of drain from H.NO 19 B to B-9 in kotla vill | 265700 | XXX | 67 | 109/14.12.05/EE-XXX | M/s Bansal Brothers | 23.12.05 | 30.06.06 | 265700 | Comp.
9 | Civil | 30.8.05 | 20.7.05 | Const of drain opp H.NO 381/80 near Chilla village in W.no-67/37 Sh.S | 376247 | XXX | 67 | 158/06.02.06/EE-XXX | M/s Sharma & Sharma Const.Co | 15.02.06 | 17.06.06 | 376247 | Comp.
10 | Civil | 30.8.05 | 15.6.05 | Imp of stg of road by dense carpeting from block no 25/481, to 13/30 24/280 to 24/231 21/481 20/30 ,20/280 to 20/231 and 19/481 to 19/30 in W.No 67/37 Trilok puri Sh.S | 1724469 | XXX | 67 | 26/03.05.06/EE-XXX | M/s Vinod Kumar | 12.10.07 | P | 2819133
11 | Civil | 30.8.05 | 17.6.05 | Imp /stg of road by pdg dense Carpeting from block no 31 to 36 (Wireless) road in w.no 67/37 Trilok puri Sh.S | 1846603 | XXX | 68
12 | Civil | 2.9.05 | 17.5.05 | Imp of lane by pdg drainage system from H.No. 480 to 461 31 to 60,61 to small park 110 to small park 125 to 111,126 to 140 160 to 141 161 to 180 181 to Small park 210 to small park 230 to 211,230 410 to 391 , 411 430 431 to Small park 460 to small park 280 to 251 281 to 310 and 311 to small park in block in 5 trilok puri W.no 68 Sh.S Zone | 1640641 | XXX | 68 | 25/01.05.06/EE-XXX | M/s Vijay Const.Co | 12.05.06 | 01.09.06 | 1640641 | Comp.
13 | Civil | 08.03.06 | 17.06.05 | Imp of lanes by pdg. C.c pcv ment from Dheer Singh house to Hardas Singh house along Gyan house and limks in Village Dallu pure in W.no 68 Sh.S zone | 415130 | XXX | 68 | 47/23.08.06/EE-XXX | M/s Pooja Enterprises | 31.08.06 | 18.01.07 | 414720 | Comp.
14 | Civil | 08.03.06 | 15.09.05 | Imp of lanes pdg drianges sysytems from H.NO. 15 to 286, 16 to 285, 45 to 261, 46 to small park, 70 to 241, 240 to 231, 71 to 80, 70 to 81, 230 to 221, 211 to 250, 100 to 61, 91 to 220, 115 to small park 116 to small park, 145 to 176, 146 to 175 in Block 9 in Trilokpuri W.NO 68 Sh.S zone | 1521802 | XXX | 68 | 74/27.09.06/EE-XXX | M/s Satish Budhiraja | 03.10.06 | 06.12.06 | 1506575 | Comp.
15 | Civil | 08.03.06 | 15.09.05 | Imp of lanes by pdg. Drainrgs system from H.NO 1 to 30,31 to 60,61 to small park , 110 to small park, 125 to small park, 126 to small park, 141 to 160, 161 to 180, 181 to small park, 210 to small park, 211 to 230, 231 to small park, 360 to small park 375 to small park, 411 to 430, 431 to small park, 460 to small park, 461 to 480 & 481to 500 in H.NO. 18 Trilok puri W.no. 68 Sh.S zone | 1265144 | XXX | 68 | 76/11.10.06/EE-XXX | M/s Satish Budhiraja | 23.10.06 | 08.12.06 | 1259413 | Comp.
16 |  |  |  | Calcelled
17 | Civil | 08.03.06 | 20.06.05 | Imp /stg of road by pdg dense Carpeting from block no26/30 to 36/481, 27/231 to 35/280, 28/30 to 34/473, 29/231 to 33/281, 33/481 to Sulabh Sauchalya, 30/231 to 32/281 and 30/30 to 32/28 in W.no 67/37 Sh.S zone | 3758900 | XXX | 67 | 89/01.10.07/EE-XXX | M/s Asian Resurfacing of road rpad ageny pvt. Ltd. | 24.04.08 | 05.05.08 | 3758900 | Comp.
|  |  |  | Total | 15594079 | [6 empty] | 14401302

## 38-
STATUS REPORT OF MLA FOR THE YEAR 2005-06
Municipal Corporation of Delhi
Shahdra South
|  | Name Of MLA |  | Sh. Amrish Gautam | AC-38 |  | year 2005-06 |  | Allocation |  | 100 |  | Dated:-
|  | Name of Constituency |  | Patparganj
|  | Ward Nos and Names |  | 69,Mayur Vihar 70 Kondli
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Civil | 19.9.05 | 16.8.05 | Imp of lane Opp H.No 144 in Patpar Ganj Vill AC-38/69 ( by C.C) |  | XXX | 69 | Work cancled as per MLA concent letter dared 21.05.06 & order by C E-II dated 15.06.06
2 | Civil | 19.9.05 | 16.8.05 | Imp of lane by pdg c.c. near H.No 245 & 317 in pocket E. Mayur Vihar Ph-II AC38/69 Sh.S | 457334 | XXX | 69 | 164/02.03.06/EE-XXX | M/s H.L Puri & Sons. | 10.03.06 | p | 368718 |  |  | In Prog.
3 | Civil | 19.9.05 | 16.8.05 | Imp of lane by pdg c.c. & drain near H.No 241 & opp Kabristan in patpar Ganj Vill in AC-38/69 Sh.S | 227871 | XXX | 69 | 178/10.03.06/EE-XXX | M/s Satish Budhiraji | 17.03.06 | 29.05.06 | 210331 |  |  | Comp.
4 | Civil | 19.9.05 | 12.8.05 | Imp of drain from H.NO 379 to 544 in vill Gharoli W-70 A | 474177 | XXX | 70 | 171/10.03.06/EE-XXX | M/s Vijay Const.Co | 31.03.06 | 07.06.06 | 471108 |  |  | Comp.
5 | Civil | 19.9.05 | 12.8.05 | Const of B/wall in block w no-2 near Bus Stand & Imp of green belt in front of mkt of block W no-3 in Khichripur R/ C W-70 Sh.S | 314359 | XXX | 70 | 161/17.02.06/XXX | M/s Satish Budhiraji | 24.02.06 | 26.05.06 | 314359 |  |  | Comp.
6 | Civil | 19.9.05 | 12.8.05 | Imp of lane by pdg c.c. pav in Mkt. Of block no 3 & 5 and pdg M.S crossing in block no 345 in Khichripur R/C W-70 B Sh.S | 453397 | XXX | 70 | 203/21.03.06/EE-XXX | M/s Satish Bhudhiraji | 31.03.06 | 28.06.06 | 453397 |  |  | Comp.
7 | Civil | 19.9.05 | 12.8.05 | Imp of park near H.NO 14/110 and 14/141 in block no 14 and near H.NO 12/181 in block no 12 in Kalyanpuri W-70 Sh.S | 531505 | XXX | 70 | 156/06.02.06/XXX | M/s Satish Budhiraja | 24.12.06 | 07.04.06 | 531505 |  |  | Comp.
8 | Civil | 19.9.05 | 12.8.05 | Imp of lane by pdg c.c. pav in market of block no 9 and from mother dairy to maindir along khichripur road in block no 9 r/c Kichripur W-70 Sh.S | 249955 | XXX | 70 | 170/10.03.06/EE-XXX | M/s Vijay Const.Co | 01.04.06 | 06.06.06 | 249955 |  |  | Comp.
9 | Civil | 19.9.05 | 16.8.05 | Imp of drainage system of Patparganj road infront of E block pandav nagr in AC-38/69 in Sh.S | 495847 | XXX | 70 | 30/15.06.06/EE-XXX | M/s Darshan Singh Gujral | 24.06.06 | 10.01.07 | 472061 |  |  | Comp.
10 | Civil | 23.9.05 | 12.8.05 | Const of walkway from H.NO B-514 to 1362 in central park of Gharoli Dairy from in 70 A Sh.S | 977107 | XXX | 70 | 17/21.04.06/EE-XXX | M/s Narendra Const. | 30.04.06 | 27.07.06 | 967095 |  |  | Comp.
11 | Civil | 23.9.05 | 16.8.05 | Imp of drain from chilla Chwok to kukreja Nirsing home in Acharya Niketan in AC-38/69 Sh.S | 1257253 | XXX | 70 | 199/21.03.06/EE-XXX | M/s Narendra Const. | 30.03.06 | 17.07.06 | 1252707 |  |  | Comp.
12 | Civil | 23.9.05 | 16.8.05 | Imp of outfall drain in pocket D Mayur vihar Ph-II in AC-38/69 Sh.S | 1088888 | XXX | 70 | 19/21.04.06/EE-XXX | M/s Vijay Const.Co | 12.05.06 | P | 1081160 |  |  | In Prog.
13 | Civil | 30.9.05 | 12.8.05 | Imp of drain from state Bank of patialx to Laxmi Tent hs in Kondli ( R) vill w.no 70 A | 781651 | XXX | 70 | 200/21.03.06/EE-XXX | M/s Narendra Const. | 31.03.06 | 28.06.06 | 781490 |  |  | Comp.
14 | Civil | 09.03.06 | 04.12.05 | Imp of drain from Transfarmer to X-ing of Gheroli Vill (LHS) Ac-38/70A | 335655 | XXX | 70A | 46/23.08.06/EE-XXX | M/s Puri Builders & Associates | 17.04.07 | 11.06.07 | 305655 |  |  | In Prog.
15 | Civil | 14.03.06 | 09.12.05 | Imp of side berms of road by pdg cc from Jeewan Anmol Hospital to Qubristan in Ac-38/69 | 395739 | XXX | 69 | 40/23.08.06/EE-XXX | M/s Ram Gopal Sharma | 20.01.07 | 30.03.07 | 395739 |  |  | Comp.
16 | Civil | 14.03.06 | 09.12.05 | Imp of lanes by pdg. Cc near community hall at Kichripur village in Ac-38/69 | 260980 | XXX | 69 | 42/23.08.06/EE-XXX | M/s Puri Builders & Associates | 01.09.06 | 05.11.06 | 260980 |  |  | Comp.
17 | Civil | 14.03.06 | 09.12.05 | Imp of lanes by pdg. C.C.A arain opp. MC by School and it linkes in village Khichripur Ac 38/69 | 449170 | XXX | 69 | 41/23.08.06/EE-XXX | M/s Puri Builders & Associates | 26.12.06 | 12.06.07 | 449169 |  |  | Comp.
18 | Civil | 14.03.06 | 09.12.05 | Imp of culvert opp. DDA Market in Mayur Vihar Ph-II Ac-38/69 | 233958 | XXX | 69 | 43/23.08.06/EE-XXX | M/s Puri Builders & Associates | 22.11.06 | 17.05.07 | 233958 |  |  | Comp.
19 | Civil | 14.03.06 | 09.12.05 | Imp of culvert near Radha Swami satrang Bhawan Mayur vihar Ph-II Ac-38/69 | 182605 | XXX | 69 | 51/23.08.06/EE-XXX | M/s Raj pal Bharti | 10.01.07 | 28.01.08 | 167065 |  |  | Comp.
20 | Civil | 14.03.06 | 09.12.05 | Imp of lane near Sulabh Sauchalya by pdg cc and drain in Village Khichripur Ac-38/69 | 296943 | XXX | 69 | 44/23.08.06/EE-XXX | M/s Puri Builders & Associates | 30.09.06 | 26.12.06 | 296943 |  |  | Comp.
21 | Civil | 14.03.06 | 09.12.05 | Imp of road by pdg M/P CC and drain from D-40 to c-2 in Acharya Niketen Ac-38/69 | 386893 | XXX | 69 | 45/23.08.06/EE-XXX | M/s Puri Builders & Associates | 13.03.07 | P | 376893 |  |  | In Prog.
22 | Civil | 23.03.06 | 04.12.05 | Imp of lanes by pdg. CCA drain from H.NO B-627 to B634, 490 to 491 1257 to 1262 A-25 to park 1255 to 1258 B-137 to 144 in Gheroli Dairy Farm Ac-38/70 A Sh(S) zone | 719531 | XXX | 70 | 73/27.09.06/EE-XXX | M/s Narendra Const. | 07.10.06 | 31.01.07 | 719531 |  |  | Comp.
23 | Civil | 23.03.06 | 04.12.05 | Imp of side berms by pdg cc Adrash from H.No A-698 to A-1312 Gheroli Dairy Farm in Mayur Vihar Ph-III W.no 70A SH.(S) zone | 682810 | XXX | 70 | 67/21.09.06/EE-XXX | M/s Sanjay Builders | 11.10.06 | 19.01.07 | 682810 |  |  | Comp.
24 | Civil | 23.03.06 | 04.12.05 | Imp of lanes by pdg CC and drain from National Harward School to Kishan Sharma house, Mahesh house to Ajju house in Pandit Mohalla and Ram Chetter house to Devi Ram house in Kondli Village in Ac-38/70 A Sh(S) zone | 626332 | XXX | 70 | 102/17.11.06/EE-XXX | M/s Narendra Const. | 27.11.06 | 31.01.07 | 626332 |  |  | Comp.
25 | Civil | 23.03.06 | 04.12.05 | Imp of open surface by pdg CCA drain near H.NO 13/180, 4/61, 9/236 A14/180 in Khichripur Kalyan puri Ac-38/70 B Sh(s) zone | 541123 | XXX | 70 | 115/22.11.06/EE-XXX | M/s Satish & Bros. | 02.12.06 | 06.03.07 | 541123 |  |  | Comp.
26 | Civil | 23.03.06 | 04.12.05 | Imp of open surface by pdg CCA drain near H.NO 16/481, 19/150, 11/440 & B.NO 17 near Sulabh Sauchaly Kalyan Puri Ac-38/70 Sh(S) zone | 632674 | XXX | 70 | 69/21.09.06/EE-XXX | M/s Vijay Const.Co | 21.09.06 | 14.12.06 | 592686 |  |  | Comp.
|  |  |  | Total | 13053757 | [6 empty] | 12802770
Remarks:- No. of works booked=26, No. of works cancelled=1

## 39-
STATUS REPORT OF MLA FOR THE YEAR 2005-06
Municipal Corporation of Delhi
Shahdra South
|  | Name Of MLA |  | Smt Meera Bhardwaj | AC-39 |  | year 2004-05 |  | Allocation | 100
|  | Name of Constituency |  | Mandawali
|  | Ward Nos and Names |  | 71,Sakar pur 72 Mandwali
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Div. | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Elect | 6.12.05 | 21.10.05 | Imp to gali from H.No 647 to R 558 and H.No 410 and adj H.No 554 and 195 by pdg c.c. & drain in Mandawali Fajal pur in C-72 /AC-39 | 522300 | XI | 72 | 452/17.03.06/EE-XI | M/s Singhala Const.Co | 26.03.06 | 24.06.06 | 377072 | Comp.
2 | Elect | 6.12.05 | 21.10.05 | Imp to gali from H.No 218 to R 129/1 130 to 14, H.No 95 to 228 and adj H.No 34 A , 35 by pdg c.c. & drain in Mandawali Fajal pur in C-72 /AC-39 | 556300 | XI | 72 | 450/17.03.06/EE-XI | M/s Maneet Const.Co | 22.03.06 | 23.06.06 | 402811 | Comp.
3 | Elect | 6.12.05 | 21.10.05 | Imp to Gali by pdg c.c. & drain from H.No A/24 , A/198 to 39/A, A/43 to A/44 in Mandwal, Fazal pur in c-752/AC-39 Sh (S) | 588550 | XI | 72 | 451/17.03.06/EE-XI | M/s Maneet Const.Co | 26.03.06 | 24.06.06 | 427142 | Comp.
4 | Elect | 6.12.05 | 21.10.05 | Imp to gali by pavement and drain from Buddha Marg to H.No 348 A., H.Ni A-362 to 318 , adj H.No 1324,A-1599 , 209 and H.No A217/3 to 217/9 B in Mandawali Fazal pur C-72 AC-39 Sh (S) | 567500 | XI | 72 | 106/26.06.06/EE-XI | M/s Aspiration Builders | 29.06.06 | 23.10.06 | 422614 | Comp.
5 | Elect | 15.12.05 | 5.12.05 | Imp to gali from H.No A-117 to A-140 , A-65 A-58 to A-60 , A-22 to A-56 , A-53 to A-54 and A-38 to A-50 by pdg c.c. and drain in Mandawali fazal pur in (No-72/AC-39 | 699600 | XI | 72 | 468/22.03.06/EE-XI | M/s Suresh Enterprises | 01.04.06 | 24.06.06 | 524325 | Comp.
|  |  |  | Total | 2934250 | [6 empty] | 2153964

## 40-
STATUS REPORT OF MLA FOR THE YEAR 2005-06
STATUS REPORT OF THE MLA FOR THE YEAR 2005-06
Municipal Corporation of Delhi
Shahdra South
|  | Name Of MLA |  | Dr A.K. Walia | AC-40 |  | year 2005-06 |  | Allocation |  | 200
|  | Name of Constituency |  | Geeta Coloney
|  | Ward Nos and Names |  | 73,Geeta Coloney 74 Laxmi Nagar
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Div. | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Civil | 2.8.05 | 31.5.05 | Imp of drainage system and berm of lane from HNO 7/197 to main Nallah in block 7 & 5 in Geeta coloney C-73 AC-40 | 311015 | XIV | 73 | 221/30.8.05/XIV | M/s Bacchan Const co | 8.9.05 | 23.11.05 | 310625 | Completed
2 | Civil | 2.8.05 | 31.5.05 | Imp of lanes by pdg drain and c.c adj. HNO 5/210 and 7/156 in Geeta coloney C-73/AC-40 | 245316 | XIV | 73 | 230/12.9.05/XIV | M/s Lalit Asso. | 23.9.05 | 12.12.05 | 244248 | Completed
3 | Civil | 2.8.05 | 31.5.05 | Imp of lanes by pdg c.c. & drain adj. To HNO 15/57 in block 15 Geeta Coloney in C-73/AC-40 | 334900 | XIV | 73 | 473/27.01.06/EE-XIV | M/s Kamal Enterprises | 20.03.06 | 15.06.06 | 233472 | Completed
4 | Civil | 2.8.05 | 31.5.05 | Imp of lanes by pdg RMC and drain adj. To HNO 21 to 15 in west Laxmi Market shastri Nagr in C-73/AC-40 | 425000 | XIV | 73 | 290/18.10.05/EE-XIV | M/s Maneet Const.Co | 21.10.05 | 27.09.06 | 356996 | Completed
5 | Civil | 2.8.05 | 31.5.05 | Imp of side berm adj to HNO 15/42 and Culverts of service lane in block 15 Geeta Coloney in c-73/AC-40 | 188347 | XIV | 73 | 242/19.9.05/ XIV | Ms Anuj Enterp | 22.9.05 | 7.11.05 | 187927 | Completed
6 | Civil | 2.8.05 | 17.5.05 | Imp of back lane by pdg RMC near H.No 156 in Bank enclave C-74 Sh.S | 232400 | XIV | 74 | 413/28.12.05/XIV | M/s Maneet Const.Co | 10.01.06 | 01.03.06 | 225103 | Completed
7 | Civil | 2.8.05 | 18.5.05 | Imp of lane near H.No-9 in K- block by pdg D/s and c.c. in Laxmi Ngr C-74/41 | 223910 | XIV | 74 | 281/10.10.05/XIV | M/s Sharma & Sharma Const.Co | 14.10.05 | 16.12.05 | 222096 | Completed
8 | Civil | 2.8.05 | 18.5.05 | Imp of lane by pg D/s and RMC near H.No F-40 back side of state bank of India Mangal Bazar in Laxmi Ngr C-74 | 449200 | XIV | 74 | 287/18.10.05XIV | Ms Singhlaji Const Co | 20.10.05 | 17.12.05 | 429744 | Completed
9 | Civil | 2.8.05 | 18.5.05 | Imp of lane by pdg RMC in bank enclave near H.NO 285 in Laxmi Nagr C-74 | 445000 | XIV | 74 | 261/30.9.05/XIV | M/s Subhash Kr Goyal | 1.10.05 | 21.11.05 | 444814 | Completed
10 | Civil | 2.8.05 | 18.5.05 | Imp of lane by pdg RMC and D/s near H.No F-234 B and near F-90 A in Mangal Bazar in Laxmi Nagr C-74 | 285000 | XIV | 74 | 288/18.10.05/XIV | M/s Singhlaji Const co | 20.10.05 | 17.12.05 | 271214 | Completed
11 | Civil | 2.8.05 | 18.5.05 | Imp of lane by pdg c.c & d/s near H.NO 8 in east end enclave in Laxmi Ngr Sh.S C-74 | 169438 | XIV | 74 | 258/22.09.05/EE-XIV | M/s Dhanesh Mittal | 22.09.05 | 25.11.05 | 165772 | Completed
12 | Civil | 4.8.05 | 18.5.05 | Imp of back lane near H.NO 10 and along park by pdg R.M.C in Bank enclave Laxmi Nagr C-74/40 | 480000 | XIV | 74 | 262/30.9.05/XIV | M/s Subhash Kr Goyal | 1.10.05 | 21.11.05 | 455818 | Completed
13 | Civil | 2.8.05 | 18.5.05 | Imp of D/s & pdg c.c. in the links pf gali no 6 and damagd portion of c.c. in main gali no 6 in D- block Laxmi Ngar C-74/41 | 224979 | XIV | 74 | 233/24.09.05/EE-XIV | M/s Uday Const.Co | 21.09.05 | 15.12.05 | 220711 | Completed
14 | Civil | 11.8.05 | 28.7.05 | Imp of lane by pdg RMC near H.No E-24 and damaged poriton of c.c. near H.No B-30 Jawahar park Laxmi Ngr C-74/40 | 380000 | XIV | 74 | 477/27.01.06/EE-XIV | M/s M.G.Goel Const.Co | 20.03.06 | 28.04.06 | 282587 | Completed
15 | Civil | 11.8.05 | 28.9.05 | Imp of lane by pdg RMC near H.NO C-2 and Link Aurna park Laxmi Ngr C-74/40 | 310000 | XIV | 74 | 407/27.12.05/EE-XIV | M/s Saraswati Const.Co | 16.01.06 | 03.04.06 | 230990 | Completed
16 | Civil | 11.8.05 | 28.9.05 | Imp of d/s and c.c. in gali no 3 & damaged portion of c.c in gali ni 4 Mohan park Laxmi Nagr C-74/40 | 326977 | XIV | 74 | 396/21.12.05/XIV | M/s N.P.A Engg. & Const | 13.01.06 | 04.03.06 | 326941 | Completed
17 | Civil | 11.8.05 | 28.9.05 | Imp of side link of gali no 12 by pdg RMC and D/s in Ramesh park Laxmi Nagr AC-40 | 294541 | XIV | 74 | 324/18.11.05/EE-XIV | M/s M.G Const.Co | 20.11.05 | 02.03.06 | 294084 | Completed
18 | Civil | 6.9.05 | 2.8.05 | Imp of gali no no-11 by pdg c.c. and drain adj to H.NO 15 &12 in New Lahore Sastri Ngr in C-73/AC-40 | 429300 | XIV | 73 | 440/16.01.06/EE-XIV | M/s Pankaj Const.Co | 25.01.06 | 24.04.06 | 291453 | Completed
19 | Civil | 6.9.05 | 2.8.05 | Imp to lane by pdg c.c & drain from H.NO 125 to 136 and link in New Lahore Sastri Ngr in C-73/AC-40 | 216782 | XIV | 73 | 344/01.12.05/EE-XIV | M/s Lalit Asso. | 15.12.05 | 11.08.06 | 140262 | Completed
20 | Civil | 6.9.05 | 2.8.05 | Imp of Dayanand Marg by pdg M/P from H.NO 2/5 Geeta coloney to Jheel chowk culvert in C-73/40 | 557300 | XIV | 73 | 414/28.12.05/XIV | M/s Wadhawan & Co. | 09.01.06 | 03.04.06 | 557300 | Completed
21 | Civil | 6.9.05 | 2.8.05 | Imp of lanes by pdg c.c. and drain adj to H.No-9,5 & 30 in West Laxmi market Sastri Ngr in C-73/41 | 259825 | XIV | 73 | 427/13.01.06/EE-XIV | M/s Vikas Associates | 02.02.06 | 20.04.06 | 249380 | Completed
22 | Civil | 6.9.05 | 2.8.05 | Imp of drainage system and berm of Satnam road from HNo -760 to 400 Jheel Khuranja C-73 AC-40 | 480000 | XIV | 73 | 439/16.01.06/EE-XIV | M/s Lalit Asso. | 02.02.06 | 24.03.06 | 357551 | Completed
23 | Civil | 8.9.05 | 28.7.05 | Imp of the Nerrow links in Krishan Kunj by pdg c.c. & D/s adj to main road Krishna Kunj in Laxmi Ngr Ac-40/74 | 199976 | XIV | 74 | 311/XIV/ 9.11.05 | M/s Satish & Bro | 11.11.05 | 14.12.05 | 199710 | Completed
24 | Civil | 8.9.05 | 26.8.05 | Imp of D/s & pdg c.c in lane near H.NO 144 J and K block Laxmi Nagr AC-40/74 | 198618 | XIV | 74 | 403/26.12.05/EE-XIV | M/s Kamal Enterprises | 05.01.06 | 03.03.06 | 192785 | Completed
25 | Civil | 8.9.05 | 26.8.05 | Imp of d/s and c.c. in D block near H.No 369 Laxmi Nagr C-74/40 | 217923 | XIV | 74 | 412/28.12.05/EE-XIV | M/s Singhla Const co | 03.01.06 | 25.03.06 | 216432 | Completed
26 | Civil | 20.10.05 | 8.10.05 | Imp of d/s lane near H.No 39 and poroviding c.c. bet ween gali no 1 & 4 in I block in W.no-74AC-=40 | 199000 | XIV | 74 | 341/01.12.05/EE-XIV | M/s Gaurav Const.Co | 09.12.05 | 22.07.06 | 198537 | Completed
27 | Civil | 20.10.05 | 8.10.05 | Imp of gali no 5,I block by pdg c,c, in Laxmi Ngr Ac-40/74 Sh.S | 198000 | XIV | 74 | 349/01.12.05/XIV | M/s Deepak Kumar | 12.12.05 | 09.02.06 | 198000 | Completed
28 | Civil | 20.10.05 | 8.10.05 | Imp of d/s and pdg c.c. in lane near H.No 147 in I block Laxmi Ngr AC-40/74 | 182647 | XIV | 74 | 347/01.12.05/XIV | M/s Vijay Const. | 12.12.05 | 03.02.06 | 182468 | Completed
29 | Civil | 20.10.05 | 8.10.05 | Imp of Gurudwara road by pdg c.c. berms opposite I block Laxmi Nagr AC-40/41 | 150000 | XIV | 74 | 348/01.12.05/XIV | M/s Bharat Bhushan | 22.12.05 | 08.02.06 | 148974 | Completed
30 | Civil | 20.10.05 | 8.10.05 | Imp of D/s of gali no 5 in Mohan park Laxmi Nagr C-40/74 | 188000 | XIV | 74 | 350/01.12.05/EE-XIV | M/s Prinkle Const.Co | 08.12.05 | 11.03.06 | 187603 | Completed
31 | Civil | 21.1.05 | 10.1.05 | Imp of lane by pdg RMC ner H.No 34 to 88 Kishan Kunj Maxmi Ngr AC-40/74 | 290000 | XIV | 74 | 540/02.03.06/EE-XIV | M/s Sarasweth Const.Co | 02.03.06 | 20.04.06 | 290000 | Completed
32 | Civil | 07.02.06 | 16.01.06 | Imp of Gali no.6 J.Exts by pdg CC in Laxmi Nagar Ac 40/74 Sh(S) zone | 199233 | XIV | 74 | 532/28.02.06/EE-XIV | M/s Wadhawan & Co. | 08.03.06 | 17.06.06 | 199100 | Completed
33 | Civil | 07.02.06 | 16.01.06 | Imp of gali no.6 pdg D/s in Ramesh park Laxmi Nagar Ac 40/74 Sh(S) zone | 194657 | XIV | 74 | 535/28.02.06/EE-XIV | M/s Baldev Raj Gupta | 09.03.06 | 28.06.06 | 194601 | Completed
34 | Civil | 07.02.06 | 16.01.06 | Pdg D/S Ac.C in J-block near NO 72 Laxmi Nagar AC-40/74 Sh(S) zone | 199987 | XIV | 74 | 530/28.02.06/EE-XIV | M/s Bhagwan Dass Aco. | 20.03.06 | 02.05.06 | 199911 | Completed
35 | Civil | 07.02.06 | 16.01.06 | Pdg RMC & D/S in gali no. 2A & 4 in D block, Laxmi Nagar Ac-40/74 Sh(S) zone | 199726 | XIV | 74 | 653/28.03.06/EE-XIV | M/s Prem Kumar | 29.03.06 | 05.06.06 | 199726 | Completed
36 | Civil | 16.02.06 | 16.01.06 | Imp of D/S and pdg C.c in Lalita park gali no.9 and link in Laxmi Nagar Ac-40/74 | 339310 | XIV | 74 | 16/04.05.06/EE-XIV | M/s Ajay Associates | 30.06.06 | 12.08.06 | 339027 | Completed
37 | Civil | 16.02.06 | 16.01.06 | Imp of LHS D/S opp. Anarwali Masjid in J-exts and pdg CC in link near H.NO 3/116 and 3/129 in Laxmi Nagar Ac-40/74 | 257687 | XIV | 74 | 32/26.05.06/EE-XIV | M/s Bacchan Const co | 29.05.06 | 25.07.06 | 257687 | Completed
38 | Civil | 16.02.06 | 16.01.06 | Imp of D/S in gali no.4 J-Exts Laxmi Nagar AC-40/74 | 280000 | XIV | 74 | 17/04.05.06/EE-XIV | M/s Ajay Associates | 14.06.06 | 11.08.06 | 231007 | Completed
39 | Civil | 06.03.06 | 16.01.06 | Imp to D/s and pdg CC in gali no.8 and CC neaar H.NO 7/317 in Lalita park, Laxmi Nagar Ac-40/74 | 347697 | XIV | 74 | 03/25.04.06/EE-XIV | M/s Sarasweth Const.Co | 29.05.06 | 25.07.06 | 347623 | Completed
40 | Civil | 22.03.06 | 12.02.06 | Imp of chowk by pdg are in AC.c pavement adjacent to H.NO 3/48 and 3/91 in block 3 Geeta Colony in Ac-40/73 | 431429 | XIV | 74 | 35/08.06.06/EE-XIV | M/s Suresh Kumar Goel | 26.06.06 | 21.08.06 | 430228 | Completed
41 | Civil | 22.03.06 | 12.02.06 | Imp of Chowk by pdg drain and CC pavement adjacent to H.NO 3/39 and 3/100 in block 3 Geeta Colony in Ac-40/73 | 560000 | XIV | 74 | 33/08.06.06/EE-XIV | M/s Singla Const.Co | 04.07.06 | 12.09.06 | 397284 | Completed
42 | Civil | 22.03.06 | 12.02.06 | Imp of side lane by pdg CC pavement from Telephone Exchange to H.NO 512/2 in Jheel Khuranja Ac-40/73 | 460000 | XIV | 74 | 34/08.06.06/EE-XIV | M/s Adrash Const.Co | 26.06.06 | 07.08.06 | 354647 | Completed
43 | Civil | 22.03.06 | 12.02.06 | Imp of lane by pdg drain and CC from H.NO 13/254 to 13/230 in block 13 Geeta colony Ac-40/73 | 405401 | XIV | 74 | 36/08.06.06/EE-XIV | M/s Vikas Associates | 02.07.06 | 11.09.06 | 403144 | Completed
44 | Civil | 27.03.06 | 16.01.06 | Imp of D/S and pdg R.M.C in the link road between main bazar Laxmi Nagar and P.P.G road in Laxmi Nagar C-74/40 | 597600 | XIV | 74 | 15/02.05.06/EE-XIV | M/s P.S Const.Co | 09.05.06 | 03.07.06 | 597600 | Completed
[5 empty] | 13566121 | [6 empty] | 12465182

## 41-
STATUS REPORT OF MLA FOR THE YEAR 2005-06
MINICIPAL CORPOATION OF DELHI
Shahdra South
|  | Name Of MLA |  | Sh. A.S. Lovely | AC-41 |  | year 2005-06 |  | Allocation | 192.68
|  | Name of Constituency |  | Gandhi Nagar
|  | Ward Nos and Names |  | 75 Gandi Nagar , 76 Raghbar Pura
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 16
1 | Civil | 8.7.05 | 20.4.05 | Pdg C.c. pav& drainage in link from HNO 5514 to 5538 & link near HNO 5517 to 5527 Seelam pur Village C-76/41 Sh.S. | 335173 | XIV | 76 | 306/09.11.05/EE-XIV | M/s Jitender Kumar | 26.12.05 | 14.02.06 | 296292 | Comp.
2 | Civil | 8.7.05 | 20.4.05 | Imp the drainage system in gali from HNO 3741 to 3720 shanti Mohalla C-76/41 Sh.S. | 381106 | XIV | 77 | 239/14.09.05/XIV | M/s Surender Kumar Garg | 20.09.05 | 08.11.05 | 371716 | Comp.
3 | Civil | 11.7.05 | 27.6.05 | Imp of depresred portion of Ashok gali by pdg C.C. pav. & D/S inGandhi Nagar. | 156970 | XIV | 78 | 211/17.8.05/ XIV | M/s Satish & Bro | 22.8.05 | 27.9.05 | 155477 | Comp.
4 | Civil | 11.7.05 | 27.6.05 | Imp of lane back side of Janta gali by pdg C.C. pav and D/S in Gandhi Ngr. C-75/41 | 199975 | XIV | 78 | 209/17.9.05/XIV | M/s Gajinder Kumar | 22.8.05 | 25.10.05 | 199885 | Comp.
5 | Civil | 11.7.05 | 27.6.05 | Imp of Subhash road from XI/152 to IX /1267 by pdg C.C. Pav & D/s in Gandhi Ngr. C-75/41. | 199369 | XIV | 78 | 208/11.8.05/XIV | M/s Rajesh Assoc. | 20.8.05 | 29.9.05 | 199278 | Comp.
6 | Civil | 18.7.05 | 30.6.05 | Imp to lane near Satyanagreyan Mandir by pdg C.C pav and D/S inGadhi Ngr. C-75/41 | 275515 | XIV | 78 | 295/18.10.05/XIV | M/s Surender Kumar Garg | 25.10.05 | 19.01.06 | 268826 | Comp.
7 | Civil | 18.7.05 | 30.6.05 | Imp to syam Gali and its lines by pdg C.C pav and D/S in Gandhi Nagr.C-75/41 | 321423 | XIV | 78 | 232/14.09.05/XIV | M/s Surender Kumar Garg | 20.09.05 | 21.11.05 | 313271 | Comp.
8 | Civil | 18.7.05 | 30.6.05 | Imp to lane near DAV School by pdg C.C pav and d/S in Gandhi Ngr. | 555000 | XIV | 78 | 238/14.09.05/XIV | M/s Surender Kumar Garg | 20.09.05 | 07.12.05 | 347042 | Comp.
9 | Civil | 18.7.05 | 27.6.05 | Imp to Subhash road from IX/1271 to police port by pdg C.C. pav & D/S in Gandhi Ngr. | 194931 | XIV | 78 | 212/17.8.05/XIV | M/s N.K.G Enterpriseis | 22.8.05 | 5.10.05 | 194375 | Comp.
10 | Civil | 18.7.05 | 30.6.05 | Imp to d/s system of Gali no 5 Dharam pura from III link to Nallah in Ghandhi Nagar c-75/41 | 234304 | XIV | 78 | 296/18.10.05/XIV | M/s Surender Kumar Garg | 25.01.05 | 10.01.06 | 233884 | Comp.
11 | Civil | 18.7.05 | 30.6.05 | Imp to lane from Mahavir chowk to Subhash Mohalla road by pdg C.C. pav and d/s in Gandhi Ngr. C-74 | 286888 | XIV | 78 | 237/14.09.05/XIV | M/s Surender Kumar Garg | 20.09.05 | 21.12.05 | 277275 | Comp.
12 | Civil | 18.7.05 | 30.6.05 | Imp to Gyan Mohalla gali No 3 by pdg C.C pav and D/S in Gandhi Ngr. C-75 | 366614 | XIV | 78 | 236/14.09.06/XIV | M/s Surender Kumar Garg | 20.09.06 | 06.12.05 | 354556 | Comp.
13 | Civil | 18.7.05 | 30.6.05 | Imp to Dharma pura Gali no 3 from Iind link to Nalla by pdg C.C pav and D/s in Gandhi Ngr. C-75 | 285059 | XIV | 78 | 235/14.09.05/XIV | M/s Surender Kumar Garg | 20.09.05 | 21.11.05 | 277212 | Comp.
14 | Civil | 18.7.05 | 30.6.05 | Imp to Seelampur gali no 10 & its link by pdg c.c. pav & D/s in Gandhi Ngr.C-75 | 212126 | XIV | 78 | 297/18.10.05/XIV | M/s Surender Kumar Garg | 25.01.05 | 12.01.06 | 206888 | Comp.
15 | Civil | 18.7.05 | 30.6.05 | Imp to Kailash Ngr gali no 16 by pdg C.C pav and d/s in Gandhi Ngr. | 420632 | XIV | 78 | 298/18.10.05/XIV | M/s Surender Kumar Garg | 25.10.05 | 24.01.06 | 406752 | Comp.
16 | Civil | 18.7.05 | 30.6.05 | Imp to Dharma pura Extn. Gali no 1 by pdg C.C pav and d/S in Gandhi Ngr C-75 | 256670 | XIV | 78 | 299/18.10.05/XIV | M/s Surender Kumar Garg | 25.10.05 | 13.01.06 | 248834 | Comp.
17 | Civil | 28.7.05 | 20.4.05 | pdg c.c pav & drainage in gali near HNO 4792 & its link from Seelam pur road to Nala Seelam pur village C-76/41. | 259400 | XIV | 76 | 222/30.8.05/XIV | M/s Vinod Const co | 21.9.05 | P | 197781 | In Prog
18 | Civil | 28.7.05 | 20.4.05 | Pdg c.c. pav & & drainage in Harijan gali & link near HNO 4770 Seelam pur Village in C-76/41. | 176470 | XIV | 76 | 228/7.9.05/XIV | M/s Jai Chanda Asso. | 13.9.05 | P | 168169 | In Prog
19 | Civil | 28.7.05 | 20.4.05 | Pdg c.c pave & drainage in link of Harijan gali near HNO 4767,4769 and near HNO 4782,4783 Seelam pur Village . | 188480 | XIV | 76 | 203/11.8.05/IV | M/s Jai Chanda Asso. | 16.8.05 | 26.9.05 | 187896 | Comp.
20 | Civil | 28.7.05 | 20.4.05 | Pdg c.c pav & drainage in link from HNO 5319 to 5333 and near HNO 5538 Seelam pur Village. | 163983 | XIV | 76 | 204/11.8.05/XIV | M/s Jai Chanda Asso. | 16.8.05 | P | 155018 | In Prog
21 | Civil | 18.8.05 | 15.7.05 | Pdg C.c. pav on Raghubar pura road C-76/41 Sh.SZ | 357478 | XIV | 76 | 327/23.11.05/XIV | M/s Atul Const.Co | 24.11.05 | 19.12.05 | 339770 | Comp.
22 | Civil | 18.8.05 | 15.7.05 | pdg c.c pav and drainage in main road Ajeeh Ngr from M.C pry School to Gali no -11 Ajeeh Nagar C-76/41 | 411981 | XIV | 76 | 325/18.11.05/EE-XIV | M/s Vee-CEE enterprises | 05.01.06 | 14.02.06 | 368060 | Comp.
23 | Civil | 1.9.05 | 15.7.05 | Imp of drainage system in gali no 6 & its link near H.No 2653 Raghubar pura -II C-76/41 Sh.S | 319629 | XIV | 76 | 331/24.11.05/EE-XIV | M/s Atul Const.Co | 06.12.05 | 13.02.06 | 287351 | Comp.
24 | Civil | 1.9.05 | 15.7.05 | Pdg c.c. pav and drainagy in gali no 1 & its link Raghubar pura -I C-76/41 Sh.S Zone | 346222 | XIV | 76 | 358/07.12.05/EE-XIV | M/s Shree Associates | 15.02.06 | 04.04.06 | 325879 | Comp.
25 | Civil | 1.9.05 | 15.7.05 | pdg c.c. pav & drainage in gali no 9 A from H.NO 4335 to 4314 Ajeet Nagr C-76/41 Sh.S | 262700 | XIV | 76 | 375/13.10.05/EE-XIV | M/s Sunil Bhuteri | 15.02.06 | 31.03.06 | 151947 | Comp.
26 | Civil | 1.9.05 | 15.7.05 | Pdg c.c. pav & drainage in lane near H.NO 1734 , 1769, 1770 and 1798 Rajgarh coloney C-76/41 Sh.S | 269091 | XIV | 76 | 628/13.03.06/EE-XIV | M/s Shree Associates | 01.05.06 | 06.06.06 | 254774 | Comp.
27 | Civil | 1.9.05 | 15.7.05 | Pdg c.c. pav & drainage in Tagore gali and its link near h.No 138,149 in Ram Nagar C-76/41 | 357051 | XIV | 76 | 359/07.12.05/EE-XIV | M/s Shree Associates | 14.02.06 | 04.04.06 | 342361 | Comp.
28 | Civil | 2.9.05 | 22.8.05 | Imp to Subhash Mohalla road by pdg RMC in Gandhi Nagr C-75/41 | 583150 | XIV | 75 | 416/02.01.06/XIV | M/s Rajesh Assoc. | 05.01.06 | 22.02.06 | 561535 | Comp.
29 | Civil | 2.9.05 | 22.8.05 | Imp to Seelampur road by pdg RMC in Gandhi Nagr C-75/41 | 790200 | XIV | 75 | 01/25.04.06/EE-XIV | M/s Lalit Associates | 03.05.06 | 10.07.06 | 771080 | Comp.
30 | Civil | 2.8.05 | 30.6.05 | Imp to lane from Dhavampura Gali no to Kailash Nagr gali no 16 by pdg c.c. pav and D/s in Gandhi Ngr C-75/41 | 194200 | XIV | 75 | 274/04.10.05/XIV | M/s R.P.Const.Co | 10.10.05 | 24.11.05 | 193478 | Comp.
31 | Civil | 9.9.05 | 15.7.05 | pdg c,c pav & drainage in gali no 12 & its inks in Raghubar pura -II C-76/41 | 423200 | XIV | 76 | 383/13.12.05/XIV | M/s Atul Const co | 16.12.05 | 9.1.06 | 422818 | Comp.
32 | Elect | 24.11.05 | 10.9.05 | P/o 150 W HPSv fittings in Kaushil puri , Old Seekampur , New Chand Mohalla Raghuverpura No-2 in Ac-41 Sh (s) Zone | 199677 | EE(E)V | 41 | 230/27.02.06/EE(E)V | M/s Krishna Electric Works | 27.02.06 | 08.03.06 | 193238 | Comp.
33 | Civil | 24.11.05 | 30.6.05 | Imp to Seelam pur gali no-11 by pdg c.c. pav & D/s in Gandhi Nagar in C-75/41 | 234987 | EEE_V | 41 | 587/13.03.06/EE-XIV | M/s Prakash Builders | 20.03.06 | 07.06.06 | 223384 | Comp.
34 | Civil | 24.11.05 | 30.6.05 | Imp to Seelam pur gali no-12 by pdg c.c. pav & D/s in Gandhi Nagar in C-75/41 | 283705 | EEE_V | 41 | 500/15.02.06/EE-XIV | M/s Atul Const.Co | 22.02.06 | 20.05.06 | 281214 | Comp.
35 | Civil | 24.11.05 | 30.6.05 | Imp to Seelam pur gali no 13 by pdg c,c, pav D/S in Gandhi Nagar C-75/41 | 203968 | EEE_V | 41 | 568/10.03.06/EE-XIV | M/s Atul Const.Co | 17.03.06 | 07.06.06 | 191684 | Comp.
36 | Civil | 24.11.05 | 30.6.05 | Imp to IIIrd link of Dharmapura from gali no -5 Dharampura to gali no 17 Kailash Nag by pdg c.c. pav A D/s in Gandhi Nagar | 230825 | XIV | 75 | 501/15.02.06/EE-XIV | M/s Atul Const.Co | 21.02.06 | 27.03.06 | 216355 | Comp.
37 | Civil | 24.11.05 | 30.6.05 | Imp to Dharmpura Extn gali no-2 by pdg c.c. pav A D/s in Gnadhi Ngar in C-75/41 | 239196 | XIV | 75 | 502/15.02.06/EE-XIV | M/s Atul Const.Co | 17.02.06 | 27.03.06 | 227636 | Comp.
38 | Civil | 24.11.05 | 30.6.05 | Imp to Dharmapura Extn gali no 3 by pdg c.c. pav A D/s Gandhi nagar C-75/41 | 225227 | XIV | 75 | 503/15.02.06/EE-XIV | M/s Atul Const.Co | 17.02.06 | 27.03.06 | 223195 | Comp.
39 | Civil | 24.11.05 | 30.6.05 | Imp to Malhotra gali by pdg no 3 by pdg c.c. pav & D/s in Gandhi Ngr C-75/41 | 300068 | XIV | 75 | 499/15.02.06/EE-XIV | M/s Atul Const.Co | 22.02.06 | 28.04.06 | 288692 | Comp.
40 | Civil | 24.11.05 | 30.6.05 | Imp to Dhrampura Gali no -1 by pdg cc. Pav & D/s in gandhi Ngar C-75/41 | 325346 | XIV | 75 | 511/17.02.06/EE-XIV | M/s Atul Const.Co | 24.02.06 | 24.05.06 | 313982 | Comp.
41 | Civil | 24.11.05 | 30.6.05 | Imp to Kailash Ngr gali no 9 by pdg C.C pav and d/s in Gandhi Ngr. In C-75/41 | 309452 | XIV | 75 | 566/10.03.06/EE-XIV | M/s Atul Const.Co | 17.03.06 | 12.06.06 | 294511 | Comp.
42 | Civil | 24.11.05 | 30.6.05 | Imp to lane near M.L. pry School Ashok gali by pdg c.c. pave & D/s in Gandhi Ngr. C-75/41 | 269406 | XIV | 75 | 544/02.03.06/EE-XIV | M/s Atul Const.Co | 09.03.06 | 02.06.06 | 258276 | Comp.
43 | Civil | 24.11.05 | 1.9.05 | P/o 150 W HPSv fittings in main road Gandhi Ngr , Netaji gali Shavitri gali , Mukherji gali kashyap mohalla, Subhash road kothi Bhagwan Dass in AC-41 Sh-19. | 199645 | XIV | 75 | 231/27.02.06/EE(E)-V | M/s Krishna Electric Works | 27.02.06 | 31.03.06 | 193392 | Comp.
44 | Civil | 28.11.05 | 30.9.05 | Pdg c.c. pave & drainage in gali no and its link shanti Mohalla C-76/41 Sh s Zone | 694500 | XIV | 75 | 529/28.02.06/XIV | M/s Vikas Associates | 28.02.06 | 6.09.06 | 662182 | Comp.
45 | Civil | 28.11.05 | 29.8.05 | pdg c.c. pave in gali no 4 Raghubarpura -II C-76/41 Sh S Zone | 697200 | XIV | 75 | 525/23.02.06/EE-XIV | M/s Shree Associates | 24.02.06 | 07.04.06 | 696601 | Comp.
46 | Civil | 28.11.05 | 29.8.05 | Pdg c.c pav & drainage in link from H.No 5319 to 5333 and near HNO 5538 Seelam pur Village. | 480400 | XIV | 76 | 419/06.01.06/XIV | M/s Lalit Associates | 25.01.06 | 06.03.06 | 479185 | Comp.
47 | Civil | 28.11.05 | 1.8.05 | Imp to lane from 1*/1348 to Aggarwal sweeta by pdg c.c pav and D/s in Shembhu Nath bldg South Gandhi Ngr C-75/41 | 571100 | XIV | 76 | 418/06.01.06/XIV | M/s Atul Const.Co | 09.01.06 | 29.03.06 | 567583 | Comp.
48 | Civil | 28.11.05 | 30.9.05 | Imp to gali no-2 in shambhau Nath bldg by pdg C.c. pav & D/s in South Gandhi Nagr C-75/41 | 515900 | XIV | 76 | 620/13.03.06/EE-XIV | M/s Jitender Kumar | 22.03.06 | 21.06.06 | 335978 | Comp.
49 | Civil | 29.11.05 | 14.9.05 | Imp to drainage system in gali no 18 & 22 Shanti Mohalla C-76/41 | 262300 | XIV | 76 | 638/23.03.06/EE-XIV | M/s Saraswati Const.CO | 05.04.06 | 30.05.06 | 220878 | Comp.
50 | Civil | 29.11.05 | 14.9.05 | Imp to lane from 11*/3877 to IX /3839 in Dharampura Extn. By pdg RMC in Gandhi Ngar C-75/41 | 527800 | XIV | 75 | 564/10.03.06/XIV | M/s S.C.Goel Acco. | 11.03.06 | 29.03.06 | 525969 | Comp.
51 | Civil | 29.11.05 | 3.10.05 | Imp to Nehru gali by pdg RMC in Gandhi Ngr C-75/41 | 742600 | XIV | 75 | 25/04.05.05/EE-XIV | M/s Lalit Associates | 11.05.06 | 06.07.06 | 732620 | Comp.
52 | Civil | 29.11.05 | 3.10.05 | Imp to lanes in Rehishi Phool singh by pdg c.c. pav & D/s in Gandhi Ngar C-75/41 | 481000 | XIV | 75 | 581/13.03.06/EE-XIV | M/s Vikas Associates | 20.03.06 | 24.05.06 | 466393 | Comp.
53 |  |  |  | Cancelled |  | XIV | 75
54 |  |  |  | Cancelled |  | XIV | 75
55 | Civil | 29.11.05 | 8.11.05 | Imp to Partap gali by pdg RMC in Gandhi Nagr C-75/41 | 471894 | XIV | 76 | 89/05.10.06/EE-XIV | M/s Surender Kumar Garg | 10.10.06 | 24.11.06 | 465493 | Comp.
56 | Civil | 20.12.05 | 30.11.05 | Pdg c,c pav & drainage in link of satsang marg near H.No 1263, 1266 and 1277 in Raj Garh colony C-76/41 Sh S. Zone. | 198704 | XIV | 76 | 461/24.01.06/XIV | M/s R.A Assocites | 27.01.06 | 23.02.06 | 198689 | Comp.
57 | Civil | 20.12.05 | 30.11.05 | pdg c,c, pav & drainage in gali no 2 and its kink from H.No 930 to 871 in Chand mohalla C-76/41 Sh S.Zone | 199764 | XIV | 76 | 459/24.01.06/XIV | M/s Ashwini Kumar Aggarwal | 25.01.06 | 23.02.06 | 199621 | Comp.
58 | Civil | 20.12.05 | 30.11.05 | pdg c.c. pav & drainafge in gali no 10 and link between gali no 11 & 12 Ajeet Ngr C-76/41 | 198276 | XIV | 76 | 465/24.01.06/XIV | M/s N.K.G Enterpriseis | 01.02.06 | 06.03.06 | 197767 | Comp.
59 | Civil | 20.12.05 | 30.11.05 | Pdg c.c pav & drainage gali no 12 and 12 a H.No 4127 to 4113 Ajeet Ngr C-76/41 | 198493 | XIV | 76 | 460/24.01.06/XIV | M/s Kausal Builders | 01.02.06 | 02.03.06 | 198225 | Comp.
60 | Civil | 16.1.05 | 8.11.05 | Imp to subhash raod near Tikona park by pdg c.c. pav andD/s in Gandhi Ngr C-75/41 | 198633 | XIV | 76 | 658/28.03.06/EE-XIV | M/s Himalya Const.Co | 04.04.06 | 02.06.06 | 196612 | Comp.
61 | Civil | 16.6.05 | 5.10.05 | Imp to lane behind sibal public school by pdg RMC in Gandhi Ngr C-75/41 | 695600 | XIV | 76 | 02/25.04.06/EE-XIV | M/s Surender Kumar Garg | 01.05.06 | 21.06.06 | 690624 | Comp.
62 | Civil | 30.01.06 | 20.01.06 | Pdg CC pavement and drainage in gali no.10 Raghubar pura-II in C-76/41 (Additional Amt booked) | 137762 | XIV | 76 | 495/15.02.06/XIV | M/s Shree Associates | 16.02.06 | 24.03.06 | 137431 | Comp.
|  |  |  | Total | 20078418 | [6 empty] | 18956890

## 42-
STATUS REPORT OF MLA FOR THE YEAR 2005-06
MUNICIPAL CORPORATION OF DELHI
Shahdra South
|  | Name Of MLA |  | Dr. Harshwardhan | AC -42 |  |  |  | Allocation | 164.23
|  | Name of Constituency |  | Krishna Nagar
|  | Ward Nos and Names |  | C-77 Krishan Nagar C-78 Jagatpuri
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 16
1 | Elect | 4.8.05 | 6.7.05 | P/o Semi high Mast ner J.K. properties , Krishna Nagr in Ac-42 under Sh.North | 165400 | EE(E)-IV | 77 | 261/21.03.06/EE(E)V | M/s Chandra Electricals Contractor & Builder | 29.03.06 | 25.05.06 | 157701 | Comp.
2 | Elect | 4.8.05 | 13.7.05 | P/o Semi high mast near Raju puri Walan Shiv puri patpar Ganj road under Sh.south Zone. | 165171 | EE(E)-IV | 78 | 195/07.02.06/EE(E)-V | M/s Kohinoor Electriclas | 14.02.06 | 13.03.06 | 131195 | Comp.
3 | Elect | 4.8.05 | 19.7.05 | P/o Semi high mast at parking site of musical fountain Balder park under sh.S | 167388 | EE(E)-IV | 78 | 29/12.12.05/EEE-IV | M/s Sushma Electrical | 19.12.05 | 3.1.06 | 159478 | Comp.
4 | Elect | 4.8.05 | 8.7.05 | P/o Semi high mast ner Channder Nagr Bus Stop in Ac-42 under Sh.South | 166279 | EE(E)-IV | 67 | 30/12.12.05/EE(E)-V | M/s Sushma Electrical | 19.12.05 | 3.1.06 | 155867 | Comp.
5 | Elect | 4.8.05 | 16.7.05 | P/o Semi high mast ner Jitar Nagr Mandir in AC-42 under Sh.S | 165844 | EE(E)-IV | 78 | 37/14.12.05/EE(E)V | M/s Khanna Sales Const. | 20.12.05 | 12.01.06 | 159722 | Comp.
6 | Elect | 4.8.05 | 4.7.05 | P/o Semi high mast near Mahesh Timber, Shastri park Chander Nagar road in AC-42 under Sh.South | 163980 | EE(E)-IV | 78 | 28/12.12.05/EE(E)-V | M/s Sushma Electrical | 19.12.05 | 3.1.06 | 160263 | Comp.
7 | Elect | 9.8.05 | 20.7.05 | P/o Semi high mast at near Suri paint Chandra Ngr. Road (Dr. Chandi wala) under Sh.S. | 166279 | EE(E)-V | 78 | 35/14.12.05/EE(E)V | M/s Khanna Sales Const. | 12.01.06 | 14.01.06 | 160507 | Comp.
8 | Civil | 31.8.05 | 11.8.05 | Imp to road by pdg mastic arphalt from H.No G-39 to g-32 in Radhey puri in C-77/42 Sh.S | 295620 | XIV | 77 | 597/13.03.06/EE-XIV | M/s Balaji & Associates | 20.03.06 | 03.07.06 | 295620 | Comp.
9 | Civil | 31.8.05 | 11.8.05 | Imp to raod by pdg mastic asphalt from H.No F-4/1 to E-14/2 in e block Krishna Nagr in C-77/42Sh.S | 489555 | XIV | 77 | 616/13.03.06/EE-XIV | M/s Pawan Bros. | 5.10.07 | 22.11.07 | 483857 | Comp.
10 | Civil | 31.8.05 | 11.8.05 | Imp to road by pdg mastic arphalt from M.c pary School Kanti Nagr to transforme H.No A34 to road no 57 in A block Kanti Nagr in C-77/42 Sh.S | 535247 | XIV | 77 | 617/13.03.06/EE-XIV | M/s Pawan Bros. | 5.10.07 | 22.11.07 | 525524 | Comp.
11 | Civil | 22.9.05 | 11.8.05 | Imp to road by pdg c.c pav from A-9 to A-1 in A block kirhsna Nagr in C-77/44 | 198472 | XIV | 77 | 310/09.11.05/XIV | M/s Wadhawan Acco. | 17.11.05 | 04.01.06 | 196876 | Comp.
12 | Civil | 22.9.05 | 7.9.05 | Imp to pav. & imp to drain from H.No F-12 to F-23 in Radhey puri Sh.S | 199439 | XIV | 77 | 312/.9.11.05/XIV | M/s S.C.Goels & Co | 16.11.05 | 06.01.06 | 197080 | Comp.
13 | Civil | 28.9.05 | 11.8.05 | Imp to lane by pdg c.c. pav. & drain near H.No A2/25 ,A-2/9 A2/2 in A block Krishan Nagr in C-77/42 Sh.S | 191058 | XIV | 77 | 374/13.12.05/EE-XIV | M/s Jagdish Pdsharma | 20.02.06 | 20.02.06 | 161013 | Comp.
14 | Civil | 28.9.05 | 11.8.05 | Imp to road by pdg mastic arphalt from H.No C-10/1 to C-10/14 in Krishan Ngr. C-77/42 Sh.S | 597350 | XIV | 77 | 444/16.01.06/XIV | M/s Balaji & Associates | 24.01.06 | 18.03.06 | 597350 | Comp.
15 | Civil | 28.9.05 | 11.8.05 | Imp to road by pdg mastic Asphalt from H.No 2/1 to H-1/18 in H block Krishan Ngr. In c-77/42Sh.S | 554700 | XIV | 78 | 388/15.12.05/XIV | M/s A.K Enterprises | 10.01.06 | 25.01.06 | 543908 | Comp.
16 | Civil | 28.9.05 | 7.9.05 | Imp to road by pdg mastic Asphalt from H.No B-8/ to Mandir marg in B block Krishna Nagr C-77/42Sh.S | 565000 | XIV | 78 | 438/16.01.06/XIV | M/s Amit Const.CO | 30.01.06 | 20.03.06 | 564003 | Comp.
17 | Civil | 28.9.05 | 7.9.05 | Imp to road by pdg mastic Asphalt from H.No C--1 tp C-18 & H.NO E-15/13 to C-39 in C block east Krishna Nagr C-77/42Sh.S | 555550 | XIV | 78 | 351/1.12.05/XIV | M/s M.G. Goyal Cont Co | 2.12.05 | 18.1.06 | 550274 | Comp.
18 | Civil | 28.9.05 | 7.9.05 | Imp to road by pdg mastic Asphalt from H.No ,F-12/1 to F-12/9 , F-12/10 to F-12/28 f-12/24 to F-12/35in F block Krishna Nagr C-77/42Sh.S | 682700 | XIV | 78 | 401/22.12.05/XIV | M/s M.G. Goyal Cont Co | 2.12.05 | 25.01.06 | 679795 | In Prog.
19 | Civil | 28.9.05 | 7.9.05 | Imp to road by pdg mastic Asphalt from H.No f-10/10 to F-10/35 in F block Krishna Nagr C-77/42Sh.S | 558286 | XIV | 78 | 408/27.12.05/XIV | M/s Subhash Bros. | 05.01.06 | 10.02.06 | 557528 | Comp.
20 | Civil | 28.9.05 | 7.9.05 | Imp to road by pdg mastic Asphalt from H.No f-5/10 to f-5/35 in f block Krishan Nagr Krishna Nagr C-77/42Sh.S | 540000 | XIV | 78 | 387/15.12.05/XIV | M/s A.K Enterprises | 10.01.06 | 25.01.06 | 540000 | Comp.
21 | Civil | 3.10.05 | 12.8.05 | Imp to road by pdg mastic Asphalt from Patpar Ganj raod to H.No 9 Shiv Puri Extn C-78/42 Sh.S | 295620 | XIV | 78 | 596/13.03.06/EEXIV | M/s Balaji & Associates | 24.05.06 | 28.08.07 | 295580 | Comp.
22 | Civil | 3.10.05 | 12.8.05 | Imp to main raod near H.NO 13 A shiv puri extn and Semi or Sr. Sec School chander Nagr in C-78/42 by pdg mastic ashphat | 514027 | XIV | 78 | 615/13.03.06/EE-XIV | M/s Pawan Bros. | 13.10.06 | 31.01.07 | 512877 | Comp.
23 | Civil | 3.10.05 | 12.8.05 | Imp to Bhagat Singh road from Vaish eye entre to Kamal Tailors in C-78/42 by mastic arphalt | 509137 | XIV | 78 | 613/13.03.06/EE-XIV | M/s Pawan Bros. | 5.10.07 | 15.11.07 | 508683 | Comp.
24 | Civil | 3.10.05 | 12.8.05 | Imp to main raod from Haryawan Dair to H.No 16 in Shyam Nagr in C-78/42. | 522192 | XIV | 78 | 614/13.03.06/EE-XIV | M/s Pawan Bros. | 5.10.07 | 15.11.07 | 522114 | Comp.
25 | Civil | 3.10.05 | 12.8.05 | Imp to road by pdg mastic arphalt from H.No A-23 to f-15 New Gonid pura ext in C-78/42 | 258667 | XIV | 78
26 | Civil | 3.10.05 | 12.8.05 | Imp of main road from gali no-7 New gobid pura to apawana raod in C-78/42 by mastic asphalt | 377735 | XIV | 78
27 | Civil | 3.10.05 | 12.8.05 | Imp to side berms from H.No 18/17/12 Old Gobind pura to Parwana road along muricla fountain in C-78/12 | 445500 | XIV | 78 | 399/22.12.05/XIV | M/s Rajesh Associates | 04.01.06 | 21.03.06 | 445500 | Comp.
28 | Civil | 3.10.05 | 12.8.05 | Imp to side lane along Chopal in village Ghodli in C-78/12/by C.c. | 245600 | XIV | 78 | 483/03.02.06/XIV | M/s Bachan Const.Co | 06.02.06 | 06.03.06 | 245600 | Comp.
29 | Civil | 3.10.05 | 12.8.05 | Imp of road by pdg mastic from patpar Ganj road to H.No /C in Pandit park in C-78/42 | 410700 | XIV | 78 | 389/15.12.05/XIV | M/s A.K Enterprises | 02.01.06 | 07.02.06 | 410247 | Comp.
30 | Civil | 10.10.05 | 3.10.05 | Imp to lane along H.No B-27 west Chander Ngr & H.No 33 Silver park in C-78/42 | 154390 | XIV | 78 | 352/05.12.05/XIV | M/s Baldev Raj Gupta | 06.12.05 | 13.01.06 | 154151 | Comp.
31 | Civil | 10.10.05 | 3.10.05 | Imp of lane along K-15,I-II,4 K-27 A & Adj. Potion in different lanes by pdg C.c. in New Gobind pura in C-78/42 | 319828 | XIV | 78 | 634/20.03.06/EE-XIV | M/s Amit Associates | 15.04.06 | 23.05.06 | 317030 | Comp.
32 | Civil | 10.10.05 | 3.10.05 | Imp of parwana road by pdg mastic asphalt faorm Bhagat Singh road to patpar Ganj road in in C-78/42 | 415018 | XIV | 78 | 516/21.02.06/XIV | M/s Man Mohan Singh Wadhwa | 22.02.06 | 30.03.06 | 415014 | Comp.
33 | Civil | 21.10.05 | 11.8.05 | Imp to lane by pdg c.c. tebein in gali no9 near H.NO 83 in East Azad Ngr C-77. | 190348 | XIV | 78 | 368/07.12.05/XIV | M/s Gajender Kumar | 19.12.05 | 20.01.06 | 187246 | Comp.
34 | Civil | 25.1.05 | 21.9.05 | Imp to raod by pdg mastic asphalt from H.No F-1/1 to F-1/35 in F block Krishna Nagr in C-77/42Sh.S | 541194 | XIV | 77 | 590/13.03.06/EE-XIV | M/s Balaji & Associates | 30.03.06 | 21.06.06 | 540588 | Comp.
35 | Civil | 25.1.05 | 7.10.05 | Imp to road drainage system be covering drain from Musical fourtain Baldev park to Sukhvihar road crossing along parwana road in C-78/42 | 690000 | XIV | 77 | 644/27.03.06/EE-XIV | M/s S.C.Goels & Co | 02.05.06 | 20.06.06 | 689556 | Comp.
36 | Civil | 25.1.06 | 7.10.05 | Imp of road by pdg Mastic Ashphalt from H.No G-65 to Parwana road in Jagat Puri in C-78/42 | 452708 | XIV | 78 | 519/21.02.06/XIV | M/s Man Mohan Singh Wadhwa | 27.02.06 | 31.03.06 | 451810 | Comp.
37 | Civil | 25.1.06 | 7.10.05 | Imp of road by pdg mastic from patpar Ganj road to H.No 93, South Anakali Extn H. No 82, South Anarkali Exnt C-78/42 | 399926 | XIV | 78 | 517/21.02.06/XIV | M/s Man Mohan Singh Wadhwa | 27.02.06 | 31.03.06 | 398987 | Comp.
38 | Civil | 25.1.06 | 7.10.05 | Imp of drainage system by coverring of drain from sukha vihar road corssing to Jagat puri drain in East Baldev park in C-78/42 | 637502 | XIV | 78 | 643/27.03.06/EE-XIV | M/s R.P Const.Co | 12.05.06 | 20.06.06 | 636956 | Comp.
39 | Civil | 25.1.06 | 7.10.05 | Imp of road by pdg mastic Ashphalt from H.No-83 Old Anarkali to Ram Nagr road in Old Anarlali in C-78/42 | 544501 | XIV | 78 | 518/21.02.06/XIV | M/s Man Mohan Singh Wadhwa | 22.03.06 | 31.03.06 | 544501 | Comp.
40 | Civil | 25.1.06 | 24.10.05 | Imp to gali by pdg c.c. pave from H.No A-1 to A-10in Lamman Park in C-78/2 | 175000 | XIV | 78 | 666/28.03.06/EE-XIV | M/s Rajeev Kaushik | 22.06.06 | 17.08.06 | 175000 | Comp.
41 | Civil | 25.1.05 | 24.10.05 | Imp to Shiv kala Mandir road by pdg Mastic Ashphalt in Ram Nagr in C-78/41 | 351426 | XIV | 78 | 588/13.03.06/EE-XIV | M/s Balaji & Associates | 13.04.06 | 20.06.06 | 350160 | Comp.
42 | Civil | 25.1.05 | 24.10.05 | Imp of Parwana road from Swami Dayanand Marg to H.No F-17 , Jagathpuri by pdg Mastic Ashphalt in C-78/42 | 543035 | XIV | 78 | 592/13.03.06/EE-XIV | M/s Balaji & Associates | 13.04.06 | 22.06.06 | 542342 | Comp.
43 | Civil | 25.1.06 | 8.11.05 | Imp to road by pdg Mastic Asphalt from H.No A-124 to H.No 61 South Anarkali Extn in C-78/42 | 440955 | XIV | 78 | 589/13.03.06/EE-XIV | M/s Balaji & Associates | 27.03.06 | 21.06.06 | 440841 | Comp.
44 | Civil | 25.1.06 | 8.11.05 | Imp to side berm by pdg c.c. from H.No 188 south Anarkali to 27/4 South Anarkali Extn in C-78/42 | 199211 | XIV | 78 | 551/10.03.06/EE-XIV | M/s Ishwar Associates | 23.03.06 | 18.05.06 | 198514 | Comp.
45 | Civil | 30.1.06 | 24.10.05 | Imp to side berm by pdg c.c. from H.No 152 Old Anarkali to Ram Nagr Nath road in C-78/41 | 297387 | XIV | 78 | 633/20.03.06/EE-XIV | M/s Amit Associates | 25.04.06 | 20.06.06 | 297190 | Comp.
46 | Civil | 30.1.06 | 24.10.05 | Imp to lane by pdg c.c.along H.No 17/9 in Ram Nagr in C-78/42 | 115627 | XIV | 78 | 641/24.03.06/EE-XIV | M/s Lalit Sharma | 08.04.06 | 17.05.06 | 115429 | Comp.
|  |  |  | Total | 17170552 | [6 empty] | 16373477

## 43-
STATUS REPORT OFMLA FOR THE YEAR 2005-06
MUNICIPAL CORPORATION OF DELHI
Shahdra South
|  | Name Of MLA |  | Sh. Naseeb singh | AC-43 |  | year 2005-06 |  | Allocation | 173 |  |  | Dated:-
|  | Name of Constituency |  | Viswas Nagar
|  | Ward Nos and Names |  | C-79 Preet Vihar C-80 Vihwas Nagar
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14
1 | Civil | 24.6.05 | 17.6.05 | Imp to road metalling & Premixing from J.J. Slum office to 18 Qtr road in W.W.80/AC43.Sh.S | 199450 | XI | 80 | 158/4.8.05/EE-XI | M/s Alakar builder | 13.8.05 | 15.10.05 | 199450 |  |  | Comp.
2 | Civil | 24.6.05 | 17.6.05 | Imp to road by metalling & premixcing on 18 Qtr road from Pandav road to Viswas road in w.NO 80/Ac43 sh.S | 199300 | XI | 80 | 157/4.8.05/EE-XI | M/s Deepak Associates | 13.8.05 | 2.8.05 | 198437 |  |  | Comp.
3 | Civil | 8.7.05 | 17.6.05 | Imp to back lane by c.c. pav. HNO-438 to 452 , 408 to 411 ,403 to 392 and 365 in c. block Yojha Vihar in w.no 80/AC-43/Sh.S | 455000 | XI | 80 | 232/19.12.05/EE-XI | M/s Vinod Const.Co | 20.12.05 | 20.02.06 | 396119 |  |  | Comp.
4 | Civil | 8.7.05 | 17.6.05 | Imp of road by Premixcing ner HNO 205 to 226 ,105 to 160 100 to 120 and jain Mandir to 227 in suraj Mal Vihar A block w.no 80 Sh.S | 347100 | XI | 80 | 222/12.12.05/EE-XI | M/s Kapil Const.CO | 21.12.05 | 20.02.06 | 315526 |  |  | Comp.
5 | Elect | 18.7.05 | 26.5.05 | P/o lighting arrangement at Apprached road to New Sanjay Amar colony near working womens Hostel in W.no 80 under Sh.s. Zone. | 73999 | EEE-V | 80 | 79/27.12.05/EE(E)V | M/s Illuminator cuircuters | 02.01.06 | 03.02.06 | 61372 |  |  | Comp.
6 | Elect | 5.9.05 | 10.8.05 | P/o lighting arrangement in Kasturba Gandhi park and 18 Qtr Chowk in W.NO-80 | 73691 | EEE-V | 80 | 251/14.03.06/EE(E)-IV | M/s Forward Engineers | 16.03.06 | 30.03.06 | 73691 |  |  | Comp.
7 | Civil | 5.9.05 | 10.8.05 | Imp to 18 Qtr link road near Kasturba Nagr drain by pdg RMC pur in vishwas Ngr w.no 80/Ac-43/ShS | 639200 | XI | 80 | 248/26.12.05/EE-XI | M/s Jindal Builders | 31.12.05 | 03.04.06 | 523265 |  |  | Comp.
8 | Civil | 5.9.05 | 10.8.05 | Imp to gali no 17 by pdg c,c pav and drain in Bhikam singh coloney in W.No 80/AC-43 Sh.S | 504300 | XI | 80 | 209/01.12.05/EE-XI | M/s Bansal Builders | 05.12.05 | 09.02.06 | 357434 |  |  | Comp.
9 | Civil | 5.9.05 | 10.8.05 | Imp to road along ( K. Nagar drain ) Nalla side from Patel gali to Bagichi gali by pdg RMC and drain in vishwas nagar in W.No 80/AC 43 sh.S | 688900 | XI | 80 | 404/10.03.06/EE-XI | M/s Anil Kumar Sharma | 15.05.06 | 13.06.06 | 673004 |  |  | Comp.
10 | Civil | 5.9.05 | 10.8.05 | Imp to road along ( K. Nagar drain ) Nalla side from Patel gali by pdg RMC and drain in vishwas nagar in W.No 80/AC 43 sh.S | 688200 | XI | 80 | 230/19.12.05/EE-XI | M/s M.G Goel Const.Co | 20.12.05 | 24.03.06 | 559831 |  |  | Comp.
11 | Civil | 5.9.05 | 10.8.05 | pdg & laying ready wise corner on lane near D block Vivek Vihar market in w.No 80/AC43/Sh.S | 300000 | XI | 80 | 228/19.12.05/EE-XI | M/s M.G Goel Const.Co | 21.12.05 | 31.03.06 | 242953 |  |  | Comp.
12 | Civil | 5.9.05 | 10.8.05 | Imp to lane parallel to Kasturba Nagr drain farom gali no 5 to 15 in Bhikam singh coloney by pdg c.c. pave & drain in w. no 80/ AC-43 Sh.S | 599800 | XI | 80 | 198/01.12.05/XI | M/s Mittal Const.CO | 10.12.05 | 09.02.06 | 451308 |  |  | Comp.
13 | Civil | 5.9.05 | 10.8.05 | Imp to lanes in Tosh factory (P.R.S) near Mahender hs between karkari road and gali no 3 by ready mise conc & drain in Vishwas Nagr in w.No-80 AC-43/ShS | 699500 | XI | 80 | 367/28.02.06/XI | M/s Baldev Raj Gupta | 28.02.06 | 03.03.06 | 654971 |  |  | Comp.
14 | Civil | 5.9.05 | 10.8.05 | Imp to lane to connectling link from gali no 3 to Karkai road ( near tas factory ) by RMC & drain in Vishwan Nagar in W.No-80 /AC 43/ Sh.S | 699400 | XI | 80 | 488/31.03.06/EE-XI | M/s Wadhwan & Co. | 03.04.06 | 06.07.06 | 627884 |  |  | Comp.
15 | Civil | 5.9.05 | 10.8.05 | Imp to lanes in Tasfactory ( V.R.S. ) near H.No 1/190 bet Karkari road and gali no-3 by RMC & drain in Vishwan Nagar in W.No 80/AC43/Sh.S | 699000 | XI | 80 | 337/30.01.06/EE-XI | M/s Wadhwan & Co. | 04.02.06 | 07.05.06 | 629220 |  |  | Comp.
16 | Civil | 5.9.05 | 10.8.05 | Imp to road along ( K.Nagr drain ) Nalla side from Bagichi gali to Nellur gali by pdg RMC & drain in Vishwas Nagar in W.No 80/AC-43/Sh.S | 672300 | XI | 80 | 403/10.03.06/EE-XI | M/s Anil Kumar Sharma | 11.03.06 | 18.06.06 | 648959 |  |  | Comp.
17 | Civil | 26.9.05 | 17.6.05 | Pro. And fixing precast RCC slab grating on 30' and 50' road in c block Anand Viahr in w.No-80/AC-43 Sh.S | 1705400 | XI | 80 | 336/30.01.06/XI | M/s Man Mohan Singh wadhwa | 08.02.06 | 02.06.06 | 1144996 |  |  | Comp.
18 | Civil | 26.9.05 | 17.9.05 | P/f Precent RCC Slab grating on 30' road at B block Anand vihar in W-80/AC-43/Sh.S | 685600 | XI | 80 | 487/31.03.06/EE-XI | M/s Wadhwan & Co. | 31.05.06 | 04.06.06 | 531153 |  |  | Comp.
19 | Civil | 8.11.05 | 17.6.05 | Pro & Fix preent RCC slab grating on 30' to 45' prc "A" block Anand Vihar in W.Np 80/ Sh.S | 1302400 | XI | 80 | 90/29.05.06/EE-XI | M/s Man Mohan Singh wadhwa | 26.06.06 | 12.07.06 | 771908 |  |  | Comp.
20 | Civil | 10.10.06 | 29.8.05 | Imp/Stg of road inchitra Vihar in Ac-43 by pdg B.M.& M.SS | 1152000 | Sh (S)Prj. | 79 |  |  |  |  | 1152000
21 | Civil | 10.10.06 | 29.8.05 | Imp/stg of road in AGCR Enclave in AC-43 by pdg B.M & M.SS | 1626000 | Sh (S)Prj. | 79 |  |  |  |  | 1626000
22 | Civil | 10.10.06 | 29.8.05 | Imp/stg of main road in Dayanand Vihar in AC-43 by pdg B.M. & MSS | 100500 | Sh (S)Prj. | 79 |  |  |  |  | 100500
23 | Civil | 10.10.06 | 29.8.05 | Imp/stg of road in "A" block in Preet Vihar in AC-43 by pdg B.M to MSS | 316000 | Sh (S)Prj. | 79 | 34/07.06.06/EE(Pr.)Sh.South | M/s Echo Builders | 21.06.06 | P | 316000 |  |  | In Prog.
24 | Civil | 10.10.06 | 29.8.05 | Imp/stg of road in in East Guru Anged Nagr in AC-43 by pdg B.M to MSS | 881000 | Sh (S)Prj. | 79 |  |  |  |  | 881000
25 | Civil | 10.10.06 | 29.8.05 | Imp/ Stg of road in "E" block Preet Vihar in AC-43 by pdg BM & MSS | 1038400 | Sh (S)Prj. | 79 |  |  |  |  | 1038400
26 | Civil | 10.10.06 | 29.8.05 | Imp/stg of road in Swasthya Vihar in AC-43 by pdg B.M.& MSS | 915000 | Sh (S)Prj. | 79 |  |  |  |  | 915000
27 | Civil | 10.1.06 | 25.8.05 | Const of Culvert near Vivekanand Public School, Anand Vihar AC-43/Sh(s) | 453400 | Sh (S)Prj. | 80 | 21/25.04.06/EE(Pr.)/Sh.South | M/s Deep Builders | 28.04.06 | 02.08.06 | 338911 |  |  | Comp.
28 | Civil | 10.1.06 | 29.8.05 | Imp/stg of road in Priya Enclave in Ac-43 by pdg B.M & MSS | 614000 | Sh (S)Prj. | 79 | 34/07.06.06/EE(Pr.)Sh.South | 21.06.06 | P |  | 614000 |  |  | In Prog.
|  |  |  | Total | 18328840 | [6 empty] | 16043292

## 44-
STATUS REPORT OF MLA FOR THE YEAR 2005-06
MUNICIPAL CORPORATION OFDELHI
Shahdra South
|  | Name Of MLA |  | Dr. Narender Nath | AC-44 |  | year 2005-06 |  | Allocation |  | 200 |  | Dated:-
|  | Name of Constituency |  | Shahdra
|  | Ward Nos and Names |  | 81 Shadra 82 Viviek Vihar
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Divi. | W.no | Work order no with date | Name of Agencys | D.O.S. As per agreement | D.O.C. As per agreement | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14
1 | Civil | 8.9.05 | 17.8.05 | Imp to lane by pdg RMC near B pocket and B pocket market in Dilshad Garden in C-82/AC-44 | 197000 | XI | 82 | 215/01.12.05/EE-XI | M/s Jindal Builders | 05.12.05 | 02.02.06 | 197000 |  |  | Comp.
2 | Civil | 8.9.05 | 17.8.05 | IMp to lane and drainage system near H.No E-140,110 ,14 and E-56 by RMC and Culvert in E block Jhilmil coloney inC-82/AC-44 | 197500 | XI | 82 | 190/17.11.05/EE-XI | M/s Deepak Associates | 21.11.05 | 12.01.06 | 195924 |  |  | Comp.
3 | Civil | 8.9.05 | 17.8.05 | Imp to lanes by RMc near H.NO 121, park 145,191 169,205 .217 240,243 in Gobikd Khand in c-82/ AC-44 | 195100 | XI | 82 | 191/17.11/05/EE-XI | M/s Vinod Const.Co | 23.11.05 | 22.02.06 | 194914 |  |  | Comp.
4 | Civil | 19.9.05 | 17.8.05 | Imp of road by M/P from B-13/1 to B-23 in Jhilmil Ind. Area in C-82/AC-44 | 551700 | XI | 82 | 307/06.01.06/ | M/s Narender Const. | 05.01.06 | 08.03.06 | 432069 |  |  | Comp.
5 | Civil | 21.9.05 | 31.5.05 | Imp to portion of lanes in 7 and 8 ( Idgarh road to Mani Ram Mandir road) by pdg c.c. flooring ijn Bola Nath Nagr | 311072 | XI | 81 | 419/14.03.06/EE-XI | M/s Shankar Associates | 16.03.06 | 31.08.06 | 298323 |  |  | Comp.
6 | Civil | 21.9.05 | 24.8.05 | Imp to lane by pdg RMC drain in front at Lal Bekri/ Prop w.no- A 100 in Tejab Mill Bhola Nath Nagr C-81/ AC-44 | 469269 | XI | 81 | 411/14.03.06/EE-XI | M/s Hans Kumar Jain | 15.03.06 | 15.06.06 | 469186 |  |  | Comp.
7 | Civil | 21.9.05 | 24.8.05 | Imp of road side berms & drain at Idgarh road ( from gai no-5 towards road w-57) in Behari coloney C-81/AC-44 | 181227 | XI | 81 | 341/30.01.06/EE-XI | M/s Bhagwati Const.Co. | 25.05.06 | 22.09.06 | 181227 |  |  | Comp.
8 | Civil | 21.9.05 | 24.8.05 | Imp of portion of gali no 7 and nearby in Behari coloney by pdg c.c. flooring in C-81/AC-44 | 197100 | XI | 81 | 340/30.01.06/EE-XI | M/s Bhagwati Const. | 06.02.06 | 03.05.06 | 169652 |  |  | Comp.
9 | Civil | 21.9.05 | 16.9.05 | Imp to Ajay Mandichowki by pdg c.c pav in Shahdra vill C-81 | 257100 | XI | 81 | 333/27.01.06/XI | M/s Shankar Associates | 28.01.06 | 29.03.06 | 250198 |  |  | Comp.
10 | Civil | 21.9.05 | 16.9.05 | Imp to diff lanes by c.c pav adj to H.No 800 near gali no 5 in Jwala Nagr in C-81/AC-44 | 243700 | XI | 81 | 334/27.01.06/EE-XI | M/s Shankar Associates | 03.02.06 | 31.03.06 | 239859 |  |  | Comp.
11 | Civil | 21.9.05 | 16.9.05 | Imp to lane by pdg c. c pave adj to prop no B-115 in Janta coloney circular road Shadra C-81 AC-44 | 248900 | XI | 81 | 346/30.01.06/EE-XI | M/s Bhagwati Const.Co. | 04.02.06 | 24.04.06 | 231380 |  |  | Comp.
12 | Civil | 21.9.05 | 16.9.05 | Imp to portion of lane by c.c. pav adj to H.No R-44 in Behari Coloney C-81/AC-44 | 95000 | XI | 81 | 345/30.01.06/EE-XI | M/s Bhagwati Const.Co. | 06.02.06 | 19.04.06 | 92066 |  |  | Comp.
13 | Civil | 21.9.05 | 16.9.05 | Imp to lane by c.c pav adj to prop no P-141 in Behari Coloney C-81/AC-44 | 198700 | XI | 81 | 317/16.01.06/XI | M/s Shankar Associates | 23.01.06 | 10.03.06 | 191354 |  |  | Comp.
14 | Civil | 21.9.05 | 19.9.05 | Imp to lane by prov c.c. adj to prop w 64/4K/1 in Teliwara in Shahdra vill C-81/AC-44 | 99000 | XI | 81 | 316/16.01.06/XI | M/s Shankar Associates | 21.01.06 | 11.03.06 | 99000 |  |  | Comp.
15 | Civil | 21.9.05 | 19.9.05 | Imp to lane adj to Prop no 413 438 and Vatsalya temple by pdg c.c. pav in Jwala Nagar C-81/AC-44 | 319668 | XI | 81 | 280/04.01.06/EE-XI | M/s Guru Kirpal Enter. | 08.01.06 | 03.04.06 | 318831 |  |  | Comp.
16 | Civil | 21.9.05 | 19.9.05 | Imp to lane by pdg c,c pave adj to Prop no 4/1581 and 4/1788 in Mahavir block Shadra C-81/AC-44 | 303400 | XI | 81 | 260/26.12.05/XI | M/s Satish & Bros | 27.12.05 | 10.02.06 | 303400 |  |  | Comp.
17 | Civil | 21.9.05 | 15.9.05 | Imp to lane by c,c pav adj to H.No 104 B tejab mill and gali no 14 ( Idgarh roadto Satgarah road ) in Bhole Nath Nagr. | 247087 | XI | 81 | 362/13.02.06/EE-XI | M/s Shankar Associates | 14.02.06 | 08.06.06 | 236325 |  |  | Comp.
18 | Civil | 21.9.05 | 19.9.05 | Imp to drain & berms at road in back of Old Zonal office forash Bazzr Shadra C-81 | 238700 | XI | 81 | 273/28.12.05/XI | M/s Shankar Associates | 02.01.06 | 08.03.06 | 234860 |  |  | Comp.
19 | Civil | 21.9.05 | 22.8.05 | Imp to lane by pdg C,C. flooring adj to Prop NO 27/94 near Triangula park Jwalal Nagr behind MC School Mukerh Nagr Jwala Nagr C-81/AC-44 | 241400 | XI | 81 | 335/27.01.06/EE-XI | M/s Shankar Associates | 03.02.06 | 29.03.06 | 237085 |  |  | Comp.
20 | Civil | 21.9.05 | 19.9.05 | Imp to Chowk and lane adj P.N.B back Gujju Katra by c.c. pav in Shadra Vill C-81/AC-44 | 297608 | XI | 81 | 426/14.03.06/EE-XI | M/s Shankar Associates | 01.08.06 | 6.11.06 | 283353 |  |  | Comp.
21 | Civil | 21.9.05 | 19.9.05 | Imp to portion of gali no 3 ( adj H.No 4/2754) by pdg c.c. flooring in Behari Coloney C-81/AC-44 | 314712 | XI | 81 | 422/14.03.06/EE-XI | M/s Shankar Associates | 15.07.06 | 24.11.06 | 305003 |  |  | Comp.
22 | Civil | 21.9.05 | 22.8.05 | Imp to portion of Idgarh road ( from gai no 5 to 4/2409 ) by pdg M/P in Behari Coloney in W-81 AC-44 | 301138 | XI | 81 | 433/17.03.06 | M/s Aarkaj Consts | 23.03.06 | 17.08.09 | 300654 |  |  | Comp.
23 | Civil | 21.9.05 | 22.8.05 | Imp to portion of gali o 15 ( H.No 280) in Bhola Nath Nagr and gali no 7 ( H.No 4/3251) in Behari coloney by pdg c.c. flooring in w-81 Sh.S | 371174 | XI | 81 | 368/28.02.06/EE-XI | M/s Shankar Associates | 06.03.06 | 10.07.06 | 353452 |  |  | Comp.
24 | Civil | 21.9.05 | 22.8.05 | P/F M.s Crossings at diff drain corssing in Bhola Nath Nagr & Behari coloney C-81 | 99400 | XI | 81 | 347/30.01.06/EE-XI | M/s Bhagwati Const. | 03.02.06 | 31.03.06 | 94999 |  |  | Comp.
25 | Civil | 21.9.05 | 22.8.05 | Imp to lanes by c.c. flooring adj to H.No 319 & 475 in Jwala Nagr w.no-81/AC-44 | 199348 | XI | 81 | 239/19.12.05/XI | M/s Mayur Enterprises | 23.12.05 | 20.03.06 | 198808 |  |  | Comp.
26 | Civil | 21.9.05 | 22.8.05 | Imp to lanes by pdg c.c flooring adj indira park ,MC pry School in Jwala Nagr W.noi 81/AC-44 | 199014 | XI | 81 | 219/12.12.05/XI | M/s Mani Blds. | 19.12.05 | 08.03.06 | 198567 |  |  | Comp.
27 | Civil | 21.9.05 | 22.8.05 | Imp to roads by pdg premixing adk to P no 1/17 and near by in Shalimar park Shadrah C-81 | 196714 | XI | 81 | 243/26.12.05/XI | M/s Vikas Jain | 02.01.06 | 27.02.06 | 195533 |  |  | Comp.
28 | Civil | 21.9.05 | 22.8.05 | Imp to road by premixing adj to P no 94/7A/4 near Amar Ashram and Triangula park in jwala nagr in C-81 | 192909 | XI | 81 | 244/26.12.05/EE-XI | M/s Laxman Sharma | 02.01.06 | 27.02.06 | 192230 |  |  | Comp.
29 | Civil | 21.9.05 | 22.8.05 | Re of drian in lanes prop w 460/B/4 in Mahabir block in Shadara c-81 | 198500 | XI | 81 | 220/12.12.05/XI | M/s Sharma & Sharma Const. | 18.12.05 | 08.02.06 | 198500 |  |  | Comp.
30 | Civil | 21.9.05 | 22.8.05 | Const of RCC Culvert under Rly bridge at Bhola Nath Nagr road C-81/44 , Bhola Nath Nagr. | 137400 | XI | 81 | 309/06.01.06/EE-XI | M/s Manoj Kumar | 12.01.06 | 08.06.06 | 135586 |  |  | Comp.
31 | Civil | 21.9.05 | 24.8.05 | Imp to D/s near Status of Maharaja Aggarsenji in Ajay Mandir Shadard vill C-81 | 184400 | XI | 81 | 274/28.12.05/XI | M/s Shankar Associates | 02.01.06 | 03.03.06 | 179212 |  |  | Comp.
32 | Civil | 21.9.05 | 20.9.05 | Imp to lane by pdg c.c. pave adj to prop 438 in Mohalla mahavn Shahdra villa C-81 AC-44 | 257900 | XI | 81 | 272/28.12.05/XI | M/s Shankar Associates | 02.01.06 | 08.03.06 | 252644 |  |  | Comp.
33 | Civil | 21.9.05 | 27.6.05 | Imp to lane by pdg c.c. flooring adj to P/W 422 & 429 Markara Kuan and 4/20 in Pathan piura in Shahdra C-81 /AC-44 | 192784 | XI | 81 | 210/01.12.05/XI | M/s Kirti Associates | 07.12.05 | 09.02.06 | 192784 |  |  | Comp.
34 | Civil | 21.9.05 | 27.6.05 | Imp to gali no 2 in Mukesh Nagr and lanes adj to H.No 95 ,401 loni gate Shahdra in C-81 | 168706 | XI | 81 | 238/19.12.05/XI | M/s Appear Const. & Engg. | 23.12.05 | 24.02.06 | 167827 |  |  | Comp.
35 | Civil | 21.9.05 | 16.9.05 | Imp to gali no 4 and lane adj to Nalah in Shalimar park by pdg c.c. pav in C-81 AC-44 | 310174 | XI | 81 | 421/14.03.06/EE-XI | M/s Shankar Associates | 20.03.06 | 17.07.06 | 297837 |  |  | Comp.
36 | Civil | 21.9.05 | 22.8.05 | Imp to approach of Teliwara along railway line storing from railway bridge at Bhola Nath Nagr road in Teliwara Shahdra C-81 | 414945 | XI | 81 | 417/14.03.06 | M/s Shankar Associates | 14.08.06 | 13.02.07 | 393824 |  |  | Comp.
37 | Civil | 21.9.05 | 24.8.05 | Imp to lane by pdg c.c. flooring adj to Prop no 152/7/215 and 1/155 etc Mohalla Jwahar, Shahdra vill in C-81 | 290577 | XI | 81 | 418/14.03.06/EE-XI | M/s Shankar Associates | 21.03.06 | 8.02.07 | 275475 |  |  | Comp.
38 | Civil | 21.9.05 | 24.8.05 | Imp to portion of lane no 6 ( Mani ram mandir road to Shiv Jharkhandi mandir road and gali no 9 from school lane to Maharaja Aggarsen marg by c.c. in Bhola Nath Nagr. | 196572 | XI | 81 | 420/14.03.06/EE-XI | M/s Shankar Associates | 18.03.06 | 28.08.06 | 181050 |  |  | Comp.
39 | Civil | 21.9.05 | 31.5.05 | Imp to portion of lanes w 3,4,5,6,9, adj to Satgarah road in Bhola Nath Nagr by pdg c.c. flooring C-81 | 288723 | XI | 81 | 386/02.03.06/EE-XI | M/s Shankar Associates | 09.03.06 | 28.08.06 | 277857 |  |  | Comp.
40 | C.S.E | 24.11.05 | 18.11.05 | P/l of RCC Pipe line along Rly Ember in Mukesh Ngr Sh (s) | 672000 | CSE Sh (S) | 82
41 | C.S.E | 24.11.05 | 18.11.05 | Imp of Nalla along block N& M Dilshad Garden in W.No-82 sh (s) | 508600 | CSE Sh (S) | 82 | 106/14.03.06/EE(CSE)South | M/s Sachin Const.Co | 02.05.06 | P | 326418 |  |  | In Prog.
42 | Civil | 28.11.05 | 28.10.05 | Imp to lane adj lane to Shp NO-1697 by pdg c.c. pave in Mahabir Block Sh C-81 | 266600 | XI | 81 | 436/17.03.06/EE-XI | M/s Aarkaj Consts | 18.03.06 | 09.06.06 | 199740 |  |  | Comp.
43 | Civil | 28.11.05 | 28.10.05 | Imp to Shri Gopal Shrama Marg by pdg bitumen Mastic in Mohalla Mehram Sh. Vill C-81 Ac-44 | 548700 | XI | 81
44 | Civil | 28.11.05 | 28.10.05 | Imp to drainage in lane adj to Prop No 106/6 in Teliwara in Sh in c-81/ AC-44 | 58900 | XI | 81 | 434/17.03.06/EE-XI | M/s Aarkaj Consts | 22.03.06 | 22.05.06 | 46438 |  |  | Comp.
45 | Civil | 28.11.05 | 28.10.05 | Imp to lane portion by pdg CC pav adj to H.No 753 Jwala Nagr in C-81/ AC-44 | 76760 | XI | 81 | 104/26.06.06/EE-XI | M/s Aspiration Builders | 27.06.06 | 28.08.06 | 76583 |  |  | Comp.
46 | Civil | 28.11.05 | 28.10.05 | Imp to lane by c.c. pav adj to Prop No 4/2918 Sri Ram Coloney Behari Coloney C-81/ AC-44 | 195400 | XI | 81 | 435/17.03.06/EE-XI | M/s Aarkaj Consts | 23.03.06 | 25.05.06 | 145416 |  |  | Comp.
47 | Civil | 28.11.05 | 28.10.05 | Imp to portion of gali no 6 y pdg c.c. flooring in Jwala Nagr C-81 | 450588 | XI | 81 | 423/14.03.06/EE-XI | M/s Surender Kumar Garg | 20.03.06 | 22.07.06 | 448966 |  |  | Comp.
48 | Civil | 28.11.05 | 28.10.05 | Imp to lane by c.c pave adj to prop no 700/5 in Tejab mill Bhola Nath Nagr in C-81/ AC-44 | 339300 | XI | 81 | 425/14.03.06/EE-XI | M/s A.S.Const.Co | 16.03.06 | 08.06.06 | 245041 |  |  | Comp.
49 | Civil | 12.12.05 | 21.10.05 | Imp to road by M/P hear DDA block Mpl school Gurudwara interline road etc in Dilshed Garden in c-82/44 Sh (s) Zone. | 370000 | XI | 81 | 448/17.03.06/EE-XI | M/s Beldev Raj Gupta | 18.03.06 | 07.04.06 | 324847 |  |  | Comp.
50 | Civil | 12.12.05 | 21.10.05 | Imp to lanes by pdg RMC adj to park near flat No-55,68 etc in B pkt Dilshed Garden in C-82/AC-44 Sh (s) Zone | 386300 | XI | 82 | 449/17.03.06/EE-XI | M/s Lalita Associates | 18.03.06 | 10.05.06 | 317525 |  |  | Comp.
51 | Civil | 10.10.06 | 21.12.05 | Imp to lane & links by c.c. pav adj to Shop No 240 in Jwala Ngar in C-81 AC-44 | 211138 | XI | 81 | 35/21.04.06/EE-XI | M/s Y.K Builders | 26.04.06 | 28.07.06 | 211138 |  |  | Comp.
52 | Civil | 10.1.06 | 26.12.05 | Imp to lane by pdg c.c. pav adj to Shop no P-157 and 2668 in beheri (by inC-81)AC-44 | 214218 | XI | 81 | 34/21.04.06/EE-XI | M/s Y.K Builders | 24.04.06 | 11.07.06 | 212368 |  |  | Comp.
53 | Civil | 20.03.06 | 26.12.05 | Imp of lane by pdg cc pevement near veer Abhimanyu park in Beherkly C-81 Ac-44 | 352236 | XI | 81 | 102/08.06.06/EE-XI | M/s Guru Kirpa Enter. | 08.06.06 | 08.08.06 | 350774 |  |  | Comp.
54 | Civil | 20.03.06 | 26.12.05 | Imp to portion of gali no 13 by pdg CC pevement in Bhola Nath Nagar C-81 Ac-44 | 437637 | XI | 81 | 101/08.06.06/EE-XI | M/s Guru Kirpa Enter. | 14.06.06 | 14.11.06 | 434314 |  |  | Comp.
55 | Civil | 20.03.06 | 26.12.05 | Imp of portion of lane no.11 *14 (Shiv Jharkhendi Road to Mahiram Mandir Marg) by pdg CC pevement in Bhola Nath Nagar in C-81 Ac-44 | 345192 | XI | 81 | 100/08.06.06/EE-XI | M/s Guru Kirpa Enter. | 15.06.06 | 24.08.06 | 344403 |  |  | Comp.
56 | Civil | 20.03.06 | 06.02.06 | Imp to lanes near Ram Lila ground Shiv Mandir and links of gali no-6 in Jwala Nagar by pdg cc pevement in C-81 Ac-44 | 261934 | XI | 81 | 99/08.06.06/EE-XI | M/s Guru Kirpa Enter. | 09.06.06 | 04.08.06 | 261661 |  |  | Comp.
57 | Civil | 20.03.06 | 06.02.06 | Imp to Hari Mandir gali by pdg cc pav. In Jwala Nagar C-81 | 430160 | XI | 81 | 94/08.06.06/EE-XI | M/s Kapil Cosnt.Co | 14.6.06 | 16.10.06 | 430142 |  |  | Comp.
58 | Civil | 20.03.06 | 06.02.06 | Imp to lane by pdg CC pav. Adj. CSE office Shalimar park in C-81, AC-44 | 184636 | XI | 81 | 95/08.06.06/EE-XI | M/s Surender Kumar Garg | 14.06.06 | 04.08.06 | 183883 |  |  | Comp.
59 | Civil | 20.03.06 | 06.02.06 | Imp to drain to road Adj. To property no 4/1600 in mahavir block shahdara C-81 /Ac-44 | 232108 | XI | 81 | 98/08.06.06/EE-XI | M/s Guru Kirpal Enter. | 15.06.06 | 06.08.06 | 231566 |  |  | Comp.
60 | Civil | 20.03.06 | 06.02.06 | Imp to lanes by pdg CC pav near school in Dalahi Mohalla Mahavir block Shahdara C-81 ac-44 | 354978 | XI | 81 | 97/08.06.06/EE-XI | M/s Guru Kirpal Enter. | 09.06.06 | 15.09.06 | 353710 |  |  | Comp.
61 | Civil | 20.03.06 | 06.02.06 | Imp to back lane and links of Shiv Shakti Temple in Jwala Nagar by CC Pav. In C-81 | 242652 | XI | 81 | 96/08.06.06/EE-XI | M/s Guru Kirpal Enter. | 12.06.06 | 04.09.06 | 240478 |  |  | Comp.
62 | Civil | 20.03.06 | 06.02.06 | Imp of circular road by pdg CC pav. In Shahdara vill C-81 Ac-44 | 313047 | XI | 81 | 103/08.06.06/EE-XI | M/s Guru Kirpal Enter. | 14.06.06 | 31.08.06 | 310358 |  |  | Comp.
|  |  |  | Total | 17058405 | [6 empty] | 14943617