## Sh. Jile Singh
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06
Municipal Corporation of Delhi
CIVIL LINE ZONE
|  | Name Of MLA |  | Sh.Jile Singh | AC-55 |  | year 2005-06 |  | Allocation | 190
|  | Name of Constituency |  | Bhalswa
|  | Ward Nos and Names |  | C.103 , Bhalswa , Jahangir Puri C-104 , Burari
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agency | D.O.S. As per | D.O.C. As per | First Running | Second Running | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  | 13 | 16
1 | Civil | 9.5.05 | 6.5.05 | Imp to lane by RMC from Deergesh Devi Hs to 25 foota road in Parvatiya Anchal Sant Nagar Village , Burari C-104/CLZ | 1718560 | EE-XII | 104 | 63/12.05.06/EE-XII | M/s K.K Const.Co | 15.05.06 | P |  |  | 1712396 | In Prog.
2 | Civil | 9.5.05 | 6.5.05 | Imp to lane by RMC from Burari road to Paran Chug to Electric transfermer in Village I Grahimpur C-104/CLZ (Rs 1310700/-) | - | EE-XII | 104 | Work cancel as desired by area MLA vide letter no. NIL datd 30.9.05 and recommanded by E-IN-C dated 20.10.05
3 | Civil | 9.5.05 | 6.5.05 | C/o drain from Burari Raod to Durgesh Devi to 25 foota road in Parvatiya Anchal Sant Nagr Village Burari C-104/CLZ | 1317441 | EE-XII | 104 | 405/07.11.05/EE-XII | M/s A.K.& Co. | 09.11.05 | 08.11.06 |  |  | 1317381 | Comp.
4 | Civil | 16.5.05 | 17.2.05 | C/o drain and lane by B/P from Mange Ram Hs to Company and Yasim Hs to Arora Hs in Burari Garhi C-104/CLZ | 188300 | EE-XII | 104 | 169/18.07.05/EE-XII | M/s Globe CONst CO. | 21.07.05 | 26.10.05 |  |  | 187529 | Comp.
5 | Civil | 3.6.05 | 2.6.05 | Imp of drain from Jawala Tent Hs to front of Police Post Mukand pur C-104 CLZ | 195350 | EE-XII | 104 | 198/22.7.05 | M/sJyoti Const | 1.8.05 | 2.9.05 |  |  | 195159 | Comp.
6 | Civil | 24.6.05 | 1.6.05 | Imp to Phivni road by c.c. from Bhupender Rana to Babool tree in village Kadipur in c-104/CLZ | 179885 | EE-XII | 104 | 138/4.7.05 | M/s Saurabh Const | 4.7.05 | 30.7.05 |  |  | 179841 | Comp.
7 | Civil | 24.6.05 | 1.6.05 | Imp to Phirni road by c.c. from Ravinder to Samsher in village Kadepur C-104/CLZ | 198806 | EE-XII | 104 | 167/18.7.05/XII | M/s Globe CONst CO. | 20.7.05 | 24.9.05 |  |  | 198534 | Comp.
8 | Civil | 24.6.05 | 1.6.05 | Imp to lane by c.c. in block B from H.NO B-265 to H.NO B-736 in Jahangir Puri colony C-103, CLZ | 197500 | EE-XII | 103 | 223/22.7.05 | M/s Sarout Const Co. | 23.7.05 | 29.9.05 |  |  | 197422 | Comp.
9 | Civil | 13.7.05 | 17.2.05 | C/o drain from R.K. Bulders to Rajesh Hs in c block Amrit vihar village Nathu pura c-104/CLZ | 556947 | EE-XII | 104 | 247/5.8.05/XII | M/s jaswant singh Dabas | 14.8.05 | 14.11.05 |  |  | 543539 | Comp.
10 | Civil | 13.7.05 | 17.2.05 | C/o Drain from Ram Kishan to Omkar (flood Nallah) in C block Interprastha Colony Village Nathu Pura C 104 CLZ | 545192 | EE-XII | 104 | 248/5.8.05 | M/s Jaswant Singh Dabas | 14.8.05 | 18.10.05 |  |  | 544408 | Comp.
11 | Civil | 14.7.05 | 17.2.05 | C/o drain from Ramdas to Bala Ram ( flood Nallah) in B- block , Inderprastha Coloney village Nathu pura c-104/CLZ | 581110 | EE-XII | 104 | 270/16.08.05/EE-XII | M/s Bhaiji.Contractor & Supplier | 25.08.05 | 24.012.05 |  |  | 579051 | Comp.
12 | Civil | 2.8.05 | 1.6.05 | Imp to lane by brick flooring from flood road to Marshal Modern School Milan vihar Jharoda in c-104/CLZ | 502320 | EE-XII | 104 | 421/17.11.05/XII | M.s Dinesh const co. | 19.11.05 | 2.1.06 |  |  | 502004 | Comp
13 | Civil | 2.8.05 | 1.6.05 | Imp to lane by brick flooring & drain in gali No-7 from Khasra No 385 jto Dalip Kumar hs in part-II , village Jharoda in c-104/CLZ | 276300 | EE-XII | 104
14 | Civil | 2.8.05 | 1.6.05 | Imp to lane by brick flooring from Electric transfer to Munshihal in part-III Surender colony in Village Jharoda c-104/CLZ | 348690 | EE-XII | 104 | 715/20.03.06/EE-XII | M/s Naveen Const.& co | 29.03.06 | 26.05.06 |  |  | 348424 | Comp
15 | Civil | 2.8.05 | 1.6.05 | Imp to lane by B/ flooring and drain in from Burari road to Devender Hs on 25 foota road near upkaar Colony in Village Burari C-104/CLZ | 694900 | EE-XII | 104 | 484/08.12.05/EE-XII | M/s Shyam Lal Gupta | 17.12.05 | 15.04.06 |  |  | 694900 | Comp
16 | Civil | 2.8.05 | 12.7.05 | Imp to lane by B/floring and drain from Vijinder to Ram singh Hs in Tomar colony in vilage Burari C-104/CLZ | 812109 | EE-XII | 104 | 402/07.11.05/EE-XII | M/s S.S Enterprises | 16.11.05 | 02.03.06 |  |  | 811674 | Comp
17 | Civil | 2.8.05 | 29.7.05 | Imp to road by Provding RMC from Banwari Hs to Shakti Singh hs and Naresh hs to Ramesh Hs in Kadipur village in C-104/CLZ | 199200 | EE-XII | 104
18 | Civil | 2.8.05 | 29.7.05 | Imp to Phirni road by providing RMC from Farm Hs to Babul Tree in village Kadipur C-104/CLZ | 198687 | EE-XII | 104 | 342/29.09.05/EE-XII | M/s Havshit Builders | 09.10.05 | 02.11.05 |  |  | 197457 | Comp
19 | Civil | 2.8.05 | 29.7.05 | Imp to Phirni road by providing RMC from Dall Mill to Farm Hs in Village Kadipur in C-104/CLZ | 188229 | EE-XII | 104 | 328/21.9.05/XII | M/s S.M. Const. | 28.09.05 | 27.11.05 |  |  | 187985 | Comp
20 | Civil | 8.8.05 | 1.6.05 | Imp to lane by Brick flooring and drain from sonia Clinic to Balak Ram Hs and B.D Sharma to K.K builders in D block Kamal Vihar , Kamal pur village Burari C-104/CLZ | 1004948 | EE-XII | 104 | 400/07.11.05/EE-XII | M/s S.S Enterprises | 11.11.05 | 01.03.06 |  |  | 1004739 | Comp
21 | Civil | 8.8.05 | 1.6.05 | Imp to lane by Brick flooring and drain in gali no-5 from Ram Chander to Hemram , virender to Surja and gali no- 6 from Dhermpal to Siya Ram in A block , Kaushik enclave Village Burari C-104/CLZ | 1533809 | EE-XII | 104 | 401/07.11.05/EE/XII | M/s S.S Enterprises | 16.11.05 | 01.03.06 |  |  | 1520604 | Comp
22 | Civil | 8.8.05 | 1.6.05 | Imp to lane by brick flooring and drain Parmood to Manoj Hansraj to Harish uttaranchal school to Shiv Singh and ceble factory to Tilak Raja in uttaranchal Enclave kamal pur village Burari C-104/CLZ | 630698 | EE-XII | 104 | 541/02.01.06/EE-XII | M/s Satish Const.&Co. | 03.01.06 | 28.06.06 |  |  | 630514 | Comp.
23 | Civil | 11.8.05 | 17.1.05 | Imp to lane by Brick flooring and drain from Dayanand to Manoj Jain in Tomar Colony in village Burari C-104/CLZ | 516313 | EE-XII | 104 | 696/17.03.06/EE-XII | M/s Harsh Consts. | 20.03.06 | 01.07.06 |  |  | 515633 | Comp
24 | Civil | 2.9.05 | 1.9.05 | Imp to lane by Brick pavement from Darshan to Gursharan Hs and fron Nitu Sharma to Shiv Mandir in Village Jharoda in C-104/CLZ | 315972 | EE-XII | 104 | 502/22.12.05/EE-XII | M/s Hazarika Builders | 01.01.06 | 31.05.06 |  |  | 315481 | Comp.
25 | Civil | 18.11.05 | 1.8.05 | Imp of lane by CC from Chet Ram hs to Khem Chand Hs in village Mukand pur C-104 CLZ | 199773 | EE-XII | 104 | 540/30.12.05/EE-XII | M/s Sorout Const.Co | 31.12.05 | 04.03.06 |  |  | 199747 | Comp.
26 | Civil | 18.11.05 | 1.8.05 | Imp of lane by CC in block J pkt, -J-3, in Jahangir Puri Resettlement Colony W.n. 103 CLZ | 196900 | EE-XII | 103 | 711/17.03.06/EE-XII | M/s Globe Const CO. | 17.03.06 | 08.05.06 |  |  | 196659 | Comp.
27 | Civil | 29.11.05 | 1.8.05 | C/o drain from H.NO A-793 to R-648 in Bhalswa Dairy conlony in C-103/CLZ | 448942 | EE-XII | 103 | 794/31.03.06/EE-XII | M/s Lamba Brothers | 01.04.06 | 16.06.06 |  |  | 448939 | Comp.
28 | Civil | 29.11.05 | 1.8.05 | C/o drainage from Om Parkash hs to Dr. Bhardwaj Hs in Bhalswa Dairy colony in C-103/CLZ | 609993 | EE-XII | 103 | 19/19.04.06/EE-XII | M/s Sorout Const.Co | 28.04.06 | 27.08.06 |  |  | 609308 | Comp.
29 | Civil | 29.11.05 | 1.8.05 | C/o drian from Babulal Hs to Kali Charan hs in Bhalswa Dairy colony in C-103/CLZ | 483971 | EE-XII | 103 | 519/26.12.05/EE-XII | M/s P.K.Const.Co. | 27.12.05 | 21.03.06 |  |  | 483948 | Comp.
30 | Civil | 29.11.05 | 1.8.05 | Imp to lane by pdg B/ pavement from Shashi Sharma hs to Kamla Hs front of Swami Parmanand and park in Bhalswa dairy coloney in C-103/CLZ | 466281 | EE-XII | 103 | 578/10.01.06/EE-XII | M/s Tyagi Const.Co. | 15.01.06 | 11.04.06 |  |  | 464777 | Comp.
31 | Civil | 29.11.05 | 1.8.05 | Imp to lane by pdg BP from Santosh Ram Hs to Dalip Kumar Hs and Ashraf Ali hs to Raish Ali Hs in Bhalaswa Dairy Cly in C 103 CLZ | 455592 | EE-XII | 103 | 705/17.03.06/EE-XII | M/s Ankit Associates | 17.03.06 | 12.07.06 |  |  | 455400 | Comp.
32 | Civil | 29.11.05 | 1.8.05 | Imp to lane by providing B/ pavement from Goyal property to Homed pathic Clinic along Masjid in Bhalswa Dairy colony in C-103/CLZ | 477180 | EE-XII | 103 | 704/17.03.06/EE-XII | M/s Ankit Associates | 17.03.06 | 13.07.06 |  |  | 477115 | Comp.
33 | Civil | 29.11.05 | 1.8.05 | Imp to lane by bric pavement from Shaukat Ali to Surender Singh and S.V.M public School to Tanisha Electronics in Bhalswa Dariy colony in C-103//CLZ | 628641 | EE-XII | 103 | 87/31.05.06/EE-XII | M/s Sorout Const.Co | 01.06.06 | 25.09.06 |  |  | 628513 | Comp.
34 | Civil | 29.11.05 | 1.8.05 | Imp to lane by pdg B/pavement from Tilak Raj Hs to Anita Hs along Masjid in Bhalswa Dariy coloney C-103/CLZ | 493923 | EE-XII | 103 | 571/09.01.06/EE-XII | M/s S.S.Enterprises | 11.01.06 | 11.04.06 |  |  | 493445 | Comp.
35 | Civil | 29.11.05 | 1.8.05 | Imp to lane by providing Brick pavement from Babu Ram Hs to Ram Kirpal Hs to Kali Charan hs in Bhalswa Dairy colony in C-103/CLZ | 474851 | EE-XII | 103 | 572/09.01.06/EE-XII | M/s S.S.Enterprises | 11.01.06 | 12.04.06 |  |  | 474670 | Comp.
36 | Civil | 29.11.05 | 1.8.05 | Imp to lane by pdg B/P from Mohini hs to Ram Chander Hs to Rajender Kr to Nawab Singh along Partap Singh hs in Bhalswa Dairy colony in C-103/CLZ | 478787 | EE-XII | 103 | 570/09.01.06/EE-XII | M/s. S.S.Enterprises | 10.01.06 | 12.04.06 |  |  | 478610 | Comp.
37 | Civil | 5.12.05 | 22.11.05 | Imp to lane by pdg interlocking pavers from Pankaj hs to Brij Kishore Hs in Burari village in c-104/CLZ | 199950 | EE-XII | 104 | 560/03.01.06/EE-XII | M/s Mahesh Chand & Co. | 04.01.06 | 10.03.06 |  |  | 199499 | Comp.
38 | Civil | 5.12.05 | 22.11.05 | Imp to lane by interlocking paves from Ravi Shankar to Satish Tyagi Hs in village Burari C-104/ CLZ | 181900 | EE-XII | 104
39 | Civil | 12.12.05 | 17.2.05 | Imp to lane from Burari road to Suraj mal in Sant Ngar vill Burari in C-104/clz | 361990 | EE-XII | 104 | 526/26.12.05/EE-XII | M/s Sorout Const.Co | 28.12.05 | 24.05.06 |  |  | 361899 | Comp.
40 | Civil | 12.12.05 | 17.2.05 | Imp to gali no 110 from Ravinder singh to Chanderlal in Sant Ngr , Village Burari c-104/CLZ | 389615 | EE-XII | 104 | 645/22.02.06/EE-XII | M/s Narendra Conat.Co | 01.03.06 | 07.06.06 |  |  | 389608 | Comp.
41 | Civil | 12.12.05 | 17.2.05 | Imp to lane in gali no-112 from 25 foota to Ranjeet Singh in Sant Ngr. Vill Burari c-104/ CLZ | 401320 | EE-XII | 104 | 636/13.02.06/EE-XII | M/s Ess kay Enterprises | 15.02.06 | 28.03.06 |  |  | 401075 | Comp.
42 | Civil | 12.12.05 | 8.12.05 | Imp to lane and drain from Apex road to Delip Dass to 25 foota in Sant Ngr in Vill Burari c-104/CLZ | 474564 | EE-XII | 104 | 735/21.03.06/EE-XII | M/s S.S Contractor | 30.03.06 | 14.07.06 |  |  | 474375 | Comp.
43 | Civil | 12.12.05 | 8.12.05 | Imp to gali no C-6 from 25 foota to R.K. hs in vill. Nathu pura C-104/CLZ | 214391 | EE-XII | 104 | 734/21.03.06/EE-XII | M/s S.S Contractor | 30.03.06 | 28.07.06 |  |  | 214345 | Comp.
44 | Civil | 22.12.05 | 22.12.05 | C/o Drain and road from Electric Transformer to Arora farm in B Block, Baba Colony in Village Burari | 866600 | EE-XII | 104 | 708/17.03.06/EE-XII | M/s Shyam Lal Gupta | 26.03.06 | P |  |  | 382873 | Comp.
45 | Civil | 28.2.06 | 1.9.05 | Imp to lane by Brick Pavement and Const of Drain from Som Vir to City Convent School in Village Burari in C 104 CLZ | 364800 | EE-XII | 104 | 770/24.03.06/EE-XII | M/s Elise Enterprises | 02.04.06 | 14.07.06 |  |  | 283358 | Comp.
46 | Civil | 09.03.06 | 06.07.05 | C/o lane from Mamraj to Ramavadh Sita Ram to Raja Ram and InderJeet to Flood Nala in Village Mukand pur C/104/CLZ | 1438999 | EE-XII | 104 | 125/30.06.06/EE-XII | M/s Narendra Conat.Co | 09.07.06 | 17.11.06 |  |  | 1438477 | Comp.
|  |  |  | Total | 23210229 | [8 empty] | 21941315
Remarks:- No. of works booked=46, No. of works cancelled=1

## Sh. Mangat Ram
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06
Municipal Corporation of Delhi
CIVIL LINE ZONE
|  | Name Of MLA |  | Sh. Manget Ram Singhal | AC-56 |  | year 2005-06 |  | Allocation | 127.4
|  | Name of Constituency |  | Adresh Nagar
|  | Ward Nos and Names |  | C-105 , Adresh Ngar C-106 , Sarani Pipal Thala
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agency | D.O.S. As per | D.O.C. As per | first Running | Second Running | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  | 13 | 16
1 | Civil | 6.6.05 | 20.4.05 | Imp of Shah Alam Bandh road by providing W.B.M from Bhobi Ghat Road to G.T. Rd in C-106/CLZ | 4407546 | Br-II | 106 | 89/13.03.06/EE(Pr.)II | M/s Rakesh Kumar Goel | 23.03.06 | 17.01.07 |  |  | 4406786 | Comp.
2 | Civil | 15.7.05 | 17.6.05 | Imp to road by M/P from Plot no 18 to park corner in Rajasthani Udhyogi nagar in C-106/CLZ | 455600 | EE-XVI | 106 | 234/3.10.005/XVI | M/s Subhash Const co. | 7.10.05 | 11.12.05 |  |  | 337413 | Comp
3 | Civil | 17.8.05 | 17.8.05 | Imp to lane along Green belt by pdg RMC & drainage system in block "A" from H.No A-1861 to A-1890 in Jahangir puri C-106 C.L.Z | 528300 | EE-XVI | 106 | 327/21.11.05/EE-XVI | M/s Tarun Const.Co | 21.11.05 | 30.01.06 |  |  | 515957 | Comp
4 | Civil | 17.8.05 | 23.7.05 | Reconstrcution of B/Wall of Central park near flat No 305 in Sanjay Enclave in C-106/CLZ | 1015166 | EE-XVI | 106 | 92/26.05.06/EE-XVI | M/s Raj Kumar Kesar | 05.06.06 | 11.10.06 |  |  | 1014810 | Comp.
5 | Civil | 17.8.05 | 23.7.05 | Imp to rd berms near Campa Cola Factary in Niran Kari Colony C-106/CLZ ( By pdg c.c. pavers) | 56034 | EE-XVI | 106 | 397/14.12.05/EE-XVI | M/s Prem Bros. | 14.12.05 | 20.02.06 |  |  | 55924 | Comp.
6 | Civil | 5.9.05 | 17.8.05 | Imp to G- block road between M.C Pry School and G-I, G-2 Pkt by providing RMC and drainge system in Jahangir puri C-106/CLZ | 944288 | EE-XVI | 106 | 70/09.05.06/EE-XVI | M/s Shiva Const.CO | 17.05.06 | 16.10.06 |  |  | 889050 | Comp.
7 | Civil | 5.9.05 | 17.8.05 | Imp of lane by providing RMC and drainge system in Block -H from H.No H-1 to H-50 in Jahangir puri C-106/CLZ | 1194100 | EE-XVI | 106 | 412/20.12.05/EE-XVI | M/s Jaswant Singh Dabas | 21.12.05 | 08.03.06 |  |  | 1194000 | Comp.
8 | Civil | 5.9.05 | 17.8.05 | Imp of H block Mangal Bazar road by providing M/P from Shah Alam Band to Kushal Cinema road in Jahangir puri C-106/CLZ | 975900 | EE-XVI | 106 | 480/30.01.06/EE-XVI | M/s Jaswant Singh Dabas | 08.02.06 | 07.06.06 |  |  | 975011 | Comp.
9 | Civil | 16.9.05 | 24.8.05 | Imp to B/Wall and passage by Kota stone in Main park in Block "A" ( Pkt A-1) in Jahangir puri C-106/CLZ | 568420 | EE-XVI | 106 | 51/27.04.06/EE-XVI | M/s K.K Const.Co-I | 05.05.06 | 04.09.06 |  |  | 568111 | Comp.
10 | Civil | 16.9.05 | 20.8.05 | Imp/ Reconst of B/wall and walkway in main park in block "H" near H.no. H-2/ 662-663 ( Baradaroi wala park) in Jahangir puri C-106/CLZ ( by pdg marble girl Wastand sand stone) | 601547 | EE-XVI | 106 | 592/20.03.06/EE-XVI | M/s K.K Const.Co-I | 29.03.06 | 28.07.06 |  |  | 601170 | Comp.
11 | Elect | 23.11.05 | 17.11.05 | P/o Boring with submerrsible pump set at Municipal park H.No A-140, Jahangir puri, C-106/CLZ | 175486 | EE-(E)II | 106 | 200/11.02.06/EE(E)-II | M/s Pragati Engineers | 11.02.06 | 14.03.06 |  |  | 137007 | Comp.
12 | Elect | 23.11.05 | 11.11.05 | P/o Boring with submerrsible pump set at Municipal park H.No H-4 1884-85 Green Belt , Jahangir puri, C-106/CLZ | 173653 | EE-(E)II | 106 | 203/16.02.06/EE(E)-II | M/s M.J.Electriclas & Electronics | 16.02.06 | 14.03.06 |  |  | 132892 | Comp.
13 | Elect | 6.12.05 | 1.12.05 | P/o Garden light at subash park, Adarsh Ngr. , part-I w.no-105/CLZ | 172792 | EE-(E)II | 105 | 26/18.05.06/EE(E)-II | M/s Amit Clevetor Services | 22.05.06 | 27.11.06 |  |  | 118752 | Comp.
14 | Elect | 6.12.05 | 1.12.05 | P/o Garden light at subash park, Adarsh Ngr, park-II in W.No-105/CLZ | 175244 | EE-(E)II | 105 | 27/18.05.06/EE(E)-II | M/s Bharat Elcttriclas and Electronics | 27.05.06 | 28.11.06 |  |  | 138201 | Comp.
15 | Elect | 12.12.05 | 19.11.05 | P/O boring with submessible pump sets at Municipal park, Sweeper Qtrs , Jahangir puri (Mandir Wala park) W.No-16 | 132475 | EE-(E)II | 106 | 187/06.02.06/EE(E)-II | M/s Bharat Elcttriclas and Electronics | 06.02.06 | 13.03.06 |  |  | 100249 | Comp.
16 | Elect | 12.12.05 | 18.11.05 | P/o boring with submessible pump set at municipal park ,H Block Ram Lila Ground Jahagir puir W.No-106/CLZ | 132475 | EE-(E)II | 106 | 190/06.02.06/EE(E)-II | M/s Sri Balaji Electriclas | 01.02.06 | 14.03.06 |  |  | 102591 | Comp.
17 | Elect | 12.12.05 | 11.11.05 | P/o boring with submessible pump set at Municipal park A block behind NDPL office Jahangir puri W.no-106/CLZ | 134842 | EE-(E)II | 106 | 196/07.02.06/EE(E)-II | M/s A.K.Electriclas | 07.02.06 | 14.03.06 |  |  | 103287 | Comp.
18 | Elect | 12.12.05 | 18.11.05 | P/o boring with submerssible pump set at Municipal park , B-88, pubjabi Basti Jahangir puri , W.no-106/CLZ | 132475 | EE-(E)II | 106 | 195/07.02.06/EE(E)-II | M/s A.K.Electriclas | 07.02.06 | 14.03.06 |  |  | 100702 | Comp.
19 | Elect | 12.12.05 | 19.11.05 | P/o boring submerssible pumps set at municipal park , Azad park , Nirankari colony W.no-106/CLZ | 132475 | EE-(E)II | 106 | 189/06.02.06/EE(E)-II | M/s Sri Balaji Electriclas | 14.02.06 | 14.03.06 |  |  | 102554 | Comp.
20 | Elect | 12.12.05 | 17.11.05 | P/o boring with submerssible pump set at Municipal park , Basrola w.no-106/CLZ | 133000 | EE-(E)II | 106 | 191/06.02.06/EE(E)-II | M/s Sri Balaji Electriclas | 06.02.06 | 14.03.06 |  |  | 101977 | Comp.
21 | Elect | 12.12.05 | 17.11.05 | P/O 12m Long street light at Municipal Park, B-28, Gandhi vihar in w.rno. 106 | 133258 | EE-(E)II | 106 | 32/18.05.06/EE(E)-II | M/s Khanna Sales Corp. | 18.05.06 | 25.05.06 |  |  | 99262 | Comp.
22 | Elect | 15.02.06 | 11.11.05 | P/o 12" long Street light at Municipal Park, Sarai Pipal Thala, Opp.Municipal School. W.No. 106/CLZ | 133376 | EE-(E)II | 106 | 06/21.04.06/EE(E)-II | M/s S.T.Electric.Co | 21.04.06 | 25.05.06 |  |  | 93938 | Comp.
23 | Elect | 15.02.06 | 11.11.05 | P/o 12" long Street light at Municipal Park, A block behind NDPL office at Jhangir puri W.No. 106/CLZ | 134231 | EE-(E)II | 106 | 28/18.05.06/EE(E)-II | M/s Saksham Electricals & Electronics | 18.05.06 | 25.05.06 |  |  | 110776 | Comp.
24 | Elect | 15.02.06 | 17.11.05 | P/o 12" long Street light at Municipal Park,B-88, Punjabi Basti W.No. 106/CLZ | 131549 | EE-(E)II | 106 | 3/21.04.06/EE(E)-II | M/s Sri Balaji Electriclas | 21.04.06 | 25.05.06 |  |  | 104802 | Comp.
25 | Elect | 15.02.06 | 17.11.05 | P/o 12" long Street light at Azad Park, Nirankari colony W.No. 106/CLZ | 131641 | EE-(E)II | 106 | 25/18.05.06/EE(E)-II | M/s Neeraj Electricals | 18.05.06 | 25.05.06 |  |  | 94240 | Comp.
26 | Elect | 15.02.06 | 17.11.05 | P/o 12" long Street light at Municipal Park, Sweeper Qtrs., Jahangir puri opp. Block No. 25 W.No. 106/CLZ | 131641 | EE-(E)II | 106 | 2/17.04.06/EE(E)-II | M/s Neeraj Electricals | 17.04.06 | 25.05.06 |  |  | 94959 | Comp.
27 | Elect | 15.02.06 | 17.11.05 | P/o 12" long Street light at Municipal Park, Sweeper Qtrs., Jahangir puri opp. Block No.08 W.No. 106/CLZ | 131558 | EE-(E)II | 106 | 24/18.05.06/EE(E)-II | M/s Kamal Electricals | 26.06.06 | 19.01.07 |  |  | 100776 | Comp.
28 | Elect | 15.02.06 | 17.11.05 | P/o 12" long Street light at Municipal Park, Sweeper Qtrs., Jahangir puri opp. Block No.32 W.No. 106/CLZ | 131549 | EE-(E)II | 106 | 29/18.05.06/EE(E)-II | M/s S.T.Electric.Co | 18.05.06 | 25.05.06 |  |  | 96075 | Comp.
29 | Elect | 15.02.06 | 17.11.05 | P/o 12" long Street light at Municipal Park, E-75 Gandhi Vihar W.No. 106/CLZ | 133258 | EE-(E)II | 106 | 16/26.04.06/EE(E)-II | M/s Seth Const. | 26.04.06 | 25.05.06 |  |  | 102197 | Comp.
30 | Elect | 15.02.06 | 17.11.05 | P/o 12" long Street light at Municipal Park, E-235 Gandhi Vihar W.No. 106/CLZ | 133258 | EE-(E)II | 106 | 7/21.04.06/EE(E)-II | M/s Illuminators & Circuiters | 21.04.06 | 25.05.06 |  |  | 99628 | Comp.
31 | Elect | 15.02.06 | 17.11.05 | P/o 12" long Street light at Municipal Park, A Block Gandhi Vihar opp. Jaganath Smiriti Park W.No. 106/CLZ | 133258 | EE-(E)II | 106 | 1/17.04.06/EE(E)-II | M/s Eminent Traders(India) | 17.04.06 | 25.05.06 |  |  | 95322 | Comp.
32 | Elect | 15.02.06 | 17.11.05 | P/o 12" long Street light at Municipal Park, Bharola Village W.No. 106/CLZ | 131549 | EE-(E)II | 106 | 5/21.04.06/EE(E)-II | M/s S.T.Electric.Co | 21.04.06 | 25.05.06 |  |  | 97376 | Comp.
33 | Elect | 22.2.06 | 17.11.05 | P/o 12" long Street light at Municipal Park, Near B-88 -86 in Punjabi Basti in W.No. 106/CLZ | 131558 | EE-(E)II | 106 | 4/21.04.06/EE(E)-II | M/s Raj Electricals | 21.04.06 | 25.05.06 |  |  | 102538 | Comp.
|  |  |  | Total | 13963502 | [8 empty] | 12988333

## S.P.s.(bitto)
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06
Municipal Corporation of Delhi
CIVIL LINE ZONE
|  | Name Of MLA |  | Sh.Surender Pal Singh | AC-61 |  | year 2005-06 |  | Allocation | 157.83
|  | Name of Constituency |  | Timar Pur
|  | Ward Nos and Names |  | C-115 C 116, G.T.B Nagar
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agency | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Civil | 25.5.05 | 1.5.05 | Imp to lane by Providing c.c. from H.No 1557 to 1547 in Autram Lane in C-106/CLZ | 199900 | EE-XII | 116 | 125/10.06.05 | M/s Prem Bros. | 29.8.05 | 24.1.06 | 199839 |  |  | Comp
2 | Civil | 25.5.05 | 1.5.05 | Imp to lane by Providing C.C from H.NO 1572 to 1486 in Autram lane in C-106/CLZ | 309669 | EE-XII | 116 | 709/17.03.06/EE-XII | M/s Rajvinder Singh | 01.07.06 | 21.08.06 | 309465 |  |  | Comp.
3 | Civil | 25.5.05 | 3.5.05 | Imp to lane by providing c.c. and drain from H.No 2434 to 2439 in Hudson lanes in C-116/CLZ | 258335 | EE-Br-II | 116 | 33/28.07.05/EE-Br-II | M/s Jai Maruti Consts. | 04.08.05 | 22.09.05 | 256287 |  |  | Comp.
4 | Civil | 25.5.05 | 1.5.05 | Imp to lane and drainage system from H.No 298 to 294 in Tagore park Extn. C-116/CLZ | 455183 | EE-XII | 116 | 416/11.11.05/EE-XII | M/s R.C.Bhatia | 14.11.05 | 30.01.06 | 454887 |  |  | Comp.
5 | Civil | 7.6.05 | 6.6.05 | Imp to lane providing c.c from H.No F-21 to F-33 in Vijay Nagar (s/s) in C-116/CLZ | 245546 | EE-XII | 116 | 341/6.10.05/EE-XII | M/s Lamba Brothers | 20.10.05 | 28.12.05 | 245381 |  |  | Comp
6 | Civil | 7.6.05 | 6.6.05 | C/o B/wall form H.No 1084 to H.NO 1118 in Kukherjee Nagr in c-116/CLZ | 340157 | EE-XII | 116 | 262/10.8.05/EE-XII | M/s Lamba Brothers | 30.8.05 | 16.12.05 | 339698 |  |  | Comp
7 | Civil | 7.6.05 | 6.6.05 | Imp to B/wall by Providing marble washed plaster from H.No 996 to H.No 1021 in Mukherjee Nagar C-116 C.LZ | 202092 | EE-XII | 116 | 258/10.8.05/EE-XII | M/s Lamba Brothers | 1.9.05 | 16.11.05 | 202091 |  |  | Comp
8 | Civil | 7.6.05 | 26.5.05 | Imp to lane by providing c.c. and drain from H.NO 1148 to 1154 in Mukherjee Nagar C-116/CLZ | 344600 | EE-XII | 116 | 30/18.7.05 | M/s Mehndiratta Traders | 22.7.05 | 1.9.05 | 302361 |  |  | Comp.
9 | Civil | 7.6.05 | 3.5.05 | Imp to lane by providing c.c. from H.No 1195 to 1189 in Mukherjee Nagar C-116/CLZ | 281400 | EE-XII | 116 | 32/28.7.05/BR-II | M/s Sanjeev Aggarwal | 4.8.05 | 3.10.05 | 250516 |  |  | Comp.
10 | Civil | 7.6.05 | 3.6.05 | Imp to lane by provding c.c. pavement from Akhara to Masjid and from H.No D-490 to H.No 260 in Malka Ganj Nehru Kutira in C-115/CLZ | 170100 | EE-XII | 115 | 632/13.02.06/EE-XII | M/s Baba & Co. | 22.02.06 | 13.04.06 | 169369 |  |  | Comp.
11 | Civil | 7.6.05 | 3.6.05 | Imp to lane by Providing c.c. from H.NO 805 to 803 from 772 to H.NO 168 and from 168 to H.NO 172 in Nehru Kutia Malka Ganj C-115/CLZ | 215376 | EE-XII | 115 | 441/18.11.05/XII | M/s Satbir singh | 25.11.05 | 10.1.06 | 214619 |  |  | Comp
12 | Civil | 7.6.05 | 3.6.05 | Imp to lany by providing c.c. infront of H.No D 10 and D-162 in Malka Ganj, Meat Wali Gali C-115/CLZ | 136200 | EE-XII | 115
13 | Civil | 28.6.05 | 20.6.05 | Imp to lane by Providing c.c. from H.No 278 to 351 in Parmanand Coloney C-116/CLZ | 198525 | EE-XII | 116 | 194/22.07.05/EE-XII | M/s Mahesh Chand & Co. | 03.10.05 | 27.10.05 | 198463 |  |  | Comp.
14 | Civil | 28.6.05 | 20.6.05 | Imp to lane Providing cc. From H.No 351 to 336 in Parmanad Coloney in C-116/CLZ | 196651 | EE-XII | 116 | 192/11.08.06/EE-XII | M/s Rakesh Bansal | 23.08.06 | 03.10.06 | 196411 |  |  | Comp.
15 | Civil | 28.6.05 | 20.6.05 | Imp to lane by Providing c.c. from H.NO 354 to Akhara in Parmanad Colony C-116/CLZ | 198812 | EE-XII | 116 | 256/10.8.05/XII | M/.s S.M. Consts | 1.10.05 | 14.08.06 | 198549 |  |  | Comp.
16 | Civil | 30.6.05 | 25.6.05 | Imp to lane by Providing c.c. from H.No 1901 to 1917 in Outram lane in C-116/CLZ | 496600 | EE-XII | 116 | 439/17.11.05/EE-XII | M/s Ashima Associates | 11.12.05 | 10.06.06 | 333479 |  |  | Comp.
17 | Civil | 1.7.05 | 29.6.05 | Imp to lane by Providing c.c. from H.No 301 to 237 Parmanand Coloney C-116/CLZ | 198525 | EE-XII | 116 | 449/22.11.05/EE-XII | M/s Pallki Const. Co. | 15.12.05 | 31.01.06 | 198353 |  |  | Comp
18 | Civil | 5.7.05 | 5.7.05 | Imp to Open Space and back lane infront of H.NO 6/27,6/40,6/20 and 6/46 in Vijay Ngr (D/s)C-116/CLZ Interlocking tils & c.c. | 235603 | EE-XII | 116 | 232/1.8.05/XII | M/sSanjeev Aggarwal | 12.9.05 | 28.10.5 | 235545 |  |  | Comp
19 | Civil | 18.7.05 | 4.7.05 | Imp to lane by Providing c.c. from H.No 73 to 103 in Dhaka Village in C-116/CLZ | 399900 | EE-XII | 116 | 333/21.9.05 | M/s Sandeep Associates | 20.9.05 | 28.10.05 | 291010 |  |  | Comp
20 | Civil | 18.7.05 | 4.7.05 | Imp to lane by Providing c.c. from Vayam Shalla to H.NO 468 in Parmand Coloney C 116 CLZ | 291532 | EE-XII | 116 | 334/21.9.05 | M/s Sandeep Associates | 22.9.05 | 28.10.05 | 291418 |  |  | Comp
21 | Civil | 18.7.05 | 4.7.05 | Imp to lane by Providing c.c. from H.NO 2345 to 2354 in Hudson lane in C-116/CLZ | 416300 | EE-XII | 116 | 438/17.11.05/EE-XII | M/s Ashima Associates | 25.06.06 | 13.11.06 | 288387 |  |  | Comp.
22 | Civil | 18.7.05 | 4.7.05 | Imp to lane by Providing c.c. from H.No 2365 jto 2388 in Hudson lane in c-116 CLZ | 584300 | EE-XII | 116 | 436/17.11.05/EE-XII | M/s Ashima Associates | 20.01.06 | 10.06.06 | 384641 |  |  | Comp.
23 | Civil | 18.7.05 | 4.7.05 | Imp to lane by Providing c.c. from Arya Samaj Mandir to H.NO 2324 in Hudson lane in c-116/CLZ | 520200 | EE-XII | 116 | 437/17.11.05/EE-XII | M/s Ashima Associates | 01.12.05 | 10.06.06 | 352219 |  |  | Comp.
24 | Civil | 18.7.05 | 16.7.05 | C/o B/wall of open space infront of Dr Hedge war Dharmath dispensary in Mukherjee Nag-C-116/CLZ | 99900 | EE-Br-II | 116 | 61/07.12.05/EE-Br-II | M/s Deepak Aggarwal | 05.01.06 | 03.02.06 | 99660 |  |  | Comp
25 | Civil | 22.7.05 | 16.7.05 | Imp of Main road by p?l RMC wazirabad village from RDO to 400 m in c-115/CLZ | 660000 | EE-XII | 115 | 263/12.8.05/XII | M/s Sanjeev Aggarwal | 21.8.05 | 30.11.05 | 659823 |  |  | Comp
26 | Civil | 28.7.05 | 16.7.05 | C/o walkway in park infront of Kabir Mandir in Malka Ganj in c-115/CLZ | 328485 | EEBr-II | 116 | 74/27.12.05/EE(Br)-II | M/s Gupta Enterprises | 12.01.06 | 27.03.06 | 327051 |  |  | Comp
27 | Civil | 29.7.05 | 25.7.05 | C/o walkway in park near H.No 1677 in Autram lane in C-116/CLZ | 344099 | EE-XII | 116 | 805/31.03.06/EE-XII | M/s A.R Const.Co | 10.06.06 | 07.07.06 | 344099 |  |  | Comp
28 | Civil | 29.7.05 | 25.7.05 | C/o walkway in park near H.NO N-50 in Mukherjee Nagar in C-116/CLZ | 312963 | EE-XII | 116 | 413/11.11.05/EE-XII | M/s Abhay Const co | 18.11.05 | 23.12.05 | 311277 |  |  | Comp
29 | Civil | 19.9.05 | 1.8.05 | Imp of lane by pdg CC And drain from Captan Singh Hs to Mintoo Hs I gali no 6 Manoj Hs to Mandir, Dharamvir Hs to Gupta Hs in gali no 4 Wazriabad vill C 115 CLZ | 399500 | EEBr-II | 115 | 69/16.12.05/EE-Br-II | M/s Gaurav Mehta | 30.12.05 | 15.02.06 | 399500 |  |  | Comp
30 | Elect | 11.11.05 | 27.10.05 | P/o of semi high mast ilght in park opp. Hs 1429 at Autromn lane in C 116 CLZ | 199619 | EEE-II | 116 | 158/2.1.06/EEE-II | M/s A.K Electricals | 3.1.06 | 7.1.06 | 166834 |  |  | Comp
31 | Hort. | 18.11.05 | 17.11.05 | Dev of New park adjucent to BBM Depot workshop in Indira Vihar C 116 CLZ | 581619 | DDH Clz | 116 | 24/16.05.06/DDH/CLZ | M/s Vijay Const.Co | 16.05.06 | 17.08.06 | 456404 |  |  | Comp.
32 | Hort. | 18.11.05 | 17.11.05 | Dev of New Park/Green belt in near Nallah in East mukherjee Nagar, C116 CLZ | 379373 | DDH Clz | 116 | 31/19.05.06/DDH-CLZ | M/s Vijay Const.Co | 19.05.06 | 08.06.06 | 298590 |  |  | Comp.
33 | Civil | 2.12.05 | 26.11.05 | Imp to lane by c.c and drainage system from main road to Yogander tyagi Hs , Gali no -10 in Wazirabad village, in C-115/CLZ | 388649 | EE-XII | 115 | 747/22.03.06/EE-XII | Ms/ Gaurav Mehta | 31.03.06 | 12.07.06 | 387945 |  |  | Comp.
34 | Civil | 2.12.05 | 26.11.05 | Imp to lane by pdg c.c. from Gali no-6 to Gali no-8, Indira Hs to Pramod Tyagi hs in Wazirabad vill. In C-115/CLZ | 198800 | EE-XII | 115 | 599/23.01.06/EE-XII | M/s S.M.Const. | 03.04.06 | 02.05.06 | 198391 |  |  | Comp.
35 | Civil | 2.12.05 | 26.11.05 | Imp to lane by pdg RMC from Krishan Tyagi Hs to Billu Bhati Hs in Wazirabad vill in C-115/CLZ | 451886 | EE-XII | 115 | 683/07.03.06/EE-XII | M/s Gaurav Mehta | 07.03.06 | 29.03.06 | 451195 |  |  | Comp.
36 | Civil | 2.12.05 | 26.11.05 | Imp to stg. Of road by dense carpet from H.NO B-409 to E-214 infront of Sarvodhiya Vidhalaya in Nehru Vihar in C-115/CLZ | 509500 | EE-XII | 115
37 | Civil | 2.12.05 | 26.11.05 | Imp to stag of road by dense Carpet from H.No D-1 to E-223 , Nehru Vihar in C-115/CLZ | 385600 | EE-XII | 115 | 521/18.12.06/EE-XII | M/s Sona Consultant & Contractors | 21.02.07 | 24.02.07 | 385405 |  |  | Comp.
38 | Civil | 2.12.05 | 26.8.05 | Imp to lane by c.c and drainage system from Robin Hs Brij Mohan Hs to Radhey Shyam Hs Gali no 6 in Wazirabad vill in C-115/CLZ | 199679 | EE-XII | 115 | 608/23.01.06/EE-EII | M/s Prem Bros. | 08.02.06 | 17.03.06 | 199005 |  |  | Comp.
39 | Civil | 5.12.05 | 14.10.05 | Imp to lane by pdg C.c. from H.NO 413 to 428 in Parmanand colony in C-116/CLZ | 391421 | EE-XII | 116 | 775/27.03.06/EE-XII | M/s Kalra Const.Co | 29.03.06 | 28.04.06 | 391357 |  |  | Comp.
40 | Civil | 5.12.05 | 14.10.05 | Imp to lane by pdg c.c. from H.No 28/1 to Dheer pur Mandir and H.No 29/1 in Indira Vihar colony inC-116/CLZ | 391371 | EE-XII | 116 | 677/07.03.06/EE-XII | M/s Gourav Mehta | 22.05.06 | 28.06.06 | 390079 |  |  | Comp.
41 | Civil | 5.12.05 | 14.10.05 | C/o walkway in park near H.No 2614 in Hudson line in c-116/CLZ | 205063 | EE-XII | 116 | 198/30.08.06/EE-XII | M/s Sagar Const.Co | 18.09.06 | 22.11.06 | 204547 |  |  | Comp.
42 | Civil | 5.12.05 | 14.10.05 | Imp to lane by pdg c.c. from H.No C-14 to C-10 B to C-17 B in Vijay Nagar in C-116/CLZ | 407094 | EE-XII | 116 | 744/22.03.06/EE-XII | M/s Gourav Mehta | 19.05.06 | 28.06.06 | 406758 |  |  | Comp.
43 | Civil | 5.12.05 | 14.10.05 | Imp to side berms by pdg Interlocking tiles from Round about Tagore park to Princes rd in Tagore park in C-116/CLZ | 598300 | EE-XII | 116 | 806/31.03.06/EE-XII | M/s Vinod Const.Co | 16.05.06 | 05.07.06 | 335701 |  |  | Comp.
44 | Civil | 5.12.05 | 14.10.05 | Imp to open Space by Interlocking tiles from H.NO E-11 to E-16/ A in Vijay Ngr I C-116/CLZ | 173042 | EE-XII | 116 | 679/07.03.06/EE-XII | M/s Gaurav Mehta | 16.03.06 | 29.03.06 | 172967 |  |  | Comp.
45 | Civil | 6.3.06 | 1.3.06 | Imp to lane by Pdg CC from Urinal toAmbedkar Park in Ambedkar Park Wali Gali in Malka Ganj in C 115 CLZ | 101526 | EE-XII | 115
46 | Civil | 6.3.06 | 1.3.06 | Imp to lane by Pdg CC near N block and Barat ghar to Ambedkar Park in Malkaganj in C 115 CLZ | 119759 | EE-XII | 115
47 | Civil | 6.3.06 | 1.3.06 | Imp to lane by Pdg CC from Shukkar Bazar Rd to Ambedkar Park Wali gali in Malka Ganj in C 115 CLZ | 128631 | EE-XII | 115
48 | Civil | 6.3.06 | 1.3.06 | Imp to lane by Pdg CC from Hs n. 143 to 159 and 268 in Ambedkar Park Wali gali in Malka Ganj in C 115 CLZ | 164586 | EE-XII | 115
49 | Civil | 6.3.06 | 1.3.06 | Imp to lane by Pdg CC from Hs n. 487 to 358 and 305 in Ambedkar Park Wali gali in Malka Ganj in C 115 CLZ | 159596 | EE-XII | 115
50 | Civil | 22.03.06 | 23.01.06 | Imp to lane and drainage system gali no-1 from Samsuddin office to Ch. Satveer Singh,Wazirabad Village in C-115/ClZ | 185591 | EE-XII | 115 | 793/31.03.06/EE-XII | M/s Gaurav Mehta | 09.04.06 | 02.05.06 | 180951 |  |  | Comp.
[5 empty] | 15361158 | [6 empty] | 12680527

## Sh K.K Singh
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06
MUNICIPAL CORPORATON OF DELHI
CIVIL LINE ZONE
|  | Name Of MLA |  | Sh. Karan Kanwar Singh | AC-62 |  | year 2005-06 |  | Allocation | 100
|  | Name of Constituency |  | Model Town
|  | Ward Nos and Names |  | C-117 Rana Partap Bagh C-118 ,Model Town
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Division | W.no | Work order no with date | Name of Agency | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Physical Target | Physical Achievement | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Civil | 24.6.05 | 20.6.05 | C/o Culverts in F block Model Town in c-118/CLZ | 99506 | EE-XII | 118 | 154/18.7.05 EE-XII | M/s Soroat Const Co. | 27.7.05 | 20.8.05 | 99322 |  |  | Completed
2 | Civil | 24.6.05 | 20.6.05 | Imp to G.T.K. road infornt of Invitation Banquet Hall by M/P in C-117/CLZ | 162686 | EE-XII | 117 | 170/18.7.05/XII | M/s Globe Const co. | 26.7.05 | 30.9.05 | 162674 |  |  | Comp
3 | Civil | 24.6.05 | 20.6.05 | Imp to lane by Providing RMC from H.No D-21 to D-17 in Rana Partap Bagh C-117/CLZ | 199600 | EE-XII | 117 | 192/22.7.05/XII | M/s Raj Associates | 26.7.05 | 30.9.05 | 199599 |  |  | Comp
4 | Civil | 24.6.05 | 20.6.05 | Imp to Chowk by providing RMc from H.No C-5 to C2/2 in Rana Pratap Bagh C-117/CLZ | 199600 | EE-XII | 117 | 237/1.8.05/EE-XII | M/s Rana Const co. | 20.8.05 | 31.10.05 | 199599 |  |  | Comp
5 | Civil | 24.6.05 | 20.6.05 | Imp to lane by providing RMc from H.No B-4 A/21 to B4 A/24 in Rana Partap Bagh in C-117/CLZ | 199600 | EE-XII | 117 | 204/22.7.05/XII | M/s Mohan & Co. | 26.7.05 | 14.10.05 | 199588 |  |  | Com.
6 | Civil | 24.6.05 | 20.6.05 | Imp to lane by providing RMc from H.No A-10/1 to A-11/1 in Rana Partap Bagh in C-117/CLZ | 199600 | EE-XII | 117 | 195/22.07.05/EE-XII | M/s Mahesh Chand & Co | 25.07.05 | 30.09.05 | 199591 |  |  | Comp.
7 | Civil | 24.6.05 | 20.6.05 | Imp to lane by providing RMC from H.No B-9/1 to B-7/1 IN Rana Partap Bagh C-117/CLZ | 199600 | EE-XII | 117 | 327/21.09.05/EE-XII | M/s Surya Kant Sharma | 28.09.05 | 29.10.05 | 199125 |  |  | Comp.
8 | Civil | 24.6.05 | 20.6.05 | Imp to lane by providing RMC from H.No D-6/16 to Gurudwara , B-2/11 to B-2/22 in Rana Partab BaghC-117//CLZ | 199600 | EE-XII | 117 | 212/22.07.05/EE-XII | M/s Prem Bros. | 25.08.05 | 18.02.05 | 199476 |  |  | Comp.
9 | Civil | 24.6.05 | 20.6.05 | Imp to lane by Providing RMC from H.No A-19 to A-17/1 and A-7/5 to A-6/5 in Rana Partap Bagh in C-117/CLZ | 199600 | EE-XII | 117 | 193/22.7.05/XII | M?s Rajesh Const CO | 23.7.05 | 30.9.05 | 199599 |  |  | comp
10 | Civil | 24.6.05 | 20.6.05 | Imp to lane by providing RMC from H.No A-8/18 to A8/45 in Rana Partap Bagh in C-117/CLZ | 199600 | EE-XII | 117 | 240/01.08.05/EE-XII | M/s Aman Deep Const.Co. | 10.08.05 | 01.12.05 | 199574 |  |  | Comp.
11 | Civil | 24.6.05 | 20.6.05 | Imp to lane by Providing RMc from H.No A-12/1 to A-12/6 in Rana Partap Bagh in c-117/CLZ | 199600 | EE-XII | 117 | 238/1.8.05/EE-XII | M/s Rana Const co. | 2.8.05 | 31.10.05 | 199599 |  |  | Comp
12 | Civil | 24.6.05 | 20.6.05 | Imp to lane by providing RMC from H.No C-5/18 to C5/13 in Rana Partap Bagh C-1147/CLZ | 199600 | EE-XII | 117 | 202/22.7.05/XII | M/s Sutail Consts. | 28.7.05 | 30.09.05 | 199598 |  |  | Comp
13 | Civil | 24.6.05 | 11.6.05 | Imp to lane from H.NO 139 to 145 in Derawal Nagar "A" block C-118/CLZ(by pdg RMC) | 198966 | EE-XII | 118 | 203/22.7.05/XII | M?s Amar chouhan | 22.7.05 | P | 129277 |  |  | In Prog.
14 | Civil | 4.7.05 | 11.6.05 | Imp / covering of drain by S.F.R.E. from H.No B-58 to B083 in Derawal Nagr B block in c-118/CLZ Rs. 99000/- |  | EE-XII | 118 | Work Cancelled as desired by area MLA vide letter no. KKS/Resi/08/731 dated 22.06.08 and approved by CE-I dated 04.07.08.
15 | Civil | 27.7.05 | 11.7.05 | C/o hut in park behind Brahama Kumarits in Derwal Nagar A block in c-118/CLZ | 267300 | EE-XII | 118 | 506/22.12.05/EE-XII | M/s Harsh Consts. | 22.12.05 | 02.03.06 | 226724 |  |  | Comp.
16 | Civil | 27.7.05 | 11.7.05 | C/o Hut in park near H.No A-46 in A block Derawal Nagar in C-118/CLZ | 226724 | EE-XII | 118 | 505/24.12.05/EE-XII | M/s Harsh Consts. | 24.12.05 | 01.03.06 | 225987 |  |  | Comp.
17 | Civil | 27.7.05 | 11.7.05 | C/o Hut in Shalimar park in Model Town -II in C-118/CLZ Rs. 267300/- |  | EE-XII | 118 | Work Cancelled as desired by area MLA vide letter no. KKS/Resi/08/731 dated 22.06.08 and approved by CE-I dated 04.07.08.
18 | Civil | 27.7.05 | 11.7.05 | C/o Hut in D- block park in Model Town-III in C-118/W.Z | 267300 | EE-XII | 118 | 514/26.12.05/EE-XII | M/s Pardeep Contractor | 26.12.05 | 28.02.06 | 222565 |  |  | Comp.
19 | Civil | 27.7.05 | 11.7.05 | C/o of Hut in park of Naniwala Bagh Commercila Complex in C-118/CLZ | 242088 | EE-XII | 118 | 515/26.12.05/EE-XII | M/s Devender Gupta | 26.12.05 | 31.03.06 | 242088 |  |  | Comp.
20 | Civil | 27.7.05 | 11.7.05 | C/o Hut in park of kewal park near Ramlila park in C-118/CLZ Rs. 267300/- |  | EE-XII | 118 | Work Cancelled as desired by area MLA vide letter no. KKS/Resi/08/731 dated 22.06.08 and approved by CE-I dated 04.07.08.
21 | Civil | 27.7.05 | 11.7.05 | C/o Hut in park of Kalyan vihar near H.No 62 in C-118/CLZ | 267300 | EE-XII | 118 | 474/0812.05/EE-XII | M/s Harsh Consts. | 08.12.05 | 01.03.06 | 267300 |  |  | Comp.
22 | Civil | 29.7.05 | 28.5.05 | Imp to lane from H.NO 14 to Arya Samaj Mandir and along DDA Market in Gurawala town part-II in C-118 /CLZ by c.c. & interlocing tiles) | 448250 | EE-XII | 118 | 272/16.8.05 | M/s Bhaiji Controctor & Suppler | 16.8.05 | 30.9.05 | 448092 |  |  | Comp.
23 | Civil | 29.7.05 | 28.5.05 | Imp to lane from H.No 122 to 130 in Derawal Nagar B block in C-118/CLZ (BY CC and interlocking tiles) | 455008 | EE-XII | 118 | 271/16.08.05/XII | M/s Bhaiji Controctor & Suppler | 16.8.05 | 31.1.06 | 454543 |  |  | Comp.
24 | Civil | 21.10.05 | 20.10.05 | Imp to Shalimar park in Model Town in C-118/CLZ | 3629894 | EE-XII | 118 | 689/13.03.06/EE-XII | M/s Anil Gupta | 23.03.06 | P | 2281318 |  |  | In Prog.
25 | Civil | 25.1.06 | 1.10.05 | Imp to lane infornt of H.no. 55 in Gujrawala town part-II C 118 CLZ (BY RMC) | 517262 | EE-XII | 118 | 643/17.02.06/EE-XII | M/s Narendra Const.Co. | 17.02.06 | 30.03.06 | 516929 |  |  | Comp.
26 | Civil | 2.2.06 | 22.1.06 | Imp to Parking space infront of H.no. E-6 and along park in CC colony in C 118 CLZ (By CC) | 99579 | EE-XII | 118
27 | Civil | 2.2.06 | 19.1.06 | Imp of lane from H>no. B 62 to b 67 in CC Cly in C 118 CLZ(by RMC) | 458108 | EE-XII | 118
28 | Civil | 23.2.06 | 22.2.06 | Imp to Open Space behind stage in Ramlila Park in CC cly in C 118 CLZ | 201519 | EE-XII | 118 | 742/22.03.06/EE-XII | M/s Vikram Malhotra | 22.05.06 | 27.07.06 | 196912 |  |  | Comp.
|  |  |  | Total | 9537490 | [6 empty] | 7469079
Remarks:- No. of wokrs booked=28, No. of works concelled=3

## Sh.Shadi Ram
STATUS REPORT OF MLA FUND FOR THE YEAR 2005-06
Municipal Corporation of Delhi
CIVIL LINE ZONE
|  | Name Of MLA |  | Sh. Shadi Ram | AC-63 |  | Allocation |  |  | 100
|  | Name of Constituency |  | KAMLA NAGAR
|  | Ward Nos and Names |  | C-119 Kamla Ngr. C-120 Shestri Ngr.
SL No. | Deptt. | Date of Booking | Date of Consent | Name of Work (With Location) | Cost of Work | Div. | W.no | Work order no with date | Name of Agencys | D.O.S. As per | D.O.C. As per | Up to date Expenditure | Remarks
[10 empty] | Actual | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 16
1 | Civil | 17.8.05 | 14.8.05 | Imp to lane by providing drainage system & C.C from H.NO 1UB to 16 UB , 63 U B to 100 UB & 98 UB to 100 UB in Jawahar Nagar in C-119/CLZ | 1356200 | EEXVI | 119 | 564/10.03.06/EE-XVI | M/s Vinod Kumar | 20.06.06 | P | 890096 | In Prog.
2 | Civil | 15.9.05 | 1.9.05 | Imp to lane by providing c.c. pavement and drainage systme from E-109 to Durga Mandir in Shastri Nagar in C-120/CLZ(RS 452500/-) |  | Br-II | 120 | Work cancelled as desired by area MLA vid letter no. NIL dated 28.12.05 and ordered by CE-I dated 21.1.06
3 | Civil | 15.9.05 | 1.9.05 | Imp to lane by providing C.c. pavement and drainage system form WZ-107 to WZ -81 and WZ-119 to B-121 in Nimri Village Shastri Nagr in C-120/CLZ(Rs-484600/-) |  | Br-II | 120 | Work cancelled as desired by area MLA vid letter no. NIL dated 28.12.05 and ordered by CE-I dated 21.1.06
4 | Civil | 16.9.05 | 1.9.05 | Imp to lane by providing c.c. pavement and drainage system from B-1910 to B-1831/1 and from Tikona park to B-1757/2 in Shastri Nagar C-120 /CLZ | 797800 | Br-II | 120 | 76/27.12.05/BR-II | M/s Shiva Const co. | 30.12.05 | 16.05.06 | 761681 | Comp.
5 | Elect | 29.9.05 | 17.9.05 | Provision of boring with submerssible pump set at Begum park Roshanara Bagh Shakti Ngr under CLZ | 132881 | EEE-II | 119 | 194/07.02.06/EE-II | M/s A.K.Electriclas | 24.02.06 | 01.03.06 | 110804 | Comp.
6 | Elect | 29.9.05 | 17.9.05 | P/o boring with submessible pump at market park Shahzada bagh Shastri Ngr under CLZ | 132881 | EEE-II | 119 | 201/11.02.06/EE(E)-II | M/s Pragati Engg. | 28.02.06 | 22.03.06 | 102674 | Comp.
7 | Elect | 29.9.05 | 17.9.05 | P/o boing with Submersible pump at park block no 2, Roop Nagr under CLZ | 132881 | EEE-II | 119 | 202/11.02.06/EE(E)-II | M/s M.J.Electtriclas & Electronics | 01.03.06 | 25.03.06 | 102573 | Comp.
8 | Elect | 29.9.05 | 17.9.05 | P/o boring with submessible pump at Park block No 30 Shakri Nagar under CLZ W No-119 | 132881 | EEE-II | 119 | 185/03.02.06/EE(E)-II | M/s M.J.Electtriclas & Electronics | 02.03.06 | 25.03.06 | 108805 | Comp.
9 | Elect | 29.9.05 | 17.9.05 | P/o boring with Submessible pump at park of Indira park, Shastri Nagr. | 132881 | EEE-II | 120 | 192/06.02.06/EEE-II | M/s Sri.Balaji Electriclas | 28.02.06 | 24.03.06 | 105810 | Comp.
10 | Elect | 29.9.05 | 17.9.05 | P/o boring with submerssible pump at park of DDA Flat Sarai Basti under CLZ | 132881 | EEE-II | 120 | 193/06.02.06/EEE-II | M/s Sri.Balaji Electriclas | 28.02.06 | 24.03.06 | 105532 | Comp.
11 | Elect | 11.10.05 | 17.9.05 | P/o boring with submerssible pump at park Green Belt Anand Nagar under CLZ | 132881 | EEE-II | 120 | 199/11.02.06/EE(E)-II | M/s Pragati Engg. | 28.02.06 | 22.03.06 | 102387 | Comp.
12 | Civil | 11.10.05 | 18.9.05 | Imp to lane by providing drinage & RMC from H.No 40/14 to 40/16 & 40/17 to 40/19 in Shakti Nagr C-119/CLZ | 407400 | EEXVI | 119 | 95/29.05.06/EE-XVI | M/s Rakesh Bansal | 07.06.06 | 30.08.06 | 280570 | Comp.
13 | Civil | 11.10.05 | 18.9.05 | Imp to lane by providing drainage & RMC from H.NO 40/1 to 40/6 to 40/9 and 40/10 to 40/13in Shakti Ngar in C-119 CLZ | 415400 | EEXVI | 119 | 21/18.04.06/EE-XVI | M/s Shiva Const co. | 27.04.06 | 10.07.06 | 291119 | Comp.
14 | Civil | 11.10.05 | 18.9.05 | Imp to lane by providing drainage & RMc from H.No 38/2 to 38/8 , 38/3 to 38/7 ,38/8 to 38/10 in Shakri Ngar C-119/CLZ | 593400 | EEXVI | 119 | 7/04.04.06/EE-XVI | M/s Shiva Const co. | 13..04.06 | 30.06.06 | 401925 | Comp.
15 | Civil | 11.10.05 | 18.9.05 | Imp to lane by providing drainage & RMC from 38/10 to 38/12, 38/15 to 38/16 and 38/17 to 38/20 in Shakti Nagar in c-119/CLZ | 532700 | EEXVI | 119 | 22/18.04.06/EE-XVI | M/s Shiva Const co. | 27.04.06 | 30.06.06 | 361187 | Comp.
16 | Civil | 11.10.05 | 18.9.05 | Imp to lane by Providing drainage and footpath by pdg inter locking pavers block 40 in Shakti Nagar C-119/CLZ | 298400 | EEXVI | 119 | 79/15.05.06/EE-XVI | M/s Bansal Consts. | 24.05.06 | 30.08.06 | 179947 | Comp.
17 | Civil | 11.10.05 | 18.9.05 | Imp to lane by providing RMc pave & drainage system near flat No 33 A and 39 A in DDA (LIG) flats in Gulabi Bagh in C-119/CLZ | 788300 | EEXVI | 119 | 84/18.05.06/EE-XVI | M/s Shiva Const co. | 27.05.06 | 21.08.06 | 552678 | Comp.
18 | Civil | 20.10.05 | 18.9.05 | Imp to lane by providing RMc pave & drainage system from h.No 39/21 to 39/25, 39/14 to 39/20 ,39/16 and 39/3 to 39/6 in block 39 Shakti Nagar in C-119/CLZ | 1051400 | EEXVI | 119 | 109/14.06.06/EE-XVI | M/s Parvesh Const.Co | 23.06.06 | 15.09.06 | 721901 | Comp.
19 | Civil | 20.10.05 | 11.10.05 | Imp to lane by Providing C.C. pave and drainage system from E-2/103 to E-2/116 and E-2/52 to E-2/66 in back lane in Shastri Ngar in c-120/CLZ | 510500 | EEXVI | 120 | 96/29.05.06/EE-XVI | M/s Bansal Consts. | 28.06.06 | 14.08.06 | 361437 | Comp.
20 | Civil | 15.12.05 | 23.11.05 | Imp to lane by pdg RMC Pav and Drainage system from L 53 to L 46 in shastri Nagar in c 20. | 424950 | EEXVI | 120 | 587/17.03.06/EE-XVI | M/s Shiva Const co. | 22.03.06 | 15.05.06 | 288430 | Comp.
21 | Civil | 15.12.05 | 28.11.05 28.11.05 | P/L CC Pav and Drainage System from H>no. NF-17 to New F 34 in Shastri Nagar C 120. | 379700 | EEXVI | 120 | 595/20.03.06/EE-XVI | M/s Sanjeev Builders | 10.04.06 | 20.05.06 | 253954 | Comp.
22 | Civil | 15.12.05 | 24.11.05 | Imp to lane by pdg CC and Drainage system to H>no. A 504/3 to A 529/8 and MC Pry School(A) Block to A 540/30 in Shastri Nagar in C 120 | 739700 | EEXVI | 120 | 605/22.03.06/EE-XVI | M/s Naresh Rai | 10.06.06 | 10.11.06 | 516937 | Comp.
23 | Civil | 1.2.06 | 29.12.05 | Imp of internal lanes by pdg CC in Block 26 Shaskti Nagar C 119 CLZ (From H.no. 26/102 to 26/105 & 26/70, 26/11 to 26/17 and 26/21) | 548086 | EE_Br-II | 119 | 18/09.06.06/EE(Br.)-II | M/s Jindal Enterprises | 15.06.06 | 23.08.06 | 548066 | Comp.
|  |  |  | Total | 9774103 | [6 empty] | 7148513
Remarks:- No. of wokrs booked=23, No. of works concelled=2
Note on G18: R.P.S: